## information (hidden)
Design |  |  | Procurement |  |  | Construction/Installation |  |  | Inspection
Outline | Definitive Design | Detail Design | Pre-PR | PO/WO | Delivery | Start | WIP | Complete | Inspection | Punch list | Closed

## 00 MASTER WORK REGISTER
MASTER WORK REGISTER
No | Type of Work | Work Code | Lot No. | System | LV1 | LV2 | Description/Title | CK | Location |  | Submission No. | Ex | Note
1 | GEN1 | DN01B1700001 | Lot01 | GEN | 1 |  | Rooms and Building Service Systems Modification in Stations Area | - |  | Station | MDW-39246-60 | 2026-08-01 |  | 10
2 | GEN1.1 | DN01B1700001 | Lot01 | GEN | 1 | 1 | Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR13 - OR17 | - |  | Station | MDW-39246 | 2026-08-01 |  | 1
3 | GEN1.2 | DN01B1700001 | Lot01 | GEN | 1 | 2 | Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR18 - OR22 | - |  | Station | MDW-39247 | 2026-08-01 |  | 1
4 | GEN1.3 | DN01B1700001 | Lot01 | GEN | 1 | 3 | Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR18 - OR22 | - |  | Station | MDW-39247 | 2026-08-01 |  | 1
5 | GEN1.4 | DN01B1700001 | Lot01 | GEN | 1 | 4 | Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR23 - OR29 | - |  | Station | MDW-39248 | 2026-08-01 |  | 1
6 | GEN1.5 | DN01B1700001 | Lot01 | GEN | 1 | 5 | Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR23 - OR29 | - |  | Station | MDW-39248 | 2026-08-01 |  | 1
7 | GEN1.6 | DN01B1700001 | Lot01 | GEN | 1 | 6 | SOR Counter and Workstation Hanging Support Installation on East Section | - |  | Station | MDW-39249 | 2026-08-01 |  | 1
8 | GEN1.7 | DN01B1700001 | Lot01 | GEN | 1 | 7 | Ticket Office Modification on East Section | - |  | Station | MDW-39250 | 2026-08-01 | งานจบ ส่ง TP แล้ว | 1
9 | GEN1.10 | DN01B1700001 | Lot01 | GEN | 1 | 10 | Modification of Eletrical System in Telecommunication Room at OR14 | - |  | Station | MDW-39251 | 2026-08-01 |  | 1
10 | GEN1.11 | DN01B1700001 | Lot01 | GEN | 1 | 11 | Modification of Fire Suppression System (N2) in Commerial Room at OR14 | - |  | Station | MDW-39252 | 2026-08-01 |  | 1
11 | GEN1.12 | DN01B1700001 | Lot01 | GEN | 1 | 12 | Modification of Civil Work in Telecommunication Room at OR14 | - |  | Station | MDW-39253 | 2026-08-01 |  | 1
12 | GEN1.13 | DN01B1700001 | Lot01 | GEN | 1 | 13 | Modification in Staff Mess Room at OR13-OR17 | - |  | Station | MDW-39254 | 2026-08-01 |  | 1
13 | GEN1.14 | DN01B1700001 | Lot01 | GEN | 1 | 14 | Modification in Staff Mess Room at OR18-OR22 | - |  | Station | MDW-39255 | 2026-08-01 |  | 1
14 | GEN1.15 | DN01B1700001 | Lot01 | GEN | 1 | 15 | Modification in Staff Mess Room at OR23-OR29 | - |  | Station | MDW-39256 | 2026-08-01 |  | 1
15 | GEN1.16 | DN01B1700001 | Lot01 | GEN | 1 | 16 | Modification of Air Conditioning in CER and SER at OR13-OR19 | - |  | Station | MDW-39257 | 2026-08-01 |  | 1
16 | GEN1.17 | DN01B1700001 | Lot01 | GEN | 1 | 17 | Modification of Air Conditioning in CER and SER at OR20-OR22 | - |  | Station | MDW-39258 | 2026-08-01 |  | 1
17 | GEN1.19 | DN01B1700001 | Lot01 | GEN | 1 | 19 | Modification of Air Conditioning in CER and SER at OR23-OR29 | - |  | Station | MDW-39259 | 2026-08-01 |  | 1
18 | GEN1.20 | DN01B1700001 | Lot01 | GEN | 1 | 20 | Modification of Air Conditioning in M&E Room at OCC Building | - |  | Depot | MDW-39260 | 2026-08-01 |  | 1
19 | GEN2 | DN01B1700002 | Lot01 | GEN | 2 |  | Rooms and Building Service Systems Modification in Depot Area | - |  | Depot | MDW-39261 | 2026-08-01 |  | 17
20 | GEN3 | DN01B1700003 | Lot01 | GEN | 3 |  | Cable Containment Modification | - |  | Station | MDW-39200-31 | 2025-05-28 |  | 32
21 | GEN4 | DN01B1700004 | Lot01 | GEN | 4 |  | Training Room and Workshop Room | - |  | Depot | - | 2026-04-01 |  | 2
22 | GEN4.0 | DN01B1700004 | Lot01 | GEN | 4 | 0 | Modification Works for Training Room at Ratchada Station | ประธาน |  | BL | MDW-39242 | 2026-04-01 |  | 1
23 | GEN4.1 | DN01B1700004 | Lot01 | GEN | 4 | 1 | AFC Training Room Modification - Civil & AR | สหชาติ | MWS | Depot | MDW-39244 | 2026-08-21 |  | 1
24 | GEN4.2 | DN01B1700004 | Lot01 | GEN | 4 | 2 | AFC Training Room Modification - Building Services | ประธาน | MWS | Depot | MDW-39245 | 2026-08-21 |  | 1
25 | GEN5 | DN01B1700005 | Lot01 | GEN | 5 |  | Raised Floor | สหชาติ |  | Station | MDW-39235 | 2026-06-01 |  | 1
26 | GEN6 | DN01B1700006 | Lot01 | GEN | 6 |  | Wayside Cable Containment in Depot | - |  |  | MDW-39271 | 2026-02-22 |  | 2
27 | GEN6.1 | DN01B1700006 | Lot01 | GEN | 6 | 1 | PSY Wayside Cable Containment for 24 Kv Cable under the Depot slab | ประธาน |  |  | MDW-39269 | 2026-02-22 | CANCLE | 1
28 | GEN6.2 | DN01B1700006 | Lot01 | GEN | 6 | 2 | COM/SIG Wayside Cable Containment in the Depot | มนตรี/ประธาน |  |  | MDW-39270 | 2026-02-22 | CANCLE | 1
29 | GEN7 | DN01B1700007 | Lot01 | GEN | 7 |  | Dangerous Waste Storage Building in Depot | สหชาติ/ประธาน |  |  | - | 2026-09-20 |  | 0
30 | GEN7.1 | DN01B1700007 | Lot01 | GEN | 7 | 1 | Dangerous Waste Storage Building in Depot - Civil & AR | สหชาติ |  |  | DWE-39024 | 2026-09-20 |  | 1
31 | GEN7.2 | DN01B1700007 | Lot01 | GEN | 7 | 2 | Dangerous Waste Storage Building in Depot - Building service | ประธาน |  |  | DWE-39025 | 2026-09-20 |  | 1
32 | GEN8 | DN01B1700008 | Lot01 | GEN | 8 |  | General Waste Storage Building in Depot | สหชาติ/ประธาน |  |  | - | 2026-09-20 |  | 0
33 | GEN8.1 | DN01B1700008 | Lot01 | GEN | 8 | 1 | General Waste Storage Building in Depot - Civil & AR | สหชาติ |  |  | DWE-39026 | 2026-09-20 |  | 1
34 | GEN8.2 | DN01B1700008 | Lot01 | GEN | 8 | 2 | General Waste Storage Building in Depot - Building service | ประธาน |  |  | DWE-39025 | 2026-09-20 |  | 1
35 | GEN9 | DN01B1700009 | Lot01 | GEN | 9 |  | Operation Support Equipment | สมศักดิ์ |  |  | DWE-39021 | 2026-08-21 |  | 1
36 | GEN10.1 | DN01B1700010 | Lot01 | GEN | 10 | 1 | Graphic and Signage Station | สหชาติ |  |  | GRS-39001-40 | 2026-08-21 |  | 0
37 | GEN10.2 | DN01B1700010 | Lot01 | GEN | 10 | 2 | Graphic and Signage Mainline & IVS,VS | สหชาติ |  |  | GRS-39001-40 | 2026-08-21 |  | 0
38 | GEN10.3 | DN01B1700010 | Lot01 | GEN | 10 | 3 | Graphic and Signage Depot | สหชาติ |  |  | GRS-39001-40 | 2026-08-21 |  | 0
39 | GEN11 | DN01B1700011 | Lot01 | GEN | 11 |  | Earthing and Bonding Modification | ประธาน |  |  | MDW-39289 | 2026-03-01 |  | 3
40 | GEN12 | DN01B1700012 | Lot01 | GEN | 12 |  | Mainline Cable Trough Modification on East Section | - |  |  | - | 2026-06-22 |  | 1
41 | GEN12.1 | DN01B1700012 | Lot01 | GEN | 12 | 1 | Main Line Cable Trough Modification (PSY) | มนต์ชัย |  |  | MDW-39233 | 2026-06-22 |  | 1
42 | GEN12.2 | DN01B1700012 | Lot01 | GEN | 12 | 2 | Main Line Cable Trough Modification (SIG/COM) | มนตรี |  |  | MDW-39234 | 2026-06-22 |  | 1
43 | GEN13 | DN01B1700013 | Lot01 | GEN | 13 |  | Bird Protection System | สหชาติ |  |  | MDW-39236 | 2026-11-19 |  | 1
44 | GEN14 | DN01B1700014 | Lot01 | GEN | 14 |  | Train Crew Office at Thailand Cultural Centre Station | สหชาติ |  |  | - | 2026-08-21 |  | 0
45 | GEN14.1 | DN01B1700014 | Lot01 | GEN | 14 | 1 | Driver Train Simulation Room and Train Crew Office at OR18 - Civil & AR | สหชาติ |  |  | MDW-39240 | 2026-08-21 |  | 1
46 | GEN14.2 | DN01B1700014 | Lot01 | GEN | 14 | 2 | Driver Train Simulation Room and Train Crew Office at OR18 - Building Services | ประธาน |  |  | MDW-39241 | 2026-08-21 |  | 1
47 | GEN15 | DN01B1700015 | Lot01 | GEN | 15 |  | Access Panel Closeout for Traction Substation Room in Main Workshop | สหชาติ |  | Depot | MDW-39239 | 2026-03-24 |  | 1
48 | GEN16 | DN01B1700016 | Lot01 | GEN | 16 |  | Level Crossing at Turnout | กำพล |  |  | MDW-39232 | 2026-08-21 | CANCLE | 1
49 | GEN17 | DN01B1700017 | Lot01 | GEN | 17 |  | Track Slab Crossing | ชฎิล/กำพล |  |  | MDW-39232 | 2026-08-21 | CANCLE | 0
50 | GEN18 | DN01B1700018 | Lot01 | GEN | 18 |  | Eye Adaptation Lighting (Lighting at Tunnel to Expose) | ประธาน |  |  | MDW-39243 | 2026-11-19 |  | 1
51 | GEN19 | DN01B1700019 | Lot01 | GEN | 19 |  | Train Simulation Room and AFC Training Room | สหชาติ/ประธาน |  |  | - | 2026-08-21 |  | 0
52 | GEN19.1 | DN01B1700019 | Lot01 | GEN | 19 | 1 | Modification AFC Training Center at OR19 - Civil & AR | สหชาติ | MWS |  | MDW-39244 | 2026-11-30 |  | 1
53 | GEN19.2 | DN01B1700019 | Lot01 | GEN | 19 | 2 | Modification AFC Training Center at OR19 - Building Services | ประธาน | MWS |  | MDW-39245 | 2026-11-30 |  | 1
54 | GEN20 | DN01B1700020 | Lot01 | GEN | 20 |  | Dormitory Cable Containments (if any) | - |  |  | - | - | CANCLE | 0
55 | GEN21 | DN01B1700021 | Lot01 | GEN | 21 |  | Project Information Management System (PIMS) | บัณฑิต |  |  |  | 2024-09-30 |  | 0
56 | GEN22 | DN01B1700022 | Lot01 | GEN | 22 |  | Central BEMS for the MRT Orange Line System | บัณฑิต |  |  | MDW-39237 | 2026-08-21 |  | 2
57 | GEN23 | DN01B1700023 | Lot01 | GEN | 23 |  | Asset Information | บัณฑิต |  |  |  | 2026-11-19 |  | 0
58 | PSD1 | DN01B1700031 | Lot01 | PSD | 1 |  | Holes for PSD Cable Wiring | กำพล |  |  | MDW-39282 | 2026-08-21 | CANCLE | 1
59 | PSD2 | DN01B1700032 | Lot01 | PSD | 2 |  | Rubber Gap Fillers on Platform Edge | กำพล |  |  | MDW-39004 | 2026-08-21 |  | 1
60 | PSD3 | DN01B1700033 | Lot01 | PSD | 3 |  | Platform Finishing | กำพล |  |  | MDW-39280 | 2026-08-21 |  | 1
61 | PSD4 | DN01B1700034 | Lot01 | PSD | 4 |  | Cladding Barrier between EWD and Station Structure | กำพล |  |  | MDW-39281 | 2026-08-21 |  | 1
62 | AFC1 | DN01B1700041 | Lot01 | AFC | 1 |  | Park and Ride System | บัณฑิต/สหชาติ |  |  | - | 2026-10-20 | CANCLE | 0
63 | AFC2 | DN01B1700042 | Lot01 | AFC | 2 |  | Ticket Issuing Machine (TIM) Wall Opening and Closing | สหชาติ |  |  | MDW-39276 | 2026-09-20 |  | 1
64 | AFC3 | DN01B1700043 | Lot01 | AFC | 3 |  | Balustrade Modification Along AFC Gate Line | สหชาติ |  |  | MDW-39279 | 2026-09-20 |  | 2
65 | AFC4 | DN01B1700044 | Lot01 | AFC | 4 |  | Underfloor Embedded Duct Modification for AFC Gates Line | สหชาติ |  |  | MDW-39278 | 2026-09-20 |  | 1
66 | SIG1 | DN01B1700051 | Lot01 | SIG | 1 |  | Test Track Shelters and Test Track Building | สหชาติ |  | Depot | MDW-39002 | 2026-06-22 |  | 3
67 | SIG2 | DN01B1700052 | Lot01 | SIG | 2 |  | Rearrangement of track crossing walkway at stabling yard to consistent with the layout of 4-car train parking | กำพล |  | Depot | MDW-39293 | 2026-06-22 |  | 1
68 | SIG3 | DN01B1700053 | Lot01 | SIG | 3 |  | Point Machine Foundation Construction | กำพล |  |  | MDW-39288 | 2026-08-21 |  | 1
69 | SIG4 | DN01B1700054 | Lot01 | SIG | 4 |  | Modification of Depot Track Route Line to Stabling Yard | สู่โชค |  | Depot | MDW-39001 | 2026-06-22 |  | 1
70 | SIG5 | DN01B1700055 | Lot01 | SIG | 5 |  | Strobe Light at Buffer Stops | ประธาน |  |  | MDW-39287 | 2026-08-21 |  | 1
71 | DWE1 | DN01B1800001 | Lot01 | DWE | 1 |  | Diesel Fuel Storage Tank for Maintenance Vehicle | สมศักดิ์ |  | Depot | DWE-39016 | 2026-09-20 |  | 1
72 | DWE2 | DN01B1800002 | Lot01 | DWE | 2 |  | Movable Height Maintenance Platform Vehicle (Boom Lift) | สมศักดิ์ |  | Depot | DWE-39011 | 2026-09-20 |  | 1
73 | DWE3 | DN01B1800003 | Lot01 | DWE | 3 |  | Fork Lift Vehicle | สมศักดิ์ |  | Depot | DWE-39012 | 2026-09-20 |  | 1
74 | DWE4 | DN01B1800004 | Lot01 | DWE | 4 |  | Compressed Air System and Portable Air Compressor for Depot | สมศักดิ์ |  | Depot | DWE-39015 | 2026-09-20 |  | 1
75 | DWE5 | DN01B1800005 | Lot01 | DWE | 5 |  | Pallet Storage Shelves in Hazardous Storage | สมศักดิ์ |  | Depot | DWE-39017 | 2026-09-20 |  | 0
76 | DWE6 | DN01B1800006 | Lot01 | DWE | 6 |  | Pallet Storage in Main Storage Room | สมศักดิ์ |  | Depot | DWE-39017 | 2026-09-20 |  | 6
77 | DWE7 | DN01B1800007 | Lot01 | DWE | 7 |  | Two-Tier Shelf | สมศักดิ์ |  | Depot | DWE-39017 | 2026-09-20 |  | 0
78 | DWE8 | DN01B1800008 | Lot01 | DWE | 8 |  | Tool Storage | สมศักดิ์ |  | Depot | DWE-39017 | 2026-09-20 |  | 0
79 | DWE9 | DN01B1800009 | Lot01 | DWE | 9 |  | Repair Equipment | สมศักดิ์ |  | Depot | DWE-39018 | 2026-09-20 |  | 1
80 | DWE10 | DN01B1800010 | Lot01 | DWE | 10 |  | Oil & Grease Disposal | สมศักดิ์ |  | Depot | DWE-39020 | 2026-09-20 |  | 1
81 | DWE11 | DN01B1800011 | Lot01 | DWE | 11 |  | Grease Dispensers | สมศักดิ์ |  | Depot | DWE-39020 | 2026-09-20 |  | 0
82 | DWE12 | DN01B1800012 | Lot01 | DWE | 12 |  | Waste Disposal | สมศักดิ์ |  | Depot | DWE-39020 | 2026-09-20 |  | 0
83 | DWE13 | DN01B1800013 | Lot01 | DWE | 13 |  | Safety Provision for Maintenance Pits | สหชาติ |  | Depot | MDW-39305 | 2026-09-20 |  | 2
84 | DWE14 | DN01B1800014 | Lot01 | DWE | 14 |  | Pit Drainage System in Main Workshop | สมศักดิ์ |  | Depot | DWE-39xxx | 2026-09-20 | CANCLE | 1
85 | DWE15 | DN01B1800015 | Lot01 | DWE | 15 |  | Provision of Civil Works and Building Services to support Train Washing Equipment | สหชาติ |  | Depot | DWE-39023 | 2026-08-01 |  | 1
86 | DWE16 | DN01B1800016 | Lot01 | DWE | 16 |  | Overhead Traveling Crane | สมศักดิ์ |  | Depot | DWE-39013 | 2026-09-20 |  | 3
87 | DWE17 | DN01B1800017 | Lot01 | DWE | 17 |  | Vehicle Inspection and Servicing Facilities | สมศักดิ์ |  | Depot | DWE-39009 | 2026-09-20 | Rail/Road Shunting Vehicel | 1
88 | DWE18 | DN01B1800018 | Lot01 | DWE | 18 |  | Permanent Way Maintenance Facility | สมศักดิ์ |  | Depot | DWE-39014 | 2026-09-20 | Trackwork Equipment and hand tools | 1
89 | DWE19 | DN01B1800019 | Lot01 | DWE | 19 |  | Permanent Way Vehicles | สมศักดิ์ |  | Depot | - | 2026-09-20 |  | 0
90 | DWE19.1 | DN01B1800019 | Lot01 | DWE | 19 | 1 | Shunting Locomotive | สมศักดิ์ |  | Depot | DWE-39001 | 2026-09-20 |  | 1
91 | DWE19.2 | DN01B1800019 | Lot01 | DWE | 19 | 2 | Tunnel Inspection and Cleaning Vehicle | สมศักดิ์ |  | Depot | DWE-39002 | 2026-09-20 |  | 1
92 | DWE19.3 | DN01B1800019 | Lot01 | DWE | 19 | 3 | Hi/Rail Maintenance Vehicle | สมศักดิ์ |  | Depot | DWE-39003 | 2026-09-20 |  | 1
93 | DWE19.4 | DN01B1800019 | Lot01 | DWE | 19 | 4 | Flat wagon | สมศักดิ์ |  | Depot | DWE-39004 | 2026-09-20 |  | 1
94 | DWE19.5 | DN01B1800019 | Lot01 | DWE | 19 | 5 | Re-railing Equipment | สมศักดิ์ |  | Depot | DWE-39005 | 2026-09-20 |  | 1
95 | DWE19.6 | DN01B1800019 | Lot01 | DWE | 19 | 6 | Self-Propelled Rail Based Inspection Vehicle | สมศักดิ์ |  | Depot | DWE-39006 | 2026-09-20 |  | 1
96 | DWE19.7 | DN01B1800019 | Lot01 | DWE | 19 | 7 | Rail Head Grinding Machine Vehicle | สมศักดิ์ |  | Depot | DWE-39007 | 2026-09-20 |  | 1
97 | DWE19.8 | DN01B1800019 | Lot01 | DWE | 19 | 8 | Multi Measuring Rail Vehicle | สมศักดิ์ |  | Depot | DWE-39008 | 2026-09-20 | CANCLE | 1
98 | DWE19.9 | DN01B1800019 | Lot01 | DWE | 19 | 9 | High Work Inspection Vehicle | สมศักดิ์ |  |  | DWE-39010 | 2026-09-20 | CANCLE | 1
99 | DWE20 | DN01B1800020 | Lot01 | DWE | 20 |  | Building Maintenance Vehicle | - |  |  | - | 2026-09-20 | CANCLE | 0
100 | PSY1 | DN01B1700061 | Lot01 | PSY | 1 |  | Diesel Fuel Storage Tanks for Power Generators | สมศักดิ์ |  |  | EPS-39001 | 2026-03-24 |  | 4
101 | PSY2 | DN01B1700062 | Lot01 | PSY | 2 |  | GIS and BSS Building and Other Facilities | สหชาติ |  |  | PSY-39001-9 | 2026-03-24 |  | 22
102 | PSY3 | DN01B1700063 | Lot01 | PSY | 3 |  | Steel Grating Raised Floor for EE Panel | สหชาติ |  |  | PSY-39011 | 2026-03-24 |  | 2 | สอบถามว่ายกเลิกไหม
103 | PSY4 | DN01B1700064 | Lot01 | PSY | 4 |  | Trapping Box between PSY Service Sub Station (SSS) and Low Volt (LV) System | - |  |  | - | 2026-08-21 | CANCLE | 0
104 | SCA1 | DN01B1700071 | Lot01 | SCA | 1 |  | Modification of BEMS to receive PSD Signal on East Section | ธารทิพย์ |  |  | SCA-39200 | 2026-08-21 | CANCLE | 0
105 | SCA2 | DN01B1700072 | Lot01 | SCA | 2 |  | Modification of Escalator Interface Point with CCTV and SCADA, East Section | - |  |  | - | 2026-08-21 | CANCLE | 0 | สอบถามว่ายกเลิกไหม
106 | SCA3 | DN01B1700073 | Lot01 | SCA | 3 |  | Magnetic of Fire Alarm System Interface Point with CCTV and SCADA | - |  |  | - | 2026-08-21 | CANCLE | 0
107 | SCA4 | DN01B1700074 | Lot01 | SCA | 4 |  | Add/Modify Civil Scada Hardwire for all Station | ประธาน/ธารทิพย์ |  |  | SCA-39203 | 2026-08-21 | CANCLE | 0
108 | COM1 | DN01B1700081 | Lot01 | COM | 1 |  | Magnetic Door Lock | มนตรี |  |  | COM-39200 | 2026-08-21 |  | 4
109 | COM2 | DN01B1700082 | Lot01 | COM | 2 |  | Intercom System in Cash Handling Room (if require) | บัณฑิต |  |  | MDW-39283 | 2026-12-19 |  | 1
110 | COM3 | DN01B1700083 | Lot01 | COM | 3 |  | Walk-Through Metal Detector System (WTMD), 1 per entrance | มนตรี |  |  | COM-39001 | 2026-11-19 |  | 3
111 | COM4 | DN01B1700084 | Lot01 | COM | 4 |  | Traveling Cable in all Lifts | มนตรี |  |  | MDW-39284 | - | CANCLE | 0
112 | COM5 | DN01B1700085 | Lot01 | COM | 5 |  | MEA Radio | ประธาน |  |  | MDW-39304 | 2026-09-20 |  | 1
113 | COM6 | DN01B1700086 | Lot01 | COM | 6 |  | Main Cable Containment for M&E Dedicated communication link to MRTA Head Quarter | มนตรี |  |  | COM-39004 | 2026-09-20 |  | 1
114 | COM7 | DN01B1700087 | Lot01 | COM | 7 |  | Mini Paging in Ticket Office | บัณฑิต |  |  | AFC-39001 | 2026-12-19 |  | 3
115 | COM8 | DN01B1700088 | Lot01 | COM | 8 |  | Provision of Cable Containment between OCC ORL and OCC BL | มนตรี |  |  | MDW-39285 | 2026-07-22 | CANCLE | 0
116 | COM9 | DN01B1700089 | Lot01 | COM | 9 |  | Power Distribution for M&E Systems at MRTA Head Quarter | มนตรี |  |  | COM-39005 | 2026-09-20 |  | 1
117 | COM10 | DN01B1700090 | Lot01 | COM | 10 |  | Underground Cable Containment at Public Areas (if require) | มนตรี |  |  | COM-39205 | 2026-08-21 |  | 0
118 | COM11 | DN01B1700091 | Lot01 | COM | 11 |  | Intercom at Ticket Issuing Machine | บัณฑิต |  |  | - | - | CANCLE | 0
119 | RST1 | DN01B1700101 | Lot01 | RST | 1 |  | Driver Training Simulator | ธัญวิทย์ |  |  | RST-39004,8 | 2026-09-20 |  | 5
120 | MO-CK1.1 | DN02B1710001 | Lot02 | MO-CK | 1 | 1 | Store Modification Works at Main Workshop - Civil&AR | สหชาติ | MWS | Depot | MDW-39500 | 2026-06-03 |  | 1
121 | MO-CK1.2 | DN02B1710001 | Lot02 | MO-CK | 1 | 2 | Store Modification Works at Main Workshop - Building Services | ประธาน | MWS | Depot | MDW-39501 | 2026-06-04 |  | 1
122 | MO-CK2 | DN02B1710002 | Lot02 | MO-CK | 2 |  | Modify room for MMC at Admin C 2 floor.(Corridor out of Lobby) | สหชาติ | Admin C | Depot | MDW-39503 | 2026-08-03 |  | 0
123 | MO-CK3 | DN02B1710003 | Lot02 | MO-CK | 3 |  | Move or link Workstation and control panel to MMC room at admin C 2nd floor | ประธาน | MWS | Depot | MDW-39504 | 2026-08-02 |  | 0
124 | MO-CK4 | DN02B1710004 | Lot02 | MO-CK | 4 |  | Bird & Rain Protection for Open space Admin C | สหชาติ | Admin | Depot | MDW-39543 | 2026-08-01 |  | 1
125 | MO-CK5 | DN02B1710005 | Lot02 | MO-CK | 5 |  | Relocate door in front of toilet and build partition wall to conceal the view in side of toilet | สหชาติ | OCC | Depot | MDW-39547 | 2026-08-02 |  | 1
126 | MO-CK6 | DN02B1710006 | Lot02 | MO-CK | 6 |  | Modify Lockset the emergency door to be used for passage between the 2nd and 3rd floors inside the building. | สหชาติ | OCC | Depot | MDW-39547 | 2026-08-03 |  | 0
127 | MO-CK7 | DN02B1710007 | Lot02 | MO-CK | 7 |  | Addition small power for lounge and pantry room at 2nd floor and Hall and observation room at 3nd floor | ประธาน | OCC | Depot | MDW-39556 | 2026-08-04 |  | 1
128 | MO-CK8 | DN02B1710008 | Lot02 | MO-CK | 8 |  | Air Condition for using store room to be pantry room. 2nd floor | ประธาน | OCC | Depot | MDW-39548 | 2026-08-05 |  | 1
129 | MO-CK9 | DN02B1710009 | Lot02 | MO-CK | 9 |  | Walk Way Hand rail high 90 cm 1 side (144 m. x 7 route) | สหชาติ | STB | Depot | MDW-39552 | 2026-10-01 |  | 1
130 | MO-CK10 | DN02B1710010 | Lot02 | MO-CK | 10 |  | Barbed wire fence Viaduct CE CW | บัณฑิต/สหชาติ | Depot slab | Depot | MDW-39544 | 2027-01-01 | ยกเลิก | 1
131 | MO-CK11 | DN02B1710011 | Lot02 | MO-CK | 11 |  | Chain Link at Cut & Cover 600m. | สหชาติ | Landscape Depot | Depot | MDW-39545 | 2026-06-01 | มีงานเพิ่ม | 1
132 | MO-CK12 | DN02B1710012 | Lot02 | MO-CK | 12 |  | Chain Link under slab high 1.70 m | สหชาติ | Landscape Depot | Depot | MDW-39546 | 2027-01-01 |  | 1
133 | MO-CK13.1 | DN02B1710013 | Lot02 | MO-CK | 13 | 1 | Satellite Store at OR21 - Civil & AR | สหชาติ | Station |  | MDW-39550 | 2027-01-02 |  | 1
134 | MO-CK13.2 | DN02B1710013 | Lot02 | MO-CK | 13 | 2 | Maintenance Room and Satellite Store at Stations - Building Services | ประธาน | Station |  | MDW-39549 | 2027-01-03 |  | 1
135 | MO-CK14 | DN02B1710014 | Lot02 | MO-CK | 14 |  | Modify Cleaner room at OR29 to be Train crew Standby office with facility system | ประธาน | Station |  | MDW-39551 | 2026-07-01 |  | 1
136 | MO-CK15.1 | DN02B1710015 | Lot02 | MO-CK | 15 | 1 | Epoxy Floor Installation and Curb Installation at the Entrance - Civil & AR | สหชาติ | Dangerous Goods | Depot | MDW-39295 | 2026-05-01 |  | 1
137 | MO-CK15.2 | DN02B1710015 | Lot02 | MO-CK | 15 | 2 | Change Electrical Equipment to be Explosion-proof type - Building Services | ประธาน | Dangerous Goods | Depot | MDW-39296 | 2026-05-01 |  | 1
138 | MO-CK16 | DN02B1710016 | Lot02 | MO-CK | 16 |  | Dangerous waste Storage 30 x 5 m. =10 room | สหชาติ | Dangerous Waste Storage | Depot | DWE-39024 | 2026-05-01 | รวมกับ GEN7.1 | 0
139 | MO-CK17 | DN02B1710017 | Lot02 | MO-CK | 17 |  | Safety Sign all Depot Area building | สหชาติ | Depot area | Depot |  | 2026-05-01 | รวมกับ GEN10 | 0
140 | MO-CK18 | DN02B1710018 | Lot02 | MO-CK | 18 |  | Emergency escape route map | สหชาติ | Depot area | Depot |  | 2027-01-01 | รวมกับ GEN10 | 0
141 | MO-CK19 | DN02B1710019 | Lot02 | MO-CK | 19 |  | Traffic Line Marking (Thermoplastic Paint) | สหชาติ | Depot slab | Depot |  | 2026-05-01 | รวมกับ GEN10 | 0
142 | MO-CK20 | DN02B1710020 | Lot02 | MO-CK | 20 |  | Emergency Car Parking location Painting in front of MWS | สหชาติ | Depot slab | Depot |  | 2026-05-01 | รวมกับ GEN10 | 0
143 | MO-CK21 | DN02B1710021 | Lot02 | MO-CK | 21 |  | Safety Line painting in MWS, Stabling Area, P-way, Track | สหชาติ | Depot slab | Depot | GRS-39022 | 2027-01-01 | รวมกับ GEN10 | 0
144 | MO-CK22 | DN02B1710022 | Lot02 | MO-CK | 22 |  | Fire escape stairs level signs in the Depot, VS and IVS areas | สหชาติ | Depot VS/IVS | Depot |  | 2027-01-01 | รวมกับ GEN10 | 0
145 | MO-CK23 | DN02B1710023 | Lot02 | MO-CK | 23 |  | General waste Storage 22 x 5 m | สหชาติ | General Waste Storage | Depot | DWE-39026 | 2026-05-01 | รวมกับ GEN8.1 | 0
146 | MO-CK24 | DN02B1710024 | Lot02 | MO-CK | 24 |  | Modify Traffic paint and traffic sign | สหชาติ | Landscape Admin | Depot |  | 2026-05-01 | รวมกับ GEN10 | 0
147 | MO-CK25 | DN02B1710025 | Lot02 | MO-CK | 25 |  | Station Area sign 28 stations | สหชาติ | Station |  |  | 2026-05-01 | รวมกับ GEN10 | 0
148 | MO-CK26 | DN02B1710026 | Lot02 | MO-CK | 26 |  | Safety and warning signage for lift and escalator at all station | สหชาติ | Station |  |  | 2027-01-01 | รวมกับ GEN10 | 0
149 | MO-CK27 | DN02B1710027 | Lot02 | MO-CK | 27 |  | Spike fence for Depot slab | สหชาติ | Depot slab | Depot | MDW-39532 | 2027-01-01 |  | 0
150 | MO-CK28 | DN02B1710028 | Lot02 | MO-CK | 28 |  | Bird net and Flashing at MWS and Skywalk to Stabling yard | สหชาติ | MWS | Depot |  | 2026-05-01 | ไม่มี | 0
151 | MO-CK29 | DN02B1710029 | Lot02 | MO-CK | 29 |  | Fire Alarm Manual Call Point signage at all elevated station | สหชาติ | Station |  | MDW-39541 | 2027-01-01 | Includeed in GRS Lot1 | 0
152 | MO-CK30 | DN02B1710030 | Lot02 | MO-CK | 30 |  | Lighting for sealed space under stairs and behind lift shaft at underground station | ประธาน | Station |  |  | 2027-01-01 |  | 0
153 | MO-CK31 | DN02B1710031 | Lot02 | MO-CK | 31 |  | Modify the access door of sealed space (under-stairs room) with a Sump Pump or ESPS cabinet | สหชาติ | Station |  |  | 2027-01-01 |  | 0
154 | MO-CK32 | DN02B1710032 | Lot02 | MO-CK | 32 |  | Lighting to the sealed space (under-stairs room) with a Sump Pump or ESPS cabinet | ประธาน | Station |  |  | 2027-01-01 |  | 0
155 | MO-CK33 | DN02B1710033 | Lot02 | MO-CK | 33 |  | Additional lighting in areas where the lux level does not meet occupational health standards | ประธาน | Station / Depot | Depot |  | 2027-01-01 |  | 0
156 | MO-CK34 | DN02B1710034 | Lot02 | MO-CK | 34 |  | Provide and install confined space signage for Station and Depot | สหชาติ | Station / Depot | Depot |  | 2027-01-01 |  | 0
157 | MO-CK35 | DN02B1710035 | Lot02 | MO-CK | 35 |  | Build room for Train crew main office at OR18 with office area, resting area, meeting room, pantry, toilet and locker room | สหชาติ/บัณฑิต/ประธาน | OR18 |  |  | - | ยกเลิก | 0
158 | MO-CK36 | DN02B1710036 | Lot02 | MO-CK | 36 |  | Dormitory Cable Containments (if any) | มนตรี | Depot | Depot |  | - | ยกเลิก | 0
159 | MO-CK37 | DN02B1710037 | Lot02 | MO-CK | 37 |  | Provide Raise floor and building Service in Training &Simulator (OCC Admin) | สหชาติ | OCC | Depot |  |  |  | 0
160 | MO-CK38 | DN02B1710038 | Lot02 | MO-CK | 38 |  | Add N2 in Playback and Training Room and Backup Control Room | บุญประเสริฐ | MWS | Depot |  |  |  | 0
161 | MO-BEM1.1 | DN02B1720001 | Lot02 | MO-BEM | 1 | 1 | Walkway from Main Work Shop to Stabling Area - Civil & AR | สหชาติ | MWS | Depot | MDW-39505 | 2026-08-02 |  | 3
162 | MO-BEM1.2 | DN02B1720001 | Lot02 | MO-BEM | 1 | 2 | Walkway from Main Work Shop to Stabling Area - Building Services | ประธาน | MWS | Depot | MDW-39506 | 2026-08-02 |  | 1
163 | MO-BEM2 | DN02B1720002 | Lot02 | MO-BEM | 2 |  | High Roof at Main Work Shop Entrance and Store | สหชาติ | MWS | Depot | MDW-39507 | 2026-08-01 |  | 2
164 | MO-BEM3 | DN02B1720003 | Lot02 | MO-BEM | 3 |  | High Roof at the entrance and exit of the under floor wheel lathe | สหชาติ | MWS | Depot | MDW-39509 | 2026-08-04 |  | 1
165 | MO-BEM4.1 | DN02B1720004 | Lot02 | MO-BEM | 4 | 1 | Maintenance Office Rooms at Main Workshop - Civil & AR | สหชาติ | MWS | Depot | MDW-39511 | 2026-07-03 |  | 2
166 | MO-BEM4.2 | DN02B1720004 | Lot02 | MO-BEM | 4 | 2 | Maintenance Office Rooms at Main Workshop - Building Services | ประธาน | MWS | Depot | MDW-39512 | 2026-07-04 |  | 1
167 | MO-BEM5 | DN02B1720005 | Lot02 | MO-BEM | 5 |  | Install Concrete car barrier along the walkway in front of MWS building | สหชาติ | Depot Slab | Depot | MDW-39513 | 2027-01-01 |  | 1
168 | MO-BEM6 | DN02B1720006 | Lot02 | MO-BEM | 6 |  | Handrail on top of the water tank on the rooftop of the Admin Building | สหชาติ | Admin | Depot |  | 2027-01-01 |  | 0
169 | MO-BEM7 | DN02B1720007 | Lot02 | MO-BEM | 7 |  | Modify maintenance service door to the roof building to easier access while maintaining safe operational standards | สหชาติ | Admin | Depot |  | 2027-01-01 |  | 0
170 | MO-BEM8 | DN02B1720008 | Lot02 | MO-BEM | 8 |  | Company logo and Central Control Room sign in CCR room. | สหชาติ | OCC | Depot | MDW-39536 | 2026-05-01 |  | 1
171 | MO-BEM9 | DN02B1720009 | Lot02 | MO-BEM | 9 |  | Soundproof insulation on the wall and structure and equipment in the CCR room. | สหชาติ | OCC | Depot | MDW-39536 | 2026-05-01 |  | 0
172 | MO-BEM10 | DN02B1720010 | Lot02 | MO-BEM | 10 |  | Relocate Fire Hose Cabinet to be outside of the clearance gauge zone 17 set | ประธาน | STB | Depot | MDW-39526 | 2026-05-01 |  | 1
173 | MO-BEM11.1 | DN02B1720011 | Lot02 | MO-BEM | 11 | 1 | Washing Area in Cleaning Staff Room at Stabling Yard - Civil & AR | สหชาติ | STB | Depot | MDW-39528 | 2026-08-03 |  | 1
174 | MO-BEM11.2 | DN02B1720011 | Lot02 | MO-BEM | 11 | 2 | Washing Area in Cleaning Staff Room at Stabling Yard - Building Services | ประธาน | STB | Depot | MDW-39529 | 2026-08-04 |  | 1
175 | MO-BEM12 | DN02B1720012 | Lot02 | MO-BEM | 12 |  | Rain protection for Water treatment Building | สหชาติ | WWTP | Depot | MDW-39522 | 2026-08-05 |  | 1
176 | MO-BEM13.1 | DN02B1720013 | Lot02 | MO-BEM | 13 | 1 | Zero Discharge Water treatment in Depot - Civil & AR | สหชาติ | WWTP | Depot | MDW-39522 | 2027-01-01 | @ เพิ่มใน MS Project | 0
177 | MO-BEM13.2 | DN02B1720013 | Lot02 | MO-BEM | 13 | 2 | Zero Discharge Water treatment in Depot - Building Services | ประธาน | WWTP | Depot | MDW-39530 | 2027-01-01 | @ เพิ่มใน MS Project | 1
178 | MO-BEM14.1 | DN02B1720014 | Lot02 | MO-BEM | 14 | 1 | Modification Works : Walkway Bridge between BL Depot and ORL Depot - Civil & AR | สหชาติ | Landscape Admin | Depot | MDW-39516 | 2026-08-02 |  | 1
179 | MO-BEM14.2 | DN02B1720014 | Lot02 | MO-BEM | 14 | 2 | Modification Works : Walkway Bridge between BL Depot and ORL Depot - Building Services | ประธาน | Landscape Admin | Depot | MDW-39517 | 2026-08-03 |  | 1
180 | MO-BEM15.1 | DN02B1720015 | Lot02 | MO-BEM | 15 | 1 | Roof for cars parking lots area (184 car)t - Civil & AR | สหชาติ | Landscape Admin | Depot | MDW-39514 | 2026-08-03 |  | 1
181 | MO-BEM15.2 | DN02B1720015 | Lot02 | MO-BEM | 15 | 2 | Roof for cars parking lots area (184 car) - Building Services | ประธาน | Landscape Admin | Depot | MDW-39515 | 2026-08-03 |  | 1
182 | MO-BEM16 | DN02B1720016 | Lot02 | MO-BEM | 16 |  | Walkway roof and High roof across the road from Admin ORL to Depot slap | สหชาติ | Landscape Admin | Depot | MDW-39519 | 2026-08-01 |  | 1
183 | MO-BEM17 | DN02B1720017 | Lot02 | MO-BEM | 17 |  | Walkway roof to car park in front of admin ORL(3x5m.) | สหชาติ | Landscape Admin | Depot | MDW-39519 | 2026-08-01 | Includeed under Item MO-BEM16 | 0
184 | MO-BEM18 | DN02B1720018 | Lot02 | MO-BEM | 18 |  | Walkway roof over the footpath near depot slab (1.50 m. x 290 m.) and stair up to depot slap. | สหชาติ | Depot Slab | Depot | MDW-39519 | 2026-08-01 | Includeed under Item MO-BEM16 | 0
185 | MO-BEM19 | DN02B1720019 | Lot02 | MO-BEM | 19 |  | Install Chain Link fence to enclose parking area | สหชาติ | Landscape Admin | Depot | MDW-39557 | 2026-10-01 | Includeed under Item MO-BEM25.1 | 0
186 | MO-BEM20 | DN02B1720020 | Lot02 | MO-BEM | 20 |  | Hose bib 1/2" 4 sets for Tree around Admin area | ประธาน | Depot area | Depot | MDW-39523 | 2026-06-01 |  | 1
187 | MO-BEM21 | DN02B1720021 | Lot02 | MO-BEM | 21 |  | Relocate Security Guard Box at Front Gate and Install Roof 3x5m. | สหชาติ | Landscape Admin | Depot | - | 2027-01-03 | รวมกับ MO-BEM52 | 0
188 | MO-BEM21.1 | DN02B1720053 | Lot02 | MO-BEM | 21 | 1 | Modification Works : Security Guard Box at ORL Depot Entrance - Civil & AR | สหชาติ | Landscape Admin | Depot | MDW-39534 | 2027-01-02 | @ เพิ่มใน MS Project | 2
189 | MO-BEM21.2 | DN02B1720053 | Lot02 | MO-BEM | 21 | 2 | Modification Works : Security Guard Box at ORL Depot Entrance - Building Services | ประธาน | Landscape Admin | Depot | MDW-39535 | 2027-01-03 | @ เพิ่มใน MS Project | 1
190 | MO-BEM22 | DN02B1720022 | Lot02 | MO-BEM | 22 |  | Addition Spike fence for MRTA fence and Chain link at Klong Chourdyai 400m. | สหชาติ | Depot ORL | Depot | MDW-39532 | 2027-01-01 |  | 1
191 | MO-BEM23 | DN02B1720023 | Lot02 | MO-BEM | 23 |  | Hand sink with eye wash station | ประธาน | Depot Slab | Depot | MDW-39527 | 2027-01-01 |  | 1
192 | MO-BEM24 | DN02B1720024 | Lot02 | MO-BEM | 24 |  | Guard rail protection for Fire Hose Cabinet 8 set | สหชาติ | Depot Slab | Depot | MDW-39531 | 2026-06-01 |  | 1
193 | MO-BEM25.1 | DN02B1720025 | Lot02 | MO-BEM | 25 | 1 | Chain Link Fence to divide controlled areas on Depot slab 3 m.x 485 m. - Civil & AR | สหชาติ | Depot Slab | Depot | MDW-39557 | 2026-10-01 |  | 1
194 | MO-BEM25.2 | DN02B1720025 | Lot02 | MO-BEM | 25 | 2 | Chain Link Fence to divide controlled areas on Depot slab 3 m.x 485 m.- Building Services | ประธาน | Depot Slab | Depot | MDW-39520 | 2026-10-01 |  | 1
195 | MO-BEM26 | DN02B1720026 | Lot02 | MO-BEM | 26 |  | Street Lighting system area between MRTA Fence and Depot slab | ประธาน | Landscape Depot | Depot | MDW-39518 | 2026-08-01 |  | 1
196 | MO-BEM27 | DN02B1720027 | Lot02 | MO-BEM | 27 |  | Compacted gravel walkway along the Test Track OR-BL 1.2 m. | สหชาติ |  | Depot | - | 2027-01-01 |  | 0
197 | MO-BEM28.1 | DN02B1720028 | Lot02 | MO-BEM | 28 | 1 | Walkway under Depot Slab for Maintenance Service - Civil & AR | สหชาติ | Depot area | Depot | MDW-39524 | 2027-01-02 |  | 1
198 | MO-BEM28.2 | DN02B1720028 | Lot02 | MO-BEM | 28 | 2 | Walkway under Depot Slab for Maintenance Service - Building Services | ประธาน | Depot area | Depot | MDW-39525 | 2027-01-03 |  | 1
199 | MO-BEM29 | DN02B1720029 | Lot02 | MO-BEM | 29 |  | Walkway Bridge across the canal for Depot area inspection patrols 3 location | สหชาติ | Landscape Depot | Depot | MDW-39521 | 2027-01-01 |  | 1
200 | MO-BEM30 | DN02B1720030 | Lot02 | MO-BEM | 30 |  | Cut down trees between Depot BL+ORL and MRTA Fence | สหชาติ | Landscape Depot | Depot | - | 2027-01-01 |  | 0
201 | MO-BEM31 | DN02B1720031 | Lot02 | MO-BEM | 31 |  | Provide facility system and interface to MMC room (Fire Alarm / CCTV / VMS / TEL / CASS / Radio / PA) | บัณฑิต | Dormitory | Depot |  | 2026-10-01 | ยกเลิก | 0
202 | MO-BEM32 | DN02B1720032 | Lot02 | MO-BEM | 32 |  | Stainless Guard rail balustrade for waiting area | สหชาติ | Dormitory | Depot | - | 2026-05-01 | ยกเลิก | 0
203 | MO-BEM33 | DN02B1720033 | Lot02 | MO-BEM | 33 |  | Concrete walkway 2 x 80 m. For fire escape route | สหชาติ | Dormitory | Depot | - | 2026-05-01 | ยกเลิก | 0
204 | MO-BEM34 | DN02B1720034 | Lot02 | MO-BEM | 34 |  | Access Gate (Full Height Turnstile) at 1st floor admin ORL | บัณฑิต | Landscape Admin | Depot | - | 2027-01-01 |  | 0
205 | MO-BEM35 | DN02B1720035 | Lot02 | MO-BEM | 35 |  | Access Gate (Tripod with Swing Gate) at MWS Entrance | บัณฑิต | MWS | Depot | - | 2027-01-01 |  | 0
206 | MO-BEM36 | DN02B1720036 | Lot02 | MO-BEM | 36 |  | Access Gate (Tripod with Swing Gate) at Admin 2nd floor connect to OCC | บัณฑิต | Landscape Admin | Depot | - | 2027-01-01 |  | 0
207 | MO-BEM37 | DN02B1720037 | Lot02 | MO-BEM | 37 |  | Access Gate (Tripod with Swing Gate) on Klong Chourdyai bridge | บัณฑิต | Landscape Admin | Depot | - | 2027-01-01 |  | 0
208 | MO-BEM38 | DN02B1720038 | Lot02 | MO-BEM | 38 |  | Access Gate (Tripod with roof covering) at parking lot OCC | บัณฑิต | Landscape Admin | Depot | - | 2027-01-01 |  | 0
209 | MO-BEM39 | DN02B1720039 | Lot02 | MO-BEM | 39 |  | Access Gate (Tripod with roof covering) at Stair up to Depot slab | บัณฑิต | Landscape Admin | Depot | - | 2027-01-01 |  | 0
210 | MO-BEM40 | DN02B1720040 | Lot02 | MO-BEM | 40 |  | Access Control (2 Factors, Card + Finger Print) at High Security rooms - CCR/PTR/Store | บัณฑิต | OCC/MWS | Depot | - | 2027-01-01 |  | 0
211 | MO-BEM41 | DN02B1720041 | Lot02 | MO-BEM | 41 |  | Link CCTV Landscape of all depot ORL area for MMC BL monitoring. | บัณฑิต | Depot ORL | Depot | - | 2027-01-01 | จัดจ้าง STE | 0
212 | MO-BEM42 | DN02B1720042 | Lot02 | MO-BEM | 42 |  | Fire Suppression Control Panel Cover which located in tunnel | สู่โชค | Station |  | - | 2027-01-01 | ยกเลิก | 0
213 | MO-BEM43 | DN02B1720043 | Lot02 | MO-BEM | 43 |  | Handrails for ladder at IVS and Vent buildings | สหชาติ | IVS / Vent |  | MDW-39537 | 2026-09-01 |  | 1
214 | MO-BEM44 | DN02B1720044 | Lot02 | MO-BEM | 44 |  | Escalator Anti-Slide device for all station. | สหชาติ | Station |  | MDW-39538 | 2026-09-01 |  | 1
215 | MO-BEM45 | DN02B1720045 | Lot02 | MO-BEM | 45 |  | Roof for control panel on vent building | สหชาติ | Station |  | MDW-39539 | 2027-01-01 |  | 0
216 | MO-BEM46 | DN02B1720046 | Lot02 | MO-BEM | 46 |  | Provide Standing plate or ladder to access the Fire Valve in at Omega points for all underground stations. | สหชาติ | Station |  | MDW-39553 | 2027-01-01 |  | 1
217 | MO-BEM47 | DN02B1720047 | Lot02 | MO-BEM | 47 |  | Water drop protection above UPS cabinet at station and Depot | สหชาติ | Station / Depot | Depot | MDW-39540 | 2027-01-01 |  | 1
218 | MO-BEM48 | DN02B1720048 | Lot02 | MO-BEM | 48 |  | Fire alarm manual call point cover in public area at all station | ประธาน | Station |  | MDW-39541 | 2027-01-01 |  | 1
219 | MO-BEM49 | DN02B1720049 | Lot02 | MO-BEM | 49 |  | Emergency stop button cover for escalator at all station. | สหชาติ | Station |  | MDW-39542 | 2027-01-01 |  | 1
220 | MO-BEM50 | DN02B1720050 | Lot02 | MO-BEM | 50 |  | Modify maintenance service door to the roof of OR13 vent building to easier access while maintaining safe operational standards | สู่โชค | Station |  |  | 2027-01-01 |  | 1
221 | MO-BEM51 | DN02B1720051 | Lot02 | MO-BEM | 51 |  | Modify existing car park to be 220 motorcycle parking lots including floor painting and parking roof | สหชาติ | Landscape Admin | Depot | MDW-39514 | 2026-08-01 |  | 0
222 | MO-BEM52 | DN02B1720052 | Lot02 | MO-BEM | 52 |  | Modify the sidewalk for temporary parking at entrance | สหชาติ | Landscape Admin | Depot | MDW-39534 | 2027-01-01 | รวมกับ MO-BEM21.1 | 0
223 | MO-BEM53.1 | DN02B1720053 | Lot02 | MO-BEM | 53 | 1 | Modification Works : Security Guard Box at OCC Parking Area - Civil & AR | สหชาติ | Landscape Admin | Depot | MDW-39554 | 2027-01-02 | @ เพิ่มใน MS Project | 1
224 | MO-BEM53.2 | DN02B1720053 | Lot02 | MO-BEM | 53 | 2 | Modification Works : Security Guard Box at OCC Parking Area - Building Services | ประธาน | Landscape Admin | Depot | MDW-39555 | 2027-01-02 | @ เพิ่มใน MS Project | 1
225 | MO-BEM54 | DN02B1720054 | Lot02 | MO-BEM | 54 |  | Strengthen the Maintenance Walkway of the TEF fan | สหชาติ | Station |  | NoDrawing | 2027-01-01

## 01 Summary
[11 empty] | D | 10% |  | P | 10% |  | M | 10% |  | C&I | 60% |  | T | 5% |  | TP | 1% |  | I | 1% |  | TR | 3% |  |  | 100%
[11 empty] | Design |  |  | Procurement |  |  | Manufacturing / Delivery Process |  |  | Construction/Installation |  |  | T&C |  |  | Test Procedure |  |  | Inspection |  |  | Test Report | [8 empty] | CV/AR | E&M | CV/AR+E&M
| No. | Design Submission | Lot No. | Code | System | Activity Name | CK Responsible Person | Priority | Location | Expected Completion Month | Design (PLAN) | Design (%) | Design (Status) | Procurement (PLAN) | Procurement (%) | Procurement (Status) | Manufacturing / Delivery Process (PLAN) | Manufacturing / Delivery Process (%) | Manufacturing / Delivery (Status) | Construction /Installation (PLAN) | Construction /Installation (%) | Construction /Installation (Status) | T&C (PLAN) | T&C (%) | T&C (Status) | Test Procedure (PLAN) | Test Procedure (%) | Test Procedure (Status) | Inspection (PLAN) | Inspection (%) | Inspection (Status) | Test Report (PLAN) | Test Report (%) | Test Report (Status) | Forecast Finish | Overall (%) | Overall (Status) | Note | remark | Detail |  | แผนก |  | de | pro | re
1 | 1 | MDW-39246-60 | Lot01 | GEN1 | GEN | Rooms and Building Service Systems Modification in Stations Area | - |  |  | 2026-08-01 | [26 empty] | Late |  | 0 |  | #REF! |  |  | MDW-39246 | MDW-69259 | MDW-69260
2 | 2 | MDW-39246 | Lot01 | GEN1.1 | GEN | Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR13 - OR17 | ประธาน |  |  | 2026-08-01 | 2026-01-30 | 100% | Completed | 2026-03-01 | 100% | Completed |  |  |  | 2026-03-31 | 100% | Completed |  |  |  | 2026-09-30 | 100% | Completed | 2026-10-31 | 100% | Completed | 2026-10-31 | 0% | On Schedule |  | 96.47% | Late |  | 0 | เพิ่มปลั๊ก ที่ห้อง SOR/Ticket Office/Cash handling room |  |  |  | MDW-39246 | MDW-69259 | MDW-69260
3 | 3 | MDW-39247 | Lot01 | GEN1.2 | GEN | Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR18 - OR22 | ประธาน |  |  | 2026-08-01 | 2025-12-30 | 100% | Completed | 2026-01-29 | 100% | Completed |  |  |  | 2026-02-28 | 100% | Completed |  |  |  | 2026-09-30 | 100% | Completed | 2026-10-31 | 100% | Completed | 2026-10-31 | 0% | On Schedule |  | 96.47% | Late |  | 0 | เพิ่มปลั๊ก ที่ห้อง SOR/Ticket Office/Cash handling room |  |  |  | MDW-39247 | MDW-69259 | MDW-69261
4 | 4 | MDW-39248 | Lot01 | GEN1.3 | GEN | Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR23 - OR29 | ประธาน |  |  | 2026-08-01 | 2026-01-30 | 100% | Completed | 2026-03-01 | 100% | Completed |  |  |  | 2026-03-31 | 100% | Completed |  |  |  | 2026-09-30 | 100% | Completed | 2026-10-31 | 100% | Completed | 2026-10-31 | 0% | On Schedule |  | 96.47% | Late |  | 0 | เพิ่มปลั๊ก ที่ห้อง SOR/Ticket Office/Cash handling room |  |  |  | MDW-39248 | MDW-69259 | MDW-69262
5 | 5 | MDW-39252 | Lot01 | GEN1.4 | GEN | Modification of Fire Suppression System (N2) in Commerial Room at OR14 | ประธาน |  |  | 2026-08-01 | 2025-12-30 | 100% | Completed | 2026-01-29 | 100% | Completed |  |  |  | 2026-02-28 | 100% | Completed |  |  |  | 2026-09-30 | 100% | Completed | 2026-10-31 | 100% | Completed | 2026-10-31 | 0% | On Schedule |  | 96.47% | Late |  | 0 |  |  |  |  | MDW-39252 | MDW-69269 | MDW-69270
6 | 6 | MDW-39253 | Lot01 | GEN1.5 | GEN | Modification of Civil Work in Telecommunication Room at OR14 | สหชาติ |  |  | 2026-08-01 | 2025-12-30 | 100% | Completed | 2026-01-29 | 100% | Completed |  |  |  | 2026-02-28 | 100% | Completed |  |  |  | 2026-09-30 | 100% | Completed |  |  |  | 2026-10-31 | 0% | On Schedule |  | 96.43% | Late |  | 0 |  |  |  |  | MDW-39253 | MDW-69271 | MDW-69272
7 | 7 | MDW-39254 | Lot01 | GEN1.6 | GEN | Modification in Staff Mess Room at OR13-OR17 | ประธาน |  |  | 2026-08-01 | 2026-01-30 | 100% | Completed | 2026-03-01 | 100% | Completed |  |  |  | 2026-03-31 | 100% | Completed |  |  |  | 2026-09-30 | 100% | Completed | 2026-10-31 | 100% | Completed | 2026-10-31 | 0% | On Schedule |  | 96.47% | Late |  | 0 |  |  |  |  | MDW-39254 | MDW-69273 | MDW-69274
8 | 8 | MDW-39255 | Lot01 | GEN1.7 | GEN | Modification in Staff Mess Room at OR18-OR22 | ประธาน |  |  | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed |  |  |  | 2026-09-30 | 100% | Completed |  |  |  | 2026-09-30 | 100% | Completed | 2026-10-31 | 0% | On Schedule | 2026-10-31 | 0% | On Schedule |  | 95.29% | Late |  | งานจบ ส่ง TP แล้ว |  |  |  |  | MDW-39255 | MDW-69273 | MDW-69275
9 | 9 | MDW-39256 | Lot01 | GEN1.8 | GEN | Modification in Staff Mess Room at OR23-OR29 | ประธาน |  |  | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed |  |  |  | 2026-09-30 | 100% | Completed |  |  |  | 2026-09-30 | 100% | Completed | 2026-11-30 | 0% | On Schedule | 2026-10-31 | 0% | On Schedule |  | 95.29% | Late | [6 empty] | MDW-39256 | MDW-69273 | MDW-69276
10 | 10 | MDW-39257 | Lot01 | GEN1.9 | GEN | Modification of Air Conditioning in CER and SER at OR13-OR19 | ประธาน |  |  | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed |  |  |  | 2026-09-30 | 99% | Late |  |  |  | 2026-09-30 | 100% | Completed | 2026-11-30 | 0% | On Schedule | 2026-10-31 | 0% | On Schedule |  | 94.59% | Late | [6 empty] | MDW-39257 | MDW-69277 | MDW-69278
11 | 11 | MDW-39258 | Lot01 | GEN1.10 | GEN | Modification of Air Conditioning in CER and SER at OR20-OR22 | ประธาน |  |  | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed |  |  |  | 2026-09-30 | 99% | Late |  |  |  | 2026-09-30 | 100% | Completed | 2026-11-30 | 0% | On Schedule | 2026-10-31 | 0% | On Schedule |  | 94.59% | Late |  | 0 |  |  |  |  | MDW-39258 | MDW-69277 | MDW-69279
12 | 12 | MDW-39259 | Lot01 | GEN1.11 | GEN | Modification of Air Conditioning in CER and SER at OR23-OR29 | ประธาน |  |  | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed |  |  |  | 2026-09-30 | 99% | Late |  |  |  | 2026-09-30 | 100% | Completed | 2026-11-30 | 0% | On Schedule | 2026-10-31 | 0% | On Schedule |  | 94.59% | Late |  | 0 |  |  |  |  | MDW-39259 | MDW-69277 | MDW-69280
13 | 13 | MDW-39272 | Lot01 | GEN1.12 | GEN | Modification of New M&E Room at IVS15 - IVS17 Civil & AR | สหชาติ |  |  | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed |  |  |  | 2026-09-30 | 100% | Completed |  |  |  | 2026-09-30 | 100% | Completed |  |  |  | 2026-10-31 | 0% | On Schedule |  | 96.43% | Late |  | 0 |  |  |  |  | MDW-39272 | MDW-69299 | MDW-69300
14 | 14 | MDW-39273 | Lot01 | GEN1.13 | GEN | Modification of New M&E UPS Room at IVS15-IVS17 - Building Services | ประธาน |  |  | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed |  |  |  | 2026-09-30 | 99% | Late |  |  |  | 2026-09-30 | 100% | Completed | 2026-11-30 | 0% | On Schedule | 2026-10-31 | 0% | On Schedule |  | 94.59% | Late |  | 0 |  |  |  |  | MDW-39273 | MDW-69301 | MDW-69302
15 | 15 | MDW-39294 | Lot01 | GEN1.14 | GEN | Provision of Architectural Work in new M&E UPS room at OR23 | สหชาติ |  |  | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed |  |  |  | 2026-09-30 | 100% | Completed |  |  |  | 2026-09-30 | 100% | Completed |  |  |  | 2026-10-31 | 0% | On Schedule |  | 96.43% | Late |  | 0 |  |  |  |  | MDW-39294 | MDW-69339 | MDW-69340
16 | 16 | MDW-39299 | Lot01 | GEN1.15 | GEN | Provision of Air Conditioning System in Commercial Room at OR13-OR19 | ประธาน |  |  | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed |  |  |  | 2026-09-30 | 100% | Completed |  |  |  | 2026-09-30 | 100% | Completed | 2026-10-31 | 0% | On Schedule | 2026-10-31 | 0% | On Schedule |  | 95.29% | Late |  | 0 |  |  |  |  | MDW-39299 | MDW-69349 | MDW-69350
17 | 17 | MDW-39306 | Lot01 | GEN1.16 | GEN | Modification CER and First Aid Room at OR14 - Building Services | ประธาน |  |  | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed |  |  |  | 2026-09-30 | 100% | Completed |  |  |  | 2026-09-30 | 100% | Completed | 2026-10-31 | 100% | Completed | 2026-10-31 | 0% | On Schedule |  | 96.47% | Late |  | 0 |  |  |  |  | MDW-39306 | MDW-69363 | MDW-69364
18 | 18 | MDW-39307 | Lot01 | GEN1.17 | GEN | Additional Fence at Back of House OR13 - OR22 and IVS East Section | สหชาติ |  |  | 2026-08-01 | 2026-09-30 | 100% | Completed | 2026-10-31 | 50% | On Schedule |  |  |  | 2026-12-31 | 0% | On Schedule |  |  |  | 2026-09-30 | 100% | Completed |  |  |  | 2027-01-30 | 0% | On Schedule |  | 19.05% | Late |  | 0 |  |  |  |  | MDW-39307 | MDW-69365 | MDW-69366
19 | 19 | MDW-39249 | Lot01 | GEN1.18 | GEN | SOR Counter and Workstation Hanging Support Installation on East Section | สหชาติ |  |  | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed |  |  |  | 2026-09-30 | 100% | Completed |  |  |  | 2026-09-30 | 100% | Completed |  |  |  | 2026-10-31 | 0% | On Schedule |  | 96.43% | Late |  |  | เพิ่ม Counter และ Workstation Hanging Support ที่ SOR at all Station |  |  |  | MDW-39249 | MDW-69263 | MDW-69264
20 | 20 | MDW-39250 | Lot01 | GEN1.19 | GEN | Ticket Office Modification on East Section | สหชาติ |  |  | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed |  |  |  | 2026-09-30 | 100% | Completed |  |  |  | 2026-09-30 | 100% | Completed |  |  |  | 2026-10-31 | 0% | On Schedule |  | 96.43% | Late |  | 0 | ปรับ Raise floor เพื่อเพิ่มช่องว่างระหว่าง Counter กับพื้นให้ได้ 65cm. (รวมความสูงจากบนCounterถึงพื้นคือ75cm) ทำ Counter ใหม่ให้ได้ระดับกับ Raise floor (รวมรื้อ Counterเดิมออก) |  |  |  | MDW-39250 | MDW-69265 | MDW-69266
21 | 21 | MDW-39261 | Lot01 | GEN2 | GEN | Rooms and Building Service Systems Modification in Depot Area | - |  | Depot | 2026-08-01 | [28 empty] | 0 |  | #REF! |  |  | MDW-39261 | MDW-69283 | MDW-69284
22 | 22 | MDW-39260 | Lot01 | GEN2.1 | GEN | Modification of Air Conditioning in M&E Room at OCC Building | ประธาน |  |  | 2026-08-01 | 2025-12-30 | 100% | Completed | 2026-01-29 | 100% | Completed |  |  |  | 2026-02-28 | 100% | Completed |  |  |  | 2026-09-30 | 100% | Completed | 2026-10-31 | 100% | Completed | 2026-10-31 | 0% | On Schedule |  | 96.47% | Late | [6 empty] | MDW-39260 | MDW-69281 | MDW-69282
23 | 23 | MDW-39261 | Lot01 | GEN2.2 | GEN | Provision of UPS for MDB Control at Main Workshop, OCC Building, Admin Building, Stabling Yard and Train Washing Plant | ประธาน |  |  | 2026-08-01 | 2026-09-01 | 100% | Completed | 2026-10-01 | 100% | Completed |  |  |  | 2026-10-31 | 90% | On Schedule |  |  |  | 2026-09-30 | 100% | Completed | 2026-10-31 | 0% | On Schedule | 2026-11-30 | 0% | On Schedule |  | 88.24% | Late |  |  | Add small UPS for MDB Control at MMW/OCC/Admin/Stabling/Train Washing Plant |  |  |  | MDW-39261 | MDW-69283 | MDW-69284
24 | 24 | MDW-39262 | Lot01 | GEN2.3 | GEN | Provision of Redundant MDB at OCC Building, Admin Building and Canteen | ประธาน |  |  | 2026-08-01 | 2026-09-01 | 100% | Completed | 2026-10-01 | 100% | Completed |  |  |  | 2026-10-31 | 95% | On Schedule |  |  |  | 2026-09-30 | 100% | Completed | 2026-10-31 | 0% | On Schedule | 2026-11-30 | 0% | On Schedule |  | 91.76% | Late | [6 empty] | MDW-39262 | MDW-69285 | MDW-69286
25 | 25 | MDW-39263 | Lot01 | GEN2.4 | GEN | Additonal Lighting System at Depot Area | ประธาน |  |  | 2026-08-01 | 2026-04-01 | 100% | Completed | 2026-05-01 | 100% | Completed |  |  |  | 2026-05-31 | 100% | Completed |  |  |  | 2026-09-30 | 100% | Completed | 2026-10-31 | 100% | Completed | 2026-10-31 | 0% | On Schedule |  | 96.47% | Late | [6 empty] | MDW-39263 | MDW-69287 | MDW-69288
26 | 26 | MDW-39290 | Lot01 | GEN2.5 | GEN | Modification Room for PSY at Depot Buildings - Building Services | ประธาน |  |  | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed |  |  |  | 2026-09-30 | 100% | Completed |  |  |  | 2026-09-30 | 100% | Completed | 2026-10-31 | 0% | On Schedule | 2026-10-31 | 0% | On Schedule |  | 95.29% | Late | [6 empty] | MDW-39290 | MDW-69331 | MDW-69332
27 | 27 | MDW-39300 | Lot01 | GEN2.6 | GEN | Modification SIG-PSD Office at Main Workshop - Building Services | ประธาน |  |  | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed |  |  |  | 2026-09-30 | 100% | Completed |  |  |  | 2026-09-30 | 100% | Completed | 2026-10-31 | 0% | On Schedule | 2026-10-31 | 0% | On Schedule |  | 95.29% | Late | [6 empty] | MDW-39300 | MDW-69351 | MDW-69352
28 | 28 | MDW-39301 | Lot01 | GEN2.7 | GEN | Modification Backup CCR Room at Main Workshop - Building Services | ประธาน |  |  | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed |  |  |  | 2026-09-30 | 100% | Completed |  |  |  | 2026-09-30 | 100% | Completed | 2026-10-31 | 0% | On Schedule | 2026-10-31 | 0% | On Schedule |  | 95.29% | Late | [6 empty] | MDW-39301 | MDW-69353 | MDW-69354
29 | 29 | MDW-39302 | Lot01 | GEN2.8 | GEN | Modification SER at Main Workshop - Building Services | ประธาน |  |  | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed |  |  |  | 2026-09-30 | 100% | Completed |  |  |  | 2026-09-30 | 100% | Completed | 2026-10-31 | 0% | On Schedule | 2026-10-31 | 0% | On Schedule |  | 95.29% | Late | [6 empty] | MDW-39302 | MDW-69355 | MDW-69356
30 | 30 | MDW-39303 | Lot01 | GEN2.9 | GEN | Modification CER & SCADA Room at Main Workshop - Building Services | ประธาน |  |  | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed |  |  |  | 2026-09-30 | 100% | Completed |  |  |  | 2026-09-30 | 100% | Completed | 2026-10-31 | 0% | On Schedule | 2026-10-31 | 0% | On Schedule |  | 95.29% | Late | [6 empty] | MDW-39303 | MDW-69357 | MDW-69358
31 | 31 | MDW-39309 | Lot01 | GEN2.10 | GEN | Modification Air Conditioning System at CCR | ประธาน |  |  | 2026-08-01 | 2026-10-01 | 100% | Completed | 2026-10-31 | 100% | Completed |  |  |  | 2026-12-31 | 80% | On Schedule |  |  |  | 2026-09-30 | 100% | Completed | 2026-10-31 | 0% | On Schedule | 2027-01-30 | 0% | On Schedule |  | 81.18% | Late | [6 empty] | MDW-39309 | MDW-69369 | MDW-69370
32 | 32 | MDW-39312 | Lot01 | GEN2.11 | GEN | Modification Electronic Workshop at Main Workshop - Building Services | ประธาน |  |  | 2026-08-01 | 2026-10-31 | 100% | Completed | 2026-11-30 | 100% | Completed |  |  |  | 2026-12-31 | 0% | On Schedule |  |  |  | 2026-11-30 | 0% | On Schedule | 2026-10-31 | 0% | On Schedule | 2027-01-30 | 0% | On Schedule |  | 23.53% | Late | [6 empty] | MDW-39312 | MDW-69375 | MDW-69376
33 | 33 | MDW-39313 | Lot01 | GEN2.12 | GEN | Modification Battery Charger Room at Main Workshop - Building Services | ประธาน |  |  | 2026-08-01 | 2026-10-31 | 100% | Completed | 2026-11-30 | 100% | Completed |  |  |  | 2026-12-31 | 0% | On Schedule |  |  |  | 2026-11-30 | 0% | On Schedule | 2026-10-31 | 0% | On Schedule | 2027-01-30 | 0% | On Schedule |  | 23.53% | Late | [6 empty] | MDW-39313 | MDW-69377 | MDW-69378
34 | 34 | MDW-39314 | Lot01 | GEN2.13 | GEN | Modification Machining Room at Main Workshop - Building Services | ประธาน |  |  | 2026-08-01 | 2026-10-31 | 90% | On Schedule | 2026-11-30 | 0% | On Schedule |  |  |  | 2026-12-31 | 0% | On Schedule |  |  |  | 2026-11-30 | 0% | On Schedule | 2026-10-31 | 0% | On Schedule | 2027-01-30 | 0% | On Schedule |  | 10.59% | Late | [6 empty] | MDW-39314 | MDW-69379 | MDW-69380
35 | 35 | MDW-39315 | Lot01 | GEN2.14 | GEN | Modification Electronic Workshop, Battery Charger and Machining Room at Main Workshop - Civil & AR | สหชาติ |  |  | 2026-08-01 | 2026-10-31 | 70% | On Schedule | 2026-11-30 | 90% | On Schedule |  |  |  | 2026-12-31 | 0% | On Schedule |  |  |  | 2026-11-30 | 0% | On Schedule |  |  |  | 2027-01-30 | 0% | On Schedule |  | 19.05% | Late | [6 empty] | MDW-39315 | MDW-69383 | MDW-69384
36 | 36 | MDW-39297 | Lot01 | GEN2.15 | GEN | Training Room at Ratchada Station (Part 2) | สหชาติ |  |  | 2026-08-01 | 2026-08-01 | 0% | Late | 2026-08-31 | 100% | Completed |  |  |  | 2026-09-30 | 100% | Completed |  |  |  | 2026-11-30 | 0% | On Schedule |  |  |  | 2026-10-30 | 0% | On Schedule |  | 83.33% | Late | [6 empty] | MDW-39297 | MDW-69345 | MDW-69346
37 | 37 | MDW-39291 | Lot01 | GEN2.16 | GEN | Conductor Rail Arrangement Modification at Main Line East Section | กำพล |  |  | 2026-08-01 | 2026-09-30 | 100% | Completed | 2026-09-30 | 100% | Completed |  |  |  | 2026-12-31 | 90% | On Schedule |  |  |  | 2026-11-30 | 0% | On Schedule |  |  |  | 2027-01-30 | 0% | On Schedule |  | 88.1% | Late | [6 empty] | MDW-39291 | MDW-69333 | MDW-69334
38 | 38 | MDW-39292 | Lot01 | GEN2.17 | GEN | Conductor Rail Arrangement Modification at Depot | กำพล |  |  | 2026-08-01 | 2026-09-30 | 100% | Completed | 2026-09-30 | 100% | Completed |  |  |  | 2026-12-31 | 90% | On Schedule |  |  |  | 2026-11-30 | 0% | On Schedule |  |  |  | 2027-01-30 | 0% | On Schedule |  | 88.1% | Late | [6 empty] | MDW-39292 | MDW-69335 | MDW-69336
39 | 39 | MDW-39295 | Lot01 | GEN2.18 | GEN | Dangerous Goods Building in Depot - Civil & AR | สหชาติ |  |  | 2026-08-01 | 2026-01-27 | 100% | Completed | 2026-02-27 | 100% | Completed |  |  |  | 2026-04-30 | 100% | Completed |  |  |  | 2026-04-30 | 100% | Completed |  |  |  | 2026-10-31 | 0% | On Schedule |  | 96.43% | Late | [6 empty] | MDW-39295 | MDW-69341 | MDW-69342
40 | 40 | MDW-39296 | Lot01 | GEN2.19 | GEN | Dangerous Goods Building in Depot - Building Services | ประธาน |  |  | 2026-08-01 | 2025-12-13 | 100% | Completed | 2026-01-28 | 100% | Completed |  |  |  | 2026-04-30 | 100% | Completed |  |  |  | 2026-04-30 | 100% | Completed | 2026-10-31 | 0% | On Schedule | 2026-10-31 | 0% | On Schedule |  | 95.29% | Late | [6 empty] | MDW-39296 | MDW-69343 | MDW-69344
41 | 41 | MDW-39308 | Lot01 | GEN2.20 | GEN | Additional Locking Devices for Main Line Tandem Turnouts 2007, 2010 & 2013 and Depot Turnout D16 | กำพล |  |  | 2026-08-01 | 2026-11-30 | 50% | On Schedule | 2026-09-30 | 100% | Completed |  |  |  | 2026-12-31 | 0% | On Schedule |  |  |  | 2026-11-30 | 0% | On Schedule |  |  |  | 2027-01-30 | 0% | On Schedule |  | 17.86% | Late | [6 empty] | MDW-39308 | MDW-69367 | MDW-69368
42 | 42 | MDW-39200-31 | Lot01 | GEN3 | GEN | Cable Containment Modification | - |  |  | 2025-05-28 | [28 empty] | 0 |  | #REF! |  |  | MDW-39200
43 | 43 | - | Lot01 | GEN4 | GEN | Training Room and Workshop Room | - |  |  | 2026-04-01 | [28 empty] | 0 |  | #REF! |  |  |  | 0 | 0
44 | 44 | MDW-39242 | Lot01 | GEN4.0 | GEN | Modification Works for Training Room at Ratchada Station | ประธาน |  |  | 2026-04-01 | 2025-12-30 | 100% | Completed | 2026-01-31 | 100% | Completed |  |  |  | 2026-03-31 | 100% | Completed |  |  |  | 2026-03-16 | 100% | Completed | 2026-09-30 | 100% | Completed | 2026-10-21 | 100% | Completed |  | 100% | Completed |  | 0 | จัดเตรียมห้อง Training Room and Workshop Room ที่สถานีรัชดา BL19 (เพิ่มท่อน้ำ เพิ่มถังดักไขมัน) | #REF! |  |  | MDW-39242 | MDW-69251 | MDW-69252
45 | 45 | MDW-39244 | Lot01 | GEN4.1 | GEN | AFC Training Room Modification - Civil & AR | สหชาติ |  |  | 2026-08-21 | 2026-09-30 | 10% | Late | 2026-10-15 | 100% | Completed |  |  |  | 2026-11-15 | 0% | On Schedule |  |  |  | 2026-10-31 | 0% | On Schedule | 2026-11-22 | 0% | On Schedule | 2026-12-15 | 0% | On Schedule |  | 12.94% | Late | อยู่ระหว่างจัดทำแบบก่อสร้าง | 0 | จัดเตรียมห้อง Training Room and Workshop Room ที่สถานีรัชดา BL19 (เพิ่มท่อน้ำ เพิ่มถังดักไขมัน) |  | CV/AR |  | MDW-39244 | MDW-69255 | MDW-69256
46 | 46 | MDW-39245 | Lot01 | GEN4.2 | GEN | AFC Training Room Modification - Building Services | ประธาน |  |  | 2026-08-21 | 2025-12-30 | 100% | Completed | 2026-01-31 | 100% | Completed |  |  |  | 2026-03-31 | 100% | Completed |  |  |  | 2026-03-24 | 100% | Completed | 2026-08-07 | 100% | Completed | 2026-09-30 | 0% | Late |  | 96.47% | Late |  | 0 | จัดเตรียมห้อง Training Room and Workshop Room ที่สถานีรัชดา BL19 (เพิ่มท่อน้ำ เพิ่มถังดักไขมัน) | #REF! | E&M |  | MDW-39245 | MDW-69257 | MDW-69258
47 | 47 | MDW-39235 | Lot01 | GEN5 | GEN | Raised Floor | สหชาติ |  |  | 2026-06-01 | 2025-05-15 | 100% | Completed | 2024-12-14 | 100% | Completed | 2025-08-04 | 100% | Completed | 2025-12-28 | 100% | Completed |  |  |  | 2025-11-28 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late |  | 95.79% | Late |  | 0 | จัดเตรียมและปรับปรุง Raised Floor สำหรับ M&E rooms | #REF! | CV/AR |  | MDW-39235 | MDW-69237 | MDW-69238
48 | 48 | MDW-39271 | Lot01 | GEN6 | GEN | Wayside Cable Containment in Depot | - |  | Depot | 2026-02-22 | 2025-05-15 | 100% | Completed | 2024-12-14 | 100% | Completed | 2025-08-04 | 100% | Completed | 2025-12-28 | 100% | Completed |  |  |  | 2026-08-26 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late |  | 95.79% | Late |  | 0 | จัดเตรียมและติดตั้ง cable containment | #REF! |  |  | MDW-39271 | MDW-69297 | MDW-69298
49 | 49 | MDW-39269 | Lot01 | GEN6.1 | GEN | PSY Wayside Cable Containment for 24 Kv Cable under the Depot slab | ประธาน |  | Depot | 2026-02-22 | [28 empty] | CANCLE | งานท่อสาย (PSY) เชื่อมระหว่างอาคารใน Depot | #REF! |  |  | MDW-39269 | MDW-69293 | MDW-69294
50 | 50 | MDW-39270 | Lot01 | GEN6.2 | GEN | COM/SIG Wayside Cable Containment in the Depot | มนตรี/ประธาน |  | Depot | 2026-02-22 | [28 empty] | CANCLE | งานท่อ HDPE (COM/SIG)/tray เชื่อมระหว่างอาคารใน Depot | #REF! |  |  | MDW-39270 | MDW-69295 | MDW-69296
51 | 51 | - | Lot01 | GEN7 | GEN | Dangerous Waste Storage Building in Depot | - |  | Depot | 2026-09-20 | [28 empty] | 0 | ก่อสร้างอาคารและงานระบบ Dangerous Waste Storage | #REF! |  |  |  | 0 | 0
52 | 52 | DWE-39024 | Lot01 | GEN7.1 | GEN | Dangerous Waste Storage Building in Depot - Civil & AR | สหชาติ |  | Depot | 2026-09-20 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed |  |  |  | 2026-04-30 | 100% | Completed |  |  |  | 2026-07-15 | 100% | Completed | 2026-06-08 | 100% | Completed | 2026-09-30 | 0% | Late |  | 96.47% | On Schedule |  | 0 | ก่อสร้างอาคาร Dangerous Waste Storage(เพิ่มขนาดอาคารเป็น 100 ตร.ม.) | #REF! | CV/AR+E&M |  | DWE-39024 | DWE-69024 | DWE-69124
53 | 53 | DWE-39025 | Lot01 | GEN7.2 | GEN | Dangerous Waste Storage Building in Depot - Building service | ประธาน |  | Depot | 2026-09-20 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed |  |  |  | 2026-06-30 | 100% | Completed |  |  |  | 2026-04-20 | 100% | Completed | 2026-06-08 | 100% | Completed | 2026-09-30 | 0% | Late |  | 96.47% | On Schedule |  | 0 | เพิ่มงานระบบ Dangerous Waste Storage(เพิ่มระบบZero waste) | #REF! | CV/AR+E&M |  | DWE-39025 | DWE-69025 | DWE-69125
54 | 54 | - | Lot01 | GEN8 | GEN | General Waste Storage Building in Depot | - |  | Depot | 2026-09-20 | [28 empty] | 0 | ก่อสร้างอาคารและงานระบบ General Waste Storage | #REF! |  |  |  | 0 | 0
55 | 55 | DWE-39026 | Lot01 | GEN8.1 | GEN | General Waste Storage Building in Depot - Civil & AR | สหชาติ |  | Depot | 2026-09-20 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed |  |  |  | 2026-04-30 | 100% | Completed |  |  |  | 2026-07-15 | 100% | Completed | 2026-06-08 | 100% | Completed | 2026-09-30 | 0% | Late |  | 96.47% | On Schedule |  | 0 | ก่อสร้างอาคาร General Waste Storage | #REF! | CV/AR+E&M |  | DWE-39026 | DWE-69026 | DWE-69126
56 | 56 | DWE-39025 | Lot01 | GEN8.2 | GEN | General Waste Storage Building in Depot - Building service | ประธาน |  | Depot | 2026-09-20 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed |  |  |  | 2026-06-30 | 100% | Completed |  |  |  | 2026-04-20 | 100% | Completed | 2026-06-08 | 100% | Completed | 2026-09-30 | 0% | Late |  | 96.47% | On Schedule |  | 0 | เพิ่มงานระบบ General Waste Storage | #REF! | CV/AR+E&M |  | DWE-39025 | DWE-69025 | DWE-69125
57 | 57 | DWE-39021 | Lot01 | GEN9 | GEN | Operation Support Equipment | สมศักดิ์ |  | Depot | 2026-08-21 | 2025-03-02 | 100% | Completed | 2025-11-02 | 100% | Completed | 2026-11-16 | 90% | On Schedule | [6 empty] | 2026-10-17 | 0% | Late | 2026-11-23 | 0% | On Schedule | 2026-12-16 | 0% | On Schedule |  | 82.86% | Late | คงเหลือจัดส่ง Signal Lamp | 0 | จัดเตรียม Short Circuit Device(236 set), Voltage Detector(118 set), Signal Lamp(248 set) | #REF! |  |  | DWE-39021 | DWE-69021 | DWE-69121
58 | 58 | GRS-39001-40 | Lot01 | GEN10.1 | GEN | Graphic and Signage Station | สหชาติ |  |  | 2026-08-21 | 2026-06-30 | 100% | Completed | 2026-05-31 | 95% | Late | 2027-01-31 | 76% | On Schedule | 2027-02-28 | 34% | On Schedule | [13 empty] | 52.78% | Late | GRS | 0 | จัดเตรียมงาน Graphic and Signage(ตะวันออก, ตะวันตก) ที่ station | #REF! | CV/AR |  | GRS-39001 | GRS-69001 | GRS-69002
59 | 59 | GRS-39001-40 | Lot01 | GEN10.2 | GEN | Graphic and Signage Mainline & IVS,VS | สหชาติ |  |  | 2026-08-21 | 2026-06-15 | 79% | Late | 2026-05-31 | 95% | Late | 2026-07-31 | 0% | Late | 2026-07-31 | 0% | Late | [13 empty] | 19.33% | Late | GRS | 0 | จัดเตรียมงาน Graphic and Signage(ตะวันออก, ตะวันตก) ที่ mainline & IVS,VS |  |  |  | GRS-39001 | GRS-69001 | GRS-69002
60 | 60 | GRS-39001-40 | Lot01 | GEN10.3 | GEN | Graphic and Signage Depot | สหชาติ |  |  | 2026-08-21 | 2026-08-15 | 90% | Late | 2026-07-31 | 93% | Late | 2026-06-30 | 56% | Late | 2026-06-30 | 19% | Late | [13 empty] | 39.22% | Late | GRS | 0 | จัดเตรียมงาน Graphic and Signage(ตะวันออก, ตะวันตก) ที่ Depot |  |  |  | GRS-39001 | GRS-69001 | GRS-69002
61 | 61 | MDW-39289 | Lot01 | GEN11 | GEN | Earthing and Bonding Modification | ประธาน |  |  | 2026-03-01 | 2025-01-31 | 100% | Completed | 2025-09-30 | 100% | Completed |  |  |  | 2026-02-28 | 100% | Completed | 2026-03-30 | 100% | Completed | 2026-09-23 | 0% | Late | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late |  | 94.44% | Late |  | 0 | จัดหาและติดตั้ง Earth Mat, Earth bus bar รวมถึงสายดิน | #REF! |  |  | MDW-39289 | MDW-69329 | MDW-69330
62 | 62 | - | Lot01 | GEN12 | GEN | Mainline Cable Trough Modification on East Section | - |  |  | 2026-06-22 | 2025-10-31 | 100% | Completed | 2025-11-30 | 100% | Completed | 2025-12-30 | 100% | Completed | 2026-03-30 | 100% | Completed |  |  |  | 2026-09-30 | 80% | Late | 2026-10-07 | 0% | Late | 2026-10-30 | 0% | On Schedule |  | 95.58% | Late |  | 0 | ปรับปรุง concrete cable trough เดิม | #REF! |  |  |  | 0 | 0
63 | 63 | MDW-39233 | Lot01 | GEN12.1 | GEN | Main Line Cable Trough Modification (PSY) | มนต์ชัย |  | Depot | 2026-06-22 | 2025-10-31 | 100% | Completed | 2025-11-30 | 100% | Completed | 2025-12-30 | 100% | Completed | 2026-03-30 | 100% | Completed |  |  |  | 2026-09-30 | 80% | Late | 2026-10-07 | 0% | Late | 2026-10-30 | 0% | On Schedule |  | 95.58% | Late |  | 0 | แก้ Cable Trough เดิมบน ELEV Station 4จุด ต่อสถานี | #REF! |  |  | MDW-39233
64 | 64 | MDW-39234 | Lot01 | GEN12.2 | GEN | Main Line Cable Trough Modification (SIG/COM) | มนตรี |  |  | 2026-06-22 | 2025-10-31 | 100% | Completed | 2025-11-30 | 100% | Completed | 2025-12-30 | 100% | Completed | 2026-03-30 | 100% | Completed |  |  |  | 2026-09-30 | 80% | Late | 2026-10-07 | 0% | Late | 2026-10-30 | 0% | On Schedule |  | 95.58% | Late | งานจบแล้ว | 0 | ทำ Cable Trough เพิ่มเติมในส่วนที่ Civil ทำไม่ครบ(OR24-25) | #REF! |  |  | MDW-39234 | MDW-69234 | MDW-69236
65 | 65 | MDW-39236 | Lot01 | GEN13 | GEN | Bird Protection System | สหชาติ |  |  | 2026-11-19 | 2025-06-30 | 100% | Completed | 2025-09-30 | 100% | Completed |  |  |  | 2026-01-26 | 100% | Completed |  |  |  | 2026-07-15 | 100% | Completed | 2026-09-30 | 100% | Completed | 2026-10-21 | 0% | Late |  | 96.47% | On Schedule |  | 0 | จัดทำตาข่ายกันนก | #REF! | CV/AR |  | MDW-39236 | MDW-69239 | MDW-69240
66 | 66 | - | Lot01 | GEN14 | GEN | Train Crew Office at Thailand Cultural Centre Station | สหชาติ |  |  | 2026-08-21 | 2025-09-30 | 100% | Completed | 2026-02-27 | 100% | Completed |  |  |  | 2026-05-31 | 100% | Completed |  |  |  | 2026-09-23 | 0% | Late | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late |  | 94.12% | Late |  | 0 |  | #REF! |  |  |  | 0 | 0
67 | 67 | MDW-39240 | Lot01 | GEN14.1 | GEN | Driver Train Simulation Room and Train Crew Office at OR18 - Civil & AR | สหชาติ |  | Depot | 2026-08-21 | 2025-09-30 | 100% | Completed | 2026-02-28 | 100% | Completed |  |  |  | 2026-04-30 | 100% | Completed |  |  |  | 2026-07-15 | 100% | Completed | 2026-08-07 | 100% | Completed | 2026-09-30 | 0% | Late |  | 96.47% | Late |  | 0 | จัดเตรียมห้องสำนักงานสำหรับพนักงานรถไฟฟ้า รวมห้องน้ำช-ญ รองรับพนักงาน 200 คน (พื้นที่อย่างน้อย 400 ตร.ม.) | #REF! | CV/AR+E&M |  | MDW-39240 | MDW-69247 | MDW-69248
68 | 68 | MDW-39241 | Lot01 | GEN14.2 | GEN | Driver Train Simulation Room and Train Crew Office at OR18 - Building Services | ประธาน |  |  | 2026-08-21 | 2025-09-30 | 100% | Completed | 2026-02-28 | 100% | Completed |  |  |  | 2026-04-30 | 100% | Completed |  |  |  | 2026-03-12 | 100% | Completed | 2026-08-07 | 100% | Completed | 2026-09-30 | 0% | Late |  | 96.47% | Late |  | 0 | จัดเตรียมห้องสำนักงานสำหรับพนักงานรถไฟฟ้า รวมห้องน้ำช-ญ รองรับพนักงาน 200 คน (พื้นที่อย่างน้อย 400 ตร.ม.) | #REF! | CV/AR+E&M |  | MDW-39241 | MDW-69249 | MDW-69250
69 | 69 | MDW-39239 | Lot01 | GEN15 | GEN | Access Panel Closeout for Traction Substation Room in Main Workshop | สหชาติ |  |  | 2026-03-24 | 2026-01-30 | 100% | Completed | 2026-03-01 | 100% | Completed |  |  |  | 2026-03-31 | 100% | Completed |  |  |  | 2026-07-15 | 100% | Completed | 2026-09-30 | 100% | Completed | 2026-10-21 | 0% | Late |  | 96.47% | Late |  | 0 | ออกแบบ จัดเตรียมแผงปิดทางเข้าห้อง TSS ที่ MWS | #REF! | CV/AR |  | MDW-39239 | MDW-69245 | MDW-69246
70 | 70 | MDW-39232 | Lot01 | GEN16 | GEN | Level Crossing at Turnout | กำพล |  |  | 2026-08-21 | 2026-09-30 | 100% | Completed | 2026-09-30 | 100% | Completed |  |  |  | 2026-11-15 | 46% | On Schedule |  |  |  |  | 0% | On Schedule |  | 0% | On Schedule |  | 0% | On Schedule |  | 56% | On Schedule |  |  | ติดตั้ง Level Crossing บริเวณ Turnout | #REF! |  |  | MDW-39232 | MDW-69232 | MDW-69233
71 | 71 | MDW-39232 | Lot01 | GEN17 | GEN | Track Slab Crossing | ชฎิล/กำพล |  |  | 2026-08-21 | [28 empty] | CANCLE | ปิดช่องว่างระหว่าง Track Slab | #REF! |  |  | MDW-39232 | MDW-69232 | MDW-69233
72 | 72 | MDW-39243 | Lot01 | GEN18 | GEN | Eye Adaptation Lighting (Lighting at Tunnel to Expose) | ประธาน |  |  | 2026-11-19 | 2025-09-30 | 100% | Completed | 2025-10-30 | 100% | Completed |  |  |  | 2026-04-13 | 100% | Completed |  |  |  | 2026-02-18 | 100% | Completed | 2026-10-07 | 0% | Late | 2026-10-30 | 0% | On Schedule |  | 95.29% | On Schedule | Progress DPA1 : 100% Progress DPA2 : 100% Progress Cut&Cover OR22 : 95% | 0 | จัดเตรียมไฟส่องสว่างบริเวณ Approach Ramp จากอุโมงค์ไปทางวิ่งยกระดับ / จากอุโมงค์เข้า Depot (2จุด) | #REF! |  |  | MDW-39243 | MDW-69253 | MDW-69254
73 | 73 | - | Lot01 | GEN19 | GEN | Train Simulation Room and AFC Training Room | - |  |  | 2026-08-21 | [27 empty] | Progress DPA2 : 100% | 0 |  | #REF! |  |  |  | 0 | 0
74 | 74 | MDW-39244 | Lot01 | GEN19.1 | GEN | Modification AFC Training Center at OR19 - Civil & AR | สหชาติ |  |  | 2026-11-30 | 2026-09-30 | 100% | Completed | 2026-10-31 | 58% | On Schedule |  |  |  | 2026-11-30 | 0% | On Schedule |  |  |  | 2026-10-31 | 0% | On Schedule | 2026-12-07 | 0% | On Schedule | 2026-12-28 | 0% | On Schedule |  | 18.59% | On Schedule | Progress Cut&Cover OR22 : 95% | 0 |  | #REF! | CV/AR+E&M |  | MDW-39244 | MDW-69255 | MDW-69256
75 | 75 | MDW-39245 | Lot01 | GEN19.2 | GEN | Modification AFC Training Center at OR19 - Building Services | ประธาน | บัณฑิต |  | 2026-11-30 | 2026-09-30 | 100% | Completed | 2026-10-31 | 100% | Completed |  |  |  | 2026-11-30 | 0% | On Schedule |  |  |  | 2026-10-31 | 0% | On Schedule | 2026-12-07 | 0% | On Schedule | 2026-12-28 | 0% | On Schedule |  | 23.53% | On Schedule |  | 0 |  | #REF! | CV/AR+E&M |  | MDW-39245 | MDW-69257 | MDW-69258
76 | 76 | - | Lot01 | GEN20 | GEN | Dormitory Cable Containments (if any) | - |  |  | - | [28 empty] | CANCLE |  | #REF! |  |  |  | 0 | 0
77 | 77 |  | Lot01 | GEN21 | GEN | Project Information Management System (PIMS) | บัณฑิต |  |  | 2024-09-30 | 2024-08-10 | 100% | Completed | 2024-08-15 | 100% | Completed |  |  |  | 2024-09-04 | 100% | Completed | 2024-09-14 | 100% | Completed | 2026-09-23 | 0% | Late | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late |  | 94.44% | Late | งานจบแล้ว | 0 |  | #REF!
78 | 78 | MDW-39237 | Lot01 | GEN22 | GEN | Central BEMS for the MRT Orange Line System | บัณฑิต |  |  | 2026-08-21 | 2026-04-30 | 0% | Late | 2026-06-30 | 0% | Late |  |  |  | 2026-08-15 | 0% | Late | 2026-08-31 | 0% | Late | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 0% | Late | PPR Oct-26 กำลังเปรียบเทียบ Spec | 0 | เตรียม Workstation Server (Software by BEM) | #REF! |  |  | MDW-39237 | MDW-69241 | MDW-69242
79 | 79 |  | Lot01 | GEN23 | GEN | Asset Information | บัณฑิต |  |  | 2026-11-19 |  |  |  | 2026-08-30 | 100% | Completed | [19 empty] | 100% | Completed |  | 0 | งานซื้ออุปกรณ์ให้ BEM (โต๊ะ คอม ฯลฯ) รอตรวจสอบข้อมูลและรายการ | #REF!
80 | 80 | MDW-39282 | Lot01 | PSD1 | PSD | Holes for PSD Cable Wiring | กำพล |  |  | 2026-08-21 | [28 empty] | CANCLE | เจาะรูเพื่อการเดินสายของระบบ PSD | #REF! |  |  | MDW-39282 | MDW-69315 | MDW-69316
81 | 81 | MDW-39004 | Lot01 | PSD2 | PSD | Rubber Gap Fillers on Platform Edge | กำพล |  |  | 2026-08-21 | 2025-07-30 | 100% | Completed | 2026-01-31 | 100% | Completed |  |  |  | 2026-08-31 | 40% | Late |  |  |  | 2026-09-30 | 25% | Late | 2026-10-07 | 0% | Late | 2026-10-30 | 50% | On Schedule |  | 53.82% | Late | แผนเข้าติดตั้ง 1/10/26-30/11/26 | 0 | ออกแบบ, จัดหา และติดตั้งวัสดุยางปิดช่องว่างระหว่างขอบชานชาลาและประตูรถไฟฟ้า | #REF! |  |  | MDW-39004 | MDW-69007 | MDW-69008
82 | 82 | MDW-39280 | Lot01 | PSD3 | PSD | Platform Finishing | กำพล |  |  | 2026-08-21 | 2025-07-30 | 100% | Completed | 2025-09-16 | 100% | Completed |  |  |  | 2026-01-07 | 100% | Completed |  |  |  | 2026-08-17 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late |  | 95.29% | Late |  | 0 | จัดเตรียมและปรับปรุงงานพื้น finishing ชั้น Platform | #REF! |  |  | MDW-39280 | MDW-69311 | MDW-69312
83 | 83 | MDW-39281 | Lot01 | PSD4 | PSD | Cladding Barrier between EWD and Station Structure | กำพล |  |  | 2026-08-21 | 2026-02-28 | 100% | Completed | 2026-03-15 | 100% | Completed |  |  |  | 2026-08-15 | 100% | Completed |  |  |  | 2026-09-23 | 0% | Late | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late |  | 94.12% | Late |  | 0 | ทำแผงกั้นเสริมระหว่าง EWD และโครงสร้างสถานี | #REF! |  |  | MDW-39281 | MDW-69313 | MDW-69314
84 | 84 | - | Lot01 | AFC1 | AFC | Park and Ride System | บัณฑิต/สหชาติ |  |  | 2026-10-20 | [28 empty] | CANCLE | ปรับปรุง Park and Ride ที่ OR14 | #REF! |  |  |  | 0 | 0
85 | 85 | MDW-39276 | Lot01 | AFC2 | AFC | Ticket Issuing Machine (TIM) Wall Opening and Closing | สหชาติ |  |  | 2026-09-20 | 2026-01-30 | 100% | Completed | 2026-03-15 | 50% | Late |  |  |  | 2026-07-13 | 100% | Completed |  |  |  | 2026-09-30 | 50% | Late | 2026-10-07 | 0% | Late | 2026-10-30 | 0% | On Schedule |  | 88.82% | On Schedule | มีแก้ไขตำแหน่ง OR14,17,18,23 | 0 | เปิด/ปิดช่องว่างระหว่างกำแพงสำหรับเครื่อง TIM | #REF! | CV/AR |  | MDW-39276 | MDW-69303 | MDW-69304
86 | 86 | MDW-39279 | Lot01 | AFC3 | AFC | Balustrade Modification Along AFC Gate Line | สหชาติ |  |  | 2026-09-20 | 2026-06-30 | 10% | Late | 2026-08-15 | 50% | Late |  |  |  | 2026-11-06 | 0% | On Schedule |  |  |  | 2026-10-07 | 0% | Late | 2026-11-13 | 0% | On Schedule | 2026-11-30 | 0% | On Schedule |  | 7.059% | On Schedule | จัดเตรียมแบบ ออกPPR Oct-26 | 0 | ปรับตำแหน่ง Gate Line ที่สถานี | #REF! | CV/AR |  | MDW-39279 | MDW-69309 | MDW-69310
87 | 87 | MDW-39278 | Lot01 | AFC4 | AFC | Underfloor Embedded Duct Modification for AFC Gates Line | สหชาติ |  | Depot | 2026-09-20 | 2026-01-30 | 100% | Completed | 2026-04-02 | 67% | Late |  |  |  | 2026-10-09 | 81% | Late |  |  |  | 2026-09-30 | 0% | Late | 2026-10-16 | 0% | Late | 2026-10-24 | 0% | Late |  | 76.82% | Late |  | 0 | แก้ไขตำแหน่งท่อสายใต้ประตู AFC ที่สถานี | #REF! | CV/AR |  | MDW-39278 | MDW-69307 | MDW-69308
88 | 88 | MDW-39002 | Lot01 | SIG1 | SIG | Test Track Shelters and Test Track Building | สหชาติ |  |  | 2026-06-22 | 2025-11-22 | 100% | Completed | 2026-01-18 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-04-15 | 100% | Completed |  |  |  | 2026-05-15 | 100% | Completed | 2026-06-08 | 100% | Completed | 2026-09-30 | 0% | Late |  | 96.84% | Late |  | 0 | ออกแบบ, จัดหา และก่อสร้างอาคารและที่กำบัง Test Track | #REF! |  |  | MDW-39002 | MDW-69003 | MDW-69004
89 | 89 | MDW-39293 | Lot01 | SIG2 | SIG | Rearrangement of track crossing walkway at stabling yard to consistent with the layout of 4-car train parking | กำพล |  | Depot | 2026-06-22 | 2025-11-30 | 100% | Completed | 2025-12-30 | 100% | Completed |  |  |  | 2026-03-30 | 100% | Completed |  |  |  | 2026-09-30 | 50% | Late | 2026-10-07 | 0% | Late | 2026-10-30 | 0% | On Schedule |  | 94.71% | Late |  | 0 | ปรับปรุง ทางเดินข้ามรางในลานจอดรถไฟ เพื่อให้รองรับการจอดแบบ4car | #REF! |  |  | MDW-39293 | MDW-69337 | MDW-69338
90 | 90 | MDW-39288 | Lot01 | SIG3 | SIG | Point Machine Foundation Construction | กำพล |  |  | 2026-08-21 | 2025-11-21 | 100% | Completed | 2025-12-30 | 100% | Completed |  |  |  | 2026-03-19 | 100% | Completed |  |  |  | 2026-09-23 | 25% | Late | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late |  | 94.41% | Late |  | 0 | ออกแบบและก่อสร้างฐานสาหรับการติดตั้ง Point Machine | #REF! |  |  | MDW-39288 | MDW-69327 | MDW-69328
91 | 91 | MDW-39001 | Lot01 | SIG4 | SIG | Modification of Depot Track Route Line to Stabling Yard | สู่โชค |  | Depot | 2026-06-22 | 2025-10-30 | 100% | Completed | 2025-11-29 | 100% | Completed |  |  |  | 2026-05-28 | 95% | Late |  |  |  | 2026-09-30 | 50% | Late | 2026-10-07 | 0% | Late | 2026-10-30 | 0% | On Schedule |  | 91.18% | Late | คงเหลือเก็บงาน Progress by ช.ธนัท | 0 | ปรับปรุงเส้นทางรถไฟใน Depot จนถึง ลานจอดรถไฟ ให้เข้า Stabling ได้2ทาง | #REF! |  |  | MDW-39001 | MDW-69001 | MDW-69002
92 | 92 | MDW-39287 | Lot01 | SIG5 | SIG | Strobe Light at Buffer Stops | ประธาน |  | Depot | 2026-08-21 | 2026-05-30 | 100% | Completed | 2026-06-29 | 100% | Completed |  |  |  | 2026-08-28 | 100% | Completed |  |  |  | 2026-03-14 | 100% | Completed | 2026-06-30 | 0% | Late | 2026-09-30 | 0% | Late |  | 95.29% | Late |  | 0 | ออกแบบ, จัดหา และติดตั้งโคมดวงไฟ(Red Strobe Ligjt) | #REF! |  |  | MDW-39287 | MDW-69323 | MDW-69324
93 | 93 | DWE-39016 | Lot01 | DWE1 | DWE | Diesel Fuel Storage Tank for Maintenance Vehicle | สมศักดิ์ |  | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-01-16 | 100% | Completed | 2026-06-30 | 100% | Completed | 2026-07-31 | 100% | Completed | 2026-08-09 | 0% | Late | [10 empty] | 94.74% | Late | Test ช่วงต้น Nov-26 | 0 | ออกแบบ, จัดหา, ขอใบอนุญาต และติดตั้งระบบถังเก็บน้ำมันดีเซล | #REF! |  |  | DWE-39016 | DWE-69016 | DWE-69116
94 | 94 | DWE-39011 | Lot01 | DWE2 | DWE | Movable Height Maintenance Platform Vehicle (Boom Lift) | สมศักดิ์ |  | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-08-06 | 100% | Completed | 2025-12-31 | 100% | Completed | 2026-06-30 | 100% | Completed | 2026-07-09 | 0% | Late | 2026-05-22 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late |  | 91% | Late | Test 9-15/11/26 | 0 | จัดหารถแพลตฟอร์มบำรุงรักษาความสูงเคลื่อนย้ายได้ | #REF! |  |  | DWE-39011 | DWE-69011 | DWE-69111
95 | 95 | DWE-39012 | Lot01 | DWE3 | DWE | Fork Lift Vehicle | สมศักดิ์ |  | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-03-31 | 100% | Completed | 2026-06-01 | 100% | Completed | 2026-06-30 | 100% | Completed | 2026-07-30 | 0% | Late | 2026-09-30 | 0% | Late | 2026-10-07 | 0% | Late | 2026-10-28 | 0% | Late |  | 90% | Late | Test 9-15/11/26 | 0 | จัดหารถโฟล์คลิฟต์ (Fork Lift) และคอร์สฝึกอบรม | #REF! |  |  | DWE-39012 | DWE-69012 | DWE-69112
96 | 96 | DWE-39015 | Lot01 | DWE4 | DWE | Compressed Air System and Portable Air Compressor for Depot | สมศักดิ์ |  | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-01-10 | 100% | Completed | 2026-02-15 | 100% | Completed | 2026-09-19 | 0% | Late | 2026-09-29 | 0% | Late | [10 empty] | 31.58% | Late | Forecast Install 1/11-30-11/26 | 0 | จัดหาระบบอากาศและเครื่องอัดอากาศ (รวม Piping) | #REF! |  |  | DWE-39015 | DWE-69015 | DWE-69115
97 | 97 | DWE-39017 | Lot01 | DWE5 | DWE | Pallet Storage Shelves in Hazardous Storage | สมศักดิ์ |  | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-12-16 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-05-31 | 100% | Completed | 2026-06-05 | 0% | Late | 2026-07-17 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late |  | 91% | Late | Test 26-30/10/26 | 0 | จัดหาชั้นวางจัดเก็บพาเลทในพื้นที่จัดเก็บอันตราย | #REF! |  |  | DWE-39017 | DWE-69017 | DWE-69117
98 | 98 | DWE-39017 | Lot01 | DWE6 | DWE | Pallet Storage in Main Storage Room | สมศักดิ์ |  | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-12-16 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-05-31 | 100% | Completed | 2026-06-05 | 0% | Late | 2026-07-17 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late |  | 91% | Late | Test 26-30/10/26 | 0 | จัดหาชั้นวางจัดเก็บพาเลทในห้องเก็บของหลัก | #REF! |  |  | DWE-39017 | DWE-69017 | DWE-69117
99 | 99 | DWE-39017 | Lot01 | DWE7 | DWE | Two-Tier Shelf | สมศักดิ์ |  | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-12-16 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-05-31 | 100% | Completed | 2026-06-05 | 0% | Late | 2026-07-17 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late |  | 91% | Late | Test 26-30/10/26 | 0 | ติดตั้งชั้นวางของ (ชั้นหลัก18 ชั้น, ชั้นบน 18 ชั้น,กล่องพลาสติกทึบ 150 กล่อง) | #REF! |  |  | DWE-39017 | DWE-69017 | DWE-69117
100 | 100 | DWE-39017 | Lot01 | DWE8 | DWE | Tool Storage | สมศักดิ์ |  | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-12-16 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-05-31 | 100% | Completed | 2026-06-05 | 0% | Late | 2026-07-17 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late |  | 91% | Late | Test 26-30/10/26 | 0 | จัดหาที่เก็บเครื่องมือ(ตู้มีลิ้นชัก 12 ชุด, ตู้มีชั้นวาง 8 ชุด, โต๊ะทางานพร้อมลิ้นชัก2 ชุด) | #REF! |  |  | DWE-39017 | DWE-69017 | DWE-69117
101 | 101 | DWE-39018 | Lot01 | DWE9 | DWE | Repair Equipment | สมศักดิ์ |  | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-07-31 | 50% | Late | 2026-10-30 | 70% | On Schedule | 2027-03-03 | 0% | On Schedule | 2027-04-02 | 0% | On Schedule | 2027-03-03 | 0% | On Schedule | 2027-04-09 | 0% | On Schedule | 2027-05-02 | 0% | On Schedule |  | 22% | Late | คงเหลือจัดส่งอุปกรณ์ | 0 | จัดหาซื้ออุปกรณ์สำหรับงาน maintanence | #REF! |  |  | DWE-39018 | DWE-69018 | DWE-69118
102 | 102 | DWE-39020 | Lot01 | DWE10 | DWE | Oil & Grease Disposal | สมศักดิ์ |  | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-01-16 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-03-31 | 100% | Completed | 2026-07-05 | 0% | Late | 2026-09-30 | 0% | Late | 2026-10-07 | 0% | Late | 2026-10-28 | 0% | Late |  | 90% | Late | Test 9-15/11/26 | 0 | จัดหาอุปกรณ์สำหรับการกำจัดน้ำมันและจารบี | #REF! |  |  | DWE-39020 | DWE-69020 | DWE-69120
103 | 103 | DWE-39020 | Lot01 | DWE11 | DWE | Grease Dispensers | สมศักดิ์ |  | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-01-16 | 100% | Completed | 2026-04-28 | 100% | Completed | 2026-05-25 | 100% | Completed | 2026-07-05 | 0% | Late | 2026-09-30 | 0% | Late | 2026-10-07 | 0% | Late | 2026-10-28 | 0% | Late |  | 90% | Late | Test 9-15/11/26 | 0 | จัดหาอุปกรณ์สำหรับจ่ายจารบี | #REF! |  |  | DWE-39020 | DWE-69020 | DWE-69120
104 | 104 | DWE-39020 | Lot01 | DWE12 | DWE | Waste Disposal | สมศักดิ์ |  | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-01-16 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-03-31 | 100% | Completed | 2026-07-05 | 0% | Late | 2026-09-30 | 0% | Late | 2026-10-07 | 0% | Late | 2026-10-28 | 0% | Late |  | 90% | Late | Test 9-15/11/26 | 0 | จัดหาอุปกรณ์สำหรับของเสีย | #REF! |  |  | DWE-39020 | DWE-69020 | DWE-69120
105 | 105 | MDW-39305 | Lot01 | DWE13 | DWE | Safety Provision for Maintenance Pits | สหชาติ |  | Depot | 2026-09-20 | 2025-11-30 | 100% | Completed | 2026-04-29 | 100% | Completed |  |  |  | 2026-07-29 | 70% | Late |  |  |  | 2026-09-30 | 50% | Late | 2026-10-07 | 0% | Late | 2026-10-30 | 0% | On Schedule |  | 73.53% | Late | งาน Handrail ที่ Pits Wheel Reprofling Plant ติดตั้งแล้วเหลืองานเก็บสี | 0 | งาน Handrail ที่ Pits Wheel Reprofling Plant | #REF! |  |  | MDW-39305 | MDW-69361 | MDW-69362
106 | 106 | DWE-39xxx | Lot01 | DWE14 | DWE | Pit Drainage System in Main Workshop | สมศักดิ์ |  | Depot | 2026-09-20 | [28 empty] | CANCLE | จัดติดตั้งระบบระบายน้ำและหาอุปกรณ์สาหรับการระบายน้ำในหลุม (Pit Drainge) | #REF! |  |  | DWE-39xxx | MDW-69361 | MDW-69362 | cacel
107 | 107 | DWE-39023 | Lot01 | DWE15 | DWE | Provision of Civil Works and Building Services to support Train Washing Equipment | สหชาติ |  | Depot | 2026-08-01 | 2025-11-30 | 100% | Completed | 2026-03-31 | 100% | Completed |  |  |  | 2026-05-31 | 100% | Completed |  |  |  | 2026-08-31 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-15 | 0% | Late |  | 95.29% | Late |  | 0 | จัดทำ จัดหา อาคารอุปกรณ์สำหรับ ล้างรถไฟ | #REF! |  |  | DWE-39023 | DWE-69023 | DWE-69123
108 | 108 | DWE-39013 | Lot01 | DWE16 | DWE | Overhead Traveling Crane | สมศักดิ์ |  | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-04-30 | 100% | Completed | 2026-03-20 | 100% | Completed |  |  |  | 2026-04-04 | 100% | Completed | 2026-05-26 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late |  | 90% | Late |  | 0 | จัดหา Crane สำหรับใช้ยกรถไฟ | #REF! |  |  | DWE-39013 | DWE-69013 | DWE-69113-513
109 | 109 | DWE-39009 | Lot01 | DWE17 | DWE | Vehicle Inspection and Servicing Facilities | สมศักดิ์ |  | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-12-18 | 100% | Completed | 2026-09-07 | 100% | Completed |  |  |  | 2026-10-01 | 0% | Late | [10 empty] | 85.71% | On Schedule | Test 9-15/11/26 | Rail/Road Shunting Vehicel | Rail/Road Shunting Vehicel | #REF! |  |  | DWE-39009 | DWE-69009 | DWE-69109
110 | 110 | DWE-39014 | Lot01 | DWE18 | DWE | Permanent Way Maintenance Facility | สมศักดิ์ |  | Depot | 2026-09-20 | 2025-04-30 | 100% | Completed | 2027-02-28 | 100% | Completed | 2027-01-15 | 70% | On Schedule |  |  |  | 2027-03-30 | 0% | On Schedule | [10 empty] | 77.14% | On Schedule | Test 18-30/1/27 | Trackwork Equipment and hand tools | Trackwork Equipment and hand tools | #REF! |  |  | DWE-39014 | DWE-69014 | DWE-69114
111 | 111 | - | Lot01 | DWE19 | DWE | Permanent Way Vehicles | สมศักดิ์ |  | Depot | 2026-09-20 | [28 empty] | 0 |  | #REF! |  |  |  | 0 | 0
112 | 112 | DWE-39001 | Lot01 | DWE19.1 | DWE | Shunting Locomotive | สมศักดิ์ |  | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-12-18 | 100% | Completed | 2026-12-15 | 50% | On Schedule |  |  |  | 2026-12-30 | 0% | On Schedule | [10 empty] | 71.43% | Late | Delivery to Thailand Feb-27 | 0 | จัดซื้อ Shunting Locomotive 1 คัน | #REF! |  |  | DWE-39001 | DWE-69001 | DWE-69101
113 | 113 | DWE-39002 | Lot01 | DWE19.2 | DWE | Tunnel Inspection and Cleaning Vehicle | สมศักดิ์ |  | Depot | 2026-09-20 | 2025-08-31 | 0% | Late | 2025-12-18 | 100% | Completed | 2026-12-30 | 40% | On Schedule |  |  |  | 2026-10-11 | 0% | Late | [10 empty] | 40% | Late | Delivery to Thailand Feb-27 | 0 | จัดซื้อ Tunnel Inspection and Cleaning Vehicle 1 คัน | #REF! |  |  | DWE-39002 | DWE-69002 | DWE-69102
114 | 114 | DWE-39003 | Lot01 | DWE19.3 | DWE | Hi/Rail Maintenance Vehicle | สมศักดิ์ |  | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-12-18 | 100% | Completed | 2026-11-30 | 55% | On Schedule |  |  |  | 2026-12-16 | 0% | On Schedule | [10 empty] | 72.86% | Late | Delivery to Thailand Dec-26 | 0 | จัดซื้อ Self-propelled Hi/Rail Maintenance Vehicle 1 คัน | #REF! |  |  | DWE-39003 | DWE-69003 | DWE-69103
115 | 115 | DWE-39004 | Lot01 | DWE19.4 | DWE | Flat wagon | สมศักดิ์ |  | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-12-18 | 100% | Completed | 2026-10-30 | 68% | On Schedule |  |  |  | 2026-08-11 | 0% | Late | [10 empty] | 76.57% | Late | Delivery to Thailand Dec-26 | 0 | จัดซื้อ Flat wagon 2 คัน | #REF! |  |  | DWE-39004 | DWE-69004 | DWE-69104
116 | 116 | DWE-39005 | Lot01 | DWE19.5 | DWE | Re-railing Equipment | สมศักดิ์ |  | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-11-10 | 100% | Completed | 2026-07-15 | 90% | Late |  |  |  | 2026-08-31 | 0% | Late | [10 empty] | 82.86% | Late | Test 16-22/11/26 | 0 | จัดซื้อ Re-railing vedhicle 1 คัน | #REF! |  |  | DWE-39005 | DWE-69005 | DWE-69105
117 | 117 | DWE-39006 | Lot01 | DWE19.6 | DWE | Self-Propelled Rail Based Inspection Vehicle | สมศักดิ์ |  | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-12-18 | 100% | Completed | 2026-11-03 | 55% | On Schedule |  |  |  | 2026-12-16 | 0% | On Schedule | [10 empty] | 72.86% | Late | Delivery to Thailand Dec-26 | 0 | จัดซื้อ Self-Propelled Rail Based Inspection Vehicle 1 คัน | #REF! |  |  | DWE-39006 | DWE-69006 | DWE-69106
118 | 118 | DWE-39007 | Lot01 | DWE19.7 | DWE | Rail Head Grinding Machine Vehicle | สมศักดิ์ |  | Depot | 2026-09-20 | 2025-08-31 | 0% | Late | 2025-12-18 | 100% | Completed | 2027-07-31 | 0% | On Schedule |  |  |  | 2027-08-31 | 0% | On Schedule | [10 empty] | 28.57% | Late |  | 0 | จัดซื้อ Rail Head Grinding Machine Vehicle 1 คัน | #REF! |  |  | DWE-39007 | DWE-69007 | DWE-69107
119 | 119 | DWE-39008 | Lot01 | DWE19.8 | DWE | Multi Measuring Rail Vehicle | สมศักดิ์ |  |  | 2026-09-20 | [28 empty] | CANCLE | จัดซื้อ Multi Measuring Rail Vehicle 1 คัน | #REF! |  |  | DWE-39008 | DWE-69008 | DWE-69108
120 | 120 | DWE-39010 | Lot01 | DWE19.9 | DWE | High Work Inspection Vehicle | สมศักดิ์ |  |  | 2026-09-20 | [28 empty] | CANCLE | จัดซื้อ High Work Inspection Vehicle 1 คัน | #REF! |  |  | DWE-39010
121 | 121 | - | Lot01 | DWE20 | DWE | Building Maintenance Vehicle | - |  |  | 2026-09-20 | [28 empty] | CANCLE |  | #REF! |  |  |  | 0 | 0
122 | 122 | EPS-39001 | Lot01 | PSY1 | PSY | Diesel Fuel Storage Tanks for Power Generators | สมศักดิ์ |  |  | 2026-03-24 | 2026-01-16 | 100% | Completed | 2026-03-31 | 100% | Completed | 2026-03-31 | 100% | Completed | 2026-06-30 | 75% | Late | 2026-07-10 | 0% | Late | 2026-10-23 | 0% | Late | 2026-10-30 | 0% | On Schedule | 2026-11-20 | 0% | On Schedule |  | 75% | Late | คงเหลืองานเดินท่อและ Pump น้ำมัน | 0 | จัดหา, ติดตั้ง ถังเก็บเชื่อเพลิงดีเซลสำหรับเครื่องกำเนิดไฟฟ้า | #REF! |  |  | EPS-39001 | EPS-69001 | EPS-69002
123 | 123 | PSY-39001-9 | Lot01 | PSY2 | PSY | GIS and BSS Building and Other Facilities | สหชาติ |  |  | 2026-03-24 | 2024-08-29 | 100% | Completed | 2024-09-28 | 69% | Late |  |  |  | 2025-12-04 | 100% | Completed |  |  |  | 2026-09-23 | 100% | Completed | 2026-09-30 | 100% | Completed | 2026-10-21 | 50% | Late |  | 94.59% | Late |  | 0 | งานสร้างอาคาร GIS และ BSS และงานระบบภายในอาคาร | #REF! | CV/AR |  | PSY-39001 | PSY-69001 | PSY-69002
124 | 124 | PSY-39011 | Lot01 | PSY3 | PSY | Steel Grating Raised Floor for EE Panel | สหชาติ |  |  | 2026-03-24 | 2024-09-30 | 100% | Completed | 2024-10-30 | 75% | Late |  |  |  | 2025-07-14 | 100% | Completed |  |  |  | 2026-06-14 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late |  | 92.35% | Late |  | 0 | ออกแบบ, จัดหา, ติดตั้งเหล็กตะแกรง สำหรับห้อง TSS และ SSS | #REF! |  |  | PSY-39011 | PSY-69015 | PSY-69016
125 | 125 | - | Lot01 | PSY4 | PSY | Trapping Box between PSY Service Sub Station (SSS) and Low Volt (LV) System | - |  |  | 2026-08-21 | [28 empty] | CANCLE |  | #REF! |  |  |  | 0 | 0
126 | 126 | SCA-39200 | Lot01 | SCA1 | SCA | Modification of BEMS to receive PSD Signal on East Section | ธารทิพย์ |  |  | 2026-08-21 | [28 empty] | CANCLE |  | #REF! |  |  | SCA-39200 | SCA-69200 | SCA-69201
127 | 127 | - | Lot01 | SCA2 | SCA | Modification of Escalator Interface Point with CCTV and SCADA, East Section | - |  |  | 2026-08-21 | [28 empty] | CANCLE |  | #REF! |  |  |  | 0 | 0
128 | 128 | - | Lot01 | SCA3 | SCA | Magnetic of Fire Alarm System Interface Point with CCTV and SCADA | - |  |  | 2026-08-21 | [28 empty] | CANCLE |  | #REF! |  |  |  | 0 | 0
129 | 129 | SCA-39203 | Lot01 | SCA4 | SCA | Add/Modify Civil Scada Hardwire for all Station | ประธาน/ธารทิพย์ |  |  | 2026-08-21 | [28 empty] | CANCLE |  | #REF! |  |  | SCA-39203 | SCA-69206 | SCA-69207
130 | 130 | COM-39200 | Lot01 | COM1 | COM | Magnetic Door Lock | มนตรี |  |  | 2026-08-21 | 2025-06-30 | 100% | Completed | 2026-05-15 | 100% | Completed |  |  |  | 2026-12-31 | 27.25% | On Schedule |  |  |  | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 42.76% | Late | กำลังดำเนินการ Progress by CIP | 0 | จัดหา, ติดตั้งชุดล็อคประตูแม่เหล็กพร้อมเซ็นเซอร์ประตู | #REF! |  |  | COM-39200 | COM-69200 | COM-69201
131 | 131 | MDW-39283 | Lot01 | COM2 | COM | Intercom System in Cash Handling Room (if require) | บัณฑิต |  |  | 2026-12-19 | 2025-09-30 | 100% | Completed | 2026-06-30 | 50% | Late |  |  |  | 2026-10-31 | 0% | On Schedule | 2026-12-30 | 0% | On Schedule | 2026-09-30 | 0% | Late | 2026-11-07 | 0% | On Schedule | 2026-11-28 | 0% | On Schedule |  | 16.67% | On Schedule | รอพื้นที่เข้าติดตั้ง | 0 | จัดหาระบบ Intercom สำหรับห้องจัดการเงินสด | #REF! |  |  | MDW-39283 | MDW-69317 | MDW-69318
132 | 132 | COM-39001 | Lot01 | COM3 | COM | Walk-Through Metal Detector System (WTMD), 1 per entrance | มนตรี |  |  | 2026-11-19 | 2025-08-31 | 0% | Late | 2026-06-30 | 0% | Late |  |  |  | 2027-02-28 | 0% | On Schedule |  |  |  | 2027-01-29 | 0% | On Schedule | 2027-03-07 | 0% | On Schedule | 2027-03-28 | 0% | On Schedule |  | 0% | On Schedule | รอออก PPR อยู่ระหว่างการตรวจสอบสินค้า | 0 | จัดหา, ติดตั้งระบบตรวจจับโลหะแบบเดินผ่าน (68 set) | #REF! |  |  | COM-39001 | COM-69001 | COM-69002
133 | 133 | MDW-39284 | Lot01 | COM4 | COM | Traveling Cable in all Lifts | มนตรี |  |  | - | [28 empty] | CANCLE |  | #REF! |  |  | MDW-39284 | MDW-69319 | MDW-69320
134 | 134 | MDW-39304 | Lot01 | COM5 | COM | MEA Radio | ประธาน |  |  | 2026-09-20 | 2026-01-30 | 100% | Completed | 2026-04-30 | 100% | Completed |  |  |  | 2026-06-30 | 95% | Late | 2026-09-30 | 0% | Late | 2026-09-23 | 0% | Late | 2026-10-07 | 0% | Late | 2026-10-30 | 0% | On Schedule |  | 85.56% | On Schedule | รอเฟอร์นิเจอร์ Fore cast Dec-26 | 0 | ออกแบบ, จัดหา, ติดตั้ง MEA Radio | #REF! |  |  | MDW-39304 | COM-69202 | COM-69203
135 | 135 | COM-39004 | Lot01 | COM6 | COM | Main Cable Containment for M&E Dedicated communication link to MRTA Head Quarter | มนตรี |  |  | 2026-09-20 | 2026-01-31 | 100% | Completed | 2026-02-28 | 100% | Completed |  |  |  | 2026-08-31 | 75% | Late | [13 empty] | 81.25% | On Schedule | Fore cast Oct-26 | 0 | จัดหาที่จัดเก็บสายเคเบิ้ลหลักระหว่างอาคาร OCC และ สำนักงานใหญ่ รฟม. สำหรับระบบ M&E | #REF! |  |  | COM-39004 | COM-69005 | COM-69006
136 | 136 | AFC-39001 | Lot01 | COM7 | COM | Mini Paging in Ticket Office | บัณฑิต |  |  | 2026-12-19 | 2025-09-10 | 100% | Completed | 2026-06-30 | 100% | Completed |  |  |  | 2026-09-30 | 0% | Late | 2026-11-30 | 0% | On Schedule | 2026-10-31 | 0% | On Schedule | 2026-12-07 | 0% | On Schedule | 2026-12-28 | 0% | On Schedule |  | 22.22% | On Schedule | ของมาแล้ว รอพื้นที่เข้าติดตั้ง | 0 | จัดหาชุดไมโครโฟนและลำโพง | #REF! |  |  | AFC-39002 | AFC-69003 | AFC-69004
137 | 137 | MDW-39285 | Lot01 | COM8 | COM | Provision of Cable Containment between OCC ORL and OCC BL | มนตรี |  |  | 2026-07-22 | [28 empty] | CANCLE | จัดหาที่จัดเก็บสายเคเบิ้ลระหว่างอาคาร OCC ORL และ อาคาร OCC BL | #REF! |  |  | MDW-39285
138 | 138 | COM-39005 | Lot01 | COM9 | COM | Power Distribution for M&E Systems at MRTA Head Quarter | มนตรี |  |  | 2026-09-20 | 2026-03-31 | 100% | Completed | 2026-06-30 | 100% | Completed |  |  |  | 2026-08-31 | 100% | Completed | [13 empty] | 100% | Completed | งานจบแล้ว | 0 | จัดหา, ปรับปรุงระบบ M&E ที่สำนักงานใหญ่ รฟม. | #REF! |  |  | COM-39005 | COM-69007 | COM-69008
139 | 139 | COM-39205 | Lot01 | COM10 | COM | Underground Cable Containment at Public Areas (if require) | มนตรี |  |  | 2026-08-21 | 2026-04-30 | 100% | Completed | 2026-07-31 | 100% | Completed |  |  |  | 2026-12-31 | 100% | Completed | [13 empty] | 100% | Completed | งานจบแล้ว | 0 | จัดหาที่สำหรับเก็บสายเคเบิลใต้ดินเช่นสายโทรศัพท์กับสาย Fiberoptic | #REF! |  |  | MDW-39205 | MDW-69200 | MDW-69205
140 | 140 | - | Lot01 | COM11 | COM | Intercom at Ticket Issuing Machine | บัณฑิต |  | Depot | - | [28 empty] | CANCLE |  | #REF! |  |  |  | 0 | 0
141 | 141 | RST-39004,8 | Lot01 | RST1 | RST | Driver Training Simulator | ธัญวิทย์ |  | Depot | 2026-09-20 | 2025-05-30 | 100% | Completed | 2025-06-30 | 100% | Completed |  |  |  | 2026-12-31 | 81% | On Schedule | [13 empty] | 85.75% | On Schedule |  | 0 |  | #REF! |  |  | RST-39004,8
142 | 142 | MDW-39500 | Lot02 | MO-CK1.1 | MO-CK | Store Modification Works at Main Workshop - Civil&AR | สหชาติ |  | Depot | 2026-06-03 | 2026-02-27 | 100% | Completed | 2026-03-30 | 100% | Completed |  |  |  | 2026-05-31 | 100% | Completed |  |  |  | 2026-09-30 | 50% | Late | 2026-10-07 | 100% | Completed | 2026-10-30 | 0% | On Schedule |  | 95.88% | Late |  | 0 | ปรับปรุงห้อง 1.ห้อง office store 2.two-tier shelf 3.main pallet storage 4.tool storage | #REF! | CV/AR+E&M |  | MDW-39500 | MDW-69500 | MDW-69501
143 | 143 | MDW-39501 | Lot02 | MO-CK1.2 | MO-CK | Store Modification Works at Main Workshop - Building Services | ประธาน |  | Depot | 2026-06-04 | 2026-02-12 | 100% | Completed | 2026-03-30 | 100% | Completed |  |  |  | 2026-05-28 | 100% | Completed |  |  |  | 2026-09-30 | 0% | Late | 2026-10-07 | 100% | Completed | 2026-10-30 | 0% | On Schedule |  | 95.29% | Late | รอสรุปตำแหน่ง Power Plug ชาร์จโฟลคลิฟท์ Oct-26 | 0 | ปรับปรุงห้อง 1.ห้อง office store 2.two-tier shelf 3.main pallet storage 4.tool storage | #REF! | CV/AR+E&M |  | MDW-39501 | MDW-69502 | MDW-69503
144 | 144 | MDW-39503 | Lot02 | MO-CK2 | MO-CK | New MMC at Admin Building - Civil&AR | สหชาติ |  | Depot | 2026-08-03 | 2026-04-14 | 100% | Completed | 2026-05-15 | 100% | Completed |  |  |  | 2026-07-31 | 100% | Completed |  |  |  | 2026-09-30 | 50% | Late | 2026-09-30 | 0% | Late | 2026-10-30 | 0% | On Schedule |  | 94.71% | Late | กำลังทำเอกสาร Test Report |  | ทำผนังกั้นห้องเป็นห้อง MMC (Lobby Admin) |  | CV/AR+E&M |  | MDW-39503 | MDW-69506 | MDW-69507
145 | 145 | MDW-39504 | Lot02 | MO-CK3 | MO-CK | Move or link Workstation and control panel to MMC room at admin C 2nd floor | ประธาน |  | Depot | 2026-08-02 | 2026-02-28 | 100% | Completed | 2026-04-15 | 100% | Completed |  |  |  | 2026-08-31 | 90% | Late |  |  |  | 2026-09-30 | 0% | Late | 2026-09-30 | 0% | Late | 2026-10-30 | 0% | On Schedule |  | 87.06% | Late | Fore cast Oct-26 | 0 | ย้ายตู้ Panel จากห้อง SCADA ไปที่ห้อง Storge ที่ MWS แล้ว Like ผ่านระบบ Backbone ของ STE | #REF! | CV/AR+E&M |  | MDW-39504 | MDW-69508 | MDW-69509
146 | 146 | MDW-39543 | Lot02 | MO-CK4 | MO-CK | Bird & Rain Protection for Open space Admin C | สหชาติ |  | Depot | 2026-08-01 | 2026-04-29 | 100% | Completed | 2026-05-30 | 100% | Completed |  |  |  | 2026-07-31 | 100% | Completed |  |  |  | 2026-09-30 | 50% | Late | 2026-09-30 | 0% | Late | 2026-10-30 | 0% | On Schedule |  | 94.71% | Late |  | 0 | ผนังกันฝนสาด และกันนกเข้าอาคาร Admin C (9 ช่อง) | #REF! | CV/AR |  | MDW-39543 | MDW-69586 | MDW-69587
147 | 147 | MDW-39547 | Lot02 | MO-CK5 | MO-CK | Relocate door in front of toilet and build partition wall to conceal the view in side of toilet | สหชาติ |  | Depot | 2026-08-02 | 2026-05-14 | 100% | Completed | 2026-06-14 | 100% | Completed |  |  |  | 2026-07-31 | 100% | Completed |  |  |  | 2026-07-15 | 100% | Completed | 2026-10-07 | 0% | Late | 2026-10-30 | 0% | On Schedule |  | 95.29% | Late |  | 0 | ย้ายประตูหน้าห้องน้ำและสร้างผนังกั้นเพื่อปิดบังมุมมองด้านข้างห้องน้ำ | #REF! | CV/AR |  | MDW-39547 | MDW-69594 | MDW-69595
148 | 148 | MDW-39547 | Lot02 | MO-CK6 | MO-CK | Modify Lockset the emergency door to be used for passage between the 2nd and 3rd floors inside the building. | สหชาติ |  | Depot | 2026-08-03 | 2026-04-29 | 100% | Completed | 2026-06-14 | 100% | Completed |  |  |  | 2026-07-31 | 100% | Completed |  |  |  | 2026-07-01 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late |  | 95.29% | Late |  | 0 | ปรับเปลี่ยนประตูฉุกเฉินเพื่อใช้เป็นทางเดินระหว่างชั้น 2 และ 3 ภายในอาคาร | #REF! | CV/AR |  | MDW-39547 | MDW-69594 | MDW-69595
149 | 149 | MDW-39556 | Lot02 | MO-CK7 | MO-CK | Addition small power for lounge and pantry room at 2nd floor and Hall and observation room at 3nd floor | ประธาน |  | Depot | 2026-08-04 | 2026-05-14 | 100% | Completed | 2026-06-14 | 100% | Completed |  |  |  | 2026-07-31 | 100% | Completed |  |  |  | 2026-05-05 | 100% | Completed | 2026-09-30 | 100% | Completed | 2026-10-21 | 100% | Completed |  | 100% | Late |  | 0 | เพิ่มปลั๊กในห้องนั่งเล่นและห้องเตรียมอาหารชั้น 2 และห้องโถงและห้องสังเกตการณ์ชั้น 3 | #REF! |  |  | MDW-39556 | MDW-69612 | MDW-69613
150 | 150 | MDW-39548 | Lot02 | MO-CK8 | MO-CK | Air Condition for using store room to be pantry room. 2nd floor | ประธาน |  | Depot | 2026-08-05 | 2026-04-29 | 100% | Completed | 2026-06-14 | 100% | Completed |  |  |  | 2026-07-31 | 100% | Completed |  |  |  | 2026-03-24 | 100% | Completed | 2026-09-30 | 100% | Completed | 2026-07-10 | 100% | Completed |  | 100% | Late |  | 0 | แอร์สำหรับห้องเก็บของที่จะเป็นห้องเตรียมอาหาร ชั้น 2 | #REF! |  |  | MDW-39548 | MDW-69596 | MDW-69597
151 | 151 | MDW-39552 | Lot02 | MO-CK9 | MO-CK | Walk Way Hand rail high 90 cm 1 side (144 m. x 7 route) | สหชาติ |  | Depot | 2026-10-01 | 2026-05-30 | 100% | Completed | 2026-06-30 | 100% | Completed |  |  |  | 2026-09-30 | 98.77% | Late |  |  |  | 2026-09-30 | 50% | Late | 2026-10-07 | 0% | Late | 2026-10-30 | 0% | On Schedule |  | 93.84% | On Schedule | คงเหลืองานคอนกรีตทางเดินข้ามราง | 0 | ราวจับทางเดินสูง 90 ซม. 1 ด้าน | #REF! | CV/AR |  | MDW-39552 | MDW-69604 | MDW-69605
152 | 152 | MDW-39544 | Lot02 | MO-CK10 | MO-CK | Barbed wire fence Viaduct CE CW | บัณฑิต/สหชาติ | พี่ต่อ | Depot | 2027-01-01 | [28 empty] | ยกเลิก | ติดตั้งรั้วลวดหนามหีบเพลง แนวรั้ว Viaduct CE CW ยกเลิก Barbed wire fence Viaduct CE CW มีกล้อง(ไม่มีfunction intrusion) ล้อมรอบพื้นที่ จำนวน 19 ตัว | #REF! |  |  | MDW-39544 | MDW-69588 | MDW-69589
153 | 153 | MDW-39545 | Lot02 | MO-CK11 | MO-CK | Chain Link at Cut & Cover 600m. | สหชาติ | พรพรหม | Depot | 2026-06-01 | 2026-02-27 | 100% | Completed | 2026-04-30 | 100% | Completed |  |  |  | 2026-08-31 | 100% | Completed |  |  |  | 2026-08-01 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late |  | 95.29% | Late | มีงานเพิ่มอีก 18 แผง | มีงานเพิ่ม | Chain Link ปิดด้านข้าง Cut & Cover | #REF! | CV/AR |  | MDW-39545 | MDW-69590 | MDW-69591
154 | 154 | MDW-39546 | Lot02 | MO-CK12 | MO-CK | Chain Link under slab high 1.70 m | สหชาติ |  |  | 2027-01-01 | 2026-06-30 | 100% | Completed | 2026-07-31 | 100% | Completed |  |  |  | 2026-12-31 | 67.27% | On Schedule |  |  |  | 2026-12-01 | 50% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 71.6% | On Schedule | เริ่มติดตั้ง Chainlink แล้ว | 0 | ติดตั้งรั้ว Chain Link ปิดใต้ slab สูง 1.70 ม. (3,047 ม.) | #REF! | CV/AR |  | MDW-39546 | MDW-69592 | MDW-69593
155 | 155 | MDW-39550 | Lot02 | MO-CK13.1 | MO-CK | Satellite Store at OR21 - Civil & AR | สหชาติ |  |  | 2027-01-02 | 2026-08-30 | 100% | Completed | 2026-10-15 | 0% | Late |  |  |  | 2026-12-31 | 0% | On Schedule |  |  |  | 2026-12-01 | 100% | Completed | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 12.94% | On Schedule |  | 0 | เพิ่ม Sink ล้างเครื่องมือที่ห้อง Cleaner จำนวน 6 สถานี | #REF! | CV/AR+E&M |  | MDW-39550 | MDW-69600 | MDW-695601
156 | 156 | MDW-39549 | Lot02 | MO-CK13.2 | MO-CK | Maintenance Room and Satellite Store at Stations - Building Services | ประธาน |  |  | 2027-01-03 | 2026-08-30 | 100% | Completed | 2026-10-15 | 100% | Completed |  |  |  | 2026-12-31 | 80% | On Schedule |  |  |  | 2026-11-30 | 100% | Completed | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 81.18% | On Schedule |  | 0 | -ติดแอร์ห้องMaintenance และห้อง Cleaner จำนวน 6 สถานี '-มีระบบ LAN, TEL, CASS เป็น STEE Contract scope | #REF! | CV/AR+E&M |  | MDW-39549 | MDW-69598 | MDW-69599
157 | 157 | MDW-39551 | Lot02 | MO-CK14 | MO-CK | Modify Cleaner room at OR29 to be Train crew Standby office with facility system | ประธาน |  | Depot | 2026-07-01 | 2026-03-14 | 100% | Completed | 2026-04-29 | 100% | Completed |  |  |  | 2026-06-30 | 95% | Late |  |  |  | 2026-09-30 | 100% | Completed | 2026-10-07 | 0% | Late | 2026-10-30 | 0% | On Schedule |  | 91.76% | Late |  | 0 | ห้อง Train crew Standby office พร้อม facility ที่ OR29 ชั้น concourse | #REF! |  |  | MDW-39551 | MDW-69602 | MDW-69603
158 | 158 | MDW-39295 | Lot02 | MO-CK15.1 | MO-CK | Epoxy Floor Installation and Curb Installation at the Entrance - Civil & AR | สหชาติ |  | Depot | 2026-05-01 | 2026-01-27 | 100% | Completed | 2026-02-27 | 100% | Completed |  |  |  | 2026-04-30 | 100% | Completed |  |  |  | 2026-09-30 | 50% | Late | 2026-10-07 | 100% | Completed | 2026-10-30 | 0% | On Schedule |  | 95.88% | Late |  | 0 | เทพื้น Epoxyและติดตั้ง Curb หน้าประตูทางเข้า | #REF! | CV/AR+E&M |  | MDW-39295 | MDW-69341 | MDW-69342
159 | 159 | MDW-39296 | Lot02 | MO-CK15.2 | MO-CK | Change Electrical Equipment to be Explosion-proof type - Building Services | ประธาน |  | Depot | 2026-05-01 | 2025-12-13 | 100% | Completed | 2026-01-28 | 100% | Completed |  |  |  | 2026-04-30 | 90% | Late |  |  |  | 2026-09-30 | 0% | Late | 2026-10-07 | 0% | Late | 2026-10-30 | 0% | On Schedule |  | 87.06% | Late | Fore cast Nov-26 | 0 | ติดตั้งระบบดับเพลิงชนิดโฟม | #REF! | CV/AR+E&M |  | MDW-39296 | MDW-69343 | MDW-69344
160 | 160 | DWE-39024 | Lot02 | MO-CK16 | MO-CK | Dangerous waste Storage 30 x 5 m. =10 room | สหชาติ |  | Depot | 2026-05-01 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed |  |  |  | 2026-04-30 | 100% | Completed |  |  |  | 2026-07-15 | 100% | Completed | 2026-06-08 | 100% | Completed | 2026-09-30 | 0% | Late |  | 96.47% | Late |  | รวมกับ GEN7.1 |  | #REF! | CV/AR |  | DWE-39024 | DWE-69024 | DWE-69124
161 | 161 | 0 | Lot02 | MO-CK17 | MO-CK | Safety Sign all Depot Area building | สหชาติ |  | Depot | 2026-05-01 | 2025-11-28 | 100% | Completed | 2026-06-15 | 100% | Completed | 2026-09-20 | 27% | Late | 2026-10-15 | 0% | Late |  |  |  |  | 0% | Late |  | 0% | Late |  |  | Late |  | 24.67% | Late | GRS | รวมกับ GEN10 | ติดตั้งป้าย Safety Sign ภายใน ภายนอกทุกอาคาร (2500 ป้าย) | #REF! | CV/AR |  |  | 0 | 0
162 | 162 | 0 | Lot02 | MO-CK18 | MO-CK | Emergency escape route map | สหชาติ |  | Depot | 2027-01-01 | 2026-09-30 | 0% | Late | 2026-10-30 | 50% | On Schedule | 2026-12-31 | 0% | On Schedule | 2026-12-31 | 0% | On Schedule |  |  |  | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 5.263% | On Schedule | GRS | รวมกับ GEN10 | แผนที่เส้นทางหนีไฟฉุกเฉิน | #REF! | CV/AR |  |  | 0 | 0
163 | 163 | 0 | Lot02 | MO-CK19 | MO-CK | Traffic Line Marking (Thermoplastic Paint) | สหชาติ |  | Depot | 2026-05-01 | 2026-04-30 | 100% | Completed | 2026-06-15 | 100% | Completed | 2026-10-15 | 100% | Completed | 2026-10-15 | 25% | Late |  |  |  |  | 0% | Late |  | 0% | Late |  |  | Late |  | 48.91% | Late | GRS | รวมกับ GEN10 | ตีเส้นจราจรบนพื้นที่ slab ไปตามอาคารต่างๆ - ถนน 1 เลน 4,202 ม. - ถนน 2 เลน 1,115 ม. | #REF! | CV/AR |  |  | 0 | 0
164 | 164 | 0 | Lot02 | MO-CK20 | MO-CK | Emergency Car Parking location Painting in front of MWS | สหชาติ |  | Depot | 2026-05-01 | 2026-04-30 | 100% | Completed | 2026-06-15 | 100% | Completed | 2026-10-15 | 0% | Late | 2026-10-15 | 0% | Late |  |  |  |  | 0% | Late |  | 0% | Late |  |  | Late |  | 21.74% | Late | GRS | รวมกับ GEN10 | ตีเส้นจุดจอดรถชั่วคราว รถฉุกเฉิน หน้าอาคาร MWS จุดจอดรถฉุกเฉิน ขนาด 2.5 x 7 ม. (จำนวน 5 ช่อง) จุดจอดรถชั่วคราว ขนาด 2.5 x 5 ม. (จำนวน 4 ช่อง) | #REF! | CV/AR |  |  | 0 | 0
165 | 165 | GRS-39022 | Lot02 | MO-CK21 | MO-CK | Safety Line painting in MWS, Stabling Area, P-way, Track | สหชาติ |  | Depot | 2027-01-01 | 2026-06-01 | 100% | Completed | 2026-08-01 | 100% | Completed | 2026-10-15 | 100% | Completed | 2026-12-31 | 81% | On Schedule |  |  |  | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 82.74% | On Schedule | GRS | รวมกับ GEN10 | Safety Line ใน MWS, Stabling Area, P-way และจุดที่มีความเสี่ยงอื่นๆ - safety line ใน MWS (6,658 m.) - Safety line ใน P-way (548 m.) - เส้นแดงข้าง Track (4,817 m.) - เส้นเหลืองดำ Walk way Stabling Yard (4,824 m.) | #REF! | CV/AR |  | GRS-39022 | GRS-69001 | GRS-69022
166 | 166 | 0 | Lot02 | MO-CK22 | MO-CK | Fire escape stairs level signs in the Depot, VS and IVS areas | สหชาติ |  | Depot | 2027-01-01 | 2026-09-30 | 50% | Late | 2026-10-31 | 0% | On Schedule | 2026-10-20 | 0% | Late | 2026-12-31 | 0% | On Schedule |  |  |  | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 5.263% | On Schedule | GRS | รวมกับ GEN10 | ป้ายบันไดหนีไฟที่ Depot, VS และ IVS | #REF! | CV/AR |  |  | 0 | 0
167 | 167 | DWE-39026 | Lot02 | MO-CK23 | MO-CK | General waste Storage 22 x 5 m | สหชาติ |  | Depot | 2026-05-01 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed |  |  |  | 2026-04-30 | 100% | Completed |  |  |  | 2026-07-15 | 100% | Completed | 2026-06-08 | 100% | Completed | 2026-09-30 | 0% | Late |  | 96.47% | Late |  | รวมกับ GEN8.1 |  | #REF! | CV/AR |  | DWE-39026 | DWE-69026 | DWE-69126
168 | 168 | 0 | Lot02 | MO-CK24 | MO-CK | Modify Traffic paint and traffic sign | สหชาติ |  |  | 2026-05-01 | 2026-04-30 | 100% | Completed | 2026-06-15 | 100% | Completed | 2026-10-15 | 64% | Late | 2026-10-15 | 13% | Late |  |  |  |  | 0% | Late |  | 0% | Late |  | 0% | Late |  | 36% | Late | GRS | รวมกับ GEN10 | แก้ไขสัญลักษณ์ทิศทางจราจรบนถนน และป้ายจราจร | #REF! | CV/AR |  |  | 0 | 0
169 | 169 | 0 | Lot02 | MO-CK25 | MO-CK | Station Area sign 28 stations | สหชาติ |  |  | 2026-05-01 | 2026-06-15 | 80% | Late | 2026-06-30 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-12-20 | 0% | On Schedule |  |  |  |  | 0% | Late | 2026-10-07 | 0% | Late |  | 0% | Late |  | 18.95% | Late | GRS | รวมกับ GEN10 | ติดตั้งป้าย Station Area 28 สถานี (112 ป้าย) | #REF! | CV/AR |  |  | 0 | 0
170 | 170 |  | Lot02 | MO-CK26 | MO-CK | Safety and warning signage for lift and escalator at all station | สหชาติ |  | Depot | 2027-01-01 | 2026-06-16 | 100% | Completed | 2026-07-17 | 100% | Completed | 2027-01-31 | 76% | On Schedule | 2027-02-28 | 26% | On Schedule |  |  |  | 2026-11-30 | 0% | On Schedule |  | 0% | Late |  | 0% | Late |  | 45.47% | On Schedule | GRS | รวมกับ GEN10 | ป้ายเตือนความปลอดภัยสำหรับลิฟต์และบันไดเลื่อนทุกสถานี | #REF! | CV/AR
171 | 171 | MDW-39532 | Lot02 | MO-CK27 | MO-CK | Spike fence for Depot slab | สหชาติ |  | Depot | 2027-01-01 | 2026-07-31 | 70% | Late | 2026-08-31 | 0% | Late |  |  |  | 2026-12-31 | 0% | On Schedule |  |  |  | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 8.235% | On Schedule | อยู่ระหว่างส่งขออนุมัติแบบรอ Approve | 0 | ติดตั้งรั้วเหล็กแหลม Depot slab (5,568 ม.) ยกเลิก Spike fence มีกล้องล้อมรอบ Depot platform เพิ่มรั้วหีบเพลงบริเวณจุดที่ใกล้ถนนกับจุดที่รั้วเตี้ย | #REF! |  |  | MDW-39532 | MDW-69564 | MDW-69565
172 | 172 | 0 | Lot02 | MO-CK28 | MO-CK | Bird net and Flashing at MWS and Skywalk to Stabling yard | สหชาติ |  |  | 2026-05-01 | [28 empty] | ยกเลิก |  | #REF! | CV/AR |  |  | 0 | 0
173 | 173 | MDW-39541 | Lot02 | MO-CK29 | MO-CK | Fire Alarm Manual Call Point signage at all elevated station | สหชาติ |  |  | 2027-01-01 |  |  |  | 2026-07-30 | 100% | Completed | [19 empty] | 12.5% | On Schedule |  | Includeed in GRS Lot1 | ป้ายแจ้งเหตุเพลิงไหม้แบบแมนนวลที่สถานีลอยฟ้าทั้งหมด | #REF! | CV/AR |  | MDW-39541 | MDW-69582 | MDW-69583
174 | 174 | 0 | Lot02 | MO-CK30 | MO-CK | Lighting for sealed space under stairs and behind lift shaft at underground station | ประธาน |  |  | 2027-01-01 | 2026-10-14 | 0% | Late | 2026-11-14 | 0% | On Schedule |  |  |  | 2026-12-31 | 0% | On Schedule |  |  |  | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 0% | On Schedule | ไฟส่องสว่างสำหรับพื้นที่ปิดใต้บันไดและด้านหลังช่องลิฟต์ที่สถานีรถไฟใต้ดิน | ยกเลิก | ไฟส่องสว่างสำหรับพื้นที่ปิดใต้บันไดและด้านหลังช่องลิฟต์ที่สถานีรถไฟใต้ดิน | #REF! |  |  |  | 0 | 0
175 | 175 | 0 | Lot02 | MO-CK31 | MO-CK | Modify the access door of sealed space (under-stairs room) with a Sump Pump or ESPS cabinet | สหชาติ |  |  | 2027-01-01 | 2026-07-16 | 0% | Late | 2026-08-16 | 0% | Late |  |  |  | 2026-12-31 | 0% | On Schedule |  |  |  | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 0% | On Schedule |  | 0 | ปรับเปลี่ยนประตูทางเข้าพื้นที่ปิด (ห้องใต้บันได) ด้วยตู้ Sump Pump หรือ ESPS โดยขยายไปจนถึงประตูเต็ม เพิ่มแสงสว่างให้กับห้องใต้บันได | #REF! | CV/AR |  |  | 0 | 0
176 | 176 | 0 | Lot02 | MO-CK32 | MO-CK | Lighting to the sealed space (under-stairs room) with a Sump Pump or ESPS cabinet | ประธาน |  | Depot | 2027-01-01 | 2026-11-03 | 0% | On Schedule | 2026-12-04 | 0% | On Schedule |  |  |  | 2026-12-31 | 0% | On Schedule |  |  |  | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 0% | On Schedule | ซื้อสปอร์ตไลท์+แบต จำนวน 4 ชุด แทนการลากสายไฟ | ยกเลิก | ซื้อสปอร์ตไลท์+แบต จำนวน 4 ชุด แทนการลากสายไฟ | #REF! |  |  |  | 0 | 0
177 | 177 | 0 | Lot02 | MO-CK33 | MO-CK | Additional lighting in areas where the lux level does not meet occupational health standards | ประธาน |  | Depot | 2027-01-01 | 2026-09-14 | 100% | Completed | 2026-10-15 | 100% | Completed |  |  |  | 2026-12-31 | 95% | On Schedule |  |  |  | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 90.59% | On Schedule |  | 0 | เพิ่มแสงสว่างในพื้นที่ที่ระดับลักซ์ไม่ตรงตามมาตรฐานอาชีวอนามัย | #REF! |  |  |  | 0 | 0
178 | 178 | 0 | Lot02 | MO-CK34 | MO-CK | Provide and install confined space signage for Station and Depot | สหชาติ |  |  | 2027-01-01 | 2026-08-15 | 100% | Completed | 2026-09-15 | 100% | Completed | 2027-01-31 | 76% | On Schedule | 2027-02-28 | 26% | On Schedule |  |  |  | 2026-11-30 | 0% | On Schedule |  | 0% | Late |  | 0% | Late |  | 45.47% | On Schedule | GRS | 0 | จัดทำและติดตั้งป้ายพื้นที่จำกัดสำหรับสถานีและDepot | #REF! | CV/AR |  |  | 0 | 0
179 | 179 |  | Lot02 | MO-CK35 | MO-CK | Build room for Train crew main office at OR18 with office area, resting area, meeting room, pantry, toilet and locker room | สหชาติ/บัณฑิต/ประธาน |  | Depot | - | [28 empty] | ยกเลิก |  | #REF!
180 | 180 |  | Lot02 | MO-CK36 | MO-CK | Dormitory Cable Containments (if any) | มนตรี |  | Depot | - | [28 empty] | ยกเลิก |  | #REF!
181 | 181 | 0 | Lot02 | MO-CK37 | MO-CK | Provide Raise floor and building Service in Training &Simulator (OCC Admin) | สหชาติ |  | Depot | - | [28 empty] | 0 |  | #REF! |  |  |  | 0 | 0
182 | 182 |  | Lot02 | MO-CK38 | MO-CK | Add N2 in Playback and Training Room and Backup Control Room | บุญประเสริฐ |  | Depot | - | [28 empty] | 0 |  | #REF!
183 | 183 | MDW-39505 | Lot02 | MO-BEM1.1 | MO-BEM | Walkway from Main Work Shop to Stabling Area - Civil & AR | สหชาติ |  | Depot | 2026-08-02 | 2026-04-28 | 100% | Completed | 2026-05-29 | 92% | Late |  |  |  | 2026-09-30 | 93% | Late |  |  |  | 2026-08-31 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late |  | 89.41% | Late | คงเหลืองานมุงหลังคา Metal sheet | 0 | Walkway 1.5m(W) x 2m.(H) ระดับเดียวกับ platform | #REF! | CV/AR+E&M |  | MDW-39505 | MDW-69510 | MDW-69511
184 | 184 | MDW-39506 | Lot02 | MO-BEM1.2 | MO-BEM | Walkway from Main Work Shop to Stabling Area - Building Services | ประธาน |  | Depot | 2026-08-02 | 2026-04-28 | 100% | Completed | 2026-05-29 | 100% | Completed |  |  |  | 2026-09-30 | 0% | Late |  |  |  | 2026-09-23 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late |  | 24.71% | Late | รองานหลังคา CIV Oct-26 | 0 | Walkway 1.5m(W) x 2m.(H) ระดับเดียวกับ platform | #REF! | CV/AR+E&M |  | MDW-39506 | MDW-69512 | MDW-69513
185 | 185 | MDW-39507 | Lot02 | MO-BEM2 | MO-BEM | High Roof at Main Work Shop Entrance and Store | สหชาติ |  | Depot | 2026-08-01 | 2026-02-13 | 100% | Completed | 2026-03-31 | 100% | Completed |  |  |  | 2026-07-31 | 100% | Completed |  |  |  | 2026-07-01 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late |  | 95.29% | Late | กำลังทำเอกสาร Test Report |  | 1.หลังคาสูงด้านหน้าทางเข้า MWS + Store -12x35x5.5m. = 420 sqm. 2.หลังคาสูงบน Roller Shutter หน้า Store -10x4x5.5m. = 40 sqm. |  | CV/AR |  | MDW-39507 | MDW-69514 | MDW-69515
186 | 186 | MDW-39509 | Lot02 | MO-BEM3 | MO-BEM | High Roof at the entrance and exit of the under floor wheel lathe | สหชาติ |  | Depot | 2026-08-04 | 2026-02-13 | 100% | Completed | 2026-03-31 | 100% | Completed |  |  |  | 2026-07-31 | 100% | Completed |  |  |  | 2026-07-01 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late |  | 95.29% | Late | กำลังทำเอกสาร Test Report |  | หลังคาสูงด้านหน้าทางเข้าเคริ้องกลึงล้อ -5.2 wide x 20 m long x5.5 m.high for each side |  | CV/AR |  | MDW-39509 | MDW-69518
187 | 187 | MDW-39511 | Lot02 | MO-BEM4.1 | MO-BEM | Maintenance Office Rooms at Main Workshop - Civil & AR | สหชาติ |  | Depot | 2026-07-03 | 2026-04-13 | 100% | Completed | 2026-05-14 | 100% | Completed |  |  |  | 2026-06-30 | 100% | Completed |  |  |  | 2026-05-31 | 100% | Completed | 2026-09-30 | 100% | Completed | 2026-10-21 | 0% | Late |  | 96.47% | Late |  | 0 | ติดตั้ง - หน้าต่าง - พื้นกระเบื้องเซรามิก | #REF! | CV/AR+E&M |  | MDW-39511 | MDW-69522 | MDW-69523
188 | 188 | MDW-39512 | Lot02 | MO-BEM4.2 | MO-BEM | Maintenance Office Rooms at Main Workshop - Building Services | ประธาน |  | Depot | 2026-07-04 | 2026-04-13 | 100% | Completed | 2026-05-14 | 100% | Completed |  |  |  | 2026-06-30 | 100% | Completed |  |  |  | 2026-09-23 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late |  | 95.29% | Late | รอส่งงานกับ BEM | 0 | ติดตั้ง - ระบบแอร์ - ระบบไฟแสงสว่าง - ปลั๊กไฟ | #REF! | CV/AR+E&M |  | MDW-39512 | MDW-69524 | MDW-69525
189 | 189 | MDW-39513 | Lot02 | MO-BEM5 | MO-BEM | Install Concrete car barrier along the walkway in front of MWS building | สหชาติ |  | Depot | 2027-01-01 | 2026-10-14 | 100% | Completed | 2026-11-14 | 100% | Completed |  |  |  | 2026-12-31 | 100% | Completed |  |  |  | 2026-12-01 | 50% | On Schedule | 2027-01-07 | 100% | Completed | 2027-01-28 | 0% | On Schedule |  | 95.88% | On Schedule |  | 0 | คันคอนกรีตทางเดินหน้า MWS | #REF! | CV/AR |  | MDW-39513 | MDW-69526 | MDW-69527
190 | 190 | 0 | Lot02 | MO-BEM6 | MO-BEM | Handrail on top of the water tank on the rooftop of the Admin Building | สหชาติ |  | Depot | 2027-01-01 | 2026-10-19 | 100% | Completed | 2026-11-19 | 100% | Completed |  |  |  | 2026-12-31 | 0% | On Schedule |  |  |  | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 23.53% | On Schedule |  | 0 | ราวจับบนถังเก็บน้ำบนดาดฟ้าอาคาร Admin 1.รูปแบบทำเฉพาะจุด water tank 1 ด้าน 2.เสริมguard rail ของบันได 3.ทำตัวค้ำฝาเปิด water tank | #REF! | CV/AR |  |  | 0 | 0
191 | 191 | 0 | Lot02 | MO-BEM7 | MO-BEM | Modify maintenance service door to the roof building to easier access while maintaining safe operational standards | สหชาติ |  | Depot | 2027-01-01 | 2026-10-19 | 50% | Late | 2026-11-19 | 0% | On Schedule |  |  |  | 2026-12-31 | 0% | On Schedule |  |  |  | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 5.882% | On Schedule |  | 0 | - อาคาร admin: ถังน้ำบนหลังคา - เพิ่มราวกันตกประมาณ 6 เมตร, เหล็กค้ำฝา, เพิ่มเหล็กกันหลังบันไดลิง (ของเดิมห่าง) | #REF! | CV/AR |  |  | 0 | 0
192 | 192 | MDW-39536 | Lot02 | MO-BEM8 | MO-BEM | Company logo and Central Control Room sign in CCR room. | สหชาติ |  | Depot | 2026-05-01 | 2026-01-27 | 100% | Completed | 2026-03-14 | 100% | Completed |  |  |  | 2026-04-30 | 100% | Completed |  |  |  | 2026-09-30 | 50% | Late | 2026-10-07 | 0% | Late | 2026-10-30 | 0% | On Schedule |  | 94.71% | Late |  | 0 | ติตดั้งโลโก้บริษัทแลป้ายห้องควบคุมกลางในห้อง CCR | #REF! | CV/AR |  | MDW-39536 | MDW-69572 | MDW-69573
193 | 193 | MDW-39536 | Lot02 | MO-BEM9 | MO-BEM | Soundproof insulation on the wall and structure and equipment in the CCR room. | สหชาติ |  | Depot | 2026-05-01 | 2026-01-12 | 100% | Completed | 2026-02-27 | 100% | Completed |  |  |  | 2026-04-30 | 100% | Completed |  |  |  | 2026-09-30 | 50% | Late | 2026-10-07 | 0% | Late | 2026-10-30 | 0% | On Schedule |  | 94.71% | Late |  | 0 | ฉนวนกันเสียงบนผนังและอุปกรณ์ในห้อง CCR | #REF! | CV/AR |  | MDW-39536 | MDW-69572 | MDW-69573
194 | 194 | MDW-39526 | Lot02 | MO-BEM10 | MO-BEM | Relocate Fire Hose Cabinet to be outside of the clearance gauge zone 17 set | ประธาน |  | Depot | 2026-05-01 | 2026-01-12 | 100% | Completed | 2026-02-27 | 100% | Completed |  |  |  | 2026-04-30 | 100% | Completed |  |  |  | 2026-03-18 | 100% | Completed | 2026-09-30 | 100% | Completed | 2026-05-15 | 100% | Completed |  | 100% | Late |  | 0 | ตู้ FHC ขยับหมุนให้สามารถเปิดตู้ใช้งานได้พอ (มีย้ายแค่1ตู้ที่มีปัญหาเปิดไม่ได้เลย) มีงานย้ายถังดับเพลิงด้วย | #REF! |  |  | MDW-39526 | MDW-69552 | MDW-69553
195 | 195 | MDW-39528 | Lot02 | MO-BEM11.1 | MO-BEM | Washing Area in Cleaning Staff Room at Stabling Yard - Civil & AR | สหชาติ |  | Depot | 2026-08-03 | 2026-06-03 | 100% | Completed | 2026-07-04 | 100% | Completed |  |  |  | 2026-07-31 | 100% | Completed |  |  |  | 2026-07-01 | 100% | Completed | 2026-09-30 | 50% | Late | 2026-10-15 | 0% | Late |  | 95.88% | Late |  | 0 | พื้นที่ซักล้าง มีระบบน้ำดี และระบายน้ำเสียเข้าระบบบำบัดของอาคาร | #REF! | CV/AR+E&M |  | MDW-39528 | MDW-69556 | MDW-69557
196 | 196 | MDW-39529 | Lot02 | MO-BEM11.2 | MO-BEM | Washing Area in Cleaning Staff Room at Stabling Yard - Building Services | ประธาน |  | Depot | 2026-08-04 | 2026-04-14 | 100% | Completed | 2026-05-30 | 100% | Completed |  |  |  | 2026-07-31 | 100% | Completed |  |  |  | 2026-03-31 | 100% | Completed | 2026-07-01 | 100% | Completed | 2026-07-10 | 100% | Completed |  | 100% | Completed |  | 0 | พื้นที่ซักล้าง มีระบบน้ำดี และระบายน้ำเสียเข้าระบบบำบัดของอาคาร | #REF! | CV/AR+E&M |  | MDW-39529 | MDW-69558 | MDW-69559
197 | 197 | MDW-39522 | Lot02 | MO-BEM12 | MO-BEM | Rain protection for Water treatment Building | สหชาติ |  | Depot | 2026-08-05 | 2026-04-29 | 100% | Completed | 2026-05-30 | 100% | Completed |  |  |  | 2026-07-31 | 100% | Completed |  |  |  | 2026-07-01 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late |  | 95.29% | Late |  | 0 | ติดตั้งผนัง Louver กันฝนสาด | #REF! | CV/AR |  | MDW-39522 | MDW-69544 | MDW-69545
198 | 198 | MDW-39522 | Lot02 | MO-BEM13.1 | MO-BEM | Zero Discharge Water treatment in Depot - Civil & AR | สหชาติ |  | Depot | 2027-01-01 | 2026-08-15 | 100% | Completed | 2026-09-30 | 75% | Late |  |  |  | 2026-12-31 | 63% | On Schedule | [6 empty] | 2027-01-07 | 0% | On Schedule |  |  |  |  | 68.27% | On Schedule | คงเหลืองานประกอบและติดตั้งโครงหลงัคา | @ เพิ่มใน MS Project | จากwater treatment ไปลงบ่อใหม่ (บ่อปูน) ขุดบ่อเพิ่ม ขนาด 5x5 m. | #REF! | CV/AR+E&M |  | MDW-39522 | MDW-69544 | MDW-69545 | Evaporator Pond & Sumpit
199 | 199 | MDW-39530 | Lot02 | MO-BEM13.2 | MO-BEM | Zero Discharge Water treatment in Depot - Building Services | ประธาน |  | Depot | 2027-01-01 | 2026-08-15 | 100% | Completed | 2026-09-30 | 100% | Completed |  |  |  | 2026-12-31 | 50% | On Schedule |  |  |  | 2026-10-30 | 100% | Completed | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 60% | On Schedule |  | @ เพิ่มใน MS Project | จากwater treatment ไปลงบ่อใหม่ (บ่อปูน) ขุดบ่อเพิ่ม ขนาด 5x5 m. | #REF! | CV/AR+E&M |  | MDW-39530 | MDW-69560 | MDW-69561
200 | 200 | MDW-39516 | Lot02 | MO-BEM14.1 | MO-BEM | Modification Works : Walkway Bridge between BL Depot and ORL Depot - Civil & AR | สหชาติ |  | Depot | 2026-08-02 | 2026-02-28 | 100% | Completed | 2026-06-15 | 100% | Completed |  |  |  | 2026-09-30 | 95% | Late |  |  |  | 2026-08-31 | 100% | Completed | 2026-10-07 | 0% | Late | 2026-10-21 | 0% | Late |  | 91.76% | Late | คงเหลืองานติดตั้งสะพานและปรับพื้นที่ถนน | 0 | สะพานข้ามคลองขนาดเล็ก จาก Depot ORL มายัง Depot BL สะพาน3จุด ขนาด 2 m. | #REF! | CV/AR+E&M |  | MDW-39516 | MDW-69532 | MDW-69533
201 | 201 | MDW-39517 | Lot02 | MO-BEM14.2 | MO-BEM | Modification Works : Walkway Bridge between BL Depot and ORL Depot - Building Services | ประธาน |  | Depot | 2026-08-03 | 2026-01-14 | 100% | Completed | 2026-03-01 | 100% | Completed |  |  |  | 2026-09-30 | 10% | Late |  |  |  | 2026-08-31 | 100% | Completed | 2026-10-07 | 0% | Late | 2026-10-21 | 0% | Late |  | 31.76% | Late | รองานหลังคา CIV Oct-26 | 0 | สะพานข้ามคลองขนาดเล็ก จาก Depot ORL มายัง Depot BL สะพาน3จุด ขนาด 2 m. | #REF! | CV/AR+E&M |  | MDW-39517 | MDW-69534 | MDW-69535
202 | 202 | MDW-39514 | Lot02 | MO-BEM15.1 | MO-BEM | Roof for cars parking lots area (184 car)t - Civil & AR | สหชาติ |  | Depot | 2026-08-03 | 2026-02-28 | 100% | Completed | 2026-03-31 | 100% | Completed |  |  |  | 2026-07-31 | 100% | Completed |  |  |  | 2026-07-24 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late |  | 95.29% | Late | กำลังทำเอกสาร Test Report |  | ทำหลังคาสำหรับลานจอดรถ 184 คัน |  | CV/AR |  | MDW-39514 | MDW-69528 | MDW-69529
203 | 203 | MDW-39515 | Lot02 | MO-BEM15.2 | MO-BEM | Roof for cars parking lots area (184 car) - Building Services | ประธาน |  | Depot | 2026-08-03 | 2026-02-28 | 100% | Completed | 2026-03-31 | 100% | Completed |  |  |  | 2026-07-31 | 100% | Completed |  |  |  | 2026-09-23 | 0% | Late | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late |  | 94.12% | Late | รอส่งงานกับ BEM | 0 | ทำหลังคาสำหรับลานจอดรถ 184 คัน | #REF! |  |  | MDW-39515 | MDW-69530 | MDW-69531
204 | 204 | MDW-39519 | Lot02 | MO-BEM16 | MO-BEM | Walkway roof and High roof across the road from Admin ORL to Depot slap | สหชาติ |  | Depot | 2026-08-01 | 2026-06-15 | 100% | Completed | 2026-06-30 | 100% | Completed |  |  |  | 2026-10-31 | 57% | On Schedule |  |  |  | 2026-08-31 | 100% | Completed | 2026-11-07 | 0% | On Schedule | 2026-11-28 | 0% | On Schedule |  | 64.94% | Late | คงเหลืองานโครงเหล็ก หลังคา และ Composite | 0 | หลังคาสูงข้ามถนนจากอาคาร Admin ไปยัง Depot slab เพื่อเข้า MWS หลังคาสูง 5.5m.รวมคานเหล็กกันรถสูงผ่าน | #REF! | CV/AR |  | MDW-39519 | MDW-69538 | MDW-69539 | Overhead Bridge Canteen
205 | 205 | MDW-39519 | Lot02 | MO-BEM17 | MO-BEM | Walkway roof to car park in front of admin ORL(3x5m.) | สหชาติ |  | Depot | 2026-08-01 | 2026-06-15 | 100% | Completed | 2026-06-30 | 100% | Completed |  |  |  | 2026-10-31 | 70% | On Schedule |  |  |  | 2026-08-31 | 100% | Completed | 2026-11-07 | 0% | On Schedule | 2026-11-28 | 0% | On Schedule |  | 74.12% | Late | คงเหลืองานโครงหลังคาและมุงหลังคา | Includeed under Item MO-BEM16 | หลังคากันฝนทางเดินลงลานจอดหน้าอาคารบริหาร ขนาด 3x5 ม. | #REF! | CV/AR |  | MDW-39519 | MDW-69538 | MDW-69539 | Roof at admin entrance
206 | 206 | MDW-39519 | Lot02 | MO-BEM18 | MO-BEM | Walkway roof over the footpath near depot slab (1.50 m. x 290 m.) and stair up to depot slap. | สหชาติ |  | Depot | 2026-08-01 | 2026-06-15 | 100% | Completed | 2026-06-30 | 100% | Completed |  |  |  | 2026-10-31 | 0% | On Schedule |  |  |  | 2026-08-31 | 100% | Completed | 2026-11-07 | 0% | On Schedule | 2026-11-28 | 0% | On Schedule |  | 24.71% | Late | รอ BEM สรุปว่ายกเลิกหรือทำ | Includeed under Item MO-BEM16 | ทำทางเดินฟุตบาทบริเวณ depot slab และบันไดทางขึ้น | #REF! | CV/AR |  | MDW-39519 | MDW-69538 | MDW-69539
207 | 207 | MDW-39557 | Lot02 | MO-BEM19 | MO-BEM | Install Chain Link fence to enclose parking area | สหชาติ |  | Depot | 2026-10-01 | 2026-06-29 | 100% | Completed | 2026-07-30 | 100% | Completed |  |  |  | 2026-09-30 | 0% | Late |  |  |  | 2026-09-30 | 90% | Late | 2026-10-07 | 0% | Late | 2026-10-28 | 0% | Late |  | 24.59% | On Schedule |  | Includeed under Item MO-BEM25.1 | รั้ว Chain Link ปิดกั้นพื้นที่ลานจอดรถยาว 180 ม.x สูง 2.5 ม. | #REF! | CV/AR |  | MDW-39557 | MDW-69614 | MDW-69615
208 | 208 | MDW-39523 | Lot02 | MO-BEM20 | MO-BEM | Hose bib 1/2" 4 sets for Tree around Admin area | ประธาน |  | Depot | 2026-06-01 | 2026-04-23 | 100% | Completed | 2026-06-08 | 100% | Completed |  |  |  | 2026-07-31 | 100% | Completed |  |  |  | 2026-03-31 | 100% | Completed | 2026-09-30 | 100% | Completed | 2026-07-10 | 100% | Completed |  | 100% | Late |  | 0 |  | #REF! |  |  | MDW-39523 | MDW-69546 | MDW-69547
209 | 209 | - | Lot02 | MO-BEM21 | MO-BEM | Relocate Security Guard Box at Front Gate and Install Roof 3x5m. | สหชาติ |  | Depot | 2027-01-03 | 2026-07-31 | 100% | Completed | 2026-09-30 | 75% | Late |  |  |  | 2026-12-31 | 0% | On Schedule |  |  |  | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 20.59% | On Schedule |  | รวมกับ MO-BEM52 | ย้ายป้อมรปภ.หน้าทางเข้า + ติดตั้งหลังคา 3x5 ม. | #REF! | CV/AR |  |  | 0 | 0
210 | 210 | MDW-39534 | Lot02 | MO-BEM21.1 | MO-BEM | Modification Works : Security Guard Box at ORL Depot Entrance - Civil & AR | สหชาติ |  | Depot | 2027-01-02 | 2026-07-31 | 100% | Completed | 2026-09-30 | 67% | Late |  |  |  | 2026-12-31 | 100% | Completed |  |  |  | 2026-12-01 | 50% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 90.82% | On Schedule |  | @ เพิ่มใน MS Project |  | #REF! | CV/AR+E&M |  | MDW-39534 | MDW-69568 | MDW-69569
211 | 211 | MDW-39535 | Lot02 | MO-BEM21.2 | MO-BEM | Modification Works : Security Guard Box at ORL Depot Entrance - Building Services | ประธาน |  | Depot | 2027-01-03 | 2026-07-31 | 100% | Completed | 2026-09-30 | 100% | Completed |  |  |  | 2026-12-31 | 50% | On Schedule |  |  |  | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 58.82% | On Schedule |  | @ เพิ่มใน MS Project |  | #REF! | CV/AR+E&M |  | MDW-39535 | MDW-69570 | MDW-69571
212 | 212 | MDW-39532 | Lot02 | MO-BEM22 | MO-BEM | Addition Spike fence for MRTA fence and Chain link at Klong Chourdyai 400m. | สหชาติ |  | Depot | 2027-01-01 | 2026-08-30 | 70% | Late | 2026-09-30 | 0% | Late |  |  |  | 2026-12-31 | 0% | On Schedule |  |  |  | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 8.235% | On Schedule | อยู่ระหว่างส่งขออนุมัติแบบรอ Approve | 0 | ติดตั้งรั้วเหล็กแหลม แนวรั้วรฟม.+ แนวรั้ว Chainlink ฝั่งริมคลองชวดใหญ่ ไม่ทำเหล็กแหลม ทำรั้วหีบเพลงตลอดแนว + ติดกล้อง | #REF! |  |  | MDW-39532 | MDW-69564 | MDW-69565
213 | 213 | MDW-39527 | Lot02 | MO-BEM23 | MO-BEM | Hand sink with eye wash station | ประธาน | พี่ต่อ | Depot | 2027-01-01 | 2026-08-30 | 100% | Completed | 2026-10-15 | 100% | Completed |  |  |  | 2026-12-31 | 100% | Completed |  |  |  | 2026-12-01 | 100% | Completed | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 95.29% | On Schedule |  | 0 | รูปแบบเป็นแบบอ่างล้างสำเร็จรูป ไม่เป็นก่อปูน - Eye wash ทำเป็นถังไว้ให้ ไม่ต่อท่อ - Hand wash ทำท่อลงไปยังถังบำบัดจากห้องน้ำ (มีถังดักไขมัน) | #REF! |  |  | MDW-39527 | MDW-69554 | MDW-69555
214 | 214 | MDW-39531 | Lot02 | MO-BEM24 | MO-BEM | Guard rail protection for Fire Hose Cabinet 8 set | สหชาติ |  | Depot | 2026-06-01 | 2026-03-14 | 100% | Completed | 2026-04-14 | 100% | Completed |  |  |  | 2026-08-15 | 100% | Completed |  |  |  | 2026-07-16 | 100% | Completed | 2026-09-30 | 100% | Completed | 2026-10-21 | 0% | Late |  | 96.47% | Late |  | 0 | Guard กันชนตู้ Fire Hose Cabinet สูง 1 ม. กว้าง 0.7 ม. | #REF! | CV/AR |  | MDW-39531 | MDW-69562 | MDW-69563
215 | 215 | MDW-39557 | Lot02 | MO-BEM25.1 | MO-BEM | Chain Link Fence to divide controlled areas on Depot slab 3 m.x 485 m. - Civil & AR | สหชาติ |  | Depot | 2026-10-01 | 2026-06-14 | 100% | Completed | 2026-07-30 | 100% | Completed |  |  |  | 2026-09-30 | 0% | Late |  |  |  | 2026-09-30 | 50% | Late | 2026-10-07 | 0% | Late | 2026-10-28 | 0% | Late |  | 24.12% | On Schedule |  | 0 | ติดตั้งรั้ว Chain Link แบ่งกั้นพื้นที่ควบคุมบน Depot slab สูง 3 ม.ยาว 485 ม. | #REF! | CV/AR+E&M |  | MDW-39557 | MDW-69614 | MDW-69615
216 | 216 | MDW-39520 | Lot02 | MO-BEM25.2 | MO-BEM | Chain Link Fence to divide controlled areas on Depot slab 3 m.x 485 m.- Building Services | ประธาน |  | Depot | 2026-10-01 | 2026-06-14 | 100% | Completed | 2026-07-30 | 100% | Completed |  |  |  | 2026-09-30 | 0% | Late |  |  |  | 2026-09-30 | 0% | Late | 2026-10-07 | 0% | Late | 2026-10-28 | 0% | Late |  | 23.53% | On Schedule | Fore cast Oct-26 | 0 | ติดตั้งรั้ว Chain Link แบ่งกั้นพื้นที่ควบคุมบน Depot slab สูง 3 ม.ยาว 485 ม. | #REF! | CV/AR+E&M |  | MDW-39520 | MDW-69540 | MDW-69541
217 | 217 | MDW-39518 | Lot02 | MO-BEM26 | MO-BEM | Street Lighting system area between MRTA Fence and Depot slab | ประธาน |  | Depot | 2026-08-01 | 2026-04-14 | 50% | Late | 2026-05-15 | 0% | Late |  |  |  | 2026-07-31 | 0% | Late |  |  |  | 2026-09-30 | 0% | Late | 2026-10-07 | 0% | Late | 2026-10-28 | 0% | Late |  | 5.882% | Late | อยู่ระหว่างจัดเตรียมแบบ งาน Construction จบ Mar-27 | 0 | ทางเดินหลัง MWS-Permanent way ค่า LUX. 25 Lux as minimum - 50 lux อ้างอิงกรมสวัสดิการคุ้มครองแรงงาน 2561 (ใกล้เคียงกับ BLE) | #REF! |  |  | MDW-39518 | MDW-69536 | MDW-69537
218 | 218 | - | Lot02 | MO-BEM27 | MO-BEM | Compacted gravel walkway along the Test Track OR-BL 1.2 m. | สหชาติ | พรพรหม | Depot | 2027-01-01 | 2026-08-30 | 100% | Completed | 2026-09-30 | 0% | Late |  |  |  | 2026-12-31 | 0% | On Schedule |  |  |  | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 11.76% | On Schedule |  | 0 | ไม่ทำทางเดิน ทำรั้ว Chainlink ปิดต้น-ปลายทาง + ทำประตูเล็กแทน (ใส่กุญแจล็อก) | #REF! | CV/AR |  |  | 0 | 0
219 | 219 | MDW-39524 | Lot02 | MO-BEM28.1 | MO-BEM | Walkway under Depot Slab for Maintenance Service - Civil & AR | สหชาติ |  | Depot | 2027-01-02 | 2026-09-14 | 100% | Completed | 2026-10-30 | 100% | Completed |  |  |  | 2026-12-31 | 100% | Completed |  |  |  | 2026-12-01 | 50% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 94.71% | On Schedule |  | 0 | -Walk way under slab 270m. -Walk way and support up to Waste water tank 8 set -Bridge over gutter 2 set | #REF! | CV/AR+E&M |  | MDW-39524 | MDW-69548 | MDW-69549
220 | 220 | MDW-39525 | Lot02 | MO-BEM28.2 | MO-BEM | Walkway under Depot Slab for Maintenance Service - Building Services | ประธาน |  | Depot | 2027-01-03 | 2026-09-14 | 100% | Completed | 2026-10-30 | 100% | Completed |  |  |  | 2026-12-31 | 50% | On Schedule |  |  |  | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 58.82% | On Schedule |  | 0 | -lighting for Waste water tank 7 set | #REF! | CV/AR+E&M |  | MDW-39525 | MDW-69550 | MDW-69551
221 | 221 | MDW-39521 | Lot02 | MO-BEM29 | MO-BEM | Walkway Bridge across the canal for Depot area inspection patrols 3 location | สหชาติ |  | Depot | 2027-01-01 | 2026-08-15 | 100% | Completed | 2026-09-30 | 67% | Late |  |  |  | 2026-12-31 | 95% | On Schedule |  |  |  | 2026-12-01 | 100% | Completed | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 87.88% | On Schedule | เหลืองานติดตั้งสะพานข้ามคลอง + ประตูรั้ว + Modify Chainlink | 0 | Walkway Bridge over canal for Security patrol 3 set สะพานเหล็กกว้าง 2 ม. 3 จุด | #REF! | CV/AR |  | MDW-39521 | MDW-69542 | MDW-69543
222 | 222 | - | Lot02 | MO-BEM30 | MO-BEM | Cut down trees between Depot BL+ORL and MRTA Fence | สหชาติ |  | Depot | 2027-01-01 | 2026-10-29 | 0% | Late | 2026-11-29 | 0% | On Schedule |  |  |  | 2026-12-31 | 0% | On Schedule |  |  |  | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 0% | On Schedule |  | 0 | ตัดต้นไม้ตลอดแนวรั้ว Depot BL+ORL ดำเนินการ 1 ครั้งก่อนเปิดเดินรถ | #REF! | CV/AR |  |  | 0 | 0
223 | 223 | 0 | Lot02 | MO-BEM31 | MO-BEM | Provide facility system and interface to MMC room (Fire Alarm / CCTV / VMS / TEL / CASS / Radio / PA) | บัณฑิต |  | Depot | 2026-10-01 | [28 empty] | ยกเลิก | เพิ่ม CCTV ที่ Dorm และ Link FA/CCTV/CASS ไปที่ MMC | #REF! |  |  |  | 0 | 0
224 | 224 | - | Lot02 | MO-BEM32 | MO-BEM | Stainless Guard rail balustrade for waiting area | สหชาติ |  | Depot | 2026-05-01 | [28 empty] | ยกเลิก |  | #REF! | CV/AR |  |  | 0 | 0
225 | 225 | - | Lot02 | MO-BEM33 | MO-BEM | Concrete walkway 2 x 80 m. For fire escape route | สหชาติ |  | Depot | 2026-05-01 | [28 empty] | ยกเลิก |  | #REF! | CV/AR |  |  | 0 | 0
226 | 226 | - | Lot02 | MO-BEM34 | MO-BEM | Access Gate (Full Height Turnstile) at 1st floor admin ORL | บัณฑิต |  | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed |  |  |  | 2026-12-31 | 0% | On Schedule |  |  |  | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 23.53% | On Schedule |  | 0 | Access Gate (Full Height Turnstile) ที่ทางลงลานจอดรถใต้อาคารบริหาร | #REF! | CV/AR |  |  | 0 | 0
227 | 227 | - | Lot02 | MO-BEM35 | MO-BEM | Access Gate (Tripod with Swing Gate) at MWS Entrance | บัณฑิต |  | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed |  |  |  | 2026-12-31 | 0% | On Schedule |  |  |  | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 23.53% | On Schedule | TMD เริ่มเข้าทำช่วงเดือน Oct-26 (CIV จบ) | 0 | Access Gate (Tripod with Swing Gate)ที่โถงทางเข้าออก MWS | #REF! |  |  |  | 0 | 0
228 | 228 | - | Lot02 | MO-BEM36 | MO-BEM | Access Gate (Tripod with Swing Gate) at Admin 2nd floor connect to OCC | บัณฑิต |  | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed |  |  |  | 2026-12-31 | 0% | On Schedule |  |  |  | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 23.53% | On Schedule | TMD เริ่มเข้าทำช่วงเดือน Oct-26 (CIV จบ) | 0 | Access Gate (Tripod with Swing Gate) จากตึกAdminชั้น2 ไป OCC | #REF! |  |  |  | 0 | 0
229 | 229 | - | Lot02 | MO-BEM37 | MO-BEM | Access Gate (Tripod with Swing Gate) on Klong Chourdyai bridge | บัณฑิต |  | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed |  |  |  | 2026-12-31 | 0% | On Schedule |  |  |  | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 23.53% | On Schedule | TMD เริ่มเข้าทำช่วงเดือน Oct-26 (CIV จบ) | 0 | Access Gate (Tripod with Swing Gate) บนสะพานข้ามคลองชวดใหญ่ | #REF! |  |  |  | 0 | 0
230 | 230 | - | Lot02 | MO-BEM38 | MO-BEM | Access Gate (Tripod with roof covering) at parking lot OCC | บัณฑิต |  | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed |  |  |  | 2026-12-31 | 0% | On Schedule |  |  |  | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 23.53% | On Schedule | TMD เริ่มเข้าทำช่วงเดือน Oct-26 (CIV จบ) | 0 | Access Gate (Tripod with roof covering) ที่ลานจอดรถพนักงานหลัง OCC | #REF! |  |  |  | 0 | 0
231 | 231 | - | Lot02 | MO-BEM39 | MO-BEM | Access Gate (Tripod with roof covering) at Stair up to Depot slab | บัณฑิต |  | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed |  |  |  | 2026-12-31 | 0% | On Schedule |  |  |  | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 23.53% | On Schedule | TMD เริ่มเข้าทำช่วงเดือน Oct-26 (CIV จบ) | 0 | Access Gate (Tripod with roof covering) ที่ทางขึ้นลง Depot slab | #REF! |  |  |  | 0 | 0
232 | 232 | - | Lot02 | MO-BEM40 | MO-BEM | Access Control (2 Factors, Card + Finger Print) at High Security rooms - CCR/PTR/Store | บัณฑิต |  | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed |  |  |  | 2026-12-31 | 0% | On Schedule |  |  |  | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 23.53% | On Schedule | STE เริ่มเข้าทำช่วงเดือน Oct-26 | 0 | ระบบตรวจสอบอัตลักษณ์ (2 Factors) บัตร+ลายนิ้วมือ หน้าห้องพื้นที่ Hight Security -CCR/PTR/Store | #REF! |  |  |  | 0 | 0
233 | 233 | - | Lot02 | MO-BEM41 | MO-BEM | Link CCTV Landscape of all depot ORL area for MMC BL monitoring. | บัณฑิต |  |  | 2027-01-01 | 2026-11-28 | 0% | On Schedule | 2026-11-29 | 0% | On Schedule |  |  |  | 2026-12-31 | 0% | On Schedule |  |  |  | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 0% | On Schedule | จัดจ้าง STE | จัดจ้าง STE | Link ภาพ CCTV รอบนอก ORL มายัง MMC BL เพิ่ม Workstation ที่ MMC BL แล้ว Link CCTV ORL ไป | #REF! |  |  |  | 0 | 0
234 | 234 | - | Lot02 | MO-BEM42 | MO-BEM | Fire Suppression Control Panel Cover which located in tunnel | สู่โชค |  |  | 2027-01-01 | [28 empty] | ยกเลิก |  | #REF! |  |  |  | 0 | 0
235 | 235 | MDW-39537 | Lot02 | MO-BEM43 | MO-BEM | Handrails for ladder at IVS and Vent buildings | สหชาติ |  |  | 2026-09-01 | 2026-03-31 | 70% | Late | 2026-05-01 | 0% | Late |  |  |  | 2026-08-31 | 0% | Late |  |  |  | 2026-10-31 | 0% | On Schedule | 2026-11-15 | 0% | On Schedule | 2026-11-30 | 0% | On Schedule |  | 8.235% | Late | อยู่ระหว่างส่งขออนุมัติแบบรอ Approve | 0 | ราวบันไดอาคาร IVS และ Vent | #REF! | CV/AR |  | MDW-39537 | MDW-69574 | MDW-69575
236 | 236 | MDW-39538 | Lot02 | MO-BEM44 | MO-BEM | Escalator Anti-Slide device for all station. | สหชาติ |  |  | 2026-09-01 | 2026-05-30 | 100% | Completed | 2026-06-30 | 100% | Completed | 2027-01-31 | 100% | Completed | 2027-02-28 | 70% | On Schedule |  |  |  | 2027-01-29 | 0% | On Schedule | 2027-02-28 | 0% | On Schedule | 2027-03-15 | 0% | On Schedule |  | 75.79% | On Schedule | GRS | 0 | อุปกรณ์ป้องกันการเลื่อนบันไดเลื่อนสำหรับทุกสถานี | #REF! | CV/AR |  | MDW-39538 | MDW-69576 | MDW-69577
237 | 237 | MDW-39539 | Lot02 | MO-BEM45 | MO-BEM | Roof for control panel on vent building | สหชาติ |  |  | 2027-01-01 | 2026-09-14 | 70% | Late | 2026-10-30 | 0% | On Schedule |  |  |  | 2026-12-31 | 0% | On Schedule |  |  |  | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 8.235% | On Schedule | อยู่ระหว่างส่งขออนุมัติแบบรอ Approve | 0 |  | #REF! | CV/AR |  | MDW-39539 | MDW-69578 | MDW-69579
238 | 238 | MDW-39553 | Lot02 | MO-BEM46 | MO-BEM | Provide Standing plate or ladder to access the Fire Valve in at Omega points for all underground stations. | สหชาติ |  | Depot | 2027-01-01 | 2026-09-14 | 0% | Late | 2026-10-30 | 0% | On Schedule |  |  |  | 2026-12-31 | 0% | On Schedule |  |  |  | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 0% | On Schedule |  | 0 | จัดหาบันไดสแตนเลสชั่วคราว 1ชุด/1สถานี | #REF! | CV/AR |  | MDW-39553 | MDW-69606 | MDW-69607
239 | 239 | MDW-39540 | Lot02 | MO-BEM47 | MO-BEM | Water drop protection above UPS cabinet at station and Depot | สหชาติ |  |  | 2027-01-01 | 2026-09-14 | 0% | Late | 2026-10-30 | 0% | On Schedule |  |  |  | 2026-12-31 | 0% | On Schedule |  |  |  | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 0% | On Schedule |  | 0 | ระบบป้องกันน้ำหยดเหนือตู้ UPS ที่สถานี และ Depot | #REF! | CV/AR |  | MDW-39540 | MDW-69580 | MDW-69581
240 | 240 | MDW-39541 | Lot02 | MO-BEM48 | MO-BEM | Fire alarm manual call point cover in public area at all station | ประธาน |  |  | 2027-01-01 | 2026-09-14 | 50% | Late | 2026-10-30 | 0% | On Schedule |  |  |  | 2026-12-31 | 0% | On Schedule |  |  |  | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 5.882% | On Schedule | อยูระหว่างจัดเตรียมแบบ | 0 | ฝาครอบ Manual call point ทุกสถานี | #REF! |  |  | MDW-39541 | MDW-69582 | MDW-69583
241 | 241 | MDW-39542 | Lot02 | MO-BEM49 | MO-BEM | Emergency stop button cover for escalator at all station. | สหชาติ |  |  | 2027-01-01 | 2026-09-14 | 0% | Late | 2026-10-30 | 0% | On Schedule |  |  |  | 2026-12-31 | 0% | On Schedule |  |  |  | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 0% | On Schedule |  | 0 | ฝาครอบปุ่มหยุดฉุกเฉินสำหรับบันไดเลื่อนทุกสถานี | #REF! | CV/AR |  | MDW-39542 | MDW-69584 | MDW-69585
242 | 242 | 0 | Lot02 | MO-BEM50 | MO-BEM | Modify maintenance service door to the roof of OR13 vent building to easier access while maintaining safe operational standards | สู่โชค |  | Depot | 2027-01-01 | 2026-10-29 | 0% | Late | 2026-10-30 | 100% | Completed |  |  |  | 2026-12-31 | 0% | On Schedule |  |  |  | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 11.76% | On Schedule |  | 0 | เป็นงานเก็บ Defect งานจัดจ้างภายในไซต์ - บริเวณ IVS OR13 ทางเข้าห้อง sump pump ปัจจุบันเปิดได้โดยการยก โมดิฟายเพิ่ม hinge หรือ รอกยก - ที่ ivs มีห้องบางห้อง มีช่องเปิดที่พื้นบริเวณหน้าประตู, ให้ทำราวกันตก หรือโซ่กั้นหน้าประตู | #REF! |  |  |  | 0 | 0
243 | 243 | MDW-39514 | Lot02 | MO-BEM51 | MO-BEM | Modify existing car park to be 220 motorcycle parking lots including floor painting and parking roof | สหชาติ |  | Depot | 2026-08-01 | 2026-01-29 | 100% | Completed | 2026-03-16 | 100% | Completed |  |  |  | 2026-07-31 | 100% | Completed |  |  |  | 2026-07-01 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late |  | 95.29% | Late | กำลังทำเอกสาร Test Report |  | ปรับลานจอดรถเป็นลานจอดมอเตอร์ไซค์ 220 คัน รวมทำหลังคา |  | CV/AR |  | MDW-39514 | MDW-69528 | MDW-69529
244 | 244 | MDW-39534 | Lot02 | MO-BEM52 | MO-BEM | Modify the sidewalk for temporary parking at entrance | สหชาติ |  | Depot | 2027-01-01 | 2026-07-31 | 100% | Completed | 2026-09-30 | 100% | Completed |  |  |  | 2026-12-31 | 100% | Completed |  |  |  | 2026-12-01 | 50% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 94.71% | On Schedule |  | รวมกับ MO-BEM21.1 | ปรับปรุงทางเดินเท้าให้เป็นที่จอดรถชั่วคราวบริเวณทางเข้า | #REF! | CV/AR |  | MDW-39534 | MDW-69568 | MDW-69569
245 | 245 | MDW-39554 | Lot02 | MO-BEM53.1 | MO-BEM | Modification Works : Security Guard Box at OCC Parking Area - Civil & AR | สหชาติ |  | Depot | 2027-01-02 | 2026-09-14 | 100% | Completed | 2026-10-31 | 100% | Completed |  |  |  | 2026-12-31 | 0% | On Schedule |  |  |  | 2026-12-01 | 50% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 24.12% | On Schedule |  | @ เพิ่มใน MS Project | ติดตั้งป้อมรปภ.สำเร็จรูปพร้อมเดินระบบไฟฟ้า ขนาด 1 x 2 ม ที่ลานจอดรถพนักงานหลัง OCC | #REF! | CV/AR+E&M |  | MDW-39554 | MDW-69608 | MDW-69609
246 | 246 | MDW-39555 | Lot02 | MO-BEM53.2 | MO-BEM | Modification Works : Security Guard Box at OCC Parking Area - Building Services | ประธาน |  |  | 2027-01-02 | 2026-09-14 | 100% | Completed | 2026-10-31 | 100% | Completed |  |  |  | 2026-12-31 | 50% | On Schedule |  |  |  | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 58.82% | On Schedule |  | @ เพิ่มใน MS Project | ติดตั้งป้อมรปภ.สำเร็จรูปพร้อมเดินระบบไฟฟ้า ขนาด 1 x 2 ม ที่ลานจอดรถพนักงานหลัง OCC | #REF! | CV/AR+E&M |  | MDW-39555 | MDW-69610 | MDW-69611
247 | 247 | NoDrawing | Lot02 | MO-BEM54 | MO-BEM | Strengthen the Maintenance Walkway of the TEF fan | สหชาติ |  |  | 2027-01-01 | 2026-07-16 | 100% | Completed | 2026-08-16 | 100% | Completed |  |  |  | 2026-12-31 | 0% | On Schedule |  |  |  | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | 23.53% | On Schedule |  | 0 | เสริมความแข็งแรงทางเดินซ่อมบำรุงพัดลม TEF | #REF! | CV/AR |  |  | 0 | 0
Formulas:
Expected Completion Month = XLOOKUP([Code],'00 MASTER WORK REGISTER'!$B:$B,'00 MASTER WORK REGISTER'!$M:$M,"")
Overall (Status) = IF([Overall (%)]=1, "Completed", IF([Expected Completion Month]<TODAY(), "Late", "On Schedule"))
Design = [Procurement]-30
Design (Status) = IF([Design (%)]=1, "Completed", IF([Design]<TODAY(), "Late", "On Schedule"))
Procurement = [Construction/Installation]-30
Procurement (Status) = IF([Procurement (%)]=1, "Completed", IF([Procurement]<TODAY(), "Late", "On Schedule"))
Construction /Installation (Status) = IF([Construction /Installation (%)]=1, "Completed", IF([Construction/Installation]<TODAY(), "Late", "On Schedule"))
Test Procedure (Status) = IF([Test Procedure (%)]=1, "Completed", IF([Test Procedure]<TODAY(), "Late", "On Schedule"))
Inspection (Status) = IF([Inspection (%)]=1, "Completed", IF([Inspection]<TODAY(), "Late", "On Schedule"))
Test Report (Status) = IF([Test Report (%)]=1, "Completed", IF([Test Report]<TODAY(), "Late", "On Schedule"))
Test Report = [Construction/Installation]+30
Test Report = [Inspection]+21
Test Procedure = [Construction/Installation]-15
Test Procedure = [Inspection]-7
Inspection = [Construction/Installation]+7
Inspection = [Manufacturing / Delivery Process]+7
Manufacturing / Delivery (Status) = IF([Manufacturing / Delivery Process (%)]=1, "Completed", IF([Manufacturing / Delivery Process]<TODAY(), "Late", "On Schedule"))
T&C (Status) = IF([T&C (%)]=1, "Completed", IF([T&C]<TODAY(), "Late", "On Schedule"))
Note on G117: USER: Rail Base Inspection (IMV2)
Note on G120: USER: Rail Mainternance (IMV1)
Note on V154: USER: Update 28/10/26 (98.77%) ช่างกบ
Note on V157: USER: Update 28/10/26 (67.27%) ช่างกบ
Note on G174: USER: ทำเป็นรั้วหีบเพลงแทน
Note on V210: USER: ขอ Progress จากพี่ต่อ
Note on G215: USER: ทำเป็นรั้วหีบเพลงแทน
Note on V218: USER: ขอ Progress จากพี่ต่อ

## ตามงาน
บัณฑิต
No. | Design Submission | Lot No. | Code | Activity Name | CK Responsible Person | Expected Completion Month | Design (PLAN) | Design (%) | Design (Status) | Procurement (PLAN) | Procurement (%) | Procurement (Status) | Construction /Installation (PLAN) | Construction /Installation (%) | Construction /Installation (Status) | Note
113 | MDW-39237 | Lot01 | GEN22 | Central BEMS for the MRT Orange Line System | บัณฑิต | 2026-08-21 | 2026-04-30 | 0% | Late | 2026-06-30 | 0% | Late | 2026-08-15 | 0% | Late | PPR Oct-26 กำลังเปรียบเทียบ Spec
| MDW-39283 | Lot01 | COM2 | Intercom System in Cash Handling Room (if require) | บัณฑิต | 2026-12-19 | 2025-09-30 | 100% | Completed | 2026-06-30 | 50% | Late | 2026-10-31 | 0% | On Schedule | รอพื้นที่เข้าติดตั้ง
| AFC-39001 | Lot01 | COM7 | Mini Paging in Ticket Office | บัณฑิต | 2026-12-19 | 2025-09-10 | 100% | Completed | 2026-06-30 | 100% | Completed | 2026-09-30 | 0% | Late | ของมาแล้ว รอพื้นที่เข้าติดตั้ง
| - | Lot02 | MO-BEM34 | Access Gate (Full Height Turnstile) at 1st floor admin ORL | บัณฑิต | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 2026-12-31 | 0% | On Schedule
| - | Lot02 | MO-BEM35 | Access Gate (Tripod with Swing Gate) at MWS Entrance | บัณฑิต | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 2026-12-31 | 0% | On Schedule | TMD เริ่มเข้าทำช่วงเดือน Oct-26 (CIV จบ)
| - | Lot02 | MO-BEM36 | Access Gate (Tripod with Swing Gate) at Admin 2nd floor connect to OCC | บัณฑิต | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 2026-12-31 | 0% | On Schedule | TMD เริ่มเข้าทำช่วงเดือน Oct-26 (CIV จบ)
| - | Lot02 | MO-BEM37 | Access Gate (Tripod with Swing Gate) on Klong Chourdyai bridge | บัณฑิต | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 2026-12-31 | 0% | On Schedule | TMD เริ่มเข้าทำช่วงเดือน Oct-26 (CIV จบ)
| - | Lot02 | MO-BEM38 | Access Gate (Tripod with roof covering) at parking lot OCC | บัณฑิต | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 2026-12-31 | 0% | On Schedule | TMD เริ่มเข้าทำช่วงเดือน Oct-26 (CIV จบ)
| - | Lot02 | MO-BEM39 | Access Gate (Tripod with roof covering) at Stair up to Depot slab | บัณฑิต | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 2026-12-31 | 0% | On Schedule | TMD เริ่มเข้าทำช่วงเดือน Oct-26 (CIV จบ)
| - | Lot02 | MO-BEM40 | Access Control (2 Factors, Card + Finger Print) at High Security rooms - CCR/PTR/Store | บัณฑิต | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 2026-12-31 | 0% | On Schedule | STE เริ่มเข้าทำช่วงเดือน Oct-26
| - | Lot02 | MO-BEM41 | Link CCTV Landscape of all depot ORL area for MMC BL monitoring. | บัณฑิต | 2027-01-01 | 2026-11-28 | 0% | On Schedule | 2026-11-29 | 0% | On Schedule | 2026-12-31 | 0% | On Schedule | จัดจ้าง STE
| Design Submission | Lot No. | Code | Activity Name | CK Responsible Person | Expected Completion Month | T&C (PLAN) | T&C (%) | T&C (Status) | Test Procedure (PLAN) | Inspection (%) | Test Procedure (Status) | Inspection (PLAN) | Inspection (%) | Inspection (Status) | Test Report (PLAN) | Test Report (%) | Test Report (Status) | Note
|  | Lot01 | GEN21 | Project Information Management System (PIMS) | บัณฑิต | 2024-09-30 | 2024-09-14 | 100% | Completed | 2026-09-23 | 0% | Late | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late | งานจบแล้ว
ประธาน
118
| Design Submission | Lot No. | Code | Activity Name | CK Responsible Person | Expected Completion Month | Design (PLAN) | Design (%) | Design (Status) | Procurement (PLAN) | Procurement (%) | Procurement (Status) | Construction /Installation (PLAN) | Construction /Installation (%) | Construction /Installation (Status) | Note
| 0 | Lot02 | MO-CK30 | Lighting for sealed space under stairs and behind lift shaft at underground station | ประธาน | 2027-01-01 | 2026-10-14 | 0% | Late | 2026-11-14 | 0% | On Schedule | 2026-12-31 | 0% | On Schedule | ไฟส่องสว่างสำหรับพื้นที่ปิดใต้บันไดและด้านหลังช่องลิฟต์ที่สถานีรถไฟใต้ดิน
| MDW-39518 | Lot02 | MO-BEM26 | Street Lighting system area between MRTA Fence and Depot slab | ประธาน | 2026-08-01 | 2026-04-14 | 50% | Late | 2026-05-15 | 0% | Late | 2026-07-31 | 0% | Late | อยู่ระหว่างจัดเตรียมแบบ งาน Construction จบ Mar-27
| MDW-39541 | Lot02 | MO-BEM48 | Fire alarm manual call point cover in public area at all station | ประธาน | 2027-01-01 | 2026-09-14 | 0% | Late | 2026-10-30 | 0% | On Schedule | 2026-12-31 | 0% | On Schedule | อยูระหว่างจัดเตรียมแบบ
| MDW-39289 | Lot01 | GEN11 | Earthing and Bonding Modification | ประธาน | 2026-03-01 | 2025-01-31 | 100% | Completed | 2025-09-30 | 67% | Late | 2026-02-28 | 100% | Completed
| MDW-39296 | Lot02 | MO-CK15.2 | Change Electrical Equipment to be Explosion-proof type - Building Services | ประธาน | 2026-05-01 | 2025-12-13 | 100% | Completed | 2026-01-28 | 50% | Late | 2026-04-30 | 90% | Late | Fore cast Nov-26
| MDW-39256 | Lot01 | GEN1.8 | Modification in Staff Mess Room at OR23-OR29 | ประธาน | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 2026-09-30 | 80% | Late
| MDW-39257 | Lot01 | GEN1.9 | Modification of Air Conditioning in CER and SER at OR13-OR19 | ประธาน | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 2026-09-30 | 99% | Late
| MDW-39258 | Lot01 | GEN1.10 | Modification of Air Conditioning in CER and SER at OR20-OR22 | ประธาน | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 2026-09-30 | 99% | Late
| MDW-39259 | Lot01 | GEN1.11 | Modification of Air Conditioning in CER and SER at OR23-OR29 | ประธาน | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 2026-09-30 | 99% | Late
| MDW-39273 | Lot01 | GEN1.13 | Modification of New M&E UPS Room at IVS15-IVS17 - Building Services | ประธาน | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 2026-09-30 | 99% | Late
| MDW-39299 | Lot01 | GEN1.15 | Provision of Air Conditioning System in Commercial Room at OR13-OR19 | ประธาน | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 2026-09-30 | 98% | Late
| MDW-39296 | Lot01 | GEN2.19 | Dangerous Goods Building in Depot - Building Services | ประธาน | 2026-08-01 | 2025-12-13 | 100% | Completed | 2026-01-28 | 100% | Completed | 2026-04-30 | 90% | Late
| MDW-39243 | Lot01 | GEN18 | Eye Adaptation Lighting (Lighting at Tunnel to Expose) | ประธาน | 2026-11-19 | 2025-09-30 | 100% | Completed | 2025-10-30 | 100% | Completed | 2026-04-13 | 90% | Late | Progress DPA1 : 100% Progress DPA2 : 100% Progress Cut&Cover OR22 : 95%
| MDW-39304 | Lot01 | COM5 | MEA Radio | ประธาน | 2026-09-20 | 2026-01-30 | 100% | Completed | 2026-04-30 | 100% | Completed | 2026-06-30 | 90% | Late | รอเฟอร์นิเจอร์ Fore cast Dec-26
| MDW-39501 | Lot02 | MO-CK1.2 | Store Modification Works at Main Workshop - Building Services | ประธาน | 2026-06-04 | 2026-02-12 | 100% | Completed | 2026-03-30 | 100% | Completed | 2026-05-28 | 95% | Late | รอสรุปตำแหน่ง Power Plug ชาร์จโฟลคลิฟท์ Oct-26
| MDW-39504 | Lot02 | MO-CK3 | Move or link Workstation and control panel to MMC room at admin C 2nd floor | ประธาน | 2026-08-02 | 2026-02-28 | 100% | Completed | 2026-04-15 | 100% | Completed | 2026-08-31 | 88% | Late | Fore cast Oct-26
| MDW-39506 | Lot02 | MO-BEM1.2 | Walkway from Main Work Shop to Stabling Area - Building Services | ประธาน | 2026-08-02 | 2026-04-28 | 100% | Completed | 2026-05-29 | 100% | Completed | 2026-09-30 | 0% | Late | รองานหลังคา CIV Oct-26
| MDW-39517 | Lot02 | MO-BEM14.2 | Modification Works : Walkway Bridge between BL Depot and ORL Depot - Building Services | ประธาน | 2026-08-03 | 2026-01-14 | 100% | Completed | 2026-03-01 | 100% | Completed | 2026-09-30 | 10% | Late | รองานหลังคา CIV Oct-26
| MDW-39520 | Lot02 | MO-BEM25.2 | Chain Link Fence to divide controlled areas on Depot slab 3 m.x 485 m.- Building Services | ประธาน | 2026-10-01 | 2026-06-14 | 100% | Completed | 2026-07-30 | 100% | Completed | 2026-09-30 | 0% | Late | Fore cast Oct-26
| Design Submission | Lot No. | Code | Activity Name | CK Responsible Person | Expected Completion Month | Test Procedure (PLAN) | Test Procedure (%) | Test Procedure (Status) | Inspection (PLAN) | Inspection (%) | Inspection (Status) | Test Report (PLAN) | Test Report (%) | Test Report (Status) | Note
| MDW-39242 | Lot01 | GEN4.0 | Modification Works for Training Room at Ratchada Station | ประธาน | 2026-04-01 | 2026-03-16 | 50% | Late | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late
| MDW-39245 | Lot01 | GEN4.2 | AFC Training Room Modification - Building Services | ประธาน | 2026-08-21 | 2026-03-24 | 100% | Completed | 2026-08-07 | 100% | Completed | 2026-09-30 | 0% | Late
| DWE-39025 | Lot01 | GEN7.2 | Dangerous Waste Storage Building in Depot - Building service | ประธาน | 2026-09-20 | 2026-04-20 | 100% | Completed | 2026-06-08 | 100% | Completed | 2026-09-30 | 0% | Late
| DWE-39025 | Lot01 | GEN8.2 | General Waste Storage Building in Depot - Building service | ประธาน | 2026-09-20 | 2026-04-20 | 100% | Completed | 2026-06-08 | 100% | Completed | 2026-09-30 | 0% | Late
| MDW-39289 | Lot01 | GEN11 | Earthing and Bonding Modification | ประธาน | 2026-03-01 | 2026-09-23 | 0% | Late | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late
| MDW-39241 | Lot01 | GEN14.2 | Driver Train Simulation Room and Train Crew Office at OR18 - Building Services | ประธาน | 2026-08-21 | 2026-03-12 | 100% | Completed | 2026-08-07 | 100% | Completed | 2026-09-30 | 0% | Late
| MDW-39287 | Lot01 | SIG5 | Strobe Light at Buffer Stops | ประธาน | 2026-08-21 | 2026-03-14 | 100% | Completed | 2026-06-30 | 100% | Completed | 2026-09-30 | 0% | Late
| MDW-39556 | Lot02 | MO-CK7 | Addition small power for lounge and pantry room at 2nd floor and Hall and observation room at 3nd floor | ประธาน | 2026-08-04 | 2026-05-05 | 100% | Completed | 2026-09-30 | 50% | Late | 2026-10-21 | 0% | Late
| MDW-39548 | Lot02 | MO-CK8 | Air Condition for using store room to be pantry room. 2nd floor | ประธาน | 2026-08-05 | 2026-03-24 | 100% | Completed | 2026-09-30 | 50% | Late | 2026-07-10 | 100% | Completed
| MDW-39551 | Lot02 | MO-CK14 | Modify Cleaner room at OR29 to be Train crew Standby office with facility system | ประธาน | 2026-07-01 | 2026-09-30 | 0% | Late | 2026-10-07 | 0% | Late | 2026-10-30 | 0% | On Schedule
| MDW-39512 | Lot02 | MO-BEM4.2 | Maintenance Office Rooms at Main Workshop - Building Services | ประธาน | 2026-07-04 | 2026-09-23 | 0% | Late | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late
| MDW-39526 | Lot02 | MO-BEM10 | Relocate Fire Hose Cabinet to be outside of the clearance gauge zone 17 set | ประธาน | 2026-05-01 | 2026-03-18 | 100% | Completed | 2026-09-30 | 50% | Late | 2026-05-15 | 100% | Completed | รอส่งงานกับ BEM
| MDW-39529 | Lot02 | MO-BEM11.2 | Washing Area in Cleaning Staff Room at Stabling Yard - Building Services | ประธาน | 2026-08-04 | 2026-03-31 | 100% | Completed | 2026-07-01 | 100% | Completed | 2026-07-10 | 100% | Completed
| MDW-39515 | Lot02 | MO-BEM15.2 | Roof for cars parking lots area (184 car) - Building Services | ประธาน | 2026-08-03 | 2026-09-23 | 0% | Late | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late | รอส่งงานกับ BEM
| MDW-39523 | Lot02 | MO-BEM20 | Hose bib 1/2" 4 sets for Tree around Admin area | ประธาน | 2026-06-01 | 2026-03-31 | 100% | Completed | 2026-09-30 | 50% | Late | 2026-07-10 | 100% | Completed
สมศักดิ์
| Design Submission | Lot No. | Code | Activity Name | CK Responsible Person | Expected Completion Month | Design (PLAN) | Design (%) | Design (Status) | Procurement (PLAN) | Procurement (%) | Procurement (Status) | Manufacturing / Delivery Process (PLAN) | Manufacturing / Delivery Process (%) | Manufacturing / Delivery (Status) | Construction /Installation (PLAN) | Construction /Installation (%) | Construction /Installation (Status) | Note
| DWE-39002 | Lot01 | DWE19.2 | Tunnel Inspection and Cleaning Vehicle | สมศักดิ์ | 2026-09-20 | 2025-08-31 | 0% | Late | 2025-12-18 | 100% | Completed |  |  |  | 2026-10-11 | 0% | Late | No Update
| DWE-39007 | Lot01 | DWE19.7 | Rail Head Grinding Machine Vehicle | สมศักดิ์ | 2026-09-20 | 2025-08-31 | 0% | Late | 2025-12-18 | 100% | Completed |  |  |  | 2027-08-31 | 0% | On Schedule
| DWE-39018 | Lot01 | DWE9 | Repair Equipment | สมศักดิ์ | 2026-09-20 | 2025-12-17 | 100% | Late | 2026-07-31 | 50% | On Schedule | 2026-10-30 | 70% | On Schedule | 2027-03-03 | 0% | On Schedule | คงเหลือจัดส่งอุปกรณ์
| DWE-39016 | Lot01 | DWE1 | Diesel Fuel Storage Tank for Maintenance Vehicle | สมศักดิ์ | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-01-16 | 100% | Completed | 2026-06-30 | 100% | Completed | 2026-07-31 | 99% | Late | คงเหลืองานร้อยสาย
| DWE-39015 | Lot01 | DWE4 | Compressed Air System and Portable Air Compressor for Depot | สมศักดิ์ | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-01-10 | 100% | Completed | 2026-02-15 | 100% | Completed | 2026-09-19 | 0% | Late | Forecast 1/10-30-11/26
| EPS-39001 | Lot01 | PSY1 | Diesel Fuel Storage Tanks for Power Generators | สมศักดิ์ | 2026-03-24 | 2026-01-16 | 100% | Completed | 2026-03-31 | 100% | Completed | 2026-03-31 | 100% | Completed | 2026-06-30 | 75% | Late | คงเหลืองานเดินท่อและ Pump น้ำมัน
| Design Submission | Lot No. | Code | Activity Name | CK Responsible Person | Expected Completion Month | T&C (PLAN) | T&C (%) | T&C (Status) | Test Procedure (PLAN) | Test Procedure (%) | Test Procedure (Status) | Inspection (PLAN) | Inspection (%) | Inspection (Status) | Test Report (PLAN) | Test Report (%) | Test Report (Status) | Note
| DWE-39011 | Lot01 | DWE2 | Movable Height Maintenance Platform Vehicle (Boom Lift) | สมศักดิ์ | 2026-09-20 | 2026-07-09 | 0% | Late | 2026-05-22 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late
| DWE-39012 | Lot01 | DWE3 | Fork Lift Vehicle | สมศักดิ์ | 2026-09-20 | 2026-07-30 | 0% | Late | 2026-09-30 | 0% | Late | 2026-10-07 | 0% | Late | 2026-10-28 | 0% | On Schedule
| DWE-39017 | Lot01 | DWE5 | Pallet Storage Shelves in Hazardous Storage | สมศักดิ์ | 2026-09-20 | 2026-06-05 | 0% | Late | 2026-07-17 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late
| DWE-39017 | Lot01 | DWE6 | Pallet Storage in Main Storage Room | สมศักดิ์ | 2026-09-20 | 2026-06-05 | 0% | Late | 2026-07-17 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late
| DWE-39017 | Lot01 | DWE7 | Two-Tier Shelf | สมศักดิ์ | 2026-09-20 | 2026-06-05 | 0% | Late | 2026-07-17 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late
| DWE-39017 | Lot01 | DWE8 | Tool Storage | สมศักดิ์ | 2026-09-20 | 2026-06-05 | 0% | Late | 2026-07-17 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late
| DWE-39020 | Lot01 | DWE10 | Oil & Grease Disposal | สมศักดิ์ | 2026-09-20 | 2026-07-05 | 0% | Late | 2026-09-30 | 0% | Late | 2026-10-07 | 0% | Late | 2026-10-28 | 0% | On Schedule
| DWE-39020 | Lot01 | DWE11 | Grease Dispensers | สมศักดิ์ | 2026-09-20 | 2026-07-05 | 0% | Late | 2026-09-30 | 0% | Late | 2026-10-07 | 0% | Late | 2026-10-28 | 0% | On Schedule
| DWE-39020 | Lot01 | DWE12 | Waste Disposal | สมศักดิ์ | 2026-09-20 | 2026-07-05 | 0% | Late | 2026-09-30 | 0% | Late | 2026-10-07 | 0% | Late | 2026-10-28 | 0% | On Schedule
สหชาติ
| Design Submission | Lot No. | Code | Activity Name | CK Responsible Person | Expected Completion Month | Design (PLAN) | Design (%) | Design (Status) | Procurement (PLAN) | Procurement (%) | Procurement (Status) | Manufacturing / Delivery Process (PLAN) | Manufacturing / Delivery Process (%) | Manufacturing / Delivery (Status) | Construction /Installation (PLAN) | Construction /Installation (%) | Construction /Installation (Status) | Note
| MDW-39297 | Lot01 | GEN2.15 | Training Room at Ratchada Station (Part 2) | สหชาติ | 2026-08-01 | 2026-08-01 | 0% | Late | 2026-08-31 | 100% | Completed |  |  |  | 2026-09-30 | 100% | Completed
| MDW-39244 | Lot01 | GEN4.1 | AFC Training Room Modification - Civil & AR | สหชาติ | 2026-08-21 | 2026-09-30 | 10% | Late | 2026-10-15 | 100% | Completed |  |  |  | 2026-11-15 | 0% | On Schedule | อยู่ระหว่างจัดทำแบบก่อสร้าง
| GRS-39001-40 | Lot01 | GEN10.2 | Graphic and Signage Mainline & IVS,VS | สหชาติ | 2026-08-21 | 2026-06-15 | 79% | Late | 2026-05-31 | 95% | Late | 2026-07-31 | 0% | Late | 2026-07-31 | 0% | Late | GRS
| GRS-39001-40 | Lot01 | GEN10.3 | Graphic and Signage Depot | สหชาติ | 2026-08-21 | 2026-08-15 | 90% | Late | 2026-07-31 | 93% | Late | 2026-06-30 | 56% | Late | 2026-06-30 | 19% | Late | GRS
| MDW-39279 | Lot01 | AFC3 | Balustrade Modification Along AFC Gate Line | สหชาติ | 2026-09-20 | 2026-06-30 | 10% | Late | 2026-08-15 | 50% | Late |  |  |  | 2026-11-06 | 0% | On Schedule | จัดเตรียมแบบ ออกPPR Oct-26
| 0 | Lot02 | MO-CK18 | Emergency escape route map | สหชาติ | 2027-01-01 | 2026-09-30 | 0% | Late | 2026-10-30 | 50% | On Schedule | 2026-12-31 | 0% | On Schedule | 2026-12-31 | 0% | On Schedule | GRS
| 0 | Lot02 | MO-CK22 | Fire escape stairs level signs in the Depot, VS and IVS areas | สหชาติ | 2027-01-01 | 2026-09-30 | 50% | Late | 2026-10-31 | 0% | On Schedule | 2026-10-20 | 0% | Late | 2026-12-31 | 0% | On Schedule | GRS
| 0 | Lot02 | MO-CK25 | Station Area sign 28 stations | สหชาติ | 2026-05-01 | 2026-06-15 | 80% | Late | 2026-06-30 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-12-20 | 0% | On Schedule | GRS
| MDW-39532 | Lot02 | MO-CK27 | Spike fence for Depot slab | สหชาติ | 2027-01-01 | 2026-07-31 | 70% | Late | 2026-08-31 | 0% | Late |  |  |  | 2026-12-31 | 0% | On Schedule | อยู่ระหว่างส่งขออนุมัติแบบรอ Approve
| 0 | Lot02 | MO-CK31 | Modify the access door of sealed space (under-stairs room) with a Sump Pump or ESPS cabinet | สหชาติ | 2027-01-01 | 2026-07-16 | 0% | Late | 2026-08-16 | 0% | Late |  |  |  | 2026-12-31 | 0% | On Schedule
| 0 | Lot02 | MO-BEM7 | Modify maintenance service door to the roof building to easier access while maintaining safe operational standards | สหชาติ | 2027-01-01 | 2026-10-19 | 50% | Late | 2026-11-19 | 0% | On Schedule |  |  |  | 2026-12-31 | 0% | On Schedule
| MDW-39532 | Lot02 | MO-BEM22 | Addition Spike fence for MRTA fence and Chain link at Klong Chourdyai 400m. | สหชาติ | 2027-01-01 | 2026-08-30 | 70% | Late | 2026-09-30 | 0% | Late |  |  |  | 2026-12-31 | 0% | On Schedule | อยู่ระหว่างส่งขออนุมัติแบบรอ Approve
| MDW-39537 | Lot02 | MO-BEM43 | Handrails for ladder at IVS and Vent buildings | สหชาติ | 2026-09-01 | 2026-03-31 | 70% | Late | 2026-05-01 | 0% | Late |  |  |  | 2026-08-31 | 0% | Late | อยู่ระหว่างส่งขออนุมัติแบบรอ Approve
| MDW-39539 | Lot02 | MO-BEM45 | Roof for control panel on vent building | สหชาติ | 2027-01-01 | 2026-09-14 | 70% | Late | 2026-10-30 | 0% | On Schedule |  |  |  | 2026-12-31 | 0% | On Schedule | อยู่ระหว่างส่งขออนุมัติแบบรอ Approve
| MDW-39553 | Lot02 | MO-BEM46 | Provide Standing plate or ladder to access the Fire Valve in at Omega points for all underground stations. | สหชาติ | 2027-01-01 | 2026-09-14 | 0% | Late | 2026-10-30 | 0% | On Schedule |  |  |  | 2026-12-31 | 0% | On Schedule
| MDW-39540 | Lot02 | MO-BEM47 | Water drop protection above UPS cabinet at station and Depot | สหชาติ | 2027-01-01 | 2026-09-14 | 0% | Late | 2026-10-30 | 0% | On Schedule |  |  |  | 2026-12-31 | 0% | On Schedule
| MDW-39542 | Lot02 | MO-BEM49 | Emergency stop button cover for escalator at all station. | สหชาติ | 2027-01-01 | 2026-09-14 | 0% | Late | 2026-10-30 | 0% | On Schedule |  |  |  | 2026-12-31 | 0% | On Schedule
| GRS-39001-40 | Lot01 | GEN10.1 | Graphic and Signage Station | สหชาติ | 2026-08-21 | 2026-06-30 | 100% | Completed | 2026-05-31 | 95% | Late | 2027-01-31 | 76% | On Schedule | 2027-02-28 | 34% | On Schedule | GRS
| MDW-39276 | Lot01 | AFC2 | Ticket Issuing Machine (TIM) Wall Opening and Closing | สหชาติ | 2026-09-20 | 2026-01-30 | 100% | Completed | 2026-03-15 | 50% | Late |  |  |  | 2026-07-13 | 100% | Completed | มีแก้ไขตำแหน่ง OR14,17,18,23
| MDW-39278 | Lot01 | AFC4 | Underfloor Embedded Duct Modification for AFC Gates Line | สหชาติ | 2026-09-20 | 2026-01-30 | 100% | Completed | 2026-04-02 | 67% | Late |  |  |  | 2026-10-09 | 81% | Late
| PSY-39001-9 | Lot01 | PSY2 | GIS and BSS Building and Other Facilities | สหชาติ | 2026-03-24 | 2024-08-29 | 100% | Completed | 2024-09-28 | 69% | Late |  |  |  | 2025-12-04 | 100% | Completed
| PSY-39011 | Lot01 | PSY3 | Steel Grating Raised Floor for EE Panel | สหชาติ | 2026-03-24 | 2024-09-30 | 100% | Completed | 2024-10-30 | 75% | Late |  |  |  | 2025-07-14 | 100% | Completed
| MDW-39550 | Lot02 | MO-CK13.1 | Satellite Store at OR21 - Civil & AR | สหชาติ | 2027-01-02 | 2026-08-30 | 100% | Completed | 2026-10-15 | 0% | Late |  |  |  | 2026-12-31 | 0% | On Schedule
| MDW-39505 | Lot02 | MO-BEM1.1 | Walkway from Main Work Shop to Stabling Area - Civil & AR | สหชาติ | 2026-08-02 | 2026-04-28 | 100% | Completed | 2026-05-29 | 92% | Late |  |  |  | 2026-09-30 | 85% | Late | คงเหลืองานมุงหลังคา Metal sheet
| MDW-39522 | Lot02 | MO-BEM13.1 | Zero Discharge Water treatment in Depot - Civil & AR | สหชาติ | 2027-01-01 | 2026-08-15 | 100% | Completed | 2026-09-30 | 75% | Late |  |  |  | 2026-12-31 | 63% | On Schedule | คงเหลืองานประกอบและติดตั้งโครงหลงัคา
| - | Lot02 | MO-BEM21 | Relocate Security Guard Box at Front Gate and Install Roof 3x5m. | สหชาติ | 2027-01-03 | 2026-07-31 | 100% | Completed | 2026-09-30 | 75% | Late |  |  |  | 2026-12-31 | 0% | On Schedule
| MDW-39534 | Lot02 | MO-BEM21.1 | Modification Works : Security Guard Box at ORL Depot Entrance - Civil & AR | สหชาติ | 2027-01-02 | 2026-07-31 | 100% | Completed | 2026-09-30 | 67% | Late |  |  |  | 2026-12-31 | 100% | Completed
| - | Lot02 | MO-BEM27 | Compacted gravel walkway along the Test Track OR-BL 1.2 m. | สหชาติ | 2027-01-01 | 2026-08-30 | 100% | Completed | 2026-09-30 | 0% | Late |  |  |  | 2026-12-31 | 0% | On Schedule
| MDW-39521 | Lot02 | MO-BEM29 | Walkway Bridge across the canal for Depot area inspection patrols 3 location | สหชาติ | 2027-01-01 | 2026-08-15 | 100% | Completed | 2026-09-30 | 67% | Late |  |  |  | 2026-12-31 | 95% | On Schedule | เหลืองานติดตั้งสะพานข้ามคลอง + ประตูรั้ว + Modify Chainlink
| MDW-39305 | Lot01 | DWE13 | Safety Provision for Maintenance Pits | สหชาติ | 2026-09-20 | 2025-11-30 | 100% | Completed | 2026-04-29 | 100% | Completed |  |  |  | 2026-07-29 | 0% | Late | งาน Handrail ที่ Pits Wheel Reprofling Plant
| MDW-39552 | Lot02 | MO-CK9 | Walk Way Hand rail high 90 cm 1 side (144 m. x 7 route) | สหชาติ | 2026-10-01 | 2026-05-30 | 100% | Completed | 2026-06-30 | 100% | Completed |  |  |  | 2026-09-30 | 98.5% | Late | คงเหลืองานคอนกรีตทางเดินข้ามราง
| 0 | Lot02 | MO-CK17 | Safety Sign all Depot Area building | สหชาติ | 2026-05-01 | 2025-11-28 | 100% | Completed | 2026-06-15 | 100% | Completed | 2026-09-20 | 27% | Late | 2026-10-15 | 0% | Late | GRS
| 0 | Lot02 | MO-CK19 | Traffic Line Marking (Thermoplastic Paint) | สหชาติ | 2026-05-01 | 2026-04-30 | 100% | Completed | 2026-06-15 | 100% | Completed | 2026-10-15 | 100% | Completed | 2026-10-15 | 25% | Late | GRS
| 0 | Lot02 | MO-CK20 | Emergency Car Parking location Painting in front of MWS | สหชาติ | 2026-05-01 | 2026-04-30 | 100% | Completed | 2026-06-15 | 100% | Completed | 2026-10-15 | 0% | Late | 2026-10-15 | 0% | Late | GRS
| 0 | Lot02 | MO-CK24 | Modify Traffic paint and traffic sign | สหชาติ | 2026-05-01 | 2026-04-30 | 100% | Completed | 2026-06-15 | 100% | Completed | 2026-10-15 | 64% | Late | 2026-10-15 | 13% | Late | GRS
| MDW-39516 | Lot02 | MO-BEM14.1 | Modification Works : Walkway Bridge between BL Depot and ORL Depot - Civil & AR | สหชาติ | 2026-08-02 | 2026-02-28 | 100% | Completed | 2026-06-15 | 100% | Completed |  |  |  | 2026-09-30 | 95% | Late | คงเหลืองานติดตั้งสะพานและปรับพื้นที่ถนน
| MDW-39557 | Lot02 | MO-BEM19 | Install Chain Link fence to enclose parking area | สหชาติ | 2026-10-01 | 2026-06-29 | 100% | Completed | 2026-07-30 | 100% | Completed |  |  |  | 2026-09-30 | 0% | Late | ยังไม่ทราบผู้ดูแล
| MDW-39557 | Lot02 | MO-BEM25.1 | Chain Link Fence to divide controlled areas on Depot slab 3 m.x 485 m. - Civil & AR | สหชาติ | 2026-10-01 | 2026-06-14 | 100% | Completed | 2026-07-30 | 100% | Completed |  |  |  | 2026-09-30 | 0% | Late | ยังไม่ทราบผู้ดูแล
สหชาติ
| Design Submission | Lot No. | Code | Activity Name | CK Responsible Person | Expected Completion Month | Test Procedure (PLAN) | Test Procedure (%) | Test Procedure (Status) | Inspection (PLAN) | Inspection (%) | Inspection (Status) | Test Report (PLAN) | Test Report (%) | Test Report (Status) | Note
| MDW-39235 | Lot01 | GEN5 | Raised Floor | สหชาติ | 2026-06-01 | 2025-11-28 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late
| DWE-39024 | Lot01 | GEN7.1 | Dangerous Waste Storage Building in Depot - Civil & AR | สหชาติ | 2026-09-20 | 2026-07-15 | 100% | Completed | 2026-06-08 | 100% | Completed | 2026-09-30 | 0% | Late
| DWE-39026 | Lot01 | GEN8.1 | General Waste Storage Building in Depot - Civil & AR | สหชาติ | 2026-09-20 | 2026-07-15 | 100% | Completed | 2026-06-08 | 100% | Completed | 2026-09-30 | 0% | Late
| MDW-39236 | Lot01 | GEN13 | Bird Protection System | สหชาติ | 2026-11-19 | 2026-07-15 | 100% | Completed | 2026-09-30 | 100% | Completed | 2026-10-21 | 0% | Late
| - | Lot01 | GEN14 | Train Crew Office at Thailand Cultural Centre Station | สหชาติ | 2026-08-21 | 2026-09-23 | 0% | Late | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late
| MDW-39240 | Lot01 | GEN14.1 | Driver Train Simulation Room and Train Crew Office at OR18 - Civil & AR | สหชาติ | 2026-08-21 | 2026-07-15 | 100% | Completed | 2026-08-07 | 100% | Completed | 2026-09-30 | 0% | Late
| MDW-39239 | Lot01 | GEN15 | Access Panel Closeout for Traction Substation Room in Main Workshop | สหชาติ | 2026-03-24 | 2026-07-15 | 100% | Completed | 2026-09-30 | 100% | Completed | 2026-10-21 | 0% | Late
| MDW-39002 | Lot01 | SIG1 | Test Track Shelters and Test Track Building | สหชาติ | 2026-06-22 | 2026-05-15 | 100% | Completed | 2026-06-08 | 100% | Completed | 2026-09-30 | 0% | Late
| DWE-39023 | Lot01 | DWE15 | Provision of Civil Works and Building Services to support Train Washing Equipment | สหชาติ | 2026-08-01 | 2026-08-31 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-15 | 0% | Late
| MDW-39500 | Lot02 | MO-CK1.1 | Store Modification Works at Main Workshop - Civil&AR | สหชาติ | 2026-06-03 | 2026-09-30 | 50% | Late | 2026-10-07 | 100% | Completed | 2026-10-30 | 0% | On Schedule
| MDW-39503 | Lot02 | MO-CK2 | New MMC at Admin Building - Civil&AR | สหชาติ | 2026-08-03 | 2026-09-30 | 50% | Late | 2026-09-30 | 0% | Late | 2026-10-30 | 0% | On Schedule | กำลังทำเอกสาร Test Report
| MDW-39543 | Lot02 | MO-CK4 | Bird & Rain Protection for Open space Admin C | สหชาติ | 2026-08-01 | 2026-09-30 | 50% | Late | 2026-09-30 | 0% | Late | 2026-10-30 | 0% | On Schedule
| MDW-39547 | Lot02 | MO-CK5 | Relocate door in front of toilet and build partition wall to conceal the view in side of toilet | สหชาติ | 2026-08-02 | 2026-07-15 | 100% | Completed | 2026-10-07 | 0% | Late | 2026-10-30 | 0% | On Schedule
| MDW-39547 | Lot02 | MO-CK6 | Modify Lockset the emergency door to be used for passage between the 2nd and 3rd floors inside the building. | สหชาติ | 2026-08-03 | 2026-07-01 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late
| MDW-39545 | Lot02 | MO-CK11 | Chain Link at Cut & Cover 600m. | สหชาติ | 2026-06-01 | 2026-08-01 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late | มีงานเพิ่มอีก 18 แผง
| MDW-39295 | Lot02 | MO-CK15.1 | Epoxy Floor Installation and Curb Installation at the Entrance - Civil & AR | สหชาติ | 2026-05-01 | 2026-09-30 | 50% | Late | 2026-10-07 | 100% | Completed | 2026-10-30 | 0% | On Schedule
| DWE-39024 | Lot02 | MO-CK16 | Dangerous waste Storage 30 x 5 m. =10 room | สหชาติ | 2026-05-01 | 2026-07-15 | 100% | Completed | 2026-06-08 | 100% | Completed | 2026-09-30 | 0% | Late
| DWE-39026 | Lot02 | MO-CK23 | General waste Storage 22 x 5 m | สหชาติ | 2026-05-01 | 2026-07-15 | 100% | Completed | 2026-06-08 | 100% | Completed | 2026-09-30 | 0% | Late
| MDW-39507 | Lot02 | MO-BEM2 | High Roof at Main Work Shop Entrance and Store | สหชาติ | 2026-08-01 | 2026-07-01 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late | กำลังทำเอกสาร Test Report
| MDW-39509 | Lot02 | MO-BEM3 | High Roof at the entrance and exit of the under floor wheel lathe | สหชาติ | 2026-08-04 | 2026-07-01 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late | กำลังทำเอกสาร Test Report
| MDW-39511 | Lot02 | MO-BEM4.1 | Maintenance Office Rooms at Main Workshop - Civil & AR | สหชาติ | 2026-07-03 | 2026-05-31 | 100% | Completed | 2026-09-30 | 100% | Completed | 2026-10-21 | 0% | Late
| MDW-39536 | Lot02 | MO-BEM8 | Company logo and Central Control Room sign in CCR room. | สหชาติ | 2026-05-01 | 2026-09-30 | 50% | Late | 2026-10-07 | 0% | Late | 2026-10-30 | 0% | On Schedule
| MDW-39536 | Lot02 | MO-BEM9 | Soundproof insulation on the wall and structure and equipment in the CCR room. | สหชาติ | 2026-05-01 | 2026-09-30 | 50% | Late | 2026-10-07 | 0% | Late | 2026-10-30 | 0% | On Schedule
| MDW-39528 | Lot02 | MO-BEM11.1 | Washing Area in Cleaning Staff Room at Stabling Yard - Civil & AR | สหชาติ | 2026-08-03 | 2026-07-01 | 100% | Completed | 2026-09-30 | 50% | Late | 2026-10-15 | 0% | Late
| MDW-39522 | Lot02 | MO-BEM12 | Rain protection for Water treatment Building | สหชาติ | 2026-08-05 | 2026-07-01 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late
| MDW-39514 | Lot02 | MO-BEM15.1 | Roof for cars parking lots area (184 car)t - Civil & AR | สหชาติ | 2026-08-03 | 2026-07-24 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late | กำลังทำเอกสาร Test Report
| MDW-39531 | Lot02 | MO-BEM24 | Guard rail protection for Fire Hose Cabinet 8 set | สหชาติ | 2026-06-01 | 2026-07-16 | 100% | Completed | 2026-09-30 | 100% | Completed | 2026-10-21 | 0% | Late
| MDW-39514 | Lot02 | MO-BEM51 | Modify existing car park to be 220 motorcycle parking lots including floor painting and parking roof | สหชาติ | 2026-08-01 | 2026-07-01 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late | กำลังทำเอกสาร Test Report
มนตรี
| Design Submission | Lot No. | Code | Activity Name | CK Responsible Person | Expected Completion Month | Design (PLAN) | Design (%) | Design (Status) | Procurement (PLAN) | Procurement (%) | Procurement (Status) | Construction /Installation (PLAN) | Construction /Installation (%) | Construction /Installation (Status) | Note
| COM-39001 | Lot01 | COM3 | Walk-Through Metal Detector System (WTMD), 1 per entrance | มนตรี | 2026-11-19 | 2025-06-30 | 100% | Completed | 2026-05-15 | 100% | Completed | 2026-12-31 | 17.97% | On Schedule | รอออก PPR อยู่ระหว่างการตรวจสอบสินค้า
| COM-39004 | Lot01 | COM6 | Main Cable Containment for M&E Dedicated communication link to MRTA Head Quarter | มนตรี | 2026-09-20 | 2025-08-31 | 100% | Completed | 2026-06-30 | 0% | Late | 2027-02-28 | 0% | On Schedule | Fore cast Oct-26
| COM-39200 | Lot01 | COM1 | Magnetic Door Lock | มนตรี | 2026-08-21 | 2026-01-31 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-08-31 | 75% | Late | กำลังดำเนินการ Progress by CIP
| Design Submission | Lot No. | Code | Activity Name | CK Responsible Person | Expected Completion Month | Test Procedure (PLAN) | Test Procedure (%) | Test Procedure (Status) | Inspection (PLAN) | Inspection (%) | Inspection (Status) | Test Report (PLAN) | Test Report (%) | Test Report (Status) | Note
| MDW-39234 | Lot01 | GEN12.2 | Main Line Cable Trough Modification (SIG/COM) | มนตรี | 2026-06-22 | 2026-09-30 | 80% | Late | 2026-10-07 | 0% | Late | 2026-10-30 | 0% | Late | งานจบแล้ว
กำพล
| Design Submission | Lot No. | Code | Activity Name | CK Responsible Person | Expected Completion Month | Design (PLAN) | Design (%) | Design (Status) | Procurement (PLAN) | Procurement (%) | Procurement (Status) | Construction /Installation (PLAN) | Construction /Installation (%) | Construction /Installation (Status) | Note
| MDW-39004 | Lot01 | PSD2 | Rubber Gap Fillers on Platform Edge | กำพล | 2026-08-21 | 2025-07-30 | 100% | Completed | 2026-01-31 | 100% | Completed | 2026-08-31 | 0% | Late | แผนเข้าติดตั้ง 1-31/10/26
| MDW-39291 | Lot01 | GEN2.16 | Conductor Rail Arrangement Modification at Main Line East Section | กำพล | 2026-08-01 | 2026-09-30 | 100% | Completed | 2026-09-30 | 100% | Completed | 2026-12-31 | 90% | On Schedule
| MDW-39292 | Lot01 | GEN2.17 | Conductor Rail Arrangement Modification at Depot | กำพล | 2026-08-01 | 2026-09-30 | 100% | Completed | 2026-09-30 | 100% | Completed | 2026-12-31 | 90% | On Schedule
| MDW-39308 | Lot01 | GEN2.20 | Additional Locking Devices for Main Line Tandem Turnouts 2007, 2010 & 2013 and Depot Turnout D16 | กำพล | 2026-08-01 | 2026-11-30 | 50% | On Schedule | 2026-09-30 | 100% | Completed | 2026-12-31 | 0% | On Schedule
| MDW-39232 | Lot01 | GEN16 | Level Crossing at Turnout | กำพล | 2026-08-21 |  | 0% | On Schedule |  | 100% | Completed |  | 0% | On Schedule
| Design Submission | Lot No. | Code | Activity Name | CK Responsible Person | Expected Completion Month | Test Procedure (PLAN) | Test Procedure (%) | Test Procedure (Status) | Inspection (PLAN) | Inspection (%) | Inspection (Status) | Test Report (PLAN) | Test Report (%) | Test Report (Status) | Note
| MDW-39280 | Lot01 | PSD3 | Platform Finishing | กำพล | 2026-08-21 | 2026-08-17 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late
| MDW-39281 | Lot01 | PSD4 | Cladding Barrier between EWD and Station Structure | กำพล | 2026-08-21 | 2026-09-23 | 0% | Late | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late
| MDW-39293 | Lot01 | SIG2 | Rearrangement of track crossing walkway at stabling yard to consistent with the layout of 4-car train parking | กำพล | 2026-06-22 | 2026-09-30 | 50% | Late | 2026-10-07 | 0% | Late | 2026-10-30 | 0% | On Schedule
| MDW-39288 | Lot01 | SIG3 | Point Machine Foundation Construction | กำพล | 2026-08-21 | 2026-09-23 | 25% | Late | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late
สู่โชค
| Design Submission | Lot No. | Code | Activity Name | CK Responsible Person | Expected Completion Month | Design (PLAN) | Design (%) | Design (Status) | Procurement (PLAN) | Procurement (%) | Procurement (Status) | Construction /Installation (PLAN) | Construction /Installation (%) | Construction /Installation (Status) | Note
| MDW-39001 | Lot01 | SIG4 | Modification of Depot Track Route Line to Stabling Yard | สู่โชค | 2026-06-22 | 2025-10-30 | 100% | Completed | 2025-11-29 | 100% | Completed | 2026-05-28 | 95% | Late | คงเหลือเก็บงาน Progress by ช.ธนัท
| 0 | Lot02 | MO-BEM50 | Modify maintenance service door to the roof of OR13 vent building to easier access while maintaining safe operational standards | สู่โชค | 2027-01-01 | 2026-10-29 | 0% | On Schedule | 2026-10-30 | 100% | Completed | 2026-12-31 | 0% | On Schedule | เป็นงานเก็บ Defect งานจัดจ้างภายในไซต์ - บริเวณ IVS OR13 ทางเข้าห้อง sump pump ปัจจุบันเปิดได้โดยการยก โมดิฟายเพิ่ม hinge หรือ รอกยก - ที่ ivs มีห้องบางห้อง มีช่องเปิดที่พื้นบริเวณหน้าประตู, ให้ทำราวกันตก หรือโซ่กั้นหน้าประตู
มนต์ชัย
| Design Submission | Lot No. | Code | Activity Name | CK Responsible Person | Expected Completion Month | Test Procedure (PLAN) | Test Procedure (%) | Test Procedure (Status) | Inspection (PLAN) | Inspection (%) | Inspection (Status) | Test Report (PLAN) | Test Report (%) | Test Report (Status) | Note
| MDW-39233 | Lot01 | GEN12.1 | Main Line Cable Trough Modification (PSY) | มนต์ชัย | 2026-06-22 | 2026-09-30 | 80% | Late | 2026-10-07 | 0% | Late | 2026-10-30 | 0% | Late
Formulas:
Procurement (PLAN) = [Construction /Installation (PLAN)]-7
Procurement (PLAN) = [Design (PLAN)]+7
Procurement (Status) = IF([Construction /Installation (%)]=1, "Completed", IF([Construction /Installation (PLAN)]<TODAY(), "Late", "On Schedule"))
Construction /Installation (Status) = IF([Test Report (%)]=1, "Completed", IF([Note]<TODAY(), "Late", "On Schedule"))
Note = [Construction /Installation (PLAN)]+21
Test Report (Status) = IF(V68=1, "Completed", IF([Note]<TODAY(), "Late", "On Schedule"))
Design (Status) = IF([Procurement (%)]=1, "Completed", IF([Procurement (PLAN)]<TODAY(), "Late", "On Schedule"))
Construction /Installation (PLAN) = [Procurement (PLAN)]+21

## In (hidden)
[8 empty] | Inspection (PLAN) | ผู้รับผิดชอบ
Lot01 | PSY-39001-9 | PSY2 | PSY | GIS and BSS1 Building and Other Facilities | สหชาติ |  | 2026-03-24 | 2026-09-30 | เกียรติพล
Lot02 | MDW-39503 | Lot02 | MO-CK2 | New MMC at Admin Building - Civil&AR | สหชาติ | 2026-08-03 | 2026-09-30 | 2026-09-30 | เกียรติพล
Lot02 | MDW-39543 | MO-CK4 | MO-CK | Bird & Rain Protection for Open space Admin C | สหชาติ | Depot | 2026-08-01 | 2026-09-30 | เกียรติพล
Lot02 | MDW-39547 | MO-CK6 | MO-CK | Modify Lockset the emergency door to be used for passage between the 2nd and 3rd floors inside the building. | สหชาติ | Depot | 2026-08-03 | 2026-09-30 | เกียรติพล
Lot02 | MDW-39507 | MO-BEM2 | MO-BEM | High Roof at Main Work Shop Entrance and Store | สหชาติ | Depot | 2026-08-01 | 2026-09-30 | เกียรติพล
Lot02 | MDW-39509 | MO-BEM3 | MO-BEM | High Roof at the entrance and exit of the under floor wheel lathe | สหชาติ | Depot | 2026-08-04 | 2026-09-30 | เกียรติพล
Lot02 | MDW-39536 | Lot02 | MO-BEM8 | Company logo and Central Control Room sign in CCR room. | สหชาติ | 2026-05-01 | 2026-10-07 | 2026-10-07 | เกียรติพล
Lot02 | MDW-39536 | Lot02 | MO-BEM9 | Soundproof insulation on the wall and structure and equipment in the CCR room. | สหชาติ | 2026-05-01 | 2026-10-07 | 2026-10-07 | เกียรติพล
Lot02 | MDW-39522 | Lot02 | MO-BEM12 | Rain protection for Water treatment Building | สหชาติ | 2026-08-05 | 2026-09-30 | 2026-09-30 | เกียรติพล
Lot02 | MDW-39514 | Lot02 | MO-BEM15.1 | Roof for cars parking lots area (184 car)t - Civil & AR | สหชาติ | 2026-08-03 | 2026-09-30 | 2026-09-30 | เกียรติพล
Lot02 | MDW-39514 | Lot02 | MO-BEM51 | Modify existing car park to be 220 motorcycle parking lots including floor painting and parking roof |  |  |  | 2026-09-30 | เกียรติพล
[14 empty] | Inspection (PLAN) | ผู้รับผิดชอบ
[10 empty] | PSY-39001-9 | Lot01 | PSY2 | GIS and BSS Building and Other Facilities | 2026-09-30 | พรพรหม/ทินภัทร
[10 empty] | MDW-39545 | Lot02 | MO-CK11 | Chain Link at Cut & Cover 600m. | 2026-09-30 | พรพรหม/ก่อเกียรติ

## Design (hidden)
Design
No. | Design Submission | Lot No. | Code | System | Activity Name | CK Responsible Person |  | Location | Expected Completion Month | Design (PLAN) | Design (%) | Design (Status) | Note | Design Submission | Procedure No. | Test Report No.
1 | MDW-39246-60 | Lot01 | GEN1 | GEN | Rooms and Building Service Systems Modification in Stations Area | - | 0 | 0 | 2026-08-01 | 0 | 0 | 0 |  | MDW-39246 | MDW-69259 | MDW-69260
2 | MDW-39246 | Lot01 | GEN1.1 | GEN | Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR13 - OR17 | ประธาน | 0 | 0 | 2026-08-01 | 2026-01-30 | 100% | Completed |  | MDW-39246 | MDW-69259 | MDW-69260
3 | MDW-39247 | Lot01 | GEN1.2 | GEN | Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR18 - OR22 | ประธาน | 0 | 0 | 2026-08-01 | 2025-12-30 | 100% | Completed |  | MDW-39247 | MDW-69259 | MDW-69261
4 | MDW-39248 | Lot01 | GEN1.3 | GEN | Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR23 - OR29 | ประธาน | 0 | 0 | 2026-08-01 | 2026-01-30 | 100% | Completed |  | MDW-39248 | MDW-69259 | MDW-69262
5 | MDW-39252 | Lot01 | GEN1.4 | GEN | Modification of Fire Suppression System (N2) in Commerial Room at OR14 | ประธาน | 0 | 0 | 2026-08-01 | 2025-12-30 | 100% | Completed |  | MDW-39252 | MDW-69269 | MDW-69270
6 | MDW-39253 | Lot01 | GEN1.5 | GEN | Modification of Civil Work in Telecommunication Room at OR14 | สหชาติ | 0 | 0 | 2026-08-01 | 2025-12-30 | 100% | Completed |  | MDW-39253 | MDW-69271 | MDW-69272
7 | MDW-39254 | Lot01 | GEN1.6 | GEN | Modification in Staff Mess Room at OR13-OR17 | ประธาน | 0 | 0 | 2026-08-01 | 2026-01-30 | 100% | Completed |  | MDW-39254 | MDW-69273 | MDW-69274
8 | MDW-39255 | Lot01 | GEN1.7 | GEN | Modification in Staff Mess Room at OR18-OR22 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed |  | MDW-39255 | MDW-69273 | MDW-69275
9 | MDW-39256 | Lot01 | GEN1.8 | GEN | Modification in Staff Mess Room at OR23-OR29 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed |  | MDW-39256 | MDW-69273 | MDW-69276
10 | MDW-39257 | Lot01 | GEN1.9 | GEN | Modification of Air Conditioning in CER and SER at OR13-OR19 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed |  | MDW-39257 | MDW-69277 | MDW-69278
11 | MDW-39258 | Lot01 | GEN1.10 | GEN | Modification of Air Conditioning in CER and SER at OR20-OR22 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed |  | MDW-39258 | MDW-69277 | MDW-69279
12 | MDW-39259 | Lot01 | GEN1.11 | GEN | Modification of Air Conditioning in CER and SER at OR23-OR29 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed |  | MDW-39259 | MDW-69277 | MDW-69280
13 | MDW-39272 | Lot01 | GEN1.12 | GEN | Modification of New M&E Room at IVS15 - IVS17 Civil & AR | สหชาติ | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed |  | MDW-39272 | MDW-69299 | MDW-69300
14 | MDW-39273 | Lot01 | GEN1.13 | GEN | Modification of New M&E UPS Room at IVS15-IVS17 - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed |  | MDW-39273 | MDW-69301 | MDW-69302
15 | MDW-39294 | Lot01 | GEN1.14 | GEN | Provision of Architectural Work in new M&E UPS room at OR23 | สหชาติ | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed |  | MDW-39294 | MDW-69339 | MDW-69340
16 | MDW-39299 | Lot01 | GEN1.15 | GEN | Provision of Air Conditioning System in Commercial Room at OR13-OR19 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed |  | MDW-39299 | MDW-69349 | MDW-69350
17 | MDW-39306 | Lot01 | GEN1.16 | GEN | Modification CER and First Aid Room at OR14 - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed |  | MDW-39306 | MDW-69363 | MDW-69364
18 | MDW-39307 | Lot01 | GEN1.17 | GEN | Additional Fence at Back of House OR13 - OR22 and IVS East Section | สหชาติ | 0 | 0 | 2026-08-01 | 2026-09-30 | 100% | Completed |  | MDW-39307 | MDW-69365 | MDW-69366
19 | MDW-39249 | Lot01 | GEN1.18 | GEN | SOR Counter and Workstation Hanging Support Installation on East Section | สหชาติ | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed |  | MDW-39249 | MDW-69263 | MDW-69264
20 | MDW-39250 | Lot01 | GEN1.19 | GEN | Ticket Office Modification on East Section | สหชาติ | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed |  | MDW-39250 | MDW-69265 | MDW-69266
21 | MDW-39261 | Lot01 | GEN2 | GEN | Rooms and Building Service Systems Modification in Depot Area | - | 0 | Depot | 2026-08-01 | 0 | 0 | 0 |  | MDW-39261 | MDW-69283 | MDW-69284
22 | MDW-39260 | Lot01 | GEN2.1 | GEN | Modification of Air Conditioning in M&E Room at OCC Building | ประธาน | 0 | 0 | 2026-08-01 | 2025-12-30 | 100% | Completed |  | MDW-39260 | MDW-69281 | MDW-69282
23 | MDW-39261 | Lot01 | GEN2.2 | GEN | Provision of UPS for MDB Control at Main Workshop, OCC Building, Admin Building, Stabling Yard and Train Washing Plant | ประธาน | 0 | 0 | 2026-08-01 | 2026-09-01 | 100% | Completed |  | MDW-39261 | MDW-69283 | MDW-69284
24 | MDW-39262 | Lot01 | GEN2.3 | GEN | Provision of Redundant MDB at OCC Building, Admin Building and Canteen | ประธาน | 0 | 0 | 2026-08-01 | 2026-09-01 | 100% | Completed |  | MDW-39262 | MDW-69285 | MDW-69286
25 | MDW-39263 | Lot01 | GEN2.4 | GEN | Additonal Lighting System at Depot Area | ประธาน | 0 | 0 | 2026-08-01 | 2026-04-01 | 100% | Completed |  | MDW-39263 | MDW-69287 | MDW-69288
26 | MDW-39290 | Lot01 | GEN2.5 | GEN | Modification Room for PSY at Depot Buildings - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed |  | MDW-39290 | MDW-69331 | MDW-69332
27 | MDW-39300 | Lot01 | GEN2.6 | GEN | Modification SIG-PSD Office at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed |  | MDW-39300 | MDW-69351 | MDW-69352
28 | MDW-39301 | Lot01 | GEN2.7 | GEN | Modification Backup CCR Room at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed |  | MDW-39301 | MDW-69353 | MDW-69354
29 | MDW-39302 | Lot01 | GEN2.8 | GEN | Modification SER at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed |  | MDW-39302 | MDW-69355 | MDW-69356
30 | MDW-39303 | Lot01 | GEN2.9 | GEN | Modification CER & SCADA Room at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed |  | MDW-39303 | MDW-69357 | MDW-69358
31 | MDW-39309 | Lot01 | GEN2.10 | GEN | Modification Air Conditioning System at CCR | ประธาน | 0 | 0 | 2026-08-01 | 2026-10-01 | 100% | Completed |  | MDW-39309 | MDW-69369 | MDW-69370
32 | MDW-39312 | Lot01 | GEN2.11 | GEN | Modification Electronic Workshop at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-10-31 | 100% | Completed |  | MDW-39312 | MDW-69375 | MDW-69376
33 | MDW-39313 | Lot01 | GEN2.12 | GEN | Modification Battery Charger Room at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-10-31 | 100% | Completed |  | MDW-39313 | MDW-69377 | MDW-69378
34 | MDW-39314 | Lot01 | GEN2.13 | GEN | Modification Machining Room at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-10-31 | 90% | On Schedule |  | MDW-39314 | MDW-69379 | MDW-69380
35 | MDW-39315 | Lot01 | GEN2.14 | GEN | Modification Electronic Workshop, Battery Charger and Machining Room at Main Workshop - Civil & AR | สหชาติ | 0 | 0 | 2026-08-01 | 2026-10-31 | 70% | On Schedule |  | MDW-39315 | MDW-69383 | MDW-69384
36 | MDW-39297 | Lot01 | GEN2.15 | GEN | Training Room at Ratchada Station (Part 2) | สหชาติ | 0 | 0 | 2026-08-01 | 2026-08-01 | 0% | Late |  | MDW-39297 | MDW-69345 | MDW-69346
37 | MDW-39291 | Lot01 | GEN2.16 | GEN | Conductor Rail Arrangement Modification at Main Line East Section | กำพล | 0 | 0 | 2026-08-01 | 2026-09-30 | 100% | Completed |  | MDW-39291 | MDW-69333 | MDW-69334
38 | MDW-39292 | Lot01 | GEN2.17 | GEN | Conductor Rail Arrangement Modification at Depot | กำพล | 0 | 0 | 2026-08-01 | 2026-09-30 | 100% | Completed |  | MDW-39292 | MDW-69335 | MDW-69336
39 | MDW-39295 | Lot01 | GEN2.18 | GEN | Dangerous Goods Building in Depot - Civil & AR | สหชาติ | 0 | 0 | 2026-08-01 | 2026-01-27 | 100% | Completed |  | MDW-39295 | MDW-69341 | MDW-69342
40 | MDW-39296 | Lot01 | GEN2.19 | GEN | Dangerous Goods Building in Depot - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2025-12-13 | 100% | Completed |  | MDW-39296 | MDW-69343 | MDW-69344
41 | MDW-39308 | Lot01 | GEN2.20 | GEN | Additional Locking Devices for Main Line Tandem Turnouts 2007, 2010 & 2013 and Depot Turnout D16 | กำพล | 0 | 0 | 2026-08-01 | 2026-11-30 | 50% | On Schedule |  | MDW-39308 | MDW-69367 | MDW-69368
42 | MDW-39200-31 | Lot01 | GEN3 | GEN | Cable Containment Modification | - | 0 | 0 | 2025-05-28 | 0 | 0 | 0 | อยู่ระหว่างจัดทำแบบก่อสร้าง | MDW-39200
43 | - | Lot01 | GEN4 | GEN | Training Room and Workshop Room | - | 0 | 0 | 2026-04-01 | 0 | 0 | 0 |  |  | 0 | 0
44 | MDW-39242 | Lot01 | GEN4.0 | GEN | Modification Works for Training Room at Ratchada Station | ประธาน | 0 | 0 | 2026-04-01 | 2025-12-30 | 100% | Completed |  | MDW-39242 | MDW-69251 | MDW-69252
45 | MDW-39244 | Lot01 | GEN4.1 | GEN | AFC Training Room Modification - Civil & AR | สหชาติ | 0 | 0 | 2026-08-21 | 2026-09-30 | 10% | Late |  | MDW-39244 | MDW-69255 | MDW-69256
46 | MDW-39245 | Lot01 | GEN4.2 | GEN | AFC Training Room Modification - Building Services | ประธาน | 0 | 0 | 2026-08-21 | 2025-12-30 | 100% | Completed |  | MDW-39245 | MDW-69257 | MDW-69258
47 | MDW-39235 | Lot01 | GEN5 | GEN | Raised Floor | สหชาติ | 0 | 0 | 2026-06-01 | 2025-05-15 | 100% | Completed |  | MDW-39235 | MDW-69237 | MDW-69238
48 | MDW-39271 | Lot01 | GEN6 | GEN | Wayside Cable Containment in Depot | - | 0 | Depot | 2026-02-22 | 2025-05-15 | 100% | Completed |  | MDW-39271 | MDW-69297 | MDW-69298
49 | MDW-39269 | Lot01 | GEN6.1 | GEN | PSY Wayside Cable Containment for 24 Kv Cable under the Depot slab | ประธาน | 0 | Depot | 2026-02-22 | 0 | 0 | 0 |  | MDW-39269 | MDW-69293 | MDW-69294
50 | MDW-39270 | Lot01 | GEN6.2 | GEN | COM/SIG Wayside Cable Containment in the Depot | มนตรี/ประธาน | 0 | Depot | 2026-02-22 | 0 | 0 | 0 | คงเหลือจัดส่ง Signal Lamp | MDW-39270 | MDW-69295 | MDW-69296
51 | - | Lot01 | GEN7 | GEN | Dangerous Waste Storage Building in Depot | - | 0 | Depot | 2026-09-20 | 0 | 0 | 0 | GRS |  | 0 | 0
52 | DWE-39024 | Lot01 | GEN7.1 | GEN | Dangerous Waste Storage Building in Depot - Civil & AR | สหชาติ | 0 | Depot | 2026-09-20 | 2025-09-30 | 100% | Completed | GRS | DWE-39024 | DWE-69024 | DWE-69124
53 | DWE-39025 | Lot01 | GEN7.2 | GEN | Dangerous Waste Storage Building in Depot - Building service | ประธาน | 0 | Depot | 2026-09-20 | 2025-09-30 | 100% | Completed | GRS | DWE-39025 | DWE-69025 | DWE-69125
54 | - | Lot01 | GEN8 | GEN | General Waste Storage Building in Depot | - | 0 | Depot | 2026-09-20 | 0 | 0 | 0 |  |  | 0 | 0
55 | DWE-39026 | Lot01 | GEN8.1 | GEN | General Waste Storage Building in Depot - Civil & AR | สหชาติ | 0 | Depot | 2026-09-20 | 2025-09-30 | 100% | Completed |  | DWE-39026 | DWE-69026 | DWE-69126
56 | DWE-39025 | Lot01 | GEN8.2 | GEN | General Waste Storage Building in Depot - Building service | ประธาน | 0 | Depot | 2026-09-20 | 2025-09-30 | 100% | Completed |  | DWE-39025 | DWE-69025 | DWE-69125
57 | DWE-39021 | Lot01 | GEN9 | GEN | Operation Support Equipment | สมศักดิ์ | 0 | Depot | 2026-08-21 | 2025-03-02 | 100% | Completed | งานจบแล้ว | DWE-39021 | DWE-69021 | DWE-69121
58 | GRS-39001-40 | Lot01 | GEN10.1 | GEN | Graphic and Signage Station | สหชาติ | 0 | 0 | 2026-08-21 | 2026-06-30 | 100% | Completed |  | GRS-39001 | GRS-69001 | GRS-69002
59 | GRS-39001-40 | Lot01 | GEN10.2 | GEN | Graphic and Signage Mainline & IVS,VS | สหชาติ | 0 | 0 | 2026-08-21 | 2026-06-15 | 79% | Late |  | GRS-39001 | GRS-69001 | GRS-69002
60 | GRS-39001-40 | Lot01 | GEN10.3 | GEN | Graphic and Signage Depot | สหชาติ | 0 | 0 | 2026-08-21 | 2026-08-15 | 90% | Late |  | GRS-39001 | GRS-69001 | GRS-69002
61 | MDW-39289 | Lot01 | GEN11 | GEN | Earthing and Bonding Modification | ประธาน | 0 | 0 | 2026-03-01 | 2025-01-31 | 100% | Completed |  | MDW-39289 | MDW-69329 | MDW-69330
62 | - | Lot01 | GEN12 | GEN | Mainline Cable Trough Modification on East Section | - | 0 | 0 | 2026-06-22 | 2025-10-31 | 100% | Completed |  |  | 0 | 0
63 | MDW-39233 | Lot01 | GEN12.1 | GEN | Main Line Cable Trough Modification (PSY) | มนต์ชัย | 0 | Depot | 2026-06-22 | 2025-10-31 | 100% | Completed |  | MDW-39233
64 | MDW-39234 | Lot01 | GEN12.2 | GEN | Main Line Cable Trough Modification (SIG/COM) | มนตรี | 0 | 0 | 2026-06-22 | 2025-10-31 | 100% | Completed | Progress DPA1 : 100% Progress DPA2 : 100% Progress Cut&Cover OR22 : 95% | MDW-39234 | MDW-69234 | MDW-69236
65 | MDW-39236 | Lot01 | GEN13 | GEN | Bird Protection System | สหชาติ | 0 | 0 | 2026-11-19 | 2025-06-30 | 100% | Completed | Progress Cut&Cover OR22 : 95% | MDW-39236 | MDW-69239 | MDW-69240
66 | - | Lot01 | GEN14 | GEN | Train Crew Office at Thailand Cultural Centre Station | สหชาติ | 0 | 0 | 2026-08-21 | 2025-09-30 | 100% | Completed |  |  | 0 | 0
67 | MDW-39240 | Lot01 | GEN14.1 | GEN | Driver Train Simulation Room and Train Crew Office at OR18 - Civil & AR | สหชาติ | 0 | Depot | 2026-08-21 | 2025-09-30 | 100% | Completed | งานจบแล้ว | MDW-39240 | MDW-69247 | MDW-69248
68 | MDW-39241 | Lot01 | GEN14.2 | GEN | Driver Train Simulation Room and Train Crew Office at OR18 - Building Services | ประธาน | 0 | 0 | 2026-08-21 | 2025-09-30 | 100% | Completed | PPR Oct-26 กำลังเปรียบเทียบ Spec | MDW-39241 | MDW-69249 | MDW-69250
69 | MDW-39239 | Lot01 | GEN15 | GEN | Access Panel Closeout for Traction Substation Room in Main Workshop | สหชาติ | 0 | 0 | 2026-03-24 | 2026-01-30 | 100% | Completed |  | MDW-39239 | MDW-69245 | MDW-69246
70 | MDW-39232 | Lot01 | GEN16 | GEN | Level Crossing at Turnout | กำพล | 0 | 0 | 2026-08-21 | 2026-09-30 | 100% | Completed | แผนเข้าติดตั้ง 1-31/10/26 | MDW-39232 | MDW-69232 | MDW-69233
71 | MDW-39232 | Lot01 | GEN17 | GEN | Track Slab Crossing | ชฎิล/กำพล | 0 | 0 | 2026-08-21 | 0 | 0 | 0 |  | MDW-39232 | MDW-69232 | MDW-69233
72 | MDW-39243 | Lot01 | GEN18 | GEN | Eye Adaptation Lighting (Lighting at Tunnel to Expose) | ประธาน | 0 | 0 | 2026-11-19 | 2025-09-30 | 100% | Completed |  | MDW-39243 | MDW-69253 | MDW-69254
73 | - | Lot01 | GEN19 | GEN | Train Simulation Room and AFC Training Room | - | 0 | 0 | 2026-08-21 | 0 | 0 | 0 | มีแก้ไขตำแหน่ง OR14,17,18,23 |  | 0 | 0
74 | MDW-39244 | Lot01 | GEN19.1 | GEN | Modification AFC Training Center at OR19 - Civil & AR | สหชาติ | 0 | 0 | 2026-11-30 | 2026-09-30 | 100% | Completed | จัดเตรียมแบบ ออกPPR Oct-26 | MDW-39244 | MDW-69255 | MDW-69256
75 | MDW-39245 | Lot01 | GEN19.2 | GEN | Modification AFC Training Center at OR19 - Building Services | ประธาน | บัณฑิต | 0 | 2026-11-30 | 2026-09-30 | 100% | Completed |  | MDW-39245 | MDW-69257 | MDW-69258
76 | - | Lot01 | GEN20 | GEN | Dormitory Cable Containments (if any) | - | 0 | 0 | - | 0 | 0 | 0 |  |  | 0 | 0
77 |  | Lot01 | GEN21 | GEN | Project Information Management System (PIMS) | บัณฑิต | 0 | 0 | 2024-09-30 | 2024-08-10 | 100% | Completed
78 | MDW-39237 | Lot01 | GEN22 | GEN | Central BEMS for the MRT Orange Line System | บัณฑิต | 0 | 0 | 2026-08-21 | 2026-04-30 | 0% | Late |  | MDW-39237 | MDW-69241 | MDW-69242
79 |  | Lot01 | GEN23 | GEN | Asset Information | บัณฑิต | 0 | 0 | 2026-11-19 | 0 | 0 | 0 | คงเหลือเก็บงาน Progress by ช.ธนัท
80 | MDW-39282 | Lot01 | PSD1 | PSD | Holes for PSD Cable Wiring | กำพล | 0 | 0 | 2026-08-21 | 0 | 0 | 0 |  | MDW-39282 | MDW-69315 | MDW-69316
81 | MDW-39004 | Lot01 | PSD2 | PSD | Rubber Gap Fillers on Platform Edge | กำพล | 0 | 0 | 2026-08-21 | 2025-07-30 | 100% | Completed | Test ช่วงต้น Nov-26 | MDW-39004 | MDW-69007 | MDW-69008
82 | MDW-39280 | Lot01 | PSD3 | PSD | Platform Finishing | กำพล | 0 | 0 | 2026-08-21 | 2025-07-30 | 100% | Completed | Test 9-15/11/26 | MDW-39280 | MDW-69311 | MDW-69312
83 | MDW-39281 | Lot01 | PSD4 | PSD | Cladding Barrier between EWD and Station Structure | กำพล | 0 | 0 | 2026-08-21 | 2026-02-28 | 100% | Completed | Test 9-15/11/26 | MDW-39281 | MDW-69313 | MDW-69314
84 | - | Lot01 | AFC1 | AFC | Park and Ride System | บัณฑิต/สหชาติ | 0 | 0 | 2026-10-20 | 0 | 0 | 0 | Forecast Install 1/11-30-11/26 |  | 0 | 0
85 | MDW-39276 | Lot01 | AFC2 | AFC | Ticket Issuing Machine (TIM) Wall Opening and Closing | สหชาติ | 0 | 0 | 2026-09-20 | 2026-01-30 | 100% | Completed | Test 26-30/10/26 | MDW-39276 | MDW-69303 | MDW-69304
86 | MDW-39279 | Lot01 | AFC3 | AFC | Balustrade Modification Along AFC Gate Line | สหชาติ | 0 | 0 | 2026-09-20 | 2026-06-30 | 10% | Late | Test 26-30/10/26 | MDW-39279 | MDW-69309 | MDW-69310
87 | MDW-39278 | Lot01 | AFC4 | AFC | Underfloor Embedded Duct Modification for AFC Gates Line | สหชาติ | 0 | Depot | 2026-09-20 | 2026-01-30 | 100% | Completed | Test 26-30/10/26 | MDW-39278 | MDW-69307 | MDW-69308
88 | MDW-39002 | Lot01 | SIG1 | SIG | Test Track Shelters and Test Track Building | สหชาติ | 0 | 0 | 2026-06-22 | 2025-11-22 | 100% | Completed | Test 26-30/10/26 | MDW-39002 | MDW-69003 | MDW-69004
89 | MDW-39293 | Lot01 | SIG2 | SIG | Rearrangement of track crossing walkway at stabling yard to consistent with the layout of 4-car train parking | กำพล | 0 | Depot | 2026-06-22 | 2025-11-30 | 100% | Completed | คงเหลือจัดส่งอุปกรณ์ | MDW-39293 | MDW-69337 | MDW-69338
90 | MDW-39288 | Lot01 | SIG3 | SIG | Point Machine Foundation Construction | กำพล | 0 | 0 | 2026-08-21 | 2025-11-21 | 100% | Completed | Test 9-15/11/26 | MDW-39288 | MDW-69327 | MDW-69328
91 | MDW-39001 | Lot01 | SIG4 | SIG | Modification of Depot Track Route Line to Stabling Yard | สู่โชค | 0 | Depot | 2026-06-22 | 2025-10-30 | 100% | Completed | Test 9-15/11/26 | MDW-39001 | MDW-69001 | MDW-69002
92 | MDW-39287 | Lot01 | SIG5 | SIG | Strobe Light at Buffer Stops | ประธาน | 0 | Depot | 2026-08-21 | 2026-05-30 | 100% | Completed | Test 9-15/11/26 | MDW-39287 | MDW-69323 | MDW-69324
93 | DWE-39016 | Lot01 | DWE1 | DWE | Diesel Fuel Storage Tank for Maintenance Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | งาน Handrail ที่ Pits Wheel Reprofling Plant ติดตั้งแล้วเหลืองานเก็บสี | DWE-39016 | DWE-69016 | DWE-69116
94 | DWE-39011 | Lot01 | DWE2 | DWE | Movable Height Maintenance Platform Vehicle (Boom Lift) | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed |  | DWE-39011 | DWE-69011 | DWE-69111
95 | DWE-39012 | Lot01 | DWE3 | DWE | Fork Lift Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed |  | DWE-39012 | DWE-69012 | DWE-69112
96 | DWE-39015 | Lot01 | DWE4 | DWE | Compressed Air System and Portable Air Compressor for Depot | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | Test 9-15/11/26 | DWE-39015 | DWE-69015 | DWE-69115
97 | DWE-39017 | Lot01 | DWE5 | DWE | Pallet Storage Shelves in Hazardous Storage | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | Test 18-30/1/27 | DWE-39017 | DWE-69017 | DWE-69117
98 | DWE-39017 | Lot01 | DWE6 | DWE | Pallet Storage in Main Storage Room | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | Delivery to Thailand Feb-27 | DWE-39017 | DWE-69017 | DWE-69117
99 | DWE-39017 | Lot01 | DWE7 | DWE | Two-Tier Shelf | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | Delivery to Thailand Feb-27 | DWE-39017 | DWE-69017 | DWE-69117
100 | DWE-39017 | Lot01 | DWE8 | DWE | Tool Storage | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | Delivery to Thailand Dec-26 | DWE-39017 | DWE-69017 | DWE-69117
101 | DWE-39018 | Lot01 | DWE9 | DWE | Repair Equipment | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | Delivery to Thailand Dec-26 | DWE-39018 | DWE-69018 | DWE-69118
102 | DWE-39020 | Lot01 | DWE10 | DWE | Oil & Grease Disposal | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | Test 16-22/11/26 | DWE-39020 | DWE-69020 | DWE-69120
103 | DWE-39020 | Lot01 | DWE11 | DWE | Grease Dispensers | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | Delivery to Thailand Dec-26 | DWE-39020 | DWE-69020 | DWE-69120
104 | DWE-39020 | Lot01 | DWE12 | DWE | Waste Disposal | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed |  | DWE-39020 | DWE-69020 | DWE-69120
105 | MDW-39305 | Lot01 | DWE13 | DWE | Safety Provision for Maintenance Pits | สหชาติ | 0 | Depot | 2026-09-20 | 2025-11-30 | 100% | Completed | คงเหลืองานเดินท่อและ Pump น้ำมัน | MDW-39305 | MDW-69361 | MDW-69362
106 | DWE-39xxx | Lot01 | DWE14 | DWE | Pit Drainage System in Main Workshop | สมศักดิ์ | 0 | Depot | 2026-09-20 | 0 | 0 | 0 |  | DWE-39xxx | MDW-69361 | MDW-69362
107 | DWE-39023 | Lot01 | DWE15 | DWE | Provision of Civil Works and Building Services to support Train Washing Equipment | สหชาติ | 0 | Depot | 2026-08-01 | 2025-11-30 | 100% | Completed |  | DWE-39023 | DWE-69023 | DWE-69123
108 | DWE-39013 | Lot01 | DWE16 | DWE | Overhead Traveling Crane | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | กำลังดำเนินการ Progress by CIP | DWE-39013 | DWE-69013 | DWE-69113-513
109 | DWE-39009 | Lot01 | DWE17 | DWE | Vehicle Inspection and Servicing Facilities | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | รอพื้นที่เข้าติดตั้ง | DWE-39009 | DWE-69009 | DWE-69109
110 | DWE-39014 | Lot01 | DWE18 | DWE | Permanent Way Maintenance Facility | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-04-30 | 100% | Completed | รอออก PPR อยู่ระหว่างการตรวจสอบสินค้า | DWE-39014 | DWE-69014 | DWE-69114
111 | - | Lot01 | DWE19 | DWE | Permanent Way Vehicles | สมศักดิ์ | 0 | Depot | 2026-09-20 | 0 | 0 | 0 | รอเฟอร์นิเจอร์ Fore cast Dec-26 |  | 0 | 0
112 | DWE-39001 | Lot01 | DWE19.1 | DWE | Shunting Locomotive | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | Fore cast Oct-26 | DWE-39001 | DWE-69001 | DWE-69101
113 | DWE-39002 | Lot01 | DWE19.2 | DWE | Tunnel Inspection and Cleaning Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 0% | Late | ของมาแล้ว รอพื้นที่เข้าติดตั้ง | DWE-39002 | DWE-69002 | DWE-69102
114 | DWE-39003 | Lot01 | DWE19.3 | DWE | Hi/Rail Maintenance Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | งานจบแล้ว | DWE-39003 | DWE-69003 | DWE-69103
115 | DWE-39004 | Lot01 | DWE19.4 | DWE | Flat wagon | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | งานจบแล้ว | DWE-39004 | DWE-69004 | DWE-69104
116 | DWE-39005 | Lot01 | DWE19.5 | DWE | Re-railing Equipment | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed |  | DWE-39005 | DWE-69005 | DWE-69105
117 | DWE-39006 | Lot01 | DWE19.6 | DWE | Self-Propelled Rail Based Inspection Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed |  | DWE-39006 | DWE-69006 | DWE-69106
118 | DWE-39007 | Lot01 | DWE19.7 | DWE | Rail Head Grinding Machine Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 0% | Late | รอสรุปตำแหน่ง Power Plug ชาร์จโฟลคลิฟท์ Oct-26 | DWE-39007 | DWE-69007 | DWE-69107
119 | DWE-39008 | Lot01 | DWE19.8 | DWE | Multi Measuring Rail Vehicle | สมศักดิ์ | 0 | 0 | 2026-09-20 | 0 | 0 | 0 | กำลังทำเอกสาร Test Report | DWE-39008 | DWE-69008 | DWE-69108
120 | DWE-39010 | Lot01 | DWE19.9 | DWE | High Work Inspection Vehicle | สมศักดิ์ | 0 | 0 | 2026-09-20 | 0 | 0 | 0 | Fore cast Oct-26 | DWE-39010
121 | - | Lot01 | DWE20 | DWE | Building Maintenance Vehicle | - | 0 | 0 | 2026-09-20 | 0 | 0 | 0 |  |  | 0 | 0
122 | EPS-39001 | Lot01 | PSY1 | PSY | Diesel Fuel Storage Tanks for Power Generators | สมศักดิ์ | 0 | 0 | 2026-03-24 | 2026-01-16 | 100% | Completed |  | EPS-39001 | EPS-69001 | EPS-69002
123 | PSY-39001-9 | Lot01 | PSY2 | PSY | GIS and BSS Building and Other Facilities | สหชาติ | 0 | 0 | 2026-03-24 | 2024-08-29 | 100% | Completed |  | PSY-39001 | PSY-69001 | PSY-69002
124 | PSY-39011 | Lot01 | PSY3 | PSY | Steel Grating Raised Floor for EE Panel | สหชาติ | 0 | 0 | 2026-03-24 | 2024-09-30 | 100% | Completed |  | PSY-39011 | PSY-69015 | PSY-69016
125 | - | Lot01 | PSY4 | PSY | Trapping Box between PSY Service Sub Station (SSS) and Low Volt (LV) System | - | 0 | 0 | 2026-08-21 | 0 | 0 | 0 |  |  | 0 | 0
126 | SCA-39200 | Lot01 | SCA1 | SCA | Modification of BEMS to receive PSD Signal on East Section | ธารทิพย์ | 0 | 0 | 2026-08-21 | 0 | 0 | 0 | คงเหลืองานคอนกรีตทางเดินข้ามราง | SCA-39200 | SCA-69200 | SCA-69201
127 | - | Lot01 | SCA2 | SCA | Modification of Escalator Interface Point with CCTV and SCADA, East Section | - | 0 | 0 | 2026-08-21 | 0 | 0 | 0 | มีงานเพิ่มอีก 18 แผง |  | 0 | 0
128 | - | Lot01 | SCA3 | SCA | Magnetic of Fire Alarm System Interface Point with CCTV and SCADA | - | 0 | 0 | 2026-08-21 | 0 | 0 | 0 | เริ่มติดตั้ง Chainlink แล้ว |  | 0 | 0
129 | SCA-39203 | Lot01 | SCA4 | SCA | Add/Modify Civil Scada Hardwire for all Station | ประธาน/ธารทิพย์ | 0 | 0 | 2026-08-21 | 0 | 0 | 0 |  | SCA-39203 | SCA-69206 | SCA-69207
130 | COM-39200 | Lot01 | COM1 | COM | Magnetic Door Lock | มนตรี | 0 | 0 | 2026-08-21 | 2025-06-30 | 100% | Completed |  | COM-39200 | COM-69200 | COM-69201
131 | MDW-39283 | Lot01 | COM2 | COM | Intercom System in Cash Handling Room (if require) | บัณฑิต | 0 | 0 | 2026-12-19 | 2025-09-30 | 100% | Completed |  | MDW-39283 | MDW-69317 | MDW-69318
132 | COM-39001 | Lot01 | COM3 | COM | Walk-Through Metal Detector System (WTMD), 1 per entrance | มนตรี | 0 | 0 | 2026-11-19 | 2025-08-31 | 0% | Late |  | COM-39001 | COM-69001 | COM-69002
133 | MDW-39284 | Lot01 | COM4 | COM | Traveling Cable in all Lifts | มนตรี | 0 | 0 | - | 0 | 0 | 0 | Fore cast Nov-26 | MDW-39284 | MDW-69319 | MDW-69320
134 | MDW-39304 | Lot01 | COM5 | COM | MEA Radio | ประธาน | 0 | 0 | 2026-09-20 | 2026-01-30 | 100% | Completed |  | MDW-39304 | COM-69202 | COM-69203
135 | COM-39004 | Lot01 | COM6 | COM | Main Cable Containment for M&E Dedicated communication link to MRTA Head Quarter | มนตรี | 0 | 0 | 2026-09-20 | 2026-01-31 | 100% | Completed | GRS | COM-39004 | COM-69005 | COM-69006
136 | AFC-39001 | Lot01 | COM7 | COM | Mini Paging in Ticket Office | บัณฑิต | 0 | 0 | 2026-12-19 | 2025-09-10 | 100% | Completed | GRS | AFC-39002 | AFC-69003 | AFC-69004
137 | MDW-39285 | Lot01 | COM8 | COM | Provision of Cable Containment between OCC ORL and OCC BL | มนตรี | 0 | 0 | 2026-07-22 | 0 | 0 | 0 | GRS | MDW-39285
138 | COM-39005 | Lot01 | COM9 | COM | Power Distribution for M&E Systems at MRTA Head Quarter | มนตรี | 0 | 0 | 2026-09-20 | 2026-03-31 | 100% | Completed | GRS | COM-39005 | COM-69007 | COM-69008
139 | COM-39205 | Lot01 | COM10 | COM | Underground Cable Containment at Public Areas (if require) | มนตรี | 0 | 0 | 2026-08-21 | 2026-04-30 | 100% | Completed | GRS | MDW-39205 | MDW-69200 | MDW-69205
140 | - | Lot01 | COM11 | COM | Intercom at Ticket Issuing Machine | บัณฑิต | 0 | Depot | - | 0 | 0 | 0 | GRS |  | 0 | 0
141 | RST-39004,8 | Lot01 | RST1 | RST | Driver Training Simulator | ธัญวิทย์ | 0 | Depot | 2026-09-20 | 2025-05-30 | 100% | Completed |  | RST-39004,8
142 | MDW-39500 | Lot02 | MO-CK1.1 | MO-CK | Store Modification Works at Main Workshop - Civil&AR | สหชาติ | 0 | Depot | 2026-06-03 | 2026-02-27 | 100% | Completed | GRS | MDW-39500 | MDW-69500 | MDW-69501
143 | MDW-39501 | Lot02 | MO-CK1.2 | MO-CK | Store Modification Works at Main Workshop - Building Services | ประธาน | 0 | Depot | 2026-06-04 | 2026-02-12 | 100% | Completed | GRS | MDW-39501 | MDW-69502 | MDW-69503
144 | MDW-39503 | Lot02 | MO-CK2 | MO-CK | New MMC at Admin Building - Civil&AR | สหชาติ | 0 | Depot | 2026-08-03 | 2026-04-14 | 100% | Completed | GRS | MDW-39503 | MDW-69506 | MDW-69507
145 | MDW-39504 | Lot02 | MO-CK3 | MO-CK | Move or link Workstation and control panel to MMC room at admin C 2nd floor | ประธาน | 0 | Depot | 2026-08-02 | 2026-02-28 | 100% | Completed | อยู่ระหว่างส่งขออนุมัติแบบรอ Approve | MDW-39504 | MDW-69508 | MDW-69509
146 | MDW-39543 | Lot02 | MO-CK4 | MO-CK | Bird & Rain Protection for Open space Admin C | สหชาติ | 0 | Depot | 2026-08-01 | 2026-04-29 | 100% | Completed |  | MDW-39543 | MDW-69586 | MDW-69587
147 | MDW-39547 | Lot02 | MO-CK5 | MO-CK | Relocate door in front of toilet and build partition wall to conceal the view in side of toilet | สหชาติ | 0 | Depot | 2026-08-02 | 2026-05-14 | 100% | Completed | ไฟส่องสว่างสำหรับพื้นที่ปิดใต้บันไดและด้านหลังช่องลิฟต์ที่สถานีรถไฟใต้ดิน | MDW-39547 | MDW-69594 | MDW-69595
148 | MDW-39547 | Lot02 | MO-CK6 | MO-CK | Modify Lockset the emergency door to be used for passage between the 2nd and 3rd floors inside the building. | สหชาติ | 0 | Depot | 2026-08-03 | 2026-04-29 | 100% | Completed |  | MDW-39547 | MDW-69594 | MDW-69595
149 | MDW-39556 | Lot02 | MO-CK7 | MO-CK | Addition small power for lounge and pantry room at 2nd floor and Hall and observation room at 3nd floor | ประธาน | 0 | Depot | 2026-08-04 | 2026-05-14 | 100% | Completed | ซื้อสปอร์ตไลท์+แบต จำนวน 4 ชุด แทนการลากสายไฟ | MDW-39556 | MDW-69612 | MDW-69613
150 | MDW-39548 | Lot02 | MO-CK8 | MO-CK | Air Condition for using store room to be pantry room. 2nd floor | ประธาน | 0 | Depot | 2026-08-05 | 2026-04-29 | 100% | Completed |  | MDW-39548 | MDW-69596 | MDW-69597
151 | MDW-39552 | Lot02 | MO-CK9 | MO-CK | Walk Way Hand rail high 90 cm 1 side (144 m. x 7 route) | สหชาติ | 0 | Depot | 2026-10-01 | 2026-05-30 | 100% | Completed | GRS | MDW-39552 | MDW-69604 | MDW-69605
152 | MDW-39544 | Lot02 | MO-CK10 | MO-CK | Barbed wire fence Viaduct CE CW | บัณฑิต/สหชาติ | พี่ต่อ | Depot | 2027-01-01 | 0 | 0 | 0 | คงเหลืองานมุงหลังคา Metal sheet | MDW-39544 | MDW-69588 | MDW-69589
153 | MDW-39545 | Lot02 | MO-CK11 | MO-CK | Chain Link at Cut & Cover 600m. | สหชาติ | พรพรหม | Depot | 2026-06-01 | 2026-02-27 | 100% | Completed | รองานหลังคา CIV Oct-26 | MDW-39545 | MDW-69590 | MDW-69591
154 | MDW-39546 | Lot02 | MO-CK12 | MO-CK | Chain Link under slab high 1.70 m | สหชาติ | 0 | 0 | 2027-01-01 | 2026-06-30 | 100% | Completed | กำลังทำเอกสาร Test Report | MDW-39546 | MDW-69592 | MDW-69593
155 | MDW-39550 | Lot02 | MO-CK13.1 | MO-CK | Satellite Store at OR21 - Civil & AR | สหชาติ | 0 | 0 | 2027-01-02 | 2026-08-30 | 100% | Completed | กำลังทำเอกสาร Test Report | MDW-39550 | MDW-69600 | MDW-695601
156 | MDW-39549 | Lot02 | MO-CK13.2 | MO-CK | Maintenance Room and Satellite Store at Stations - Building Services | ประธาน | 0 | 0 | 2027-01-03 | 2026-08-30 | 100% | Completed |  | MDW-39549 | MDW-69598 | MDW-69599
157 | MDW-39551 | Lot02 | MO-CK14 | MO-CK | Modify Cleaner room at OR29 to be Train crew Standby office with facility system | ประธาน | 0 | Depot | 2026-07-01 | 2026-03-14 | 100% | Completed | รอส่งงานกับ BEM | MDW-39551 | MDW-69602 | MDW-69603
158 | MDW-39295 | Lot02 | MO-CK15.1 | MO-CK | Epoxy Floor Installation and Curb Installation at the Entrance - Civil & AR | สหชาติ | 0 | Depot | 2026-05-01 | 2026-01-27 | 100% | Completed |  | MDW-39295 | MDW-69341 | MDW-69342
159 | MDW-39296 | Lot02 | MO-CK15.2 | MO-CK | Change Electrical Equipment to be Explosion-proof type - Building Services | ประธาน | 0 | Depot | 2026-05-01 | 2025-12-13 | 100% | Completed |  | MDW-39296 | MDW-69343 | MDW-69344
160 | DWE-39024 | Lot02 | MO-CK16 | MO-CK | Dangerous waste Storage 30 x 5 m. =10 room | สหชาติ | 0 | Depot | 2026-05-01 | 2025-09-30 | 100% | Completed |  | DWE-39024 | DWE-69024 | DWE-69124
161 | 0 | Lot02 | MO-CK17 | MO-CK | Safety Sign all Depot Area building | สหชาติ | 0 | Depot | 2026-05-01 | 2025-11-28 | 100% | Completed |  |  | 0 | 0
162 | 0 | Lot02 | MO-CK18 | MO-CK | Emergency escape route map | สหชาติ | 0 | Depot | 2027-01-01 | 2026-09-30 | 0% | Late |  |  | 0 | 0
163 | 0 | Lot02 | MO-CK19 | MO-CK | Traffic Line Marking (Thermoplastic Paint) | สหชาติ | 0 | Depot | 2026-05-01 | 2026-04-30 | 100% | Completed |  |  | 0 | 0
164 | 0 | Lot02 | MO-CK20 | MO-CK | Emergency Car Parking location Painting in front of MWS | สหชาติ | 0 | Depot | 2026-05-01 | 2026-04-30 | 100% | Completed |  |  | 0 | 0
165 | GRS-39022 | Lot02 | MO-CK21 | MO-CK | Safety Line painting in MWS, Stabling Area, P-way, Track | สหชาติ | 0 | Depot | 2027-01-01 | 2026-06-01 | 100% | Completed |  | GRS-39022 | GRS-69001 | GRS-69022
166 | 0 | Lot02 | MO-CK22 | MO-CK | Fire escape stairs level signs in the Depot, VS and IVS areas | สหชาติ | 0 | Depot | 2027-01-01 | 2026-09-30 | 50% | Late |  |  | 0 | 0
167 | DWE-39026 | Lot02 | MO-CK23 | MO-CK | General waste Storage 22 x 5 m | สหชาติ | 0 | Depot | 2026-05-01 | 2025-09-30 | 100% | Completed | คงเหลืองานประกอบและติดตั้งโครงหลงัคา | DWE-39026 | DWE-69026 | DWE-69126
168 | 0 | Lot02 | MO-CK24 | MO-CK | Modify Traffic paint and traffic sign | สหชาติ | 0 | 0 | 2026-05-01 | 2026-04-30 | 100% | Completed |  |  | 0 | 0
169 | 0 | Lot02 | MO-CK25 | MO-CK | Station Area sign 28 stations | สหชาติ | 0 | 0 | 2026-05-01 | 2026-06-15 | 80% | Late | คงเหลืองานติดตั้งสะพานและปรับพื้นที่ถนน |  | 0 | 0
170 |  | Lot02 | MO-CK26 | MO-CK | Safety and warning signage for lift and escalator at all station | สหชาติ | 0 | Depot | 2027-01-01 | 2026-06-16 | 100% | Completed | รองานหลังคา CIV Oct-26
171 | MDW-39532 | Lot02 | MO-CK27 | MO-CK | Spike fence for Depot slab | สหชาติ | 0 | Depot | 2027-01-01 | 2026-07-31 | 70% | Late | กำลังทำเอกสาร Test Report | MDW-39532 | MDW-69564 | MDW-69565
172 | 0 | Lot02 | MO-CK28 | MO-CK | Bird net and Flashing at MWS and Skywalk to Stabling yard | สหชาติ | 0 | 0 | 2026-05-01 |  |  | 0 | รอส่งงานกับ BEM |  | 0 | 0
173 | MDW-39541 | Lot02 | MO-CK29 | MO-CK | Fire Alarm Manual Call Point signage at all elevated station | สหชาติ | 0 | 0 | 2027-01-01 |  |  | 0 | คงเหลืองานโครงเหล็ก หลังคา และ Composite | MDW-39541 | MDW-69582 | MDW-69583
174 | 0 | Lot02 | MO-CK30 | MO-CK | Lighting for sealed space under stairs and behind lift shaft at underground station | ประธาน | 0 | 0 | 2027-01-01 | 2026-10-14 | 0% | Late | คงเหลืองานโครงหลังคาและมุงหลังคา |  | 0 | 0
175 | 0 | Lot02 | MO-CK31 | MO-CK | Modify the access door of sealed space (under-stairs room) with a Sump Pump or ESPS cabinet | สหชาติ | 0 | 0 | 2027-01-01 | 2026-07-16 | 0% | Late | รอ BEM สรุปว่ายกเลิกหรือทำ |  | 0 | 0
176 | 0 | Lot02 | MO-CK32 | MO-CK | Lighting to the sealed space (under-stairs room) with a Sump Pump or ESPS cabinet | ประธาน | 0 | Depot | 2027-01-01 | 2026-11-03 | 0% | On Schedule |  |  | 0 | 0
177 | 0 | Lot02 | MO-CK33 | MO-CK | Additional lighting in areas where the lux level does not meet occupational health standards | ประธาน | 0 | Depot | 2027-01-01 | 2026-09-14 | 100% | Completed |  |  | 0 | 0
178 | 0 | Lot02 | MO-CK34 | MO-CK | Provide and install confined space signage for Station and Depot | สหชาติ | 0 | 0 | 2027-01-01 | 2026-08-15 | 100% | Completed |  |  | 0 | 0
179 |  | Lot02 | MO-CK35 | MO-CK | Build room for Train crew main office at OR18 with office area, resting area, meeting room, pantry, toilet and locker room | สหชาติ/บัณฑิต/ประธาน | 0 | Depot | - |  |  | 0
180 |  | Lot02 | MO-CK36 | MO-CK | Dormitory Cable Containments (if any) | มนตรี | 0 | Depot | - |  |  | 0
181 | 0 | Lot02 | MO-CK37 | MO-CK | Provide Raise floor and building Service in Training &Simulator (OCC Admin) | สหชาติ | 0 | Depot | - | 0 | 0 | 0 | อยู่ระหว่างส่งขออนุมัติแบบรอ Approve |  | 0 | 0
182 |  | Lot02 | MO-CK38 | MO-CK | Add N2 in Playback and Training Room and Backup Control Room | บุญประเสริฐ | 0 | Depot | - |  |  | 0
183 | MDW-39505 | Lot02 | MO-BEM1.1 | MO-BEM | Walkway from Main Work Shop to Stabling Area - Civil & AR | สหชาติ | 0 | Depot | 2026-08-02 | 2026-04-28 | 100% | Completed |  | MDW-39505 | MDW-69510 | MDW-69511
184 | MDW-39506 | Lot02 | MO-BEM1.2 | MO-BEM | Walkway from Main Work Shop to Stabling Area - Building Services | ประธาน | 0 | Depot | 2026-08-02 | 2026-04-28 | 100% | Completed |  | MDW-39506 | MDW-69512 | MDW-69513
185 | MDW-39507 | Lot02 | MO-BEM2 | MO-BEM | High Roof at Main Work Shop Entrance and Store | สหชาติ | 0 | Depot | 2026-08-01 | 2026-02-13 | 100% | Completed | Fore cast Oct-26 | MDW-39507 | MDW-69514 | MDW-69515
186 | MDW-39509 | Lot02 | MO-BEM3 | MO-BEM | High Roof at the entrance and exit of the under floor wheel lathe | สหชาติ | 0 | Depot | 2026-08-04 | 2026-02-13 | 100% | Completed | อยู่ระหว่างจัดเตรียมแบบ งาน Construction จบ Mar-27 | MDW-39509 | MDW-69518
187 | MDW-39511 | Lot02 | MO-BEM4.1 | MO-BEM | Maintenance Office Rooms at Main Workshop - Civil & AR | สหชาติ | 0 | Depot | 2026-07-03 | 2026-04-13 | 100% | Completed |  | MDW-39511 | MDW-69522 | MDW-69523
188 | MDW-39512 | Lot02 | MO-BEM4.2 | MO-BEM | Maintenance Office Rooms at Main Workshop - Building Services | ประธาน | 0 | Depot | 2026-07-04 | 2026-04-13 | 100% | Completed |  | MDW-39512 | MDW-69524 | MDW-69525
189 | MDW-39513 | Lot02 | MO-BEM5 | MO-BEM | Install Concrete car barrier along the walkway in front of MWS building | สหชาติ | 0 | Depot | 2027-01-01 | 2026-10-14 | 100% | Completed |  | MDW-39513 | MDW-69526 | MDW-69527
190 | 0 | Lot02 | MO-BEM6 | MO-BEM | Handrail on top of the water tank on the rooftop of the Admin Building | สหชาติ | 0 | Depot | 2027-01-01 | 2026-10-19 | 100% | Completed | เหลืองานติดตั้งสะพานข้ามคลอง + ประตูรั้ว + Modify Chainlink |  | 0 | 0
191 | 0 | Lot02 | MO-BEM7 | MO-BEM | Modify maintenance service door to the roof building to easier access while maintaining safe operational standards | สหชาติ | 0 | Depot | 2027-01-01 | 2026-10-19 | 50% | Late |  |  | 0 | 0
192 | MDW-39536 | Lot02 | MO-BEM8 | MO-BEM | Company logo and Central Control Room sign in CCR room. | สหชาติ | 0 | Depot | 2026-05-01 | 2026-01-27 | 100% | Completed |  | MDW-39536 | MDW-69572 | MDW-69573
193 | MDW-39536 | Lot02 | MO-BEM9 | MO-BEM | Soundproof insulation on the wall and structure and equipment in the CCR room. | สหชาติ | 0 | Depot | 2026-05-01 | 2026-01-12 | 100% | Completed | TMD เริ่มเข้าทำช่วงเดือน Oct-26 (CIV จบ) | MDW-39536 | MDW-69572 | MDW-69573
194 | MDW-39526 | Lot02 | MO-BEM10 | MO-BEM | Relocate Fire Hose Cabinet to be outside of the clearance gauge zone 17 set | ประธาน | 0 | Depot | 2026-05-01 | 2026-01-12 | 100% | Completed | TMD เริ่มเข้าทำช่วงเดือน Oct-26 (CIV จบ) | MDW-39526 | MDW-69552 | MDW-69553
195 | MDW-39528 | Lot02 | MO-BEM11.1 | MO-BEM | Washing Area in Cleaning Staff Room at Stabling Yard - Civil & AR | สหชาติ | 0 | Depot | 2026-08-03 | 2026-06-03 | 100% | Completed | TMD เริ่มเข้าทำช่วงเดือน Oct-26 (CIV จบ) | MDW-39528 | MDW-69556 | MDW-69557
196 | MDW-39529 | Lot02 | MO-BEM11.2 | MO-BEM | Washing Area in Cleaning Staff Room at Stabling Yard - Building Services | ประธาน | 0 | Depot | 2026-08-04 | 2026-04-14 | 100% | Completed | TMD เริ่มเข้าทำช่วงเดือน Oct-26 (CIV จบ) | MDW-39529 | MDW-69558 | MDW-69559
197 | MDW-39522 | Lot02 | MO-BEM12 | MO-BEM | Rain protection for Water treatment Building | สหชาติ | 0 | Depot | 2026-08-05 | 2026-04-29 | 100% | Completed | TMD เริ่มเข้าทำช่วงเดือน Oct-26 (CIV จบ) | MDW-39522 | MDW-69544 | MDW-69545
198 | MDW-39522 | Lot02 | MO-BEM13.1 | MO-BEM | Zero Discharge Water treatment in Depot - Civil & AR | สหชาติ | 0 | Depot | 2027-01-01 | 2026-08-15 | 100% | Completed | STE เริ่มเข้าทำช่วงเดือน Oct-26 | MDW-39522 | MDW-69544 | MDW-69545
199 | MDW-39530 | Lot02 | MO-BEM13.2 | MO-BEM | Zero Discharge Water treatment in Depot - Building Services | ประธาน | 0 | Depot | 2027-01-01 | 2026-08-15 | 100% | Completed | จัดจ้าง STE | MDW-39530 | MDW-69560 | MDW-69561
200 | MDW-39516 | Lot02 | MO-BEM14.1 | MO-BEM | Modification Works : Walkway Bridge between BL Depot and ORL Depot - Civil & AR | สหชาติ | 0 | Depot | 2026-08-02 | 2026-02-28 | 100% | Completed | อยู่ระหว่างส่งขออนุมัติแบบรอ Approve | MDW-39516 | MDW-69532 | MDW-69533
201 | MDW-39517 | Lot02 | MO-BEM14.2 | MO-BEM | Modification Works : Walkway Bridge between BL Depot and ORL Depot - Building Services | ประธาน | 0 | Depot | 2026-08-03 | 2026-01-14 | 100% | Completed | GRS | MDW-39517 | MDW-69534 | MDW-69535
202 | MDW-39514 | Lot02 | MO-BEM15.1 | MO-BEM | Roof for cars parking lots area (184 car)t - Civil & AR | สหชาติ | 0 | Depot | 2026-08-03 | 2026-02-28 | 100% | Completed | อยู่ระหว่างส่งขออนุมัติแบบรอ Approve | MDW-39514 | MDW-69528 | MDW-69529
203 | MDW-39515 | Lot02 | MO-BEM15.2 | MO-BEM | Roof for cars parking lots area (184 car) - Building Services | ประธาน | 0 | Depot | 2026-08-03 | 2026-02-28 | 100% | Completed |  | MDW-39515 | MDW-69530 | MDW-69531
204 | MDW-39519 | Lot02 | MO-BEM16 | MO-BEM | Walkway roof and High roof across the road from Admin ORL to Depot slap | สหชาติ | 0 | Depot | 2026-08-01 | 2026-06-15 | 100% | Completed |  | MDW-39519 | MDW-69538 | MDW-69539
205 | MDW-39519 | Lot02 | MO-BEM17 | MO-BEM | Walkway roof to car park in front of admin ORL(3x5m.) | สหชาติ | 0 | Depot | 2026-08-01 | 2026-06-15 | 100% | Completed | อยูระหว่างจัดเตรียมแบบ | MDW-39519 | MDW-69538 | MDW-69539
206 | MDW-39519 | Lot02 | MO-BEM18 | MO-BEM | Walkway roof over the footpath near depot slab (1.50 m. x 290 m.) and stair up to depot slap. | สหชาติ | 0 | Depot | 2026-08-01 | 2026-06-15 | 100% | Completed |  | MDW-39519 | MDW-69538 | MDW-69539
207 | MDW-39557 | Lot02 | MO-BEM19 | MO-BEM | Install Chain Link fence to enclose parking area | สหชาติ | 0 | Depot | 2026-10-01 | 2026-06-29 | 100% | Completed |  | MDW-39557 | MDW-69614 | MDW-69615
208 | MDW-39523 | Lot02 | MO-BEM20 | MO-BEM | Hose bib 1/2" 4 sets for Tree around Admin area | ประธาน | 0 | Depot | 2026-06-01 | 2026-04-23 | 100% | Completed | กำลังทำเอกสาร Test Report | MDW-39523 | MDW-69546 | MDW-69547
209 | - | Lot02 | MO-BEM21 | MO-BEM | Relocate Security Guard Box at Front Gate and Install Roof 3x5m. | สหชาติ | 0 | Depot | 2027-01-03 | 2026-07-31 | 100% | Completed |  |  | 0 | 0
210 | MDW-39534 | Lot02 | MO-BEM21.1 | MO-BEM | Modification Works : Security Guard Box at ORL Depot Entrance - Civil & AR | สหชาติ | 0 | Depot | 2027-01-02 | 2026-07-31 | 100% | Completed |  | MDW-39534 | MDW-69568 | MDW-69569
211 | MDW-39535 | Lot02 | MO-BEM21.2 | MO-BEM | Modification Works : Security Guard Box at ORL Depot Entrance - Building Services | ประธาน | 0 | Depot | 2027-01-03 | 2026-07-31 | 100% | Completed |  | MDW-39535 | MDW-69570 | MDW-69571
212 | MDW-39532 | Lot02 | MO-BEM22 | MO-BEM | Addition Spike fence for MRTA fence and Chain link at Klong Chourdyai 400m. | สหชาติ | 0 | Depot | 2027-01-01 | 2026-08-30 | 70% | Late |  | MDW-39532 | MDW-69564 | MDW-69565
213 | MDW-39527 | Lot02 | MO-BEM23 | MO-BEM | Hand sink with eye wash station | ประธาน | พี่ต่อ | Depot | 2027-01-01 | 2026-08-30 | 100% | Completed |  | MDW-39527 | MDW-69554 | MDW-69555
214 | MDW-39531 | Lot02 | MO-BEM24 | MO-BEM | Guard rail protection for Fire Hose Cabinet 8 set | สหชาติ | 0 | Depot | 2026-06-01 | 2026-03-14 | 100% | Completed |  | MDW-39531 | MDW-69562 | MDW-69563
215 | MDW-39557 | Lot02 | MO-BEM25.1 | MO-BEM | Chain Link Fence to divide controlled areas on Depot slab 3 m.x 485 m. - Civil & AR | สหชาติ | 0 | Depot | 2026-10-01 | 2026-06-14 | 100% | Completed |  | MDW-39557 | MDW-69614 | MDW-69615
216 | MDW-39520 | Lot02 | MO-BEM25.2 | MO-BEM | Chain Link Fence to divide controlled areas on Depot slab 3 m.x 485 m.- Building Services | ประธาน | 0 | Depot | 2026-10-01 | 2026-06-14 | 100% | Completed |  | MDW-39520 | MDW-69540 | MDW-69541
217 | MDW-39518 | Lot02 | MO-BEM26 | MO-BEM | Street Lighting system area between MRTA Fence and Depot slab | ประธาน | 0 | Depot | 2026-08-01 | 2026-04-14 | 50% | Late | อยู่ระหว่างจัดเตรียมแบบ งาน Construction จบ Mar-27 | MDW-39518 | MDW-69536 | MDW-69537
218 | - | Lot02 | MO-BEM27 | MO-BEM | Compacted gravel walkway along the Test Track OR-BL 1.2 m. | สหชาติ | พรพรหม | Depot | 2027-01-01 | 2026-08-30 | 100% | Completed |  |  | 0 | 0
219 | MDW-39524 | Lot02 | MO-BEM28.1 | MO-BEM | Walkway under Depot Slab for Maintenance Service - Civil & AR | สหชาติ | 0 | Depot | 2027-01-02 | 2026-09-14 | 100% | Completed |  | MDW-39524 | MDW-69548 | MDW-69549
220 | MDW-39525 | Lot02 | MO-BEM28.2 | MO-BEM | Walkway under Depot Slab for Maintenance Service - Building Services | ประธาน | 0 | Depot | 2027-01-03 | 2026-09-14 | 100% | Completed |  | MDW-39525 | MDW-69550 | MDW-69551
221 | MDW-39521 | Lot02 | MO-BEM29 | MO-BEM | Walkway Bridge across the canal for Depot area inspection patrols 3 location | สหชาติ | 0 | Depot | 2027-01-01 | 2026-08-15 | 100% | Completed |  | MDW-39521 | MDW-69542 | MDW-69543
222 | - | Lot02 | MO-BEM30 | MO-BEM | Cut down trees between Depot BL+ORL and MRTA Fence | สหชาติ | 0 | Depot | 2027-01-01 | 2026-10-29 | 0% | Late | 0 |  | 0 | 0
223 | 0 | Lot02 | MO-BEM31 | MO-BEM | Provide facility system and interface to MMC room (Fire Alarm / CCTV / VMS / TEL / CASS / Radio / PA) | บัณฑิต | 0 | Depot | 2026-10-01 | 0 | 0 | 0 |  |  | 0 | 0
224 | - | Lot02 | MO-BEM32 | MO-BEM | Stainless Guard rail balustrade for waiting area | สหชาติ | 0 | Depot | 2026-05-01 |  |  | 0 |  |  | 0 | 0
225 | - | Lot02 | MO-BEM33 | MO-BEM | Concrete walkway 2 x 80 m. For fire escape route | สหชาติ | 0 | Depot | 2026-05-01 |  |  | 0 |  |  | 0 | 0
226 | - | Lot02 | MO-BEM34 | MO-BEM | Access Gate (Full Height Turnstile) at 1st floor admin ORL | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed |  |  | 0 | 0
227 | - | Lot02 | MO-BEM35 | MO-BEM | Access Gate (Tripod with Swing Gate) at MWS Entrance | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed |  |  | 0 | 0
228 | - | Lot02 | MO-BEM36 | MO-BEM | Access Gate (Tripod with Swing Gate) at Admin 2nd floor connect to OCC | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed |  |  | 0 | 0
229 | - | Lot02 | MO-BEM37 | MO-BEM | Access Gate (Tripod with Swing Gate) on Klong Chourdyai bridge | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed |  |  | 0 | 0
230 | - | Lot02 | MO-BEM38 | MO-BEM | Access Gate (Tripod with roof covering) at parking lot OCC | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed |  |  | 0 | 0
231 | - | Lot02 | MO-BEM39 | MO-BEM | Access Gate (Tripod with roof covering) at Stair up to Depot slab | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed |  |  | 0 | 0
232 | - | Lot02 | MO-BEM40 | MO-BEM | Access Control (2 Factors, Card + Finger Print) at High Security rooms - CCR/PTR/Store | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed |  |  | 0 | 0
233 | - | Lot02 | MO-BEM41 | MO-BEM | Link CCTV Landscape of all depot ORL area for MMC BL monitoring. | บัณฑิต | 0 | 0 | 2027-01-01 | 2026-11-28 | 0% | On Schedule | จัดจ้าง STE |  | 0 | 0
234 | - | Lot02 | MO-BEM42 | MO-BEM | Fire Suppression Control Panel Cover which located in tunnel | สู่โชค | 0 | 0 | 2027-01-01 |  |  | 0 |  |  | 0 | 0
235 | MDW-39537 | Lot02 | MO-BEM43 | MO-BEM | Handrails for ladder at IVS and Vent buildings | สหชาติ | 0 | 0 | 2026-09-01 | 2026-03-31 | 70% | Late | อยู่ระหว่างส่งขออนุมัติแบบรอ Approve | MDW-39537 | MDW-69574 | MDW-69575
236 | MDW-39538 | Lot02 | MO-BEM44 | MO-BEM | Escalator Anti-Slide device for all station. | สหชาติ | 0 | 0 | 2026-09-01 | 2026-05-30 | 100% | Completed |  | MDW-39538 | MDW-69576 | MDW-69577
237 | MDW-39539 | Lot02 | MO-BEM45 | MO-BEM | Roof for control panel on vent building | สหชาติ | 0 | 0 | 2027-01-01 | 2026-09-14 | 70% | Late | อยู่ระหว่างส่งขออนุมัติแบบรอ Approve | MDW-39539 | MDW-69578 | MDW-69579
238 | MDW-39553 | Lot02 | MO-BEM46 | MO-BEM | Provide Standing plate or ladder to access the Fire Valve in at Omega points for all underground stations. | สหชาติ | 0 | Depot | 2027-01-01 | 2026-09-14 | 0% | Late | 0 | MDW-39553 | MDW-69606 | MDW-69607
239 | MDW-39540 | Lot02 | MO-BEM47 | MO-BEM | Water drop protection above UPS cabinet at station and Depot | สหชาติ | 0 | 0 | 2027-01-01 | 2026-09-14 | 0% | Late | 0 | MDW-39540 | MDW-69580 | MDW-69581
240 | MDW-39541 | Lot02 | MO-BEM48 | MO-BEM | Fire alarm manual call point cover in public area at all station | ประธาน | 0 | 0 | 2027-01-01 | 2026-09-14 | 50% | Late | อยูระหว่างจัดเตรียมแบบ | MDW-39541 | MDW-69582 | MDW-69583
241 | MDW-39542 | Lot02 | MO-BEM49 | MO-BEM | Emergency stop button cover for escalator at all station. | สหชาติ | 0 | 0 | 2027-01-01 | 2026-09-14 | 0% | Late | 0 | MDW-39542 | MDW-69584 | MDW-69585
242 | 0 | Lot02 | MO-BEM50 | MO-BEM | Modify maintenance service door to the roof of OR13 vent building to easier access while maintaining safe operational standards | สู่โชค | 0 | Depot | 2027-01-01 | 2026-10-29 | 0% | Late | 0 |  | 0 | 0
243 | MDW-39514 | Lot02 | MO-BEM51 | MO-BEM | Modify existing car park to be 220 motorcycle parking lots including floor painting and parking roof | สหชาติ | 0 | Depot | 2026-08-01 | 2026-01-29 | 100% | Completed |  | MDW-39514 | MDW-69528 | MDW-69529
244 | MDW-39534 | Lot02 | MO-BEM52 | MO-BEM | Modify the sidewalk for temporary parking at entrance | สหชาติ | 0 | Depot | 2027-01-01 | 2026-07-31 | 100% | Completed |  | MDW-39534 | MDW-69568 | MDW-69569
245 | MDW-39554 | Lot02 | MO-BEM53.1 | MO-BEM | Modification Works : Security Guard Box at OCC Parking Area - Civil & AR | สหชาติ | 0 | Depot | 2027-01-02 | 2026-09-14 | 100% | Completed |  | MDW-39554 | MDW-69608 | MDW-69609
246 | MDW-39555 | Lot02 | MO-BEM53.2 | MO-BEM | Modification Works : Security Guard Box at OCC Parking Area - Building Services | ประธาน | 0 | 0 | 2027-01-02 | 2026-09-14 | 100% | Completed |  | MDW-39555 | MDW-69610 | MDW-69611
247 | NoDrawing | Lot02 | MO-BEM54 | MO-BEM | Strengthen the Maintenance Walkway of the TEF fan | สหชาติ | 0 | 0 | 2027-01-01 | 2026-07-16 | 100% | Completed |  |  | 0 | 0
Lot 1 Design
[17 empty] | CK Pesonsible Person | Total | Completed | Late | On Schedule
[17 empty] | สหชาติ | 29 | 23 | 5 | 1
[17 empty] | ประธาน | 37 | 36 | 0 | 1
[17 empty] | สมศักดิ์ | 24 | 22 | 2 | 0
[17 empty] | กำพล | 9 | 8 | 0 | 1
[17 empty] | บัณฑิต | 4 | 3 | 1 | 0
[17 empty] | สู่โชค | 1 | 1 | 0 | 0
[17 empty] | ธัญวิทย์ | 1 | 1 | 0 | 0
[17 empty] | มนตรี | 6 | 5 | 1 | 0
[17 empty] | มนต์ชัย | 1 | 1 | 0 | 0
[17 empty] | - | 2 | 2 | 0 | 0
Lot 2 Design
[17 empty] | CK Pesonsible Person | Total | Completed | Late | On Schedule
[17 empty] | สหชาติ | 61 | 48 | 13 | 0
[17 empty] | ประธาน | 25 | 21 | 3 | 1
[17 empty] | บัณฑิต | 8 | 7 | 0 | 1
[17 empty] | สู่โชค | 1 | 0 | 1 | 0

## Procurement (hidden)
Procedure
No. | Design Submission | Lot No. | Code | System | Activity Name | CK Responsible Person |  | Location | Expected Completion Month | Design (PLAN) | Design (%) | Design (Status) | Procurement (PLAN) | Procurement (%) | Procurement (Status) | Note | Design Submission | Procedure No. | Test Report No.
1 | MDW-39246-60 | Lot01 | GEN1 | GEN | Rooms and Building Service Systems Modification in Stations Area | - | 0 | 0 | 2026-08-01 | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39246 | MDW-69259 | MDW-69260
2 | MDW-39246 | Lot01 | GEN1.1 | GEN | Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR13 - OR17 | ประธาน | 0 | 0 | 2026-08-01 | 2026-01-30 | 100% | Completed | 2026-03-01 | 100% | Completed |  | MDW-39246 | MDW-69259 | MDW-69260
3 | MDW-39247 | Lot01 | GEN1.2 | GEN | Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR18 - OR22 | ประธาน | 0 | 0 | 2026-08-01 | 2025-12-30 | 100% | Completed | 2026-01-29 | 100% | Completed |  | MDW-39247 | MDW-69259 | MDW-69261
4 | MDW-39248 | Lot01 | GEN1.3 | GEN | Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR23 - OR29 | ประธาน | 0 | 0 | 2026-08-01 | 2026-01-30 | 100% | Completed | 2026-03-01 | 100% | Completed |  | MDW-39248 | MDW-69259 | MDW-69262
5 | MDW-39252 | Lot01 | GEN1.4 | GEN | Modification of Fire Suppression System (N2) in Commerial Room at OR14 | ประธาน | 0 | 0 | 2026-08-01 | 2025-12-30 | 100% | Completed | 2026-01-29 | 100% | Completed |  | MDW-39252 | MDW-69269 | MDW-69270
6 | MDW-39253 | Lot01 | GEN1.5 | GEN | Modification of Civil Work in Telecommunication Room at OR14 | สหชาติ | 0 | 0 | 2026-08-01 | 2025-12-30 | 100% | Completed | 2026-01-29 | 100% | Completed |  | MDW-39253 | MDW-69271 | MDW-69272
7 | MDW-39254 | Lot01 | GEN1.6 | GEN | Modification in Staff Mess Room at OR13-OR17 | ประธาน | 0 | 0 | 2026-08-01 | 2026-01-30 | 100% | Completed | 2026-03-01 | 100% | Completed |  | MDW-39254 | MDW-69273 | MDW-69274
8 | MDW-39255 | Lot01 | GEN1.7 | GEN | Modification in Staff Mess Room at OR18-OR22 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed |  | MDW-39255 | MDW-69273 | MDW-69275
9 | MDW-39256 | Lot01 | GEN1.8 | GEN | Modification in Staff Mess Room at OR23-OR29 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed |  | MDW-39256 | MDW-69273 | MDW-69276
10 | MDW-39257 | Lot01 | GEN1.9 | GEN | Modification of Air Conditioning in CER and SER at OR13-OR19 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed |  | MDW-39257 | MDW-69277 | MDW-69278
11 | MDW-39258 | Lot01 | GEN1.10 | GEN | Modification of Air Conditioning in CER and SER at OR20-OR22 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed |  | MDW-39258 | MDW-69277 | MDW-69279
12 | MDW-39259 | Lot01 | GEN1.11 | GEN | Modification of Air Conditioning in CER and SER at OR23-OR29 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed |  | MDW-39259 | MDW-69277 | MDW-69280
13 | MDW-39272 | Lot01 | GEN1.12 | GEN | Modification of New M&E Room at IVS15 - IVS17 Civil & AR | สหชาติ | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed |  | MDW-39272 | MDW-69299 | MDW-69300
14 | MDW-39273 | Lot01 | GEN1.13 | GEN | Modification of New M&E UPS Room at IVS15-IVS17 - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed |  | MDW-39273 | MDW-69301 | MDW-69302
15 | MDW-39294 | Lot01 | GEN1.14 | GEN | Provision of Architectural Work in new M&E UPS room at OR23 | สหชาติ | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed |  | MDW-39294 | MDW-69339 | MDW-69340
16 | MDW-39299 | Lot01 | GEN1.15 | GEN | Provision of Air Conditioning System in Commercial Room at OR13-OR19 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed |  | MDW-39299 | MDW-69349 | MDW-69350
17 | MDW-39306 | Lot01 | GEN1.16 | GEN | Modification CER and First Aid Room at OR14 - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed |  | MDW-39306 | MDW-69363 | MDW-69364
18 | MDW-39307 | Lot01 | GEN1.17 | GEN | Additional Fence at Back of House OR13 - OR22 and IVS East Section | สหชาติ | 0 | 0 | 2026-08-01 | 2026-09-30 | 100% | Completed | 2026-10-31 | 50% | On Schedule | 0 | MDW-39307 | MDW-69365 | MDW-69366
19 | MDW-39249 | Lot01 | GEN1.18 | GEN | SOR Counter and Workstation Hanging Support Installation on East Section | สหชาติ | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed |  | MDW-39249 | MDW-69263 | MDW-69264
20 | MDW-39250 | Lot01 | GEN1.19 | GEN | Ticket Office Modification on East Section | สหชาติ | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed |  | MDW-39250 | MDW-69265 | MDW-69266
21 | MDW-39261 | Lot01 | GEN2 | GEN | Rooms and Building Service Systems Modification in Depot Area | - | 0 | Depot | 2026-08-01 | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39261 | MDW-69283 | MDW-69284
22 | MDW-39260 | Lot01 | GEN2.1 | GEN | Modification of Air Conditioning in M&E Room at OCC Building | ประธาน | 0 | 0 | 2026-08-01 | 2025-12-30 | 100% | Completed | 2026-01-29 | 100% | Completed |  | MDW-39260 | MDW-69281 | MDW-69282
23 | MDW-39261 | Lot01 | GEN2.2 | GEN | Provision of UPS for MDB Control at Main Workshop, OCC Building, Admin Building, Stabling Yard and Train Washing Plant | ประธาน | 0 | 0 | 2026-08-01 | 2026-09-01 | 100% | Completed | 2026-10-01 | 100% | Completed |  | MDW-39261 | MDW-69283 | MDW-69284
24 | MDW-39262 | Lot01 | GEN2.3 | GEN | Provision of Redundant MDB at OCC Building, Admin Building and Canteen | ประธาน | 0 | 0 | 2026-08-01 | 2026-09-01 | 100% | Completed | 2026-10-01 | 100% | Completed |  | MDW-39262 | MDW-69285 | MDW-69286
25 | MDW-39263 | Lot01 | GEN2.4 | GEN | Additonal Lighting System at Depot Area | ประธาน | 0 | 0 | 2026-08-01 | 2026-04-01 | 100% | Completed | 2026-05-01 | 100% | Completed |  | MDW-39263 | MDW-69287 | MDW-69288
26 | MDW-39290 | Lot01 | GEN2.5 | GEN | Modification Room for PSY at Depot Buildings - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed |  | MDW-39290 | MDW-69331 | MDW-69332
27 | MDW-39300 | Lot01 | GEN2.6 | GEN | Modification SIG-PSD Office at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed |  | MDW-39300 | MDW-69351 | MDW-69352
28 | MDW-39301 | Lot01 | GEN2.7 | GEN | Modification Backup CCR Room at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed |  | MDW-39301 | MDW-69353 | MDW-69354
29 | MDW-39302 | Lot01 | GEN2.8 | GEN | Modification SER at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed |  | MDW-39302 | MDW-69355 | MDW-69356
30 | MDW-39303 | Lot01 | GEN2.9 | GEN | Modification CER & SCADA Room at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed |  | MDW-39303 | MDW-69357 | MDW-69358
31 | MDW-39309 | Lot01 | GEN2.10 | GEN | Modification Air Conditioning System at CCR | ประธาน | 0 | 0 | 2026-08-01 | 2026-10-01 | 100% | Completed | 2026-10-31 | 100% | Completed |  | MDW-39309 | MDW-69369 | MDW-69370
32 | MDW-39312 | Lot01 | GEN2.11 | GEN | Modification Electronic Workshop at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-10-31 | 100% | Completed | 2026-11-30 | 100% | Completed |  | MDW-39312 | MDW-69375 | MDW-69376
33 | MDW-39313 | Lot01 | GEN2.12 | GEN | Modification Battery Charger Room at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-10-31 | 100% | Completed | 2026-11-30 | 100% | Completed |  | MDW-39313 | MDW-69377 | MDW-69378
34 | MDW-39314 | Lot01 | GEN2.13 | GEN | Modification Machining Room at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-10-31 | 90% | On Schedule | 2026-11-30 | 0% | On Schedule | 0 | MDW-39314 | MDW-69379 | MDW-69380
35 | MDW-39315 | Lot01 | GEN2.14 | GEN | Modification Electronic Workshop, Battery Charger and Machining Room at Main Workshop - Civil & AR | สหชาติ | 0 | 0 | 2026-08-01 | 2026-10-31 | 70% | On Schedule | 2026-11-30 | 90% | On Schedule | 0 | MDW-39315 | MDW-69383 | MDW-69384
36 | MDW-39297 | Lot01 | GEN2.15 | GEN | Training Room at Ratchada Station (Part 2) | สหชาติ | 0 | 0 | 2026-08-01 | 2026-08-01 | 0% | Late | 2026-08-31 | 100% | Completed |  | MDW-39297 | MDW-69345 | MDW-69346
37 | MDW-39291 | Lot01 | GEN2.16 | GEN | Conductor Rail Arrangement Modification at Main Line East Section | กำพล | 0 | 0 | 2026-08-01 | 2026-09-30 | 100% | Completed | 2026-09-30 | 100% | Completed |  | MDW-39291 | MDW-69333 | MDW-69334
38 | MDW-39292 | Lot01 | GEN2.17 | GEN | Conductor Rail Arrangement Modification at Depot | กำพล | 0 | 0 | 2026-08-01 | 2026-09-30 | 100% | Completed | 2026-09-30 | 100% | Completed |  | MDW-39292 | MDW-69335 | MDW-69336
39 | MDW-39295 | Lot01 | GEN2.18 | GEN | Dangerous Goods Building in Depot - Civil & AR | สหชาติ | 0 | 0 | 2026-08-01 | 2026-01-27 | 100% | Completed | 2026-02-27 | 100% | Completed |  | MDW-39295 | MDW-69341 | MDW-69342
40 | MDW-39296 | Lot01 | GEN2.19 | GEN | Dangerous Goods Building in Depot - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2025-12-13 | 100% | Completed | 2026-01-28 | 100% | Completed |  | MDW-39296 | MDW-69343 | MDW-69344
41 | MDW-39308 | Lot01 | GEN2.20 | GEN | Additional Locking Devices for Main Line Tandem Turnouts 2007, 2010 & 2013 and Depot Turnout D16 | กำพล | 0 | 0 | 2026-08-01 | 2026-11-30 | 50% | On Schedule | 2026-09-30 | 100% | Completed |  | MDW-39308 | MDW-69367 | MDW-69368
42 | MDW-39200-31 | Lot01 | GEN3 | GEN | Cable Containment Modification | - | 0 | 0 | 2025-05-28 | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39200
43 | - | Lot01 | GEN4 | GEN | Training Room and Workshop Room | - | 0 | 0 | 2026-04-01 | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
44 | MDW-39242 | Lot01 | GEN4.0 | GEN | Modification Works for Training Room at Ratchada Station | ประธาน | 0 | 0 | 2026-04-01 | 2025-12-30 | 100% | Completed | 2026-01-31 | 100% | Completed |  | MDW-39242 | MDW-69251 | MDW-69252
45 | MDW-39244 | Lot01 | GEN4.1 | GEN | AFC Training Room Modification - Civil & AR | สหชาติ | 0 | 0 | 2026-08-21 | 2026-09-30 | 10% | Late | 2026-10-15 | 100% | Completed |  | MDW-39244 | MDW-69255 | MDW-69256
46 | MDW-39245 | Lot01 | GEN4.2 | GEN | AFC Training Room Modification - Building Services | ประธาน | 0 | 0 | 2026-08-21 | 2025-12-30 | 100% | Completed | 2026-01-31 | 100% | Completed |  | MDW-39245 | MDW-69257 | MDW-69258
47 | MDW-39235 | Lot01 | GEN5 | GEN | Raised Floor | สหชาติ | 0 | 0 | 2026-06-01 | 2025-05-15 | 100% | Completed | 2024-12-14 | 100% | Completed |  | MDW-39235 | MDW-69237 | MDW-69238
48 | MDW-39271 | Lot01 | GEN6 | GEN | Wayside Cable Containment in Depot | - | 0 | Depot | 2026-02-22 | 2025-05-15 | 100% | Completed | 2024-12-14 | 100% | Completed |  | MDW-39271 | MDW-69297 | MDW-69298
49 | MDW-39269 | Lot01 | GEN6.1 | GEN | PSY Wayside Cable Containment for 24 Kv Cable under the Depot slab | ประธาน | 0 | Depot | 2026-02-22 | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39269 | MDW-69293 | MDW-69294
50 | MDW-39270 | Lot01 | GEN6.2 | GEN | COM/SIG Wayside Cable Containment in the Depot | มนตรี/ประธาน | 0 | Depot | 2026-02-22 | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39270 | MDW-69295 | MDW-69296
51 | - | Lot01 | GEN7 | GEN | Dangerous Waste Storage Building in Depot | - | 0 | Depot | 2026-09-20 | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
52 | DWE-39024 | Lot01 | GEN7.1 | GEN | Dangerous Waste Storage Building in Depot - Civil & AR | สหชาติ | 0 | Depot | 2026-09-20 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed |  | DWE-39024 | DWE-69024 | DWE-69124
53 | DWE-39025 | Lot01 | GEN7.2 | GEN | Dangerous Waste Storage Building in Depot - Building service | ประธาน | 0 | Depot | 2026-09-20 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed |  | DWE-39025 | DWE-69025 | DWE-69125
54 | - | Lot01 | GEN8 | GEN | General Waste Storage Building in Depot | - | 0 | Depot | 2026-09-20 | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
55 | DWE-39026 | Lot01 | GEN8.1 | GEN | General Waste Storage Building in Depot - Civil & AR | สหชาติ | 0 | Depot | 2026-09-20 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed |  | DWE-39026 | DWE-69026 | DWE-69126
56 | DWE-39025 | Lot01 | GEN8.2 | GEN | General Waste Storage Building in Depot - Building service | ประธาน | 0 | Depot | 2026-09-20 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed |  | DWE-39025 | DWE-69025 | DWE-69125
57 | DWE-39021 | Lot01 | GEN9 | GEN | Operation Support Equipment | สมศักดิ์ | 0 | Depot | 2026-08-21 | 2025-03-02 | 100% | Completed | 2025-11-02 | 100% | Completed |  | DWE-39021 | DWE-69021 | DWE-69121
58 | GRS-39001-40 | Lot01 | GEN10.1 | GEN | Graphic and Signage Station | สหชาติ | 0 | 0 | 2026-08-21 | 2026-06-30 | 100% | Completed | 2026-05-31 | 95% | Late | GRS | GRS-39001 | GRS-69001 | GRS-69002
59 | GRS-39001-40 | Lot01 | GEN10.2 | GEN | Graphic and Signage Mainline & IVS,VS | สหชาติ | 0 | 0 | 2026-08-21 | 2026-06-15 | 79% | Late | 2026-05-31 | 95% | Late | GRS | GRS-39001 | GRS-69001 | GRS-69002
60 | GRS-39001-40 | Lot01 | GEN10.3 | GEN | Graphic and Signage Depot | สหชาติ | 0 | 0 | 2026-08-21 | 2026-08-15 | 90% | Late | 2026-07-31 | 93% | Late | GRS | GRS-39001 | GRS-69001 | GRS-69002
61 | MDW-39289 | Lot01 | GEN11 | GEN | Earthing and Bonding Modification | ประธาน | 0 | 0 | 2026-03-01 | 2025-01-31 | 100% | Completed | 2025-09-30 | 100% | Completed |  | MDW-39289 | MDW-69329 | MDW-69330
62 | - | Lot01 | GEN12 | GEN | Mainline Cable Trough Modification on East Section | - | 0 | 0 | 2026-06-22 | 2025-10-31 | 100% | Completed | 2025-11-30 | 100% | Completed |  |  | 0 | 0
63 | MDW-39233 | Lot01 | GEN12.1 | GEN | Main Line Cable Trough Modification (PSY) | มนต์ชัย | 0 | Depot | 2026-06-22 | 2025-10-31 | 100% | Completed | 2025-11-30 | 100% | Completed |  | MDW-39233
64 | MDW-39234 | Lot01 | GEN12.2 | GEN | Main Line Cable Trough Modification (SIG/COM) | มนตรี | 0 | 0 | 2026-06-22 | 2025-10-31 | 100% | Completed | 2025-11-30 | 100% | Completed |  | MDW-39234 | MDW-69234 | MDW-69236
65 | MDW-39236 | Lot01 | GEN13 | GEN | Bird Protection System | สหชาติ | 0 | 0 | 2026-11-19 | 2025-06-30 | 100% | Completed | 2025-09-30 | 100% | Completed |  | MDW-39236 | MDW-69239 | MDW-69240
66 | - | Lot01 | GEN14 | GEN | Train Crew Office at Thailand Cultural Centre Station | สหชาติ | 0 | 0 | 2026-08-21 | 2025-09-30 | 100% | Completed | 2026-02-27 | 100% | Completed |  |  | 0 | 0
67 | MDW-39240 | Lot01 | GEN14.1 | GEN | Driver Train Simulation Room and Train Crew Office at OR18 - Civil & AR | สหชาติ | 0 | Depot | 2026-08-21 | 2025-09-30 | 100% | Completed | 2026-02-28 | 100% | Completed |  | MDW-39240 | MDW-69247 | MDW-69248
68 | MDW-39241 | Lot01 | GEN14.2 | GEN | Driver Train Simulation Room and Train Crew Office at OR18 - Building Services | ประธาน | 0 | 0 | 2026-08-21 | 2025-09-30 | 100% | Completed | 2026-02-28 | 100% | Completed |  | MDW-39241 | MDW-69249 | MDW-69250
69 | MDW-39239 | Lot01 | GEN15 | GEN | Access Panel Closeout for Traction Substation Room in Main Workshop | สหชาติ | 0 | 0 | 2026-03-24 | 2026-01-30 | 100% | Completed | 2026-03-01 | 100% | Completed |  | MDW-39239 | MDW-69245 | MDW-69246
70 | MDW-39232 | Lot01 | GEN16 | GEN | Level Crossing at Turnout | กำพล | 0 | 0 | 2026-08-21 | 2026-09-30 | 100% | Completed | 2026-09-30 | 100% | Completed |  | MDW-39232 | MDW-69232 | MDW-69233
71 | MDW-39232 | Lot01 | GEN17 | GEN | Track Slab Crossing | ชฎิล/กำพล | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39232 | MDW-69232 | MDW-69233
72 | MDW-39243 | Lot01 | GEN18 | GEN | Eye Adaptation Lighting (Lighting at Tunnel to Expose) | ประธาน | 0 | 0 | 2026-11-19 | 2025-09-30 | 100% | Completed | 2025-10-30 | 100% | Completed |  | MDW-39243 | MDW-69253 | MDW-69254
73 | - | Lot01 | GEN19 | GEN | Train Simulation Room and AFC Training Room | - | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
74 | MDW-39244 | Lot01 | GEN19.1 | GEN | Modification AFC Training Center at OR19 - Civil & AR | สหชาติ | 0 | 0 | 2026-11-30 | 2026-09-30 | 100% | Completed | 2026-10-31 | 58% | On Schedule | Progress Cut&Cover OR22 : 95% | MDW-39244 | MDW-69255 | MDW-69256
75 | MDW-39245 | Lot01 | GEN19.2 | GEN | Modification AFC Training Center at OR19 - Building Services | ประธาน | บัณฑิต | 0 | 2026-11-30 | 2026-09-30 | 100% | Completed | 2026-10-31 | 100% | Completed |  | MDW-39245 | MDW-69257 | MDW-69258
76 | - | Lot01 | GEN20 | GEN | Dormitory Cable Containments (if any) | - | 0 | 0 | - | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
77 |  | Lot01 | GEN21 | GEN | Project Information Management System (PIMS) | บัณฑิต | 0 | 0 | 2024-09-30 | 2024-08-10 | 100% | Completed | 2024-08-15 | 100% | Completed
78 | MDW-39237 | Lot01 | GEN22 | GEN | Central BEMS for the MRT Orange Line System | บัณฑิต | 0 | 0 | 2026-08-21 | 2026-04-30 | 0% | Late | 2026-06-30 | 0% | Late | PPR Oct-26 กำลังเปรียบเทียบ Spec | MDW-39237 | MDW-69241 | MDW-69242
79 |  | Lot01 | GEN23 | GEN | Asset Information | บัณฑิต | 0 | 0 | 2026-11-19 | 0 | 0% | 0% | 2026-08-30 | 100% | Completed
80 | MDW-39282 | Lot01 | PSD1 | PSD | Holes for PSD Cable Wiring | กำพล | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39282 | MDW-69315 | MDW-69316
81 | MDW-39004 | Lot01 | PSD2 | PSD | Rubber Gap Fillers on Platform Edge | กำพล | 0 | 0 | 2026-08-21 | 2025-07-30 | 100% | Completed | 2026-01-31 | 100% | Completed |  | MDW-39004 | MDW-69007 | MDW-69008
82 | MDW-39280 | Lot01 | PSD3 | PSD | Platform Finishing | กำพล | 0 | 0 | 2026-08-21 | 2025-07-30 | 100% | Completed | 2025-09-16 | 100% | Completed |  | MDW-39280 | MDW-69311 | MDW-69312
83 | MDW-39281 | Lot01 | PSD4 | PSD | Cladding Barrier between EWD and Station Structure | กำพล | 0 | 0 | 2026-08-21 | 2026-02-28 | 100% | Completed | 2026-03-15 | 100% | Completed |  | MDW-39281 | MDW-69313 | MDW-69314
84 | - | Lot01 | AFC1 | AFC | Park and Ride System | บัณฑิต/สหชาติ | 0 | 0 | 2026-10-20 | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
85 | MDW-39276 | Lot01 | AFC2 | AFC | Ticket Issuing Machine (TIM) Wall Opening and Closing | สหชาติ | 0 | 0 | 2026-09-20 | 2026-01-30 | 100% | Completed | 2026-03-15 | 50% | Late | มีแก้ไขตำแหน่ง OR14,17,18,23 | MDW-39276 | MDW-69303 | MDW-69304
86 | MDW-39279 | Lot01 | AFC3 | AFC | Balustrade Modification Along AFC Gate Line | สหชาติ | 0 | 0 | 2026-09-20 | 2026-06-30 | 10% | Late | 2026-08-15 | 50% | Late | จัดเตรียมแบบ ออกPPR Oct-26 | MDW-39279 | MDW-69309 | MDW-69310
87 | MDW-39278 | Lot01 | AFC4 | AFC | Underfloor Embedded Duct Modification for AFC Gates Line | สหชาติ | 0 | Depot | 2026-09-20 | 2026-01-30 | 100% | Completed | 2026-04-02 | 67% | Late | 0 | MDW-39278 | MDW-69307 | MDW-69308
88 | MDW-39002 | Lot01 | SIG1 | SIG | Test Track Shelters and Test Track Building | สหชาติ | 0 | 0 | 2026-06-22 | 2025-11-22 | 100% | Completed | 2026-01-18 | 100% | Completed |  | MDW-39002 | MDW-69003 | MDW-69004
89 | MDW-39293 | Lot01 | SIG2 | SIG | Rearrangement of track crossing walkway at stabling yard to consistent with the layout of 4-car train parking | กำพล | 0 | Depot | 2026-06-22 | 2025-11-30 | 100% | Completed | 2025-12-30 | 100% | Completed |  | MDW-39293 | MDW-69337 | MDW-69338
90 | MDW-39288 | Lot01 | SIG3 | SIG | Point Machine Foundation Construction | กำพล | 0 | 0 | 2026-08-21 | 2025-11-21 | 100% | Completed | 2025-12-30 | 100% | Completed |  | MDW-39288 | MDW-69327 | MDW-69328
91 | MDW-39001 | Lot01 | SIG4 | SIG | Modification of Depot Track Route Line to Stabling Yard | สู่โชค | 0 | Depot | 2026-06-22 | 2025-10-30 | 100% | Completed | 2025-11-29 | 100% | Completed |  | MDW-39001 | MDW-69001 | MDW-69002
92 | MDW-39287 | Lot01 | SIG5 | SIG | Strobe Light at Buffer Stops | ประธาน | 0 | Depot | 2026-08-21 | 2026-05-30 | 100% | Completed | 2026-06-29 | 100% | Completed |  | MDW-39287 | MDW-69323 | MDW-69324
93 | DWE-39016 | Lot01 | DWE1 | DWE | Diesel Fuel Storage Tank for Maintenance Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-01-16 | 100% | Completed |  | DWE-39016 | DWE-69016 | DWE-69116
94 | DWE-39011 | Lot01 | DWE2 | DWE | Movable Height Maintenance Platform Vehicle (Boom Lift) | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-08-06 | 100% | Completed |  | DWE-39011 | DWE-69011 | DWE-69111
95 | DWE-39012 | Lot01 | DWE3 | DWE | Fork Lift Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-03-31 | 100% | Completed |  | DWE-39012 | DWE-69012 | DWE-69112
96 | DWE-39015 | Lot01 | DWE4 | DWE | Compressed Air System and Portable Air Compressor for Depot | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-01-10 | 100% | Completed |  | DWE-39015 | DWE-69015 | DWE-69115
97 | DWE-39017 | Lot01 | DWE5 | DWE | Pallet Storage Shelves in Hazardous Storage | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-12-16 | 100% | Completed |  | DWE-39017 | DWE-69017 | DWE-69117
98 | DWE-39017 | Lot01 | DWE6 | DWE | Pallet Storage in Main Storage Room | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-12-16 | 100% | Completed |  | DWE-39017 | DWE-69017 | DWE-69117
99 | DWE-39017 | Lot01 | DWE7 | DWE | Two-Tier Shelf | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-12-16 | 100% | Completed |  | DWE-39017 | DWE-69017 | DWE-69117
100 | DWE-39017 | Lot01 | DWE8 | DWE | Tool Storage | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-12-16 | 100% | Completed |  | DWE-39017 | DWE-69017 | DWE-69117
101 | DWE-39018 | Lot01 | DWE9 | DWE | Repair Equipment | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-07-31 | 50% | Late | คงเหลือจัดส่งอุปกรณ์ | DWE-39018 | DWE-69018 | DWE-69118
102 | DWE-39020 | Lot01 | DWE10 | DWE | Oil & Grease Disposal | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-01-16 | 100% | Completed |  | DWE-39020 | DWE-69020 | DWE-69120
103 | DWE-39020 | Lot01 | DWE11 | DWE | Grease Dispensers | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-01-16 | 100% | Completed |  | DWE-39020 | DWE-69020 | DWE-69120
104 | DWE-39020 | Lot01 | DWE12 | DWE | Waste Disposal | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-01-16 | 100% | Completed |  | DWE-39020 | DWE-69020 | DWE-69120
105 | MDW-39305 | Lot01 | DWE13 | DWE | Safety Provision for Maintenance Pits | สหชาติ | 0 | Depot | 2026-09-20 | 2025-11-30 | 100% | Completed | 2026-04-29 | 100% | Completed |  | MDW-39305 | MDW-69361 | MDW-69362
106 | DWE-39xxx | Lot01 | DWE14 | DWE | Pit Drainage System in Main Workshop | สมศักดิ์ | 0 | Depot | 2026-09-20 | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39xxx | MDW-69361 | MDW-69362
107 | DWE-39023 | Lot01 | DWE15 | DWE | Provision of Civil Works and Building Services to support Train Washing Equipment | สหชาติ | 0 | Depot | 2026-08-01 | 2025-11-30 | 100% | Completed | 2026-03-31 | 100% | Completed |  | DWE-39023 | DWE-69023 | DWE-69123
108 | DWE-39013 | Lot01 | DWE16 | DWE | Overhead Traveling Crane | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-04-30 | 100% | Completed |  | DWE-39013 | DWE-69013 | DWE-69113-513
109 | DWE-39009 | Lot01 | DWE17 | DWE | Vehicle Inspection and Servicing Facilities | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-12-18 | 100% | Completed |  | DWE-39009 | DWE-69009 | DWE-69109
110 | DWE-39014 | Lot01 | DWE18 | DWE | Permanent Way Maintenance Facility | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-04-30 | 100% | Completed | 2027-02-28 | 100% | Completed |  | DWE-39014 | DWE-69014 | DWE-69114
111 | - | Lot01 | DWE19 | DWE | Permanent Way Vehicles | สมศักดิ์ | 0 | Depot | 2026-09-20 | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
112 | DWE-39001 | Lot01 | DWE19.1 | DWE | Shunting Locomotive | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-12-18 | 100% | Completed |  | DWE-39001 | DWE-69001 | DWE-69101
113 | DWE-39002 | Lot01 | DWE19.2 | DWE | Tunnel Inspection and Cleaning Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 0% | Late | 2025-12-18 | 100% | Completed |  | DWE-39002 | DWE-69002 | DWE-69102
114 | DWE-39003 | Lot01 | DWE19.3 | DWE | Hi/Rail Maintenance Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-12-18 | 100% | Completed |  | DWE-39003 | DWE-69003 | DWE-69103
115 | DWE-39004 | Lot01 | DWE19.4 | DWE | Flat wagon | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-12-18 | 100% | Completed |  | DWE-39004 | DWE-69004 | DWE-69104
116 | DWE-39005 | Lot01 | DWE19.5 | DWE | Re-railing Equipment | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-11-10 | 100% | Completed |  | DWE-39005 | DWE-69005 | DWE-69105
117 | DWE-39006 | Lot01 | DWE19.6 | DWE | Self-Propelled Rail Based Inspection Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-12-18 | 100% | Completed |  | DWE-39006 | DWE-69006 | DWE-69106
118 | DWE-39007 | Lot01 | DWE19.7 | DWE | Rail Head Grinding Machine Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 0% | Late | 2025-12-18 | 100% | Completed |  | DWE-39007 | DWE-69007 | DWE-69107
119 | DWE-39008 | Lot01 | DWE19.8 | DWE | Multi Measuring Rail Vehicle | สมศักดิ์ | 0 | 0 | 2026-09-20 | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39008 | DWE-69008 | DWE-69108
120 | DWE-39010 | Lot01 | DWE19.9 | DWE | High Work Inspection Vehicle | สมศักดิ์ | 0 | 0 | 2026-09-20 | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39010
121 | - | Lot01 | DWE20 | DWE | Building Maintenance Vehicle | - | 0 | 0 | 2026-09-20 | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
122 | EPS-39001 | Lot01 | PSY1 | PSY | Diesel Fuel Storage Tanks for Power Generators | สมศักดิ์ | 0 | 0 | 2026-03-24 | 2026-01-16 | 100% | Completed | 2026-03-31 | 100% | Completed |  | EPS-39001 | EPS-69001 | EPS-69002
123 | PSY-39001-9 | Lot01 | PSY2 | PSY | GIS and BSS Building and Other Facilities | สหชาติ | 0 | 0 | 2026-03-24 | 2024-08-29 | 100% | Completed | 2024-09-28 | 69% | Late | 0 | PSY-39001 | PSY-69001 | PSY-69002
124 | PSY-39011 | Lot01 | PSY3 | PSY | Steel Grating Raised Floor for EE Panel | สหชาติ | 0 | 0 | 2026-03-24 | 2024-09-30 | 100% | Completed | 2024-10-30 | 75% | Late | 0 | PSY-39011 | PSY-69015 | PSY-69016
125 | - | Lot01 | PSY4 | PSY | Trapping Box between PSY Service Sub Station (SSS) and Low Volt (LV) System | - | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
126 | SCA-39200 | Lot01 | SCA1 | SCA | Modification of BEMS to receive PSD Signal on East Section | ธารทิพย์ | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0 | 0 |  | SCA-39200 | SCA-69200 | SCA-69201
127 | - | Lot01 | SCA2 | SCA | Modification of Escalator Interface Point with CCTV and SCADA, East Section | - | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
128 | - | Lot01 | SCA3 | SCA | Magnetic of Fire Alarm System Interface Point with CCTV and SCADA | - | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
129 | SCA-39203 | Lot01 | SCA4 | SCA | Add/Modify Civil Scada Hardwire for all Station | ประธาน/ธารทิพย์ | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0 | 0 |  | SCA-39203 | SCA-69206 | SCA-69207
130 | COM-39200 | Lot01 | COM1 | COM | Magnetic Door Lock | มนตรี | 0 | 0 | 2026-08-21 | 2025-06-30 | 100% | Completed | 2026-05-15 | 100% | Completed |  | COM-39200 | COM-69200 | COM-69201
131 | MDW-39283 | Lot01 | COM2 | COM | Intercom System in Cash Handling Room (if require) | บัณฑิต | 0 | 0 | 2026-12-19 | 2025-09-30 | 100% | Completed | 2026-06-30 | 50% | Late | รอพื้นที่เข้าติดตั้ง | MDW-39283 | MDW-69317 | MDW-69318
132 | COM-39001 | Lot01 | COM3 | COM | Walk-Through Metal Detector System (WTMD), 1 per entrance | มนตรี | 0 | 0 | 2026-11-19 | 2025-08-31 | 0% | Late | 2026-06-30 | 0% | Late | รอออก PPR อยู่ระหว่างการตรวจสอบสินค้า | COM-39001 | COM-69001 | COM-69002
133 | MDW-39284 | Lot01 | COM4 | COM | Traveling Cable in all Lifts | มนตรี | 0 | 0 | - | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39284 | MDW-69319 | MDW-69320
134 | MDW-39304 | Lot01 | COM5 | COM | MEA Radio | ประธาน | 0 | 0 | 2026-09-20 | 2026-01-30 | 100% | Completed | 2026-04-30 | 100% | Completed |  | MDW-39304 | COM-69202 | COM-69203
135 | COM-39004 | Lot01 | COM6 | COM | Main Cable Containment for M&E Dedicated communication link to MRTA Head Quarter | มนตรี | 0 | 0 | 2026-09-20 | 2026-01-31 | 100% | Completed | 2026-02-28 | 100% | Completed |  | COM-39004 | COM-69005 | COM-69006
136 | AFC-39001 | Lot01 | COM7 | COM | Mini Paging in Ticket Office | บัณฑิต | 0 | 0 | 2026-12-19 | 2025-09-10 | 100% | Completed | 2026-06-30 | 100% | Completed |  | AFC-39002 | AFC-69003 | AFC-69004
137 | MDW-39285 | Lot01 | COM8 | COM | Provision of Cable Containment between OCC ORL and OCC BL | มนตรี | 0 | 0 | 2026-07-22 | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39285
138 | COM-39005 | Lot01 | COM9 | COM | Power Distribution for M&E Systems at MRTA Head Quarter | มนตรี | 0 | 0 | 2026-09-20 | 2026-03-31 | 100% | Completed | 2026-06-30 | 100% | Completed |  | COM-39005 | COM-69007 | COM-69008
139 | COM-39205 | Lot01 | COM10 | COM | Underground Cable Containment at Public Areas (if require) | มนตรี | 0 | 0 | 2026-08-21 | 2026-04-30 | 100% | Completed | 2026-07-31 | 100% | Completed |  | MDW-39205 | MDW-69200 | MDW-69205
140 | - | Lot01 | COM11 | COM | Intercom at Ticket Issuing Machine | บัณฑิต | 0 | Depot | - | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
141 | RST-39004,8 | Lot01 | RST1 | RST | Driver Training Simulator | ธัญวิทย์ | 0 | Depot | 2026-09-20 | 2025-05-30 | 100% | Completed | 2025-06-30 | 100% | Completed |  | RST-39004,8
142 | MDW-39500 | Lot02 | MO-CK1.1 | MO-CK | Store Modification Works at Main Workshop - Civil&AR | สหชาติ | 0 | Depot | 2026-06-03 | 2026-02-27 | 100% | Completed | 2026-03-30 | 100% | Completed |  | MDW-39500 | MDW-69500 | MDW-69501
143 | MDW-39501 | Lot02 | MO-CK1.2 | MO-CK | Store Modification Works at Main Workshop - Building Services | ประธาน | 0 | Depot | 2026-06-04 | 2026-02-12 | 100% | Completed | 2026-03-30 | 100% | Completed |  | MDW-39501 | MDW-69502 | MDW-69503
144 | MDW-39503 | Lot02 | MO-CK2 | MO-CK | New MMC at Admin Building - Civil&AR | สหชาติ | 0 | Depot | 2026-08-03 | 2026-04-14 | 100% | Completed | 2026-05-15 | 100% | Completed |  | MDW-39503 | MDW-69506 | MDW-69507
145 | MDW-39504 | Lot02 | MO-CK3 | MO-CK | Move or link Workstation and control panel to MMC room at admin C 2nd floor | ประธาน | 0 | Depot | 2026-08-02 | 2026-02-28 | 100% | Completed | 2026-04-15 | 100% | Completed |  | MDW-39504 | MDW-69508 | MDW-69509
146 | MDW-39543 | Lot02 | MO-CK4 | MO-CK | Bird & Rain Protection for Open space Admin C | สหชาติ | 0 | Depot | 2026-08-01 | 2026-04-29 | 100% | Completed | 2026-05-30 | 100% | Completed |  | MDW-39543 | MDW-69586 | MDW-69587
147 | MDW-39547 | Lot02 | MO-CK5 | MO-CK | Relocate door in front of toilet and build partition wall to conceal the view in side of toilet | สหชาติ | 0 | Depot | 2026-08-02 | 2026-05-14 | 100% | Completed | 2026-06-14 | 100% | Completed |  | MDW-39547 | MDW-69594 | MDW-69595
148 | MDW-39547 | Lot02 | MO-CK6 | MO-CK | Modify Lockset the emergency door to be used for passage between the 2nd and 3rd floors inside the building. | สหชาติ | 0 | Depot | 2026-08-03 | 2026-04-29 | 100% | Completed | 2026-06-14 | 100% | Completed |  | MDW-39547 | MDW-69594 | MDW-69595
149 | MDW-39556 | Lot02 | MO-CK7 | MO-CK | Addition small power for lounge and pantry room at 2nd floor and Hall and observation room at 3nd floor | ประธาน | 0 | Depot | 2026-08-04 | 2026-05-14 | 100% | Completed | 2026-06-14 | 100% | Completed |  | MDW-39556 | MDW-69612 | MDW-69613
150 | MDW-39548 | Lot02 | MO-CK8 | MO-CK | Air Condition for using store room to be pantry room. 2nd floor | ประธาน | 0 | Depot | 2026-08-05 | 2026-04-29 | 100% | Completed | 2026-06-14 | 100% | Completed |  | MDW-39548 | MDW-69596 | MDW-69597
151 | MDW-39552 | Lot02 | MO-CK9 | MO-CK | Walk Way Hand rail high 90 cm 1 side (144 m. x 7 route) | สหชาติ | 0 | Depot | 2026-10-01 | 2026-05-30 | 100% | Completed | 2026-06-30 | 100% | Completed |  | MDW-39552 | MDW-69604 | MDW-69605
152 | MDW-39544 | Lot02 | MO-CK10 | MO-CK | Barbed wire fence Viaduct CE CW | บัณฑิต/สหชาติ | พี่ต่อ | Depot | 2027-01-01 | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39544 | MDW-69588 | MDW-69589
153 | MDW-39545 | Lot02 | MO-CK11 | MO-CK | Chain Link at Cut & Cover 600m. | สหชาติ | พรพรหม | Depot | 2026-06-01 | 2026-02-27 | 100% | Completed | 2026-04-30 | 100% | Completed |  | MDW-39545 | MDW-69590 | MDW-69591
154 | MDW-39546 | Lot02 | MO-CK12 | MO-CK | Chain Link under slab high 1.70 m | สหชาติ | 0 | 0 | 2027-01-01 | 2026-06-30 | 100% | Completed | 2026-07-31 | 100% | Completed |  | MDW-39546 | MDW-69592 | MDW-69593
155 | MDW-39550 | Lot02 | MO-CK13.1 | MO-CK | Satellite Store at OR21 - Civil & AR | สหชาติ | 0 | 0 | 2027-01-02 | 2026-08-30 | 100% | Completed | 2026-10-15 | 0% | Late | 0 | MDW-39550 | MDW-69600 | MDW-695601
156 | MDW-39549 | Lot02 | MO-CK13.2 | MO-CK | Maintenance Room and Satellite Store at Stations - Building Services | ประธาน | 0 | 0 | 2027-01-03 | 2026-08-30 | 100% | Completed | 2026-10-15 | 100% | Completed |  | MDW-39549 | MDW-69598 | MDW-69599
157 | MDW-39551 | Lot02 | MO-CK14 | MO-CK | Modify Cleaner room at OR29 to be Train crew Standby office with facility system | ประธาน | 0 | Depot | 2026-07-01 | 2026-03-14 | 100% | Completed | 2026-04-29 | 100% | Completed |  | MDW-39551 | MDW-69602 | MDW-69603
158 | MDW-39295 | Lot02 | MO-CK15.1 | MO-CK | Epoxy Floor Installation and Curb Installation at the Entrance - Civil & AR | สหชาติ | 0 | Depot | 2026-05-01 | 2026-01-27 | 100% | Completed | 2026-02-27 | 100% | Completed |  | MDW-39295 | MDW-69341 | MDW-69342
159 | MDW-39296 | Lot02 | MO-CK15.2 | MO-CK | Change Electrical Equipment to be Explosion-proof type - Building Services | ประธาน | 0 | Depot | 2026-05-01 | 2025-12-13 | 100% | Completed | 2026-01-28 | 100% | Completed |  | MDW-39296 | MDW-69343 | MDW-69344
160 | DWE-39024 | Lot02 | MO-CK16 | MO-CK | Dangerous waste Storage 30 x 5 m. =10 room | สหชาติ | 0 | Depot | 2026-05-01 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed |  | DWE-39024 | DWE-69024 | DWE-69124
161 | 0 | Lot02 | MO-CK17 | MO-CK | Safety Sign all Depot Area building | สหชาติ | 0 | Depot | 2026-05-01 | 2025-11-28 | 100% | Completed | 2026-06-15 | 100% | Completed |  |  | 0 | 0
162 | 0 | Lot02 | MO-CK18 | MO-CK | Emergency escape route map | สหชาติ | 0 | Depot | 2027-01-01 | 2026-09-30 | 0% | Late | 2026-10-30 | 50% | On Schedule | GRS |  | 0 | 0
163 | 0 | Lot02 | MO-CK19 | MO-CK | Traffic Line Marking (Thermoplastic Paint) | สหชาติ | 0 | Depot | 2026-05-01 | 2026-04-30 | 100% | Completed | 2026-06-15 | 100% | Completed |  |  | 0 | 0
164 | 0 | Lot02 | MO-CK20 | MO-CK | Emergency Car Parking location Painting in front of MWS | สหชาติ | 0 | Depot | 2026-05-01 | 2026-04-30 | 100% | Completed | 2026-06-15 | 100% | Completed |  |  | 0 | 0
165 | GRS-39022 | Lot02 | MO-CK21 | MO-CK | Safety Line painting in MWS, Stabling Area, P-way, Track | สหชาติ | 0 | Depot | 2027-01-01 | 2026-06-01 | 100% | Completed | 2026-08-01 | 100% | Completed |  | GRS-39022 | GRS-69001 | GRS-69022
166 | 0 | Lot02 | MO-CK22 | MO-CK | Fire escape stairs level signs in the Depot, VS and IVS areas | สหชาติ | 0 | Depot | 2027-01-01 | 2026-09-30 | 50% | Late | 2026-10-31 | 0% | On Schedule | GRS |  | 0 | 0
167 | DWE-39026 | Lot02 | MO-CK23 | MO-CK | General waste Storage 22 x 5 m | สหชาติ | 0 | Depot | 2026-05-01 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed |  | DWE-39026 | DWE-69026 | DWE-69126
168 | 0 | Lot02 | MO-CK24 | MO-CK | Modify Traffic paint and traffic sign | สหชาติ | 0 | 0 | 2026-05-01 | 2026-04-30 | 100% | Completed | 2026-06-15 | 100% | Completed |  |  | 0 | 0
169 | 0 | Lot02 | MO-CK25 | MO-CK | Station Area sign 28 stations | สหชาติ | 0 | 0 | 2026-05-01 | 2026-06-15 | 80% | Late | 2026-06-30 | 100% | Completed |  |  | 0 | 0
170 |  | Lot02 | MO-CK26 | MO-CK | Safety and warning signage for lift and escalator at all station | สหชาติ | 0 | Depot | 2027-01-01 | 2026-06-16 | 100% | Completed | 2026-07-17 | 100% | Completed
171 | MDW-39532 | Lot02 | MO-CK27 | MO-CK | Spike fence for Depot slab | สหชาติ | 0 | Depot | 2027-01-01 | 2026-07-31 | 70% | Late | 2026-08-31 | 0% | Late | อยู่ระหว่างส่งขออนุมัติแบบรอ Approve | MDW-39532 | MDW-69564 | MDW-69565
172 | 0 | Lot02 | MO-CK28 | MO-CK | Bird net and Flashing at MWS and Skywalk to Stabling yard | สหชาติ | 0 | 0 | 2026-05-01 |  |  | 0% |  |  | 0 |  |  | 0 | 0
173 | MDW-39541 | Lot02 | MO-CK29 | MO-CK | Fire Alarm Manual Call Point signage at all elevated station | สหชาติ | 0 | 0 | 2027-01-01 |  |  | 0% | 2026-07-30 | 100% | Completed |  | MDW-39541 | MDW-69582 | MDW-69583
174 | 0 | Lot02 | MO-CK30 | MO-CK | Lighting for sealed space under stairs and behind lift shaft at underground station | ประธาน | 0 | 0 | 2027-01-01 | 2026-10-14 | 0% | Late | 2026-11-14 | 0% | On Schedule | ไฟส่องสว่างสำหรับพื้นที่ปิดใต้บันไดและด้านหลังช่องลิฟต์ที่สถานีรถไฟใต้ดิน |  | 0 | 0
175 | 0 | Lot02 | MO-CK31 | MO-CK | Modify the access door of sealed space (under-stairs room) with a Sump Pump or ESPS cabinet | สหชาติ | 0 | 0 | 2027-01-01 | 2026-07-16 | 0% | Late | 2026-08-16 | 0% | Late | 0 |  | 0 | 0
176 | 0 | Lot02 | MO-CK32 | MO-CK | Lighting to the sealed space (under-stairs room) with a Sump Pump or ESPS cabinet | ประธาน | 0 | Depot | 2027-01-01 | 2026-11-03 | 0% | On Schedule | 2026-12-04 | 0% | On Schedule | ซื้อสปอร์ตไลท์+แบต จำนวน 4 ชุด แทนการลากสายไฟ |  | 0 | 0
177 | 0 | Lot02 | MO-CK33 | MO-CK | Additional lighting in areas where the lux level does not meet occupational health standards | ประธาน | 0 | Depot | 2027-01-01 | 2026-09-14 | 100% | Completed | 2026-10-15 | 100% | Completed |  |  | 0 | 0
178 | 0 | Lot02 | MO-CK34 | MO-CK | Provide and install confined space signage for Station and Depot | สหชาติ | 0 | 0 | 2027-01-01 | 2026-08-15 | 100% | Completed | 2026-09-15 | 100% | Completed |  |  | 0 | 0
179 |  | Lot02 | MO-CK35 | MO-CK | Build room for Train crew main office at OR18 with office area, resting area, meeting room, pantry, toilet and locker room | สหชาติ/บัณฑิต/ประธาน | 0 | Depot | - |  |  | 0% |  |  | 0
180 |  | Lot02 | MO-CK36 | MO-CK | Dormitory Cable Containments (if any) | มนตรี | 0 | Depot | - |  |  | 0% |  |  | 0
181 | 0 | Lot02 | MO-CK37 | MO-CK | Provide Raise floor and building Service in Training &Simulator (OCC Admin) | สหชาติ | 0 | Depot | - | 0% | 0% | 0% | [5 empty] | 0 | 0
182 |  | Lot02 | MO-CK38 | MO-CK | Add N2 in Playback and Training Room and Backup Control Room | บุญประเสริฐ | 0 | Depot | - |  |  | 0% |  |  | 0
183 | MDW-39505 | Lot02 | MO-BEM1.1 | MO-BEM | Walkway from Main Work Shop to Stabling Area - Civil & AR | สหชาติ | 0 | Depot | 2026-08-02 | 2026-04-28 | 100% | Completed | 2026-05-29 | 92% | Late | คงเหลืองานมุงหลังคา Metal sheet | MDW-39505 | MDW-69510 | MDW-69511
184 | MDW-39506 | Lot02 | MO-BEM1.2 | MO-BEM | Walkway from Main Work Shop to Stabling Area - Building Services | ประธาน | 0 | Depot | 2026-08-02 | 2026-04-28 | 100% | Completed | 2026-05-29 | 100% | Completed |  | MDW-39506 | MDW-69512 | MDW-69513
185 | MDW-39507 | Lot02 | MO-BEM2 | MO-BEM | High Roof at Main Work Shop Entrance and Store | สหชาติ | 0 | Depot | 2026-08-01 | 2026-02-13 | 100% | Completed | 2026-03-31 | 100% | Completed |  | MDW-39507 | MDW-69514 | MDW-69515
186 | MDW-39509 | Lot02 | MO-BEM3 | MO-BEM | High Roof at the entrance and exit of the under floor wheel lathe | สหชาติ | 0 | Depot | 2026-08-04 | 2026-02-13 | 100% | Completed | 2026-03-31 | 100% | Completed |  | MDW-39509 | MDW-69518
187 | MDW-39511 | Lot02 | MO-BEM4.1 | MO-BEM | Maintenance Office Rooms at Main Workshop - Civil & AR | สหชาติ | 0 | Depot | 2026-07-03 | 2026-04-13 | 100% | Completed | 2026-05-14 | 100% | Completed |  | MDW-39511 | MDW-69522 | MDW-69523
188 | MDW-39512 | Lot02 | MO-BEM4.2 | MO-BEM | Maintenance Office Rooms at Main Workshop - Building Services | ประธาน | 0 | Depot | 2026-07-04 | 2026-04-13 | 100% | Completed | 2026-05-14 | 100% | Completed |  | MDW-39512 | MDW-69524 | MDW-69525
189 | MDW-39513 | Lot02 | MO-BEM5 | MO-BEM | Install Concrete car barrier along the walkway in front of MWS building | สหชาติ | 0 | Depot | 2027-01-01 | 2026-10-14 | 100% | Completed | 2026-11-14 | 100% | Completed |  | MDW-39513 | MDW-69526 | MDW-69527
190 | 0 | Lot02 | MO-BEM6 | MO-BEM | Handrail on top of the water tank on the rooftop of the Admin Building | สหชาติ | 0 | Depot | 2027-01-01 | 2026-10-19 | 100% | Completed | 2026-11-19 | 100% | Completed |  |  | 0 | 0
191 | 0 | Lot02 | MO-BEM7 | MO-BEM | Modify maintenance service door to the roof building to easier access while maintaining safe operational standards | สหชาติ | 0 | Depot | 2027-01-01 | 2026-10-19 | 50% | Late | 2026-11-19 | 0% | On Schedule | 0 |  | 0 | 0
192 | MDW-39536 | Lot02 | MO-BEM8 | MO-BEM | Company logo and Central Control Room sign in CCR room. | สหชาติ | 0 | Depot | 2026-05-01 | 2026-01-27 | 100% | Completed | 2026-03-14 | 100% | Completed |  | MDW-39536 | MDW-69572 | MDW-69573
193 | MDW-39536 | Lot02 | MO-BEM9 | MO-BEM | Soundproof insulation on the wall and structure and equipment in the CCR room. | สหชาติ | 0 | Depot | 2026-05-01 | 2026-01-12 | 100% | Completed | 2026-02-27 | 100% | Completed |  | MDW-39536 | MDW-69572 | MDW-69573
194 | MDW-39526 | Lot02 | MO-BEM10 | MO-BEM | Relocate Fire Hose Cabinet to be outside of the clearance gauge zone 17 set | ประธาน | 0 | Depot | 2026-05-01 | 2026-01-12 | 100% | Completed | 2026-02-27 | 100% | Completed |  | MDW-39526 | MDW-69552 | MDW-69553
195 | MDW-39528 | Lot02 | MO-BEM11.1 | MO-BEM | Washing Area in Cleaning Staff Room at Stabling Yard - Civil & AR | สหชาติ | 0 | Depot | 2026-08-03 | 2026-06-03 | 100% | Completed | 2026-07-04 | 100% | Completed |  | MDW-39528 | MDW-69556 | MDW-69557
196 | MDW-39529 | Lot02 | MO-BEM11.2 | MO-BEM | Washing Area in Cleaning Staff Room at Stabling Yard - Building Services | ประธาน | 0 | Depot | 2026-08-04 | 2026-04-14 | 100% | Completed | 2026-05-30 | 100% | Completed |  | MDW-39529 | MDW-69558 | MDW-69559
197 | MDW-39522 | Lot02 | MO-BEM12 | MO-BEM | Rain protection for Water treatment Building | สหชาติ | 0 | Depot | 2026-08-05 | 2026-04-29 | 100% | Completed | 2026-05-30 | 100% | Completed |  | MDW-39522 | MDW-69544 | MDW-69545
198 | MDW-39522 | Lot02 | MO-BEM13.1 | MO-BEM | Zero Discharge Water treatment in Depot - Civil & AR | สหชาติ | 0 | Depot | 2027-01-01 | 2026-08-15 | 100% | Completed | 2026-09-30 | 75% | Late | คงเหลืองานประกอบและติดตั้งโครงหลงัคา | MDW-39522 | MDW-69544 | MDW-69545
199 | MDW-39530 | Lot02 | MO-BEM13.2 | MO-BEM | Zero Discharge Water treatment in Depot - Building Services | ประธาน | 0 | Depot | 2027-01-01 | 2026-08-15 | 100% | Completed | 2026-09-30 | 100% | Completed |  | MDW-39530 | MDW-69560 | MDW-69561
200 | MDW-39516 | Lot02 | MO-BEM14.1 | MO-BEM | Modification Works : Walkway Bridge between BL Depot and ORL Depot - Civil & AR | สหชาติ | 0 | Depot | 2026-08-02 | 2026-02-28 | 100% | Completed | 2026-06-15 | 100% | Completed |  | MDW-39516 | MDW-69532 | MDW-69533
201 | MDW-39517 | Lot02 | MO-BEM14.2 | MO-BEM | Modification Works : Walkway Bridge between BL Depot and ORL Depot - Building Services | ประธาน | 0 | Depot | 2026-08-03 | 2026-01-14 | 100% | Completed | 2026-03-01 | 100% | Completed |  | MDW-39517 | MDW-69534 | MDW-69535
202 | MDW-39514 | Lot02 | MO-BEM15.1 | MO-BEM | Roof for cars parking lots area (184 car)t - Civil & AR | สหชาติ | 0 | Depot | 2026-08-03 | 2026-02-28 | 100% | Completed | 2026-03-31 | 100% | Completed |  | MDW-39514 | MDW-69528 | MDW-69529
203 | MDW-39515 | Lot02 | MO-BEM15.2 | MO-BEM | Roof for cars parking lots area (184 car) - Building Services | ประธาน | 0 | Depot | 2026-08-03 | 2026-02-28 | 100% | Completed | 2026-03-31 | 100% | Completed |  | MDW-39515 | MDW-69530 | MDW-69531
204 | MDW-39519 | Lot02 | MO-BEM16 | MO-BEM | Walkway roof and High roof across the road from Admin ORL to Depot slap | สหชาติ | 0 | Depot | 2026-08-01 | 2026-06-15 | 100% | Completed | 2026-06-30 | 100% | Completed |  | MDW-39519 | MDW-69538 | MDW-69539
205 | MDW-39519 | Lot02 | MO-BEM17 | MO-BEM | Walkway roof to car park in front of admin ORL(3x5m.) | สหชาติ | 0 | Depot | 2026-08-01 | 2026-06-15 | 100% | Completed | 2026-06-30 | 100% | Completed |  | MDW-39519 | MDW-69538 | MDW-69539
206 | MDW-39519 | Lot02 | MO-BEM18 | MO-BEM | Walkway roof over the footpath near depot slab (1.50 m. x 290 m.) and stair up to depot slap. | สหชาติ | 0 | Depot | 2026-08-01 | 2026-06-15 | 100% | Completed | 2026-06-30 | 100% | Completed |  | MDW-39519 | MDW-69538 | MDW-69539
207 | MDW-39557 | Lot02 | MO-BEM19 | MO-BEM | Install Chain Link fence to enclose parking area | สหชาติ | 0 | Depot | 2026-10-01 | 2026-06-29 | 100% | Completed | 2026-07-30 | 100% | Completed |  | MDW-39557 | MDW-69614 | MDW-69615
208 | MDW-39523 | Lot02 | MO-BEM20 | MO-BEM | Hose bib 1/2" 4 sets for Tree around Admin area | ประธาน | 0 | Depot | 2026-06-01 | 2026-04-23 | 100% | Completed | 2026-06-08 | 100% | Completed |  | MDW-39523 | MDW-69546 | MDW-69547
209 | - | Lot02 | MO-BEM21 | MO-BEM | Relocate Security Guard Box at Front Gate and Install Roof 3x5m. | สหชาติ | 0 | Depot | 2027-01-03 | 2026-07-31 | 100% | Completed | 2026-09-30 | 75% | Late |  |  | 0 | 0
210 | MDW-39534 | Lot02 | MO-BEM21.1 | MO-BEM | Modification Works : Security Guard Box at ORL Depot Entrance - Civil & AR | สหชาติ | 0 | Depot | 2027-01-02 | 2026-07-31 | 100% | Completed | 2026-09-30 | 67% | Late |  | MDW-39534 | MDW-69568 | MDW-69569
211 | MDW-39535 | Lot02 | MO-BEM21.2 | MO-BEM | Modification Works : Security Guard Box at ORL Depot Entrance - Building Services | ประธาน | 0 | Depot | 2027-01-03 | 2026-07-31 | 100% | Completed | 2026-09-30 | 100% | Completed |  | MDW-39535 | MDW-69570 | MDW-69571
212 | MDW-39532 | Lot02 | MO-BEM22 | MO-BEM | Addition Spike fence for MRTA fence and Chain link at Klong Chourdyai 400m. | สหชาติ | 0 | Depot | 2027-01-01 | 2026-08-30 | 70% | Late | 2026-09-30 | 0% | Late |  | MDW-39532 | MDW-69564 | MDW-69565
213 | MDW-39527 | Lot02 | MO-BEM23 | MO-BEM | Hand sink with eye wash station | ประธาน | พี่ต่อ | Depot | 2027-01-01 | 2026-08-30 | 100% | Completed | 2026-10-15 | 100% | Completed |  | MDW-39527 | MDW-69554 | MDW-69555
214 | MDW-39531 | Lot02 | MO-BEM24 | MO-BEM | Guard rail protection for Fire Hose Cabinet 8 set | สหชาติ | 0 | Depot | 2026-06-01 | 2026-03-14 | 100% | Completed | 2026-04-14 | 100% | Completed |  | MDW-39531 | MDW-69562 | MDW-69563
215 | MDW-39557 | Lot02 | MO-BEM25.1 | MO-BEM | Chain Link Fence to divide controlled areas on Depot slab 3 m.x 485 m. - Civil & AR | สหชาติ | 0 | Depot | 2026-10-01 | 2026-06-14 | 100% | Completed | 2026-07-30 | 100% | Completed |  | MDW-39557 | MDW-69614 | MDW-69615
216 | MDW-39520 | Lot02 | MO-BEM25.2 | MO-BEM | Chain Link Fence to divide controlled areas on Depot slab 3 m.x 485 m.- Building Services | ประธาน | 0 | Depot | 2026-10-01 | 2026-06-14 | 100% | Completed | 2026-07-30 | 100% | Completed |  | MDW-39520 | MDW-69540 | MDW-69541
217 | MDW-39518 | Lot02 | MO-BEM26 | MO-BEM | Street Lighting system area between MRTA Fence and Depot slab | ประธาน | 0 | Depot | 2026-08-01 | 2026-04-14 | 50% | Late | 2026-05-15 | 0% | Late |  | MDW-39518 | MDW-69536 | MDW-69537
218 | - | Lot02 | MO-BEM27 | MO-BEM | Compacted gravel walkway along the Test Track OR-BL 1.2 m. | สหชาติ | พรพรหม | Depot | 2027-01-01 | 2026-08-30 | 100% | Completed | 2026-09-30 | 0% | Late |  |  | 0 | 0
219 | MDW-39524 | Lot02 | MO-BEM28.1 | MO-BEM | Walkway under Depot Slab for Maintenance Service - Civil & AR | สหชาติ | 0 | Depot | 2027-01-02 | 2026-09-14 | 100% | Completed | 2026-10-30 | 100% | Completed |  | MDW-39524 | MDW-69548 | MDW-69549
220 | MDW-39525 | Lot02 | MO-BEM28.2 | MO-BEM | Walkway under Depot Slab for Maintenance Service - Building Services | ประธาน | 0 | Depot | 2027-01-03 | 2026-09-14 | 100% | Completed | 2026-10-30 | 100% | Completed |  | MDW-39525 | MDW-69550 | MDW-69551
221 | MDW-39521 | Lot02 | MO-BEM29 | MO-BEM | Walkway Bridge across the canal for Depot area inspection patrols 3 location | สหชาติ | 0 | Depot | 2027-01-01 | 2026-08-15 | 100% | Completed | 2026-09-30 | 67% | Late |  | MDW-39521 | MDW-69542 | MDW-69543
222 | - | Lot02 | MO-BEM30 | MO-BEM | Cut down trees between Depot BL+ORL and MRTA Fence | สหชาติ | 0 | Depot | 2027-01-01 | 2026-10-29 | 0% | Late | 2026-11-29 | 0% | On Schedule |  |  | 0 | 0
223 | 0 | Lot02 | MO-BEM31 | MO-BEM | Provide facility system and interface to MMC room (Fire Alarm / CCTV / VMS / TEL / CASS / Radio / PA) | บัณฑิต | 0 | Depot | 2026-10-01 | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
224 | - | Lot02 | MO-BEM32 | MO-BEM | Stainless Guard rail balustrade for waiting area | สหชาติ | 0 | Depot | 2026-05-01 |  |  | 0% |  |  | 0 |  |  | 0 | 0
225 | - | Lot02 | MO-BEM33 | MO-BEM | Concrete walkway 2 x 80 m. For fire escape route | สหชาติ | 0 | Depot | 2026-05-01 |  |  | 0% |  |  | 0 |  |  | 0 | 0
226 | - | Lot02 | MO-BEM34 | MO-BEM | Access Gate (Full Height Turnstile) at 1st floor admin ORL | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed |  |  | 0 | 0
227 | - | Lot02 | MO-BEM35 | MO-BEM | Access Gate (Tripod with Swing Gate) at MWS Entrance | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed |  |  | 0 | 0
228 | - | Lot02 | MO-BEM36 | MO-BEM | Access Gate (Tripod with Swing Gate) at Admin 2nd floor connect to OCC | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed |  |  | 0 | 0
229 | - | Lot02 | MO-BEM37 | MO-BEM | Access Gate (Tripod with Swing Gate) on Klong Chourdyai bridge | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed |  |  | 0 | 0
230 | - | Lot02 | MO-BEM38 | MO-BEM | Access Gate (Tripod with roof covering) at parking lot OCC | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed |  |  | 0 | 0
231 | - | Lot02 | MO-BEM39 | MO-BEM | Access Gate (Tripod with roof covering) at Stair up to Depot slab | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed |  |  | 0 | 0
232 | - | Lot02 | MO-BEM40 | MO-BEM | Access Control (2 Factors, Card + Finger Print) at High Security rooms - CCR/PTR/Store | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed |  |  | 0 | 0
233 | - | Lot02 | MO-BEM41 | MO-BEM | Link CCTV Landscape of all depot ORL area for MMC BL monitoring. | บัณฑิต | 0 | 0 | 2027-01-01 | 2026-11-28 | 0% | On Schedule | 2026-11-29 | 0% | On Schedule |  |  | 0 | 0
234 | - | Lot02 | MO-BEM42 | MO-BEM | Fire Suppression Control Panel Cover which located in tunnel | สู่โชค | 0 | 0 | 2027-01-01 |  |  | 0% |  |  | 0 |  |  | 0 | 0
235 | MDW-39537 | Lot02 | MO-BEM43 | MO-BEM | Handrails for ladder at IVS and Vent buildings | สหชาติ | 0 | 0 | 2026-09-01 | 2026-03-31 | 70% | Late | 2026-05-01 | 0% | Late |  | MDW-39537 | MDW-69574 | MDW-69575
236 | MDW-39538 | Lot02 | MO-BEM44 | MO-BEM | Escalator Anti-Slide device for all station. | สหชาติ | 0 | 0 | 2026-09-01 | 2026-05-30 | 100% | Completed | 2026-06-30 | 100% | Completed |  | MDW-39538 | MDW-69576 | MDW-69577
237 | MDW-39539 | Lot02 | MO-BEM45 | MO-BEM | Roof for control panel on vent building | สหชาติ | 0 | 0 | 2027-01-01 | 2026-09-14 | 70% | Late | 2026-10-30 | 0% | On Schedule |  | MDW-39539 | MDW-69578 | MDW-69579
238 | MDW-39553 | Lot02 | MO-BEM46 | MO-BEM | Provide Standing plate or ladder to access the Fire Valve in at Omega points for all underground stations. | สหชาติ | 0 | Depot | 2027-01-01 | 2026-09-14 | 0% | Late | 2026-10-30 | 0% | On Schedule |  | MDW-39553 | MDW-69606 | MDW-69607
239 | MDW-39540 | Lot02 | MO-BEM47 | MO-BEM | Water drop protection above UPS cabinet at station and Depot | สหชาติ | 0 | 0 | 2027-01-01 | 2026-09-14 | 0% | Late | 2026-10-30 | 0% | On Schedule |  | MDW-39540 | MDW-69580 | MDW-69581
240 | MDW-39541 | Lot02 | MO-BEM48 | MO-BEM | Fire alarm manual call point cover in public area at all station | ประธาน | 0 | 0 | 2027-01-01 | 2026-09-14 | 50% | Late | 2026-10-30 | 0% | On Schedule |  | MDW-39541 | MDW-69582 | MDW-69583
241 | MDW-39542 | Lot02 | MO-BEM49 | MO-BEM | Emergency stop button cover for escalator at all station. | สหชาติ | 0 | 0 | 2027-01-01 | 2026-09-14 | 0% | Late | 2026-10-30 | 0% | On Schedule |  | MDW-39542 | MDW-69584 | MDW-69585
242 | 0 | Lot02 | MO-BEM50 | MO-BEM | Modify maintenance service door to the roof of OR13 vent building to easier access while maintaining safe operational standards | สู่โชค | 0 | Depot | 2027-01-01 | 2026-10-29 | 0% | Late | 2026-10-30 | 100% | Completed |  |  | 0 | 0
243 | MDW-39514 | Lot02 | MO-BEM51 | MO-BEM | Modify existing car park to be 220 motorcycle parking lots including floor painting and parking roof | สหชาติ | 0 | Depot | 2026-08-01 | 2026-01-29 | 100% | Completed | 2026-03-16 | 100% | Completed |  | MDW-39514 | MDW-69528 | MDW-69529
244 | MDW-39534 | Lot02 | MO-BEM52 | MO-BEM | Modify the sidewalk for temporary parking at entrance | สหชาติ | 0 | Depot | 2027-01-01 | 2026-07-31 | 100% | Completed | 2026-09-30 | 100% | Completed |  | MDW-39534 | MDW-69568 | MDW-69569
245 | MDW-39554 | Lot02 | MO-BEM53.1 | MO-BEM | Modification Works : Security Guard Box at OCC Parking Area - Civil & AR | สหชาติ | 0 | Depot | 2027-01-02 | 2026-09-14 | 100% | Completed | 2026-10-31 | 100% | Completed |  | MDW-39554 | MDW-69608 | MDW-69609
246 | MDW-39555 | Lot02 | MO-BEM53.2 | MO-BEM | Modification Works : Security Guard Box at OCC Parking Area - Building Services | ประธาน | 0 | 0 | 2027-01-02 | 2026-09-14 | 100% | Completed | 2026-10-31 | 100% | Completed |  | MDW-39555 | MDW-69610 | MDW-69611
247 | NoDrawing | Lot02 | MO-BEM54 | MO-BEM | Strengthen the Maintenance Walkway of the TEF fan | สหชาติ | 0 | 0 | 2027-01-01 | 2026-07-16 | 100% | Completed | 2026-08-16 | 100% | Completed |  |  | 0 | 0
Lot 1 Procurement
[20 empty] | CK Pesonsible Person | Total | Completed | Late | On Schedule
[20 empty] | สหชาติ | 29 | 18 | 8 | 3
[20 empty] | ประธาน | 37 | 36 | 0 | 1
[20 empty] | สมศักดิ์ | 24 | 23 | 1 | 0
[20 empty] | กำพล | 9 | 9 | 0 | 0
[20 empty] | บัณฑิต | 5 | 3 | 2 | 0
[20 empty] | สู่โชค | 1 | 1 | 0 | 0
[20 empty] | ธัญวิทย์ | 1 | 1 | 0 | 0
[20 empty] | มนตรี | 6 | 5 | 1 | 0
[20 empty] | มนต์ชัย | 1 | 1 | 0 | 0
[20 empty] | - | 2 | 2 | 0 | 0
Lot 2 Procurement
[20 empty] | CK Pesonsible Person | Total | Completed | Late | On Schedule
[20 empty] | สหชาติ | 62 | 43 | 11 | 8
[20 empty] | ประธาน | 25 | 21 | 1 | 3
[20 empty] | บัณฑิต | 8 | 7 | 0 | 1
[20 empty] | สู่โชค | 1 | 1 | 0 | 0

## Manu-Deli (hidden)
Manufacturing/Delivery Process
No. | Design Submission | Lot No. | Code | System | Activity Name | CK Responsible Person |  | Location | Expected Completion Month | Design (PLAN) | Design (%) | Design (Status) | Procurement (PLAN) | Procurement (%) | Procurement (Status) | Manufacturing / Delivery Process (PLAN) | Manufacturing / Delivery Process (%) | Manufacturing / Delivery (Status) | Note | Design Submission | Procedure No. | Test Report No.
1 | MDW-39246-60 | Lot01 | GEN1 | GEN | Rooms and Building Service Systems Modification in Stations Area | - | 0 | 0 | 2026-08-01 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39246 | MDW-69259 | MDW-69260
2 | MDW-39246 | Lot01 | GEN1.1 | GEN | Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR13 - OR17 | ประธาน | 0 | 0 | 2026-08-01 | 2026-01-30 | 100% | Completed | 2026-03-01 | 100% | Completed | 0 | 0 | 0 |  | MDW-39246 | MDW-69259 | MDW-69260
3 | MDW-39247 | Lot01 | GEN1.2 | GEN | Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR18 - OR22 | ประธาน | 0 | 0 | 2026-08-01 | 2025-12-30 | 100% | Completed | 2026-01-29 | 100% | Completed | 0 | 0 | 0 |  | MDW-39247 | MDW-69259 | MDW-69261
4 | MDW-39248 | Lot01 | GEN1.3 | GEN | Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR23 - OR29 | ประธาน | 0 | 0 | 2026-08-01 | 2026-01-30 | 100% | Completed | 2026-03-01 | 100% | Completed | 0 | 0 | 0 |  | MDW-39248 | MDW-69259 | MDW-69262
5 | MDW-39252 | Lot01 | GEN1.4 | GEN | Modification of Fire Suppression System (N2) in Commerial Room at OR14 | ประธาน | 0 | 0 | 2026-08-01 | 2025-12-30 | 100% | Completed | 2026-01-29 | 100% | Completed | 0 | 0 | 0 |  | MDW-39252 | MDW-69269 | MDW-69270
6 | MDW-39253 | Lot01 | GEN1.5 | GEN | Modification of Civil Work in Telecommunication Room at OR14 | สหชาติ | 0 | 0 | 2026-08-01 | 2025-12-30 | 100% | Completed | 2026-01-29 | 100% | Completed | 0 | 0 | 0 |  | MDW-39253 | MDW-69271 | MDW-69272
7 | MDW-39254 | Lot01 | GEN1.6 | GEN | Modification in Staff Mess Room at OR13-OR17 | ประธาน | 0 | 0 | 2026-08-01 | 2026-01-30 | 100% | Completed | 2026-03-01 | 100% | Completed | 0 | 0 | 0 |  | MDW-39254 | MDW-69273 | MDW-69274
8 | MDW-39255 | Lot01 | GEN1.7 | GEN | Modification in Staff Mess Room at OR18-OR22 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39255 | MDW-69273 | MDW-69275
9 | MDW-39256 | Lot01 | GEN1.8 | GEN | Modification in Staff Mess Room at OR23-OR29 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39256 | MDW-69273 | MDW-69276
10 | MDW-39257 | Lot01 | GEN1.9 | GEN | Modification of Air Conditioning in CER and SER at OR13-OR19 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39257 | MDW-69277 | MDW-69278
11 | MDW-39258 | Lot01 | GEN1.10 | GEN | Modification of Air Conditioning in CER and SER at OR20-OR22 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39258 | MDW-69277 | MDW-69279
12 | MDW-39259 | Lot01 | GEN1.11 | GEN | Modification of Air Conditioning in CER and SER at OR23-OR29 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39259 | MDW-69277 | MDW-69280
13 | MDW-39272 | Lot01 | GEN1.12 | GEN | Modification of New M&E Room at IVS15 - IVS17 Civil & AR | สหชาติ | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39272 | MDW-69299 | MDW-69300
14 | MDW-39273 | Lot01 | GEN1.13 | GEN | Modification of New M&E UPS Room at IVS15-IVS17 - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39273 | MDW-69301 | MDW-69302
15 | MDW-39294 | Lot01 | GEN1.14 | GEN | Provision of Architectural Work in new M&E UPS room at OR23 | สหชาติ | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39294 | MDW-69339 | MDW-69340
16 | MDW-39299 | Lot01 | GEN1.15 | GEN | Provision of Air Conditioning System in Commercial Room at OR13-OR19 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39299 | MDW-69349 | MDW-69350
17 | MDW-39306 | Lot01 | GEN1.16 | GEN | Modification CER and First Aid Room at OR14 - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39306 | MDW-69363 | MDW-69364
18 | MDW-39307 | Lot01 | GEN1.17 | GEN | Additional Fence at Back of House OR13 - OR22 and IVS East Section | สหชาติ | 0 | 0 | 2026-08-01 | 2026-09-30 | 100% | Completed | 2026-10-31 | 50% | On Schedule | 0 | 0 | 0 |  | MDW-39307 | MDW-69365 | MDW-69366
19 | MDW-39249 | Lot01 | GEN1.18 | GEN | SOR Counter and Workstation Hanging Support Installation on East Section | สหชาติ | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39249 | MDW-69263 | MDW-69264
20 | MDW-39250 | Lot01 | GEN1.19 | GEN | Ticket Office Modification on East Section | สหชาติ | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39250 | MDW-69265 | MDW-69266
21 | MDW-39261 | Lot01 | GEN2 | GEN | Rooms and Building Service Systems Modification in Depot Area | - | 0 | Depot | 2026-08-01 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39261 | MDW-69283 | MDW-69284
22 | MDW-39260 | Lot01 | GEN2.1 | GEN | Modification of Air Conditioning in M&E Room at OCC Building | ประธาน | 0 | 0 | 2026-08-01 | 2025-12-30 | 100% | Completed | 2026-01-29 | 100% | Completed | 0 | 0 | 0 |  | MDW-39260 | MDW-69281 | MDW-69282
23 | MDW-39261 | Lot01 | GEN2.2 | GEN | Provision of UPS for MDB Control at Main Workshop, OCC Building, Admin Building, Stabling Yard and Train Washing Plant | ประธาน | 0 | 0 | 2026-08-01 | 2026-09-01 | 100% | Completed | 2026-10-01 | 100% | Completed | 0 | 0 | 0 |  | MDW-39261 | MDW-69283 | MDW-69284
24 | MDW-39262 | Lot01 | GEN2.3 | GEN | Provision of Redundant MDB at OCC Building, Admin Building and Canteen | ประธาน | 0 | 0 | 2026-08-01 | 2026-09-01 | 100% | Completed | 2026-10-01 | 100% | Completed | 0 | 0 | 0 |  | MDW-39262 | MDW-69285 | MDW-69286
25 | MDW-39263 | Lot01 | GEN2.4 | GEN | Additonal Lighting System at Depot Area | ประธาน | 0 | 0 | 2026-08-01 | 2026-04-01 | 100% | Completed | 2026-05-01 | 100% | Completed | 0 | 0 | 0 |  | MDW-39263 | MDW-69287 | MDW-69288
26 | MDW-39290 | Lot01 | GEN2.5 | GEN | Modification Room for PSY at Depot Buildings - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39290 | MDW-69331 | MDW-69332
27 | MDW-39300 | Lot01 | GEN2.6 | GEN | Modification SIG-PSD Office at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39300 | MDW-69351 | MDW-69352
28 | MDW-39301 | Lot01 | GEN2.7 | GEN | Modification Backup CCR Room at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39301 | MDW-69353 | MDW-69354
29 | MDW-39302 | Lot01 | GEN2.8 | GEN | Modification SER at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39302 | MDW-69355 | MDW-69356
30 | MDW-39303 | Lot01 | GEN2.9 | GEN | Modification CER & SCADA Room at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39303 | MDW-69357 | MDW-69358
31 | MDW-39309 | Lot01 | GEN2.10 | GEN | Modification Air Conditioning System at CCR | ประธาน | 0 | 0 | 2026-08-01 | 2026-10-01 | 100% | Completed | 2026-10-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39309 | MDW-69369 | MDW-69370
32 | MDW-39312 | Lot01 | GEN2.11 | GEN | Modification Electronic Workshop at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-10-31 | 100% | Completed | 2026-11-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39312 | MDW-69375 | MDW-69376
33 | MDW-39313 | Lot01 | GEN2.12 | GEN | Modification Battery Charger Room at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-10-31 | 100% | Completed | 2026-11-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39313 | MDW-69377 | MDW-69378
34 | MDW-39314 | Lot01 | GEN2.13 | GEN | Modification Machining Room at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-10-31 | 90% | On Schedule | 2026-11-30 | 0% | On Schedule | 0 | 0 | 0 |  | MDW-39314 | MDW-69379 | MDW-69380
35 | MDW-39315 | Lot01 | GEN2.14 | GEN | Modification Electronic Workshop, Battery Charger and Machining Room at Main Workshop - Civil & AR | สหชาติ | 0 | 0 | 2026-08-01 | 2026-10-31 | 70% | On Schedule | 2026-11-30 | 90% | On Schedule | 0 | 0 | 0 |  | MDW-39315 | MDW-69383 | MDW-69384
36 | MDW-39297 | Lot01 | GEN2.15 | GEN | Training Room at Ratchada Station (Part 2) | สหชาติ | 0 | 0 | 2026-08-01 | 2026-08-01 | 0% | Late | 2026-08-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39297 | MDW-69345 | MDW-69346
37 | MDW-39291 | Lot01 | GEN2.16 | GEN | Conductor Rail Arrangement Modification at Main Line East Section | กำพล | 0 | 0 | 2026-08-01 | 2026-09-30 | 100% | Completed | 2026-09-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39291 | MDW-69333 | MDW-69334
38 | MDW-39292 | Lot01 | GEN2.17 | GEN | Conductor Rail Arrangement Modification at Depot | กำพล | 0 | 0 | 2026-08-01 | 2026-09-30 | 100% | Completed | 2026-09-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39292 | MDW-69335 | MDW-69336
39 | MDW-39295 | Lot01 | GEN2.18 | GEN | Dangerous Goods Building in Depot - Civil & AR | สหชาติ | 0 | 0 | 2026-08-01 | 2026-01-27 | 100% | Completed | 2026-02-27 | 100% | Completed | 0 | 0 | 0 |  | MDW-39295 | MDW-69341 | MDW-69342
40 | MDW-39296 | Lot01 | GEN2.19 | GEN | Dangerous Goods Building in Depot - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2025-12-13 | 100% | Completed | 2026-01-28 | 100% | Completed | 0 | 0 | 0 |  | MDW-39296 | MDW-69343 | MDW-69344
41 | MDW-39308 | Lot01 | GEN2.20 | GEN | Additional Locking Devices for Main Line Tandem Turnouts 2007, 2010 & 2013 and Depot Turnout D16 | กำพล | 0 | 0 | 2026-08-01 | 2026-11-30 | 50% | On Schedule | 2026-09-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39308 | MDW-69367 | MDW-69368
42 | MDW-39200-31 | Lot01 | GEN3 | GEN | Cable Containment Modification | - | 0 | 0 | 2025-05-28 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39200
43 | - | Lot01 | GEN4 | GEN | Training Room and Workshop Room | - | 0 | 0 | 2026-04-01 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
44 | MDW-39242 | Lot01 | GEN4.0 | GEN | Modification Works for Training Room at Ratchada Station | ประธาน | 0 | 0 | 2026-04-01 | 2025-12-30 | 100% | Completed | 2026-01-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39242 | MDW-69251 | MDW-69252
45 | MDW-39244 | Lot01 | GEN4.1 | GEN | AFC Training Room Modification - Civil & AR | สหชาติ | 0 | 0 | 2026-08-21 | 2026-09-30 | 10% | Late | 2026-10-15 | 100% | Completed | 0 | 0 | 0 |  | MDW-39244 | MDW-69255 | MDW-69256
46 | MDW-39245 | Lot01 | GEN4.2 | GEN | AFC Training Room Modification - Building Services | ประธาน | 0 | 0 | 2026-08-21 | 2025-12-30 | 100% | Completed | 2026-01-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39245 | MDW-69257 | MDW-69258
47 | MDW-39235 | Lot01 | GEN5 | GEN | Raised Floor | สหชาติ | 0 | 0 | 2026-06-01 | 2025-05-15 | 100% | Completed | 2024-12-14 | 100% | Completed | 2025-08-04 | 100% | Completed |  | MDW-39235 | MDW-69237 | MDW-69238
48 | MDW-39271 | Lot01 | GEN6 | GEN | Wayside Cable Containment in Depot | - | 0 | Depot | 2026-02-22 | 2025-05-15 | 100% | Completed | 2024-12-14 | 100% | Completed | 2025-08-04 | 100% | Completed |  | MDW-39271 | MDW-69297 | MDW-69298
49 | MDW-39269 | Lot01 | GEN6.1 | GEN | PSY Wayside Cable Containment for 24 Kv Cable under the Depot slab | ประธาน | 0 | Depot | 2026-02-22 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39269 | MDW-69293 | MDW-69294
50 | MDW-39270 | Lot01 | GEN6.2 | GEN | COM/SIG Wayside Cable Containment in the Depot | มนตรี/ประธาน | 0 | Depot | 2026-02-22 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39270 | MDW-69295 | MDW-69296
51 | - | Lot01 | GEN7 | GEN | Dangerous Waste Storage Building in Depot | - | 0 | Depot | 2026-09-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
52 | DWE-39024 | Lot01 | GEN7.1 | GEN | Dangerous Waste Storage Building in Depot - Civil & AR | สหชาติ | 0 | Depot | 2026-09-20 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed | 0 | 0 | 0 |  | DWE-39024 | DWE-69024 | DWE-69124
53 | DWE-39025 | Lot01 | GEN7.2 | GEN | Dangerous Waste Storage Building in Depot - Building service | ประธาน | 0 | Depot | 2026-09-20 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed | 0 | 0 | 0 |  | DWE-39025 | DWE-69025 | DWE-69125
54 | - | Lot01 | GEN8 | GEN | General Waste Storage Building in Depot | - | 0 | Depot | 2026-09-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
55 | DWE-39026 | Lot01 | GEN8.1 | GEN | General Waste Storage Building in Depot - Civil & AR | สหชาติ | 0 | Depot | 2026-09-20 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed | 0 | 0 | 0 |  | DWE-39026 | DWE-69026 | DWE-69126
56 | DWE-39025 | Lot01 | GEN8.2 | GEN | General Waste Storage Building in Depot - Building service | ประธาน | 0 | Depot | 2026-09-20 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed | 0 | 0 | 0 |  | DWE-39025 | DWE-69025 | DWE-69125
57 | DWE-39021 | Lot01 | GEN9 | GEN | Operation Support Equipment | สมศักดิ์ | 0 | Depot | 2026-08-21 | 2025-03-02 | 100% | Completed | 2025-11-02 | 100% | Completed | 2026-11-16 | 90% | On Schedule | คงเหลือจัดส่ง Signal Lamp | DWE-39021 | DWE-69021 | DWE-69121
58 | GRS-39001-40 | Lot01 | GEN10.1 | GEN | Graphic and Signage Station | สหชาติ | 0 | 0 | 2026-08-21 | 2026-06-30 | 100% | Completed | 2026-05-31 | 95% | Late | 2027-01-31 | 76% | On Schedule | GRS | GRS-39001 | GRS-69001 | GRS-69002
59 | GRS-39001-40 | Lot01 | GEN10.2 | GEN | Graphic and Signage Mainline & IVS,VS | สหชาติ | 0 | 0 | 2026-08-21 | 2026-06-15 | 79% | Late | 2026-05-31 | 95% | Late | 2026-07-31 | 0% | Late | GRS | GRS-39001 | GRS-69001 | GRS-69002
60 | GRS-39001-40 | Lot01 | GEN10.3 | GEN | Graphic and Signage Depot | สหชาติ | 0 | 0 | 2026-08-21 | 2026-08-15 | 90% | Late | 2026-07-31 | 93% | Late | 2026-06-30 | 56% | Late | GRS | GRS-39001 | GRS-69001 | GRS-69002
61 | MDW-39289 | Lot01 | GEN11 | GEN | Earthing and Bonding Modification | ประธาน | 0 | 0 | 2026-03-01 | 2025-01-31 | 100% | Completed | 2025-09-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39289 | MDW-69329 | MDW-69330
62 | - | Lot01 | GEN12 | GEN | Mainline Cable Trough Modification on East Section | - | 0 | 0 | 2026-06-22 | 2025-10-31 | 100% | Completed | 2025-11-30 | 100% | Completed | 2025-12-30 | 100% | Completed |  |  | 0 | 0
63 | MDW-39233 | Lot01 | GEN12.1 | GEN | Main Line Cable Trough Modification (PSY) | มนต์ชัย | 0 | Depot | 2026-06-22 | 2025-10-31 | 100% | Completed | 2025-11-30 | 100% | Completed | 2025-12-30 | 100% | Completed |  | MDW-39233
64 | MDW-39234 | Lot01 | GEN12.2 | GEN | Main Line Cable Trough Modification (SIG/COM) | มนตรี | 0 | 0 | 2026-06-22 | 2025-10-31 | 100% | Completed | 2025-11-30 | 100% | Completed | 2025-12-30 | 100% | Completed |  | MDW-39234 | MDW-69234 | MDW-69236
65 | MDW-39236 | Lot01 | GEN13 | GEN | Bird Protection System | สหชาติ | 0 | 0 | 2026-11-19 | 2025-06-30 | 100% | Completed | 2025-09-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39236 | MDW-69239 | MDW-69240
66 | - | Lot01 | GEN14 | GEN | Train Crew Office at Thailand Cultural Centre Station | สหชาติ | 0 | 0 | 2026-08-21 | 2025-09-30 | 100% | Completed | 2026-02-27 | 100% | Completed | 0 | 0 | 0 |  |  | 0 | 0
67 | MDW-39240 | Lot01 | GEN14.1 | GEN | Driver Train Simulation Room and Train Crew Office at OR18 - Civil & AR | สหชาติ | 0 | Depot | 2026-08-21 | 2025-09-30 | 100% | Completed | 2026-02-28 | 100% | Completed | 0 | 0 | 0 |  | MDW-39240 | MDW-69247 | MDW-69248
68 | MDW-39241 | Lot01 | GEN14.2 | GEN | Driver Train Simulation Room and Train Crew Office at OR18 - Building Services | ประธาน | 0 | 0 | 2026-08-21 | 2025-09-30 | 100% | Completed | 2026-02-28 | 100% | Completed | 0 | 0 | 0 |  | MDW-39241 | MDW-69249 | MDW-69250
69 | MDW-39239 | Lot01 | GEN15 | GEN | Access Panel Closeout for Traction Substation Room in Main Workshop | สหชาติ | 0 | 0 | 2026-03-24 | 2026-01-30 | 100% | Completed | 2026-03-01 | 100% | Completed | 0 | 0 | 0 |  | MDW-39239 | MDW-69245 | MDW-69246
70 | MDW-39232 | Lot01 | GEN16 | GEN | Level Crossing at Turnout | กำพล | 0 | 0 | 2026-08-21 | 2026-09-30 | 100% | Completed | 2026-09-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39232 | MDW-69232 | MDW-69233
71 | MDW-39232 | Lot01 | GEN17 | GEN | Track Slab Crossing | ชฎิล/กำพล | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39232 | MDW-69232 | MDW-69233
72 | MDW-39243 | Lot01 | GEN18 | GEN | Eye Adaptation Lighting (Lighting at Tunnel to Expose) | ประธาน | 0 | 0 | 2026-11-19 | 2025-09-30 | 100% | Completed | 2025-10-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39243 | MDW-69253 | MDW-69254
73 | - | Lot01 | GEN19 | GEN | Train Simulation Room and AFC Training Room | - | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
74 | MDW-39244 | Lot01 | GEN19.1 | GEN | Modification AFC Training Center at OR19 - Civil & AR | สหชาติ | 0 | 0 | 2026-11-30 | 2026-09-30 | 100% | Completed | 2026-10-31 | 58% | On Schedule | 0 | 0 | 0 |  | MDW-39244 | MDW-69255 | MDW-69256
75 | MDW-39245 | Lot01 | GEN19.2 | GEN | Modification AFC Training Center at OR19 - Building Services | ประธาน | บัณฑิต | 0 | 2026-11-30 | 2026-09-30 | 100% | Completed | 2026-10-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39245 | MDW-69257 | MDW-69258
76 | - | Lot01 | GEN20 | GEN | Dormitory Cable Containments (if any) | - | 0 | 0 | - | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
77 |  | Lot01 | GEN21 | GEN | Project Information Management System (PIMS) | บัณฑิต | 0 | 0 | 2024-09-30 | 2024-08-10 | 100% | Completed | 2024-08-15 | 100% | Completed | 0 | 0 | 0
78 | MDW-39237 | Lot01 | GEN22 | GEN | Central BEMS for the MRT Orange Line System | บัณฑิต | 0 | 0 | 2026-08-21 | 2026-04-30 | 0% | Late | 2026-06-30 | 0% | Late | 0 | 0 | 0 |  | MDW-39237 | MDW-69241 | MDW-69242
79 |  | Lot01 | GEN23 | GEN | Asset Information | บัณฑิต | 0 | 0 | 2026-11-19 | 0 | 0% | 0% | 2026-08-30 | 100% | Completed | 0 | 0 | 0
80 | MDW-39282 | Lot01 | PSD1 | PSD | Holes for PSD Cable Wiring | กำพล | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39282 | MDW-69315 | MDW-69316
81 | MDW-39004 | Lot01 | PSD2 | PSD | Rubber Gap Fillers on Platform Edge | กำพล | 0 | 0 | 2026-08-21 | 2025-07-30 | 100% | Completed | 2026-01-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39004 | MDW-69007 | MDW-69008
82 | MDW-39280 | Lot01 | PSD3 | PSD | Platform Finishing | กำพล | 0 | 0 | 2026-08-21 | 2025-07-30 | 100% | Completed | 2025-09-16 | 100% | Completed | 0 | 0 | 0 |  | MDW-39280 | MDW-69311 | MDW-69312
83 | MDW-39281 | Lot01 | PSD4 | PSD | Cladding Barrier between EWD and Station Structure | กำพล | 0 | 0 | 2026-08-21 | 2026-02-28 | 100% | Completed | 2026-03-15 | 100% | Completed | 0 | 0 | 0 |  | MDW-39281 | MDW-69313 | MDW-69314
84 | - | Lot01 | AFC1 | AFC | Park and Ride System | บัณฑิต/สหชาติ | 0 | 0 | 2026-10-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
85 | MDW-39276 | Lot01 | AFC2 | AFC | Ticket Issuing Machine (TIM) Wall Opening and Closing | สหชาติ | 0 | 0 | 2026-09-20 | 2026-01-30 | 100% | Completed | 2026-03-15 | 50% | Late | 0 | 0 | 0 |  | MDW-39276 | MDW-69303 | MDW-69304
86 | MDW-39279 | Lot01 | AFC3 | AFC | Balustrade Modification Along AFC Gate Line | สหชาติ | 0 | 0 | 2026-09-20 | 2026-06-30 | 10% | Late | 2026-08-15 | 50% | Late | 0 | 0 | 0 |  | MDW-39279 | MDW-69309 | MDW-69310
87 | MDW-39278 | Lot01 | AFC4 | AFC | Underfloor Embedded Duct Modification for AFC Gates Line | สหชาติ | 0 | Depot | 2026-09-20 | 2026-01-30 | 100% | Completed | 2026-04-02 | 67% | Late | 0 | 0 | 0 |  | MDW-39278 | MDW-69307 | MDW-69308
88 | MDW-39002 | Lot01 | SIG1 | SIG | Test Track Shelters and Test Track Building | สหชาติ | 0 | 0 | 2026-06-22 | 2025-11-22 | 100% | Completed | 2026-01-18 | 100% | Completed | 2026-02-28 | 100% | Completed |  | MDW-39002 | MDW-69003 | MDW-69004
89 | MDW-39293 | Lot01 | SIG2 | SIG | Rearrangement of track crossing walkway at stabling yard to consistent with the layout of 4-car train parking | กำพล | 0 | Depot | 2026-06-22 | 2025-11-30 | 100% | Completed | 2025-12-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39293 | MDW-69337 | MDW-69338
90 | MDW-39288 | Lot01 | SIG3 | SIG | Point Machine Foundation Construction | กำพล | 0 | 0 | 2026-08-21 | 2025-11-21 | 100% | Completed | 2025-12-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39288 | MDW-69327 | MDW-69328
91 | MDW-39001 | Lot01 | SIG4 | SIG | Modification of Depot Track Route Line to Stabling Yard | สู่โชค | 0 | Depot | 2026-06-22 | 2025-10-30 | 100% | Completed | 2025-11-29 | 100% | Completed | 0 | 0 | 0 |  | MDW-39001 | MDW-69001 | MDW-69002
92 | MDW-39287 | Lot01 | SIG5 | SIG | Strobe Light at Buffer Stops | ประธาน | 0 | Depot | 2026-08-21 | 2026-05-30 | 100% | Completed | 2026-06-29 | 100% | Completed | 0 | 0 | 0 |  | MDW-39287 | MDW-69323 | MDW-69324
93 | DWE-39016 | Lot01 | DWE1 | DWE | Diesel Fuel Storage Tank for Maintenance Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-01-16 | 100% | Completed | 2026-06-30 | 100% | Completed |  | DWE-39016 | DWE-69016 | DWE-69116
94 | DWE-39011 | Lot01 | DWE2 | DWE | Movable Height Maintenance Platform Vehicle (Boom Lift) | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-08-06 | 100% | Completed | 2025-12-31 | 100% | Completed |  | DWE-39011 | DWE-69011 | DWE-69111
95 | DWE-39012 | Lot01 | DWE3 | DWE | Fork Lift Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-03-31 | 100% | Completed | 2026-06-01 | 100% | Completed |  | DWE-39012 | DWE-69012 | DWE-69112
96 | DWE-39015 | Lot01 | DWE4 | DWE | Compressed Air System and Portable Air Compressor for Depot | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-01-10 | 100% | Completed | 2026-02-15 | 100% | Completed |  | DWE-39015 | DWE-69015 | DWE-69115
97 | DWE-39017 | Lot01 | DWE5 | DWE | Pallet Storage Shelves in Hazardous Storage | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-12-16 | 100% | Completed | 2026-02-28 | 100% | Completed |  | DWE-39017 | DWE-69017 | DWE-69117
98 | DWE-39017 | Lot01 | DWE6 | DWE | Pallet Storage in Main Storage Room | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-12-16 | 100% | Completed | 2026-02-28 | 100% | Completed |  | DWE-39017 | DWE-69017 | DWE-69117
99 | DWE-39017 | Lot01 | DWE7 | DWE | Two-Tier Shelf | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-12-16 | 100% | Completed | 2026-02-28 | 100% | Completed |  | DWE-39017 | DWE-69017 | DWE-69117
100 | DWE-39017 | Lot01 | DWE8 | DWE | Tool Storage | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-12-16 | 100% | Completed | 2026-02-28 | 100% | Completed |  | DWE-39017 | DWE-69017 | DWE-69117
101 | DWE-39018 | Lot01 | DWE9 | DWE | Repair Equipment | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-07-31 | 50% | Late | 2026-10-30 | 70% | On Schedule | คงเหลือจัดส่งอุปกรณ์ | DWE-39018 | DWE-69018 | DWE-69118
102 | DWE-39020 | Lot01 | DWE10 | DWE | Oil & Grease Disposal | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-01-16 | 100% | Completed | 2026-02-28 | 100% | Completed |  | DWE-39020 | DWE-69020 | DWE-69120
103 | DWE-39020 | Lot01 | DWE11 | DWE | Grease Dispensers | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-01-16 | 100% | Completed | 2026-04-28 | 100% | Completed |  | DWE-39020 | DWE-69020 | DWE-69120
104 | DWE-39020 | Lot01 | DWE12 | DWE | Waste Disposal | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-01-16 | 100% | Completed | 2026-02-28 | 100% | Completed |  | DWE-39020 | DWE-69020 | DWE-69120
105 | MDW-39305 | Lot01 | DWE13 | DWE | Safety Provision for Maintenance Pits | สหชาติ | 0 | Depot | 2026-09-20 | 2025-11-30 | 100% | Completed | 2026-04-29 | 100% | Completed | 0 | 0 | 0 |  | MDW-39305 | MDW-69361 | MDW-69362
106 | DWE-39xxx | Lot01 | DWE14 | DWE | Pit Drainage System in Main Workshop | สมศักดิ์ | 0 | Depot | 2026-09-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39xxx | MDW-69361 | MDW-69362
107 | DWE-39023 | Lot01 | DWE15 | DWE | Provision of Civil Works and Building Services to support Train Washing Equipment | สหชาติ | 0 | Depot | 2026-08-01 | 2025-11-30 | 100% | Completed | 2026-03-31 | 100% | Completed | 0 | 0 | 0 |  | DWE-39023 | DWE-69023 | DWE-69123
108 | DWE-39013 | Lot01 | DWE16 | DWE | Overhead Traveling Crane | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-04-30 | 100% | Completed | 2026-03-20 | 100% | Completed |  | DWE-39013 | DWE-69013 | DWE-69113-513
109 | DWE-39009 | Lot01 | DWE17 | DWE | Vehicle Inspection and Servicing Facilities | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-12-18 | 100% | Completed | 2026-09-07 | 100% | Completed |  | DWE-39009 | DWE-69009 | DWE-69109
110 | DWE-39014 | Lot01 | DWE18 | DWE | Permanent Way Maintenance Facility | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-04-30 | 100% | Completed | 2027-02-28 | 100% | Completed | 46402 | 0.7 | On Schedule | Test 18-30/1/27 | DWE-39014 | DWE-69014 | DWE-69114
111 | - | Lot01 | DWE19 | DWE | Permanent Way Vehicles | สมศักดิ์ | 0 | Depot | 2026-09-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
112 | DWE-39001 | Lot01 | DWE19.1 | DWE | Shunting Locomotive | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-12-18 | 100% | Completed | 2026-12-15 | 50% | On Schedule | Delivery to Thailand Feb-27 | DWE-39001 | DWE-69001 | DWE-69101
113 | DWE-39002 | Lot01 | DWE19.2 | DWE | Tunnel Inspection and Cleaning Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 0% | Late | 2025-12-18 | 100% | Completed | 2026-12-30 | 40% | On Schedule | Delivery to Thailand Feb-27 | DWE-39002 | DWE-69002 | DWE-69102
114 | DWE-39003 | Lot01 | DWE19.3 | DWE | Hi/Rail Maintenance Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-12-18 | 100% | Completed | 2026-11-30 | 55% | On Schedule | Delivery to Thailand Dec-26 | DWE-39003 | DWE-69003 | DWE-69103
115 | DWE-39004 | Lot01 | DWE19.4 | DWE | Flat wagon | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-12-18 | 100% | Completed | 2026-10-30 | 68% | On Schedule | Delivery to Thailand Dec-26 | DWE-39004 | DWE-69004 | DWE-69104
116 | DWE-39005 | Lot01 | DWE19.5 | DWE | Re-railing Equipment | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-11-10 | 100% | Completed | 2026-07-15 | 90% | Late | Test 16-22/11/26 | DWE-39005 | DWE-69005 | DWE-69105
117 | DWE-39006 | Lot01 | DWE19.6 | DWE | Self-Propelled Rail Based Inspection Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-12-18 | 100% | Completed | 2026-11-03 | 55% | On Schedule | Delivery to Thailand Dec-26 | DWE-39006 | DWE-69006 | DWE-69106
118 | DWE-39007 | Lot01 | DWE19.7 | DWE | Rail Head Grinding Machine Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 0% | Late | 2025-12-18 | 100% | Completed | 2027-07-31 | 0% | On Schedule | 0 | DWE-39007 | DWE-69007 | DWE-69107
119 | DWE-39008 | Lot01 | DWE19.8 | DWE | Multi Measuring Rail Vehicle | สมศักดิ์ | 0 | 0 | 2026-09-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39008 | DWE-69008 | DWE-69108
120 | DWE-39010 | Lot01 | DWE19.9 | DWE | High Work Inspection Vehicle | สมศักดิ์ | 0 | 0 | 2026-09-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39010
121 | - | Lot01 | DWE20 | DWE | Building Maintenance Vehicle | - | 0 | 0 | 2026-09-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
122 | EPS-39001 | Lot01 | PSY1 | PSY | Diesel Fuel Storage Tanks for Power Generators | สมศักดิ์ | 0 | 0 | 2026-03-24 | 2026-01-16 | 100% | Completed | 2026-03-31 | 100% | Completed | 2026-03-31 | 100% | Completed |  | EPS-39001 | EPS-69001 | EPS-69002
123 | PSY-39001-9 | Lot01 | PSY2 | PSY | GIS and BSS Building and Other Facilities | สหชาติ | 0 | 0 | 2026-03-24 | 2024-08-29 | 100% | Completed | 2024-09-28 | 69% | Late | 0 | 0 | 0 |  | PSY-39001 | PSY-69001 | PSY-69002
124 | PSY-39011 | Lot01 | PSY3 | PSY | Steel Grating Raised Floor for EE Panel | สหชาติ | 0 | 0 | 2026-03-24 | 2024-09-30 | 100% | Completed | 2024-10-30 | 75% | Late | 0 | 0 | 0 |  | PSY-39011 | PSY-69015 | PSY-69016
125 | - | Lot01 | PSY4 | PSY | Trapping Box between PSY Service Sub Station (SSS) and Low Volt (LV) System | - | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
126 | SCA-39200 | Lot01 | SCA1 | SCA | Modification of BEMS to receive PSD Signal on East Section | ธารทิพย์ | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | SCA-39200 | SCA-69200 | SCA-69201
127 | - | Lot01 | SCA2 | SCA | Modification of Escalator Interface Point with CCTV and SCADA, East Section | - | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
128 | - | Lot01 | SCA3 | SCA | Magnetic of Fire Alarm System Interface Point with CCTV and SCADA | - | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
129 | SCA-39203 | Lot01 | SCA4 | SCA | Add/Modify Civil Scada Hardwire for all Station | ประธาน/ธารทิพย์ | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | SCA-39203 | SCA-69206 | SCA-69207
130 | COM-39200 | Lot01 | COM1 | COM | Magnetic Door Lock | มนตรี | 0 | 0 | 2026-08-21 | 2025-06-30 | 100% | Completed | 2026-05-15 | 100% | Completed | 0 | 0 | 0 |  | COM-39200 | COM-69200 | COM-69201
131 | MDW-39283 | Lot01 | COM2 | COM | Intercom System in Cash Handling Room (if require) | บัณฑิต | 0 | 0 | 2026-12-19 | 2025-09-30 | 100% | Completed | 2026-06-30 | 50% | Late | 0 | 0 | 0 |  | MDW-39283 | MDW-69317 | MDW-69318
132 | COM-39001 | Lot01 | COM3 | COM | Walk-Through Metal Detector System (WTMD), 1 per entrance | มนตรี | 0 | 0 | 2026-11-19 | 2025-08-31 | 0% | Late | 2026-06-30 | 0% | Late | 0 | 0 | 0 |  | COM-39001 | COM-69001 | COM-69002
133 | MDW-39284 | Lot01 | COM4 | COM | Traveling Cable in all Lifts | มนตรี | 0 | 0 | - | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39284 | MDW-69319 | MDW-69320
134 | MDW-39304 | Lot01 | COM5 | COM | MEA Radio | ประธาน | 0 | 0 | 2026-09-20 | 2026-01-30 | 100% | Completed | 2026-04-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39304 | COM-69202 | COM-69203
135 | COM-39004 | Lot01 | COM6 | COM | Main Cable Containment for M&E Dedicated communication link to MRTA Head Quarter | มนตรี | 0 | 0 | 2026-09-20 | 2026-01-31 | 100% | Completed | 2026-02-28 | 100% | Completed | 0 | 0 | 0 |  | COM-39004 | COM-69005 | COM-69006
136 | AFC-39001 | Lot01 | COM7 | COM | Mini Paging in Ticket Office | บัณฑิต | 0 | 0 | 2026-12-19 | 2025-09-10 | 100% | Completed | 2026-06-30 | 100% | Completed | 0 | 0 | 0 |  | AFC-39002 | AFC-69003 | AFC-69004
137 | MDW-39285 | Lot01 | COM8 | COM | Provision of Cable Containment between OCC ORL and OCC BL | มนตรี | 0 | 0 | 2026-07-22 | 0 | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 |  | MDW-39285
138 | COM-39005 | Lot01 | COM9 | COM | Power Distribution for M&E Systems at MRTA Head Quarter | มนตรี | 0 | 0 | 2026-09-20 | 2026-03-31 | 100% | Completed | 2026-06-30 | 100% | Completed | 0 | 0 | 0 |  | COM-39005 | COM-69007 | COM-69008
139 | COM-39205 | Lot01 | COM10 | COM | Underground Cable Containment at Public Areas (if require) | มนตรี | 0 | 0 | 2026-08-21 | 2026-04-30 | 100% | Completed | 2026-07-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39205 | MDW-69200 | MDW-69205
140 | - | Lot01 | COM11 | COM | Intercom at Ticket Issuing Machine | บัณฑิต | 0 | Depot | - | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
141 | RST-39004,8 | Lot01 | RST1 | RST | Driver Training Simulator | ธัญวิทย์ | 0 | Depot | 2026-09-20 | 2025-05-30 | 100% | Completed | 2025-06-30 | 100% | Completed | 0 | 0 | 0 |  | RST-39004,8
142 | MDW-39500 | Lot02 | MO-CK1.1 | MO-CK | Store Modification Works at Main Workshop - Civil&AR | สหชาติ | 0 | Depot | 2026-06-03 | 2026-02-27 | 100% | Completed | 2026-03-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39500 | MDW-69500 | MDW-69501
143 | MDW-39501 | Lot02 | MO-CK1.2 | MO-CK | Store Modification Works at Main Workshop - Building Services | ประธาน | 0 | Depot | 2026-06-04 | 2026-02-12 | 100% | Completed | 2026-03-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39501 | MDW-69502 | MDW-69503
144 | MDW-39503 | Lot02 | MO-CK2 | MO-CK | New MMC at Admin Building - Civil&AR | สหชาติ | 0 | Depot | 2026-08-03 | 2026-04-14 | 100% | Completed | 2026-05-15 | 100% | Completed | 0 | 0 | 0 |  | MDW-39503 | MDW-69506 | MDW-69507
145 | MDW-39504 | Lot02 | MO-CK3 | MO-CK | Move or link Workstation and control panel to MMC room at admin C 2nd floor | ประธาน | 0 | Depot | 2026-08-02 | 2026-02-28 | 100% | Completed | 2026-04-15 | 100% | Completed | 0 | 0 | 0 |  | MDW-39504 | MDW-69508 | MDW-69509
146 | MDW-39543 | Lot02 | MO-CK4 | MO-CK | Bird & Rain Protection for Open space Admin C | สหชาติ | 0 | Depot | 2026-08-01 | 2026-04-29 | 100% | Completed | 2026-05-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39543 | MDW-69586 | MDW-69587
147 | MDW-39547 | Lot02 | MO-CK5 | MO-CK | Relocate door in front of toilet and build partition wall to conceal the view in side of toilet | สหชาติ | 0 | Depot | 2026-08-02 | 2026-05-14 | 100% | Completed | 2026-06-14 | 100% | Completed | 0 | 0 | 0 |  | MDW-39547 | MDW-69594 | MDW-69595
148 | MDW-39547 | Lot02 | MO-CK6 | MO-CK | Modify Lockset the emergency door to be used for passage between the 2nd and 3rd floors inside the building. | สหชาติ | 0 | Depot | 2026-08-03 | 2026-04-29 | 100% | Completed | 2026-06-14 | 100% | Completed | 0 | 0 | 0 |  | MDW-39547 | MDW-69594 | MDW-69595
149 | MDW-39556 | Lot02 | MO-CK7 | MO-CK | Addition small power for lounge and pantry room at 2nd floor and Hall and observation room at 3nd floor | ประธาน | 0 | Depot | 2026-08-04 | 2026-05-14 | 100% | Completed | 2026-06-14 | 100% | Completed | 0 | 0 | 0 |  | MDW-39556 | MDW-69612 | MDW-69613
150 | MDW-39548 | Lot02 | MO-CK8 | MO-CK | Air Condition for using store room to be pantry room. 2nd floor | ประธาน | 0 | Depot | 2026-08-05 | 2026-04-29 | 100% | Completed | 2026-06-14 | 100% | Completed | 0 | 0 | 0 |  | MDW-39548 | MDW-69596 | MDW-69597
151 | MDW-39552 | Lot02 | MO-CK9 | MO-CK | Walk Way Hand rail high 90 cm 1 side (144 m. x 7 route) | สหชาติ | 0 | Depot | 2026-10-01 | 2026-05-30 | 100% | Completed | 2026-06-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39552 | MDW-69604 | MDW-69605
152 | MDW-39544 | Lot02 | MO-CK10 | MO-CK | Barbed wire fence Viaduct CE CW | บัณฑิต/สหชาติ | พี่ต่อ | Depot | 2027-01-01 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39544 | MDW-69588 | MDW-69589
153 | MDW-39545 | Lot02 | MO-CK11 | MO-CK | Chain Link at Cut & Cover 600m. | สหชาติ | พรพรหม | Depot | 2026-06-01 | 2026-02-27 | 100% | Completed | 2026-04-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39545 | MDW-69590 | MDW-69591
154 | MDW-39546 | Lot02 | MO-CK12 | MO-CK | Chain Link under slab high 1.70 m | สหชาติ | 0 | 0 | 2027-01-01 | 2026-06-30 | 100% | Completed | 2026-07-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39546 | MDW-69592 | MDW-69593
155 | MDW-39550 | Lot02 | MO-CK13.1 | MO-CK | Satellite Store at OR21 - Civil & AR | สหชาติ | 0 | 0 | 2027-01-02 | 2026-08-30 | 100% | Completed | 2026-10-15 | 0% | Late | 0 | 0 | 0 |  | MDW-39550 | MDW-69600 | MDW-695601
156 | MDW-39549 | Lot02 | MO-CK13.2 | MO-CK | Maintenance Room and Satellite Store at Stations - Building Services | ประธาน | 0 | 0 | 2027-01-03 | 2026-08-30 | 100% | Completed | 2026-10-15 | 100% | Completed | 0 | 0 | 0 |  | MDW-39549 | MDW-69598 | MDW-69599
157 | MDW-39551 | Lot02 | MO-CK14 | MO-CK | Modify Cleaner room at OR29 to be Train crew Standby office with facility system | ประธาน | 0 | Depot | 2026-07-01 | 2026-03-14 | 100% | Completed | 2026-04-29 | 100% | Completed | 0 | 0 | 0 |  | MDW-39551 | MDW-69602 | MDW-69603
158 | MDW-39295 | Lot02 | MO-CK15.1 | MO-CK | Epoxy Floor Installation and Curb Installation at the Entrance - Civil & AR | สหชาติ | 0 | Depot | 2026-05-01 | 2026-01-27 | 100% | Completed | 2026-02-27 | 100% | Completed | 0 | 0 | 0 |  | MDW-39295 | MDW-69341 | MDW-69342
159 | MDW-39296 | Lot02 | MO-CK15.2 | MO-CK | Change Electrical Equipment to be Explosion-proof type - Building Services | ประธาน | 0 | Depot | 2026-05-01 | 2025-12-13 | 100% | Completed | 2026-01-28 | 100% | Completed | 0 | 0 | 0 |  | MDW-39296 | MDW-69343 | MDW-69344
160 | DWE-39024 | Lot02 | MO-CK16 | MO-CK | Dangerous waste Storage 30 x 5 m. =10 room | สหชาติ | 0 | Depot | 2026-05-01 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed | 0 | 0 | 0 |  | DWE-39024 | DWE-69024 | DWE-69124
161 | 0 | Lot02 | MO-CK17 | MO-CK | Safety Sign all Depot Area building | สหชาติ | 0 | Depot | 2026-05-01 | 2025-11-28 | 100% | Completed | 2026-06-15 | 100% | Completed | 2026-09-20 | 27% | Late | GRS |  | 0 | 0
162 | 0 | Lot02 | MO-CK18 | MO-CK | Emergency escape route map | สหชาติ | 0 | Depot | 2027-01-01 | 2026-09-30 | 0% | Late | 2026-10-30 | 50% | On Schedule | 2026-12-31 | 0% | On Schedule | GRS |  | 0 | 0
163 | 0 | Lot02 | MO-CK19 | MO-CK | Traffic Line Marking (Thermoplastic Paint) | สหชาติ | 0 | Depot | 2026-05-01 | 2026-04-30 | 100% | Completed | 2026-06-15 | 100% | Completed | 2026-10-15 | 100% | Completed |  |  | 0 | 0
164 | 0 | Lot02 | MO-CK20 | MO-CK | Emergency Car Parking location Painting in front of MWS | สหชาติ | 0 | Depot | 2026-05-01 | 2026-04-30 | 100% | Completed | 2026-06-15 | 100% | Completed | 2026-10-15 | 0% | Late | GRS |  | 0 | 0
165 | GRS-39022 | Lot02 | MO-CK21 | MO-CK | Safety Line painting in MWS, Stabling Area, P-way, Track | สหชาติ | 0 | Depot | 2027-01-01 | 2026-06-01 | 100% | Completed | 2026-08-01 | 100% | Completed | 46310 | 1 | Completed |  | GRS-39022 | GRS-69001 | GRS-69022
166 | 0 | Lot02 | MO-CK22 | MO-CK | Fire escape stairs level signs in the Depot, VS and IVS areas | สหชาติ | 0 | Depot | 2027-01-01 | 2026-09-30 | 50% | Late | 2026-10-31 | 0% | On Schedule | 2026-10-20 | 0% | Late | GRS |  | 0 | 0
167 | DWE-39026 | Lot02 | MO-CK23 | MO-CK | General waste Storage 22 x 5 m | สหชาติ | 0 | Depot | 2026-05-01 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed | 0 | 0 | 0 |  | DWE-39026 | DWE-69026 | DWE-69126
168 | 0 | Lot02 | MO-CK24 | MO-CK | Modify Traffic paint and traffic sign | สหชาติ | 0 | 0 | 2026-05-01 | 2026-04-30 | 100% | Completed | 2026-06-15 | 100% | Completed | 2026-10-15 | 64% | Late | GRS |  | 0 | 0
169 | 0 | Lot02 | MO-CK25 | MO-CK | Station Area sign 28 stations | สหชาติ | 0 | 0 | 2026-05-01 | 2026-06-15 | 80% | Late | 2026-06-30 | 100% | Completed | 2026-09-30 | 0% | Late | GRS |  | 0 | 0
170 |  | Lot02 | MO-CK26 | MO-CK | Safety and warning signage for lift and escalator at all station | สหชาติ | 0 | Depot | 2027-01-01 | 2026-06-16 | 100% | Completed | 2026-07-17 | 100% | Completed | 2027-01-31 | 76% | On Schedule | GRS
171 | MDW-39532 | Lot02 | MO-CK27 | MO-CK | Spike fence for Depot slab | สหชาติ | 0 | Depot | 2027-01-01 | 2026-07-31 | 70% | Late | 2026-08-31 | 0% | Late | 0 | 0 | 0 |  | MDW-39532 | MDW-69564 | MDW-69565
172 | 0 | Lot02 | MO-CK28 | MO-CK | Bird net and Flashing at MWS and Skywalk to Stabling yard | สหชาติ | 0 | 0 | 2026-05-01 |  |  | 0% |  |  | 0% | 0 | 0 | 0 |  |  | 0 | 0
173 | MDW-39541 | Lot02 | MO-CK29 | MO-CK | Fire Alarm Manual Call Point signage at all elevated station | สหชาติ | 0 | 0 | 2027-01-01 |  |  | 0% | 2026-07-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39541 | MDW-69582 | MDW-69583
174 | 0 | Lot02 | MO-CK30 | MO-CK | Lighting for sealed space under stairs and behind lift shaft at underground station | ประธาน | 0 | 0 | 2027-01-01 | 2026-10-14 | 0% | Late | 2026-11-14 | 0% | On Schedule | 0 | 0 | 0 |  |  | 0 | 0
175 | 0 | Lot02 | MO-CK31 | MO-CK | Modify the access door of sealed space (under-stairs room) with a Sump Pump or ESPS cabinet | สหชาติ | 0 | 0 | 2027-01-01 | 2026-07-16 | 0% | Late | 2026-08-16 | 0% | Late | 0 | 0 | 0 |  |  | 0 | 0
176 | 0 | Lot02 | MO-CK32 | MO-CK | Lighting to the sealed space (under-stairs room) with a Sump Pump or ESPS cabinet | ประธาน | 0 | Depot | 2027-01-01 | 2026-11-03 | 0% | On Schedule | 2026-12-04 | 0% | On Schedule | 0 | 0 | 0 |  |  | 0 | 0
177 | 0 | Lot02 | MO-CK33 | MO-CK | Additional lighting in areas where the lux level does not meet occupational health standards | ประธาน | 0 | Depot | 2027-01-01 | 2026-09-14 | 100% | Completed | 2026-10-15 | 100% | Completed | 0 | 0 | 0 |  |  | 0 | 0
178 | 0 | Lot02 | MO-CK34 | MO-CK | Provide and install confined space signage for Station and Depot | สหชาติ | 0 | 0 | 2027-01-01 | 2026-08-15 | 100% | Completed | 2026-09-15 | 100% | Completed | 2027-01-31 | 76% | On Schedule | GRS |  | 0 | 0
179 |  | Lot02 | MO-CK35 | MO-CK | Build room for Train crew main office at OR18 with office area, resting area, meeting room, pantry, toilet and locker room | สหชาติ/บัณฑิต/ประธาน | 0 | Depot | - |  |  | 0% |  |  | 0% | 0 | 0 | 0
180 |  | Lot02 | MO-CK36 | MO-CK | Dormitory Cable Containments (if any) | มนตรี | 0 | Depot | - |  |  | 0% |  |  | 0% | 0 | 0 | 0
181 | 0 | Lot02 | MO-CK37 | MO-CK | Provide Raise floor and building Service in Training &Simulator (OCC Admin) | สหชาติ | 0 | Depot | - | 0% | 0% | 0% |  |  |  | 0 | 0 | 0 |  |  | 0 | 0
182 |  | Lot02 | MO-CK38 | MO-CK | Add N2 in Playback and Training Room and Backup Control Room | บุญประเสริฐ | 0 | Depot | - |  |  | 0% |  |  | 0% | 0 | 0 | 0
183 | MDW-39505 | Lot02 | MO-BEM1.1 | MO-BEM | Walkway from Main Work Shop to Stabling Area - Civil & AR | สหชาติ | 0 | Depot | 2026-08-02 | 2026-04-28 | 100% | Completed | 2026-05-29 | 92% | Late | 0 | 0 | 0 |  | MDW-39505 | MDW-69510 | MDW-69511
184 | MDW-39506 | Lot02 | MO-BEM1.2 | MO-BEM | Walkway from Main Work Shop to Stabling Area - Building Services | ประธาน | 0 | Depot | 2026-08-02 | 2026-04-28 | 100% | Completed | 2026-05-29 | 100% | Completed | 0 | 0 | 0 |  | MDW-39506 | MDW-69512 | MDW-69513
185 | MDW-39507 | Lot02 | MO-BEM2 | MO-BEM | High Roof at Main Work Shop Entrance and Store | สหชาติ | 0 | Depot | 2026-08-01 | 2026-02-13 | 100% | Completed | 2026-03-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39507 | MDW-69514 | MDW-69515
186 | MDW-39509 | Lot02 | MO-BEM3 | MO-BEM | High Roof at the entrance and exit of the under floor wheel lathe | สหชาติ | 0 | Depot | 2026-08-04 | 2026-02-13 | 100% | Completed | 2026-03-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39509 | MDW-69518
187 | MDW-39511 | Lot02 | MO-BEM4.1 | MO-BEM | Maintenance Office Rooms at Main Workshop - Civil & AR | สหชาติ | 0 | Depot | 2026-07-03 | 2026-04-13 | 100% | Completed | 2026-05-14 | 100% | Completed | 0 | 0 | 0 |  | MDW-39511 | MDW-69522 | MDW-69523
188 | MDW-39512 | Lot02 | MO-BEM4.2 | MO-BEM | Maintenance Office Rooms at Main Workshop - Building Services | ประธาน | 0 | Depot | 2026-07-04 | 2026-04-13 | 100% | Completed | 2026-05-14 | 100% | Completed | 0 | 0 | 0 |  | MDW-39512 | MDW-69524 | MDW-69525
189 | MDW-39513 | Lot02 | MO-BEM5 | MO-BEM | Install Concrete car barrier along the walkway in front of MWS building | สหชาติ | 0 | Depot | 2027-01-01 | 2026-10-14 | 100% | Completed | 2026-11-14 | 100% | Completed | 0 | 0 | 0 |  | MDW-39513 | MDW-69526 | MDW-69527
190 | 0 | Lot02 | MO-BEM6 | MO-BEM | Handrail on top of the water tank on the rooftop of the Admin Building | สหชาติ | 0 | Depot | 2027-01-01 | 2026-10-19 | 100% | Completed | 2026-11-19 | 100% | Completed | 0 | 0 | 0 |  |  | 0 | 0
191 | 0 | Lot02 | MO-BEM7 | MO-BEM | Modify maintenance service door to the roof building to easier access while maintaining safe operational standards | สหชาติ | 0 | Depot | 2027-01-01 | 2026-10-19 | 50% | Late | 2026-11-19 | 0% | On Schedule | 0 | 0 | 0 |  |  | 0 | 0
192 | MDW-39536 | Lot02 | MO-BEM8 | MO-BEM | Company logo and Central Control Room sign in CCR room. | สหชาติ | 0 | Depot | 2026-05-01 | 2026-01-27 | 100% | Completed | 2026-03-14 | 100% | Completed | 0 | 0 | 0 |  | MDW-39536 | MDW-69572 | MDW-69573
193 | MDW-39536 | Lot02 | MO-BEM9 | MO-BEM | Soundproof insulation on the wall and structure and equipment in the CCR room. | สหชาติ | 0 | Depot | 2026-05-01 | 2026-01-12 | 100% | Completed | 2026-02-27 | 100% | Completed | 0 | 0 | 0 |  | MDW-39536 | MDW-69572 | MDW-69573
194 | MDW-39526 | Lot02 | MO-BEM10 | MO-BEM | Relocate Fire Hose Cabinet to be outside of the clearance gauge zone 17 set | ประธาน | 0 | Depot | 2026-05-01 | 2026-01-12 | 100% | Completed | 2026-02-27 | 100% | Completed | 0 | 0 | 0 |  | MDW-39526 | MDW-69552 | MDW-69553
195 | MDW-39528 | Lot02 | MO-BEM11.1 | MO-BEM | Washing Area in Cleaning Staff Room at Stabling Yard - Civil & AR | สหชาติ | 0 | Depot | 2026-08-03 | 2026-06-03 | 100% | Completed | 2026-07-04 | 100% | Completed | 0 | 0 | 0 |  | MDW-39528 | MDW-69556 | MDW-69557
196 | MDW-39529 | Lot02 | MO-BEM11.2 | MO-BEM | Washing Area in Cleaning Staff Room at Stabling Yard - Building Services | ประธาน | 0 | Depot | 2026-08-04 | 2026-04-14 | 100% | Completed | 2026-05-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39529 | MDW-69558 | MDW-69559
197 | MDW-39522 | Lot02 | MO-BEM12 | MO-BEM | Rain protection for Water treatment Building | สหชาติ | 0 | Depot | 2026-08-05 | 2026-04-29 | 100% | Completed | 2026-05-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39522 | MDW-69544 | MDW-69545
198 | MDW-39522 | Lot02 | MO-BEM13.1 | MO-BEM | Zero Discharge Water treatment in Depot - Civil & AR | สหชาติ | 0 | Depot | 2027-01-01 | 2026-08-15 | 100% | Completed | 2026-09-30 | 75% | Late | 0 | 0 | 0 |  | MDW-39522 | MDW-69544 | MDW-69545
199 | MDW-39530 | Lot02 | MO-BEM13.2 | MO-BEM | Zero Discharge Water treatment in Depot - Building Services | ประธาน | 0 | Depot | 2027-01-01 | 2026-08-15 | 100% | Completed | 2026-09-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39530 | MDW-69560 | MDW-69561
200 | MDW-39516 | Lot02 | MO-BEM14.1 | MO-BEM | Modification Works : Walkway Bridge between BL Depot and ORL Depot - Civil & AR | สหชาติ | 0 | Depot | 2026-08-02 | 2026-02-28 | 100% | Completed | 2026-06-15 | 100% | Completed | 0 | 0 | 0 |  | MDW-39516 | MDW-69532 | MDW-69533
201 | MDW-39517 | Lot02 | MO-BEM14.2 | MO-BEM | Modification Works : Walkway Bridge between BL Depot and ORL Depot - Building Services | ประธาน | 0 | Depot | 2026-08-03 | 2026-01-14 | 100% | Completed | 2026-03-01 | 100% | Completed | 0 | 0 | 0 |  | MDW-39517 | MDW-69534 | MDW-69535
202 | MDW-39514 | Lot02 | MO-BEM15.1 | MO-BEM | Roof for cars parking lots area (184 car)t - Civil & AR | สหชาติ | 0 | Depot | 2026-08-03 | 2026-02-28 | 100% | Completed | 2026-03-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39514 | MDW-69528 | MDW-69529
203 | MDW-39515 | Lot02 | MO-BEM15.2 | MO-BEM | Roof for cars parking lots area (184 car) - Building Services | ประธาน | 0 | Depot | 2026-08-03 | 2026-02-28 | 100% | Completed | 2026-03-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39515 | MDW-69530 | MDW-69531
204 | MDW-39519 | Lot02 | MO-BEM16 | MO-BEM | Walkway roof and High roof across the road from Admin ORL to Depot slap | สหชาติ | 0 | Depot | 2026-08-01 | 2026-06-15 | 100% | Completed | 2026-06-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39519 | MDW-69538 | MDW-69539
205 | MDW-39519 | Lot02 | MO-BEM17 | MO-BEM | Walkway roof to car park in front of admin ORL(3x5m.) | สหชาติ | 0 | Depot | 2026-08-01 | 2026-06-15 | 100% | Completed | 2026-06-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39519 | MDW-69538 | MDW-69539
206 | MDW-39519 | Lot02 | MO-BEM18 | MO-BEM | Walkway roof over the footpath near depot slab (1.50 m. x 290 m.) and stair up to depot slap. | สหชาติ | 0 | Depot | 2026-08-01 | 2026-06-15 | 100% | Completed | 2026-06-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39519 | MDW-69538 | MDW-69539
207 | MDW-39557 | Lot02 | MO-BEM19 | MO-BEM | Install Chain Link fence to enclose parking area | สหชาติ | 0 | Depot | 2026-10-01 | 2026-06-29 | 100% | Completed | 2026-07-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39557 | MDW-69614 | MDW-69615
208 | MDW-39523 | Lot02 | MO-BEM20 | MO-BEM | Hose bib 1/2" 4 sets for Tree around Admin area | ประธาน | 0 | Depot | 2026-06-01 | 2026-04-23 | 100% | Completed | 2026-06-08 | 100% | Completed | 0 | 0 | 0 |  | MDW-39523 | MDW-69546 | MDW-69547
209 | - | Lot02 | MO-BEM21 | MO-BEM | Relocate Security Guard Box at Front Gate and Install Roof 3x5m. | สหชาติ | 0 | Depot | 2027-01-03 | 2026-07-31 | 100% | Completed | 2026-09-30 | 75% | Late | 0 | 0 | 0 |  |  | 0 | 0
210 | MDW-39534 | Lot02 | MO-BEM21.1 | MO-BEM | Modification Works : Security Guard Box at ORL Depot Entrance - Civil & AR | สหชาติ | 0 | Depot | 2027-01-02 | 2026-07-31 | 100% | Completed | 2026-09-30 | 67% | Late | 0 | 0 | 0 |  | MDW-39534 | MDW-69568 | MDW-69569
211 | MDW-39535 | Lot02 | MO-BEM21.2 | MO-BEM | Modification Works : Security Guard Box at ORL Depot Entrance - Building Services | ประธาน | 0 | Depot | 2027-01-03 | 2026-07-31 | 100% | Completed | 2026-09-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39535 | MDW-69570 | MDW-69571
212 | MDW-39532 | Lot02 | MO-BEM22 | MO-BEM | Addition Spike fence for MRTA fence and Chain link at Klong Chourdyai 400m. | สหชาติ | 0 | Depot | 2027-01-01 | 2026-08-30 | 70% | Late | 2026-09-30 | 0% | Late | 0 | 0 | 0 |  | MDW-39532 | MDW-69564 | MDW-69565
213 | MDW-39527 | Lot02 | MO-BEM23 | MO-BEM | Hand sink with eye wash station | ประธาน | พี่ต่อ | Depot | 2027-01-01 | 2026-08-30 | 100% | Completed | 2026-10-15 | 100% | Completed | 0 | 0 | 0 |  | MDW-39527 | MDW-69554 | MDW-69555
214 | MDW-39531 | Lot02 | MO-BEM24 | MO-BEM | Guard rail protection for Fire Hose Cabinet 8 set | สหชาติ | 0 | Depot | 2026-06-01 | 2026-03-14 | 100% | Completed | 2026-04-14 | 100% | Completed | 0 | 0 | 0 |  | MDW-39531 | MDW-69562 | MDW-69563
215 | MDW-39557 | Lot02 | MO-BEM25.1 | MO-BEM | Chain Link Fence to divide controlled areas on Depot slab 3 m.x 485 m. - Civil & AR | สหชาติ | 0 | Depot | 2026-10-01 | 2026-06-14 | 100% | Completed | 2026-07-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39557 | MDW-69614 | MDW-69615
216 | MDW-39520 | Lot02 | MO-BEM25.2 | MO-BEM | Chain Link Fence to divide controlled areas on Depot slab 3 m.x 485 m.- Building Services | ประธาน | 0 | Depot | 2026-10-01 | 2026-06-14 | 100% | Completed | 2026-07-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39520 | MDW-69540 | MDW-69541
217 | MDW-39518 | Lot02 | MO-BEM26 | MO-BEM | Street Lighting system area between MRTA Fence and Depot slab | ประธาน | 0 | Depot | 2026-08-01 | 2026-04-14 | 50% | Late | 2026-05-15 | 0% | Late | 0 | 0 | 0 |  | MDW-39518 | MDW-69536 | MDW-69537
218 | - | Lot02 | MO-BEM27 | MO-BEM | Compacted gravel walkway along the Test Track OR-BL 1.2 m. | สหชาติ | พรพรหม | Depot | 2027-01-01 | 2026-08-30 | 100% | Completed | 2026-09-30 | 0% | Late | 0 | 0 | 0 |  |  | 0 | 0
219 | MDW-39524 | Lot02 | MO-BEM28.1 | MO-BEM | Walkway under Depot Slab for Maintenance Service - Civil & AR | สหชาติ | 0 | Depot | 2027-01-02 | 2026-09-14 | 100% | Completed | 2026-10-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39524 | MDW-69548 | MDW-69549
220 | MDW-39525 | Lot02 | MO-BEM28.2 | MO-BEM | Walkway under Depot Slab for Maintenance Service - Building Services | ประธาน | 0 | Depot | 2027-01-03 | 2026-09-14 | 100% | Completed | 2026-10-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39525 | MDW-69550 | MDW-69551
221 | MDW-39521 | Lot02 | MO-BEM29 | MO-BEM | Walkway Bridge across the canal for Depot area inspection patrols 3 location | สหชาติ | 0 | Depot | 2027-01-01 | 2026-08-15 | 100% | Completed | 2026-09-30 | 67% | Late | 0 | 0 | 0 |  | MDW-39521 | MDW-69542 | MDW-69543
222 | - | Lot02 | MO-BEM30 | MO-BEM | Cut down trees between Depot BL+ORL and MRTA Fence | สหชาติ | 0 | Depot | 2027-01-01 | 2026-10-29 | 0% | Late | 2026-11-29 | 0% | On Schedule | 0 | 0 | 0 |  |  | 0 | 0
223 | 0 | Lot02 | MO-BEM31 | MO-BEM | Provide facility system and interface to MMC room (Fire Alarm / CCTV / VMS / TEL / CASS / Radio / PA) | บัณฑิต | 0 | Depot | 2026-10-01 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
224 | - | Lot02 | MO-BEM32 | MO-BEM | Stainless Guard rail balustrade for waiting area | สหชาติ | 0 | Depot | 2026-05-01 |  |  | 0% |  |  | 0% | 0 | 0 | 0 |  |  | 0 | 0
225 | - | Lot02 | MO-BEM33 | MO-BEM | Concrete walkway 2 x 80 m. For fire escape route | สหชาติ | 0 | Depot | 2026-05-01 |  |  | 0% |  |  | 0% | 0 | 0 | 0 |  |  | 0 | 0
226 | - | Lot02 | MO-BEM34 | MO-BEM | Access Gate (Full Height Turnstile) at 1st floor admin ORL | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 0 | 0 | 0 |  |  | 0 | 0
227 | - | Lot02 | MO-BEM35 | MO-BEM | Access Gate (Tripod with Swing Gate) at MWS Entrance | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 0 | 0 | 0 |  |  | 0 | 0
228 | - | Lot02 | MO-BEM36 | MO-BEM | Access Gate (Tripod with Swing Gate) at Admin 2nd floor connect to OCC | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 0 | 0 | 0 |  |  | 0 | 0
229 | - | Lot02 | MO-BEM37 | MO-BEM | Access Gate (Tripod with Swing Gate) on Klong Chourdyai bridge | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 0 | 0 | 0 |  |  | 0 | 0
230 | - | Lot02 | MO-BEM38 | MO-BEM | Access Gate (Tripod with roof covering) at parking lot OCC | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 0 | 0 | 0 |  |  | 0 | 0
231 | - | Lot02 | MO-BEM39 | MO-BEM | Access Gate (Tripod with roof covering) at Stair up to Depot slab | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 0 | 0 | 0 |  |  | 0 | 0
232 | - | Lot02 | MO-BEM40 | MO-BEM | Access Control (2 Factors, Card + Finger Print) at High Security rooms - CCR/PTR/Store | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 0 | 0 | 0 |  |  | 0 | 0
233 | - | Lot02 | MO-BEM41 | MO-BEM | Link CCTV Landscape of all depot ORL area for MMC BL monitoring. | บัณฑิต | 0 | 0 | 2027-01-01 | 2026-11-28 | 0% | On Schedule | 2026-11-29 | 0% | On Schedule | 0 | 0 | 0 |  |  | 0 | 0
234 | - | Lot02 | MO-BEM42 | MO-BEM | Fire Suppression Control Panel Cover which located in tunnel | สู่โชค | 0 | 0 | 2027-01-01 |  |  | 0% |  |  | 0% | 0 | 0 | 0 |  |  | 0 | 0
235 | MDW-39537 | Lot02 | MO-BEM43 | MO-BEM | Handrails for ladder at IVS and Vent buildings | สหชาติ | 0 | 0 | 2026-09-01 | 2026-03-31 | 70% | Late | 2026-05-01 | 0% | Late | 0 | 0 | 0 |  | MDW-39537 | MDW-69574 | MDW-69575
236 | MDW-39538 | Lot02 | MO-BEM44 | MO-BEM | Escalator Anti-Slide device for all station. | สหชาติ | 0 | 0 | 2026-09-01 | 2026-05-30 | 100% | Completed | 2026-06-30 | 100% | Completed | 2027-01-31 | 100% | Completed |  | MDW-39538 | MDW-69576 | MDW-69577
237 | MDW-39539 | Lot02 | MO-BEM45 | MO-BEM | Roof for control panel on vent building | สหชาติ | 0 | 0 | 2027-01-01 | 2026-09-14 | 70% | Late | 2026-10-30 | 0% | On Schedule | 0 | 0 | 0 |  | MDW-39539 | MDW-69578 | MDW-69579
238 | MDW-39553 | Lot02 | MO-BEM46 | MO-BEM | Provide Standing plate or ladder to access the Fire Valve in at Omega points for all underground stations. | สหชาติ | 0 | Depot | 2027-01-01 | 2026-09-14 | 0% | Late | 2026-10-30 | 0% | On Schedule | 0 | 0 | 0 |  | MDW-39553 | MDW-69606 | MDW-69607
239 | MDW-39540 | Lot02 | MO-BEM47 | MO-BEM | Water drop protection above UPS cabinet at station and Depot | สหชาติ | 0 | 0 | 2027-01-01 | 2026-09-14 | 0% | Late | 2026-10-30 | 0% | On Schedule | 0 | 0 | 0 |  | MDW-39540 | MDW-69580 | MDW-69581
240 | MDW-39541 | Lot02 | MO-BEM48 | MO-BEM | Fire alarm manual call point cover in public area at all station | ประธาน | 0 | 0 | 2027-01-01 | 2026-09-14 | 50% | Late | 2026-10-30 | 0% | On Schedule | 0 | 0 | 0 |  | MDW-39541 | MDW-69582 | MDW-69583
241 | MDW-39542 | Lot02 | MO-BEM49 | MO-BEM | Emergency stop button cover for escalator at all station. | สหชาติ | 0 | 0 | 2027-01-01 | 2026-09-14 | 0% | Late | 2026-10-30 | 0% | On Schedule | 0 | 0 | 0 |  | MDW-39542 | MDW-69584 | MDW-69585
242 | 0 | Lot02 | MO-BEM50 | MO-BEM | Modify maintenance service door to the roof of OR13 vent building to easier access while maintaining safe operational standards | สู่โชค | 0 | Depot | 2027-01-01 | 2026-10-29 | 0% | Late | 2026-10-30 | 100% | Completed | 0 | 0 | 0 |  |  | 0 | 0
243 | MDW-39514 | Lot02 | MO-BEM51 | MO-BEM | Modify existing car park to be 220 motorcycle parking lots including floor painting and parking roof | สหชาติ | 0 | Depot | 2026-08-01 | 2026-01-29 | 100% | Completed | 2026-03-16 | 100% | Completed | 0 | 0 | 0 |  | MDW-39514 | MDW-69528 | MDW-69529
244 | MDW-39534 | Lot02 | MO-BEM52 | MO-BEM | Modify the sidewalk for temporary parking at entrance | สหชาติ | 0 | Depot | 2027-01-01 | 2026-07-31 | 100% | Completed | 2026-09-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39534 | MDW-69568 | MDW-69569
245 | MDW-39554 | Lot02 | MO-BEM53.1 | MO-BEM | Modification Works : Security Guard Box at OCC Parking Area - Civil & AR | สหชาติ | 0 | Depot | 2027-01-02 | 2026-09-14 | 100% | Completed | 2026-10-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39554 | MDW-69608 | MDW-69609
246 | MDW-39555 | Lot02 | MO-BEM53.2 | MO-BEM | Modification Works : Security Guard Box at OCC Parking Area - Building Services | ประธาน | 0 | 0 | 2027-01-02 | 2026-09-14 | 100% | Completed | 2026-10-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39555 | MDW-69610 | MDW-69611
247 | NoDrawing | Lot02 | MO-BEM54 | MO-BEM | Strengthen the Maintenance Walkway of the TEF fan | สหชาติ | 0 | 0 | 2027-01-01 | 2026-07-16 | 100% | Completed | 2026-08-16 | 100% | Completed | 0 | 0 | 0 |  |  | 0 | 0
Lot 1 Manufacturing/Delivery
[23 empty] | CK Pesonsible Person | Total | Completed | Late | On Schedule
[23 empty] | สหชาติ | 5 | 2 | 2 | 1
[23 empty] | ประธาน | 0 | 0 | 0 | 0
[23 empty] | สมศักดิ์ | 24 | 14 | 1 | 9
[23 empty] | มนตรี | 1 | 1 | 0 | 0
[23 empty] | มนต์ชัย | 1 | 1 | 0 | 0
[23 empty] | - | 2 | 2 | 0 | 0
Lot 2 Manufacturing/Delivery
[23 empty] | CK Pesonsible Person | Total | Completed | Late | On Schedule
[23 empty] | สหชาติ | 11 | 3 | 5 | 3

## Con-In (hidden)
Construction/Installation
No. | Design Submission | Lot No. | Code | System | Activity Name | CK Responsible Person |  | Location | Expected Completion Month | Design (PLAN) | Design (%) | Design (Status) | Procurement (PLAN) | Procurement (%) | Procurement (Status) | Manufacturing / Delivery Process (PLAN) | Manufacturing / Delivery Process (%) | Manufacturing / Delivery (Status) | Construction /Installation (PLAN) | Construction /Installation (%) | Construction /Installation (Status) | Note | Design Submission | Procedure No. | Test Report No.
1 | MDW-39246-60 | Lot01 | GEN1 | GEN | Rooms and Building Service Systems Modification in Stations Area | - | 0 | 0 | 2026-08-01 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39246 | MDW-69259 | MDW-69260
2 | MDW-39246 | Lot01 | GEN1.1 | GEN | Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR13 - OR17 | ประธาน | 0 | 0 | 2026-08-01 | 2026-01-30 | 100% | Completed | 2026-03-01 | 100% | Completed | 0 | 0% | 0% | 2026-03-31 | 100% | Completed |  | MDW-39246 | MDW-69259 | MDW-69260
3 | MDW-39247 | Lot01 | GEN1.2 | GEN | Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR18 - OR22 | ประธาน | 0 | 0 | 2026-08-01 | 2025-12-30 | 100% | Completed | 2026-01-29 | 100% | Completed | 0 | 0% | 0% | 2026-02-28 | 100% | Completed |  | MDW-39247 | MDW-69259 | MDW-69261
4 | MDW-39248 | Lot01 | GEN1.3 | GEN | Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR23 - OR29 | ประธาน | 0 | 0 | 2026-08-01 | 2026-01-30 | 100% | Completed | 2026-03-01 | 100% | Completed | 0 | 0% | 0% | 2026-03-31 | 100% | Completed |  | MDW-39248 | MDW-69259 | MDW-69262
5 | MDW-39252 | Lot01 | GEN1.4 | GEN | Modification of Fire Suppression System (N2) in Commerial Room at OR14 | ประธาน | 0 | 0 | 2026-08-01 | 2025-12-30 | 100% | Completed | 2026-01-29 | 100% | Completed | 0 | 0% | 0% | 2026-02-28 | 100% | Completed |  | MDW-39252 | MDW-69269 | MDW-69270
6 | MDW-39253 | Lot01 | GEN1.5 | GEN | Modification of Civil Work in Telecommunication Room at OR14 | สหชาติ | 0 | 0 | 2026-08-01 | 2025-12-30 | 100% | Completed | 2026-01-29 | 100% | Completed | 0 | 0% | 0% | 2026-02-28 | 100% | Completed |  | MDW-39253 | MDW-69271 | MDW-69272
7 | MDW-39254 | Lot01 | GEN1.6 | GEN | Modification in Staff Mess Room at OR13-OR17 | ประธาน | 0 | 0 | 2026-08-01 | 2026-01-30 | 100% | Completed | 2026-03-01 | 100% | Completed | 0 | 0% | 0% | 2026-03-31 | 100% | Completed |  | MDW-39254 | MDW-69273 | MDW-69274
8 | MDW-39255 | Lot01 | GEN1.7 | GEN | Modification in Staff Mess Room at OR18-OR22 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39255 | MDW-69273 | MDW-69275
9 | MDW-39256 | Lot01 | GEN1.8 | GEN | Modification in Staff Mess Room at OR23-OR29 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39256 | MDW-69273 | MDW-69276
10 | MDW-39257 | Lot01 | GEN1.9 | GEN | Modification of Air Conditioning in CER and SER at OR13-OR19 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 99% | Late | 0 | MDW-39257 | MDW-69277 | MDW-69278
11 | MDW-39258 | Lot01 | GEN1.10 | GEN | Modification of Air Conditioning in CER and SER at OR20-OR22 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 99% | Late | 0 | MDW-39258 | MDW-69277 | MDW-69279
12 | MDW-39259 | Lot01 | GEN1.11 | GEN | Modification of Air Conditioning in CER and SER at OR23-OR29 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 99% | Late | 0 | MDW-39259 | MDW-69277 | MDW-69280
13 | MDW-39272 | Lot01 | GEN1.12 | GEN | Modification of New M&E Room at IVS15 - IVS17 Civil & AR | สหชาติ | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39272 | MDW-69299 | MDW-69300
14 | MDW-39273 | Lot01 | GEN1.13 | GEN | Modification of New M&E UPS Room at IVS15-IVS17 - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 99% | Late | 0 | MDW-39273 | MDW-69301 | MDW-69302
15 | MDW-39294 | Lot01 | GEN1.14 | GEN | Provision of Architectural Work in new M&E UPS room at OR23 | สหชาติ | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39294 | MDW-69339 | MDW-69340
16 | MDW-39299 | Lot01 | GEN1.15 | GEN | Provision of Air Conditioning System in Commercial Room at OR13-OR19 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39299 | MDW-69349 | MDW-69350
17 | MDW-39306 | Lot01 | GEN1.16 | GEN | Modification CER and First Aid Room at OR14 - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39306 | MDW-69363 | MDW-69364
18 | MDW-39307 | Lot01 | GEN1.17 | GEN | Additional Fence at Back of House OR13 - OR22 and IVS East Section | สหชาติ | 0 | 0 | 2026-08-01 | 2026-09-30 | 100% | Completed | 2026-10-31 | 50% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | MDW-39307 | MDW-69365 | MDW-69366
19 | MDW-39249 | Lot01 | GEN1.18 | GEN | SOR Counter and Workstation Hanging Support Installation on East Section | สหชาติ | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39249 | MDW-69263 | MDW-69264
20 | MDW-39250 | Lot01 | GEN1.19 | GEN | Ticket Office Modification on East Section | สหชาติ | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39250 | MDW-69265 | MDW-69266
21 | MDW-39261 | Lot01 | GEN2 | GEN | Rooms and Building Service Systems Modification in Depot Area | - | 0 | Depot | 2026-08-01 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39261 | MDW-69283 | MDW-69284
22 | MDW-39260 | Lot01 | GEN2.1 | GEN | Modification of Air Conditioning in M&E Room at OCC Building | ประธาน | 0 | 0 | 2026-08-01 | 2025-12-30 | 100% | Completed | 2026-01-29 | 100% | Completed | 0 | 0% | 0% | 2026-02-28 | 100% | Completed |  | MDW-39260 | MDW-69281 | MDW-69282
23 | MDW-39261 | Lot01 | GEN2.2 | GEN | Provision of UPS for MDB Control at Main Workshop, OCC Building, Admin Building, Stabling Yard and Train Washing Plant | ประธาน | 0 | 0 | 2026-08-01 | 2026-09-01 | 100% | Completed | 2026-10-01 | 100% | Completed | 0 | 0% | 0% | 2026-10-31 | 90% | On Schedule | 0 | MDW-39261 | MDW-69283 | MDW-69284
24 | MDW-39262 | Lot01 | GEN2.3 | GEN | Provision of Redundant MDB at OCC Building, Admin Building and Canteen | ประธาน | 0 | 0 | 2026-08-01 | 2026-09-01 | 100% | Completed | 2026-10-01 | 100% | Completed | 0 | 0% | 0% | 2026-10-31 | 95% | On Schedule | 0 | MDW-39262 | MDW-69285 | MDW-69286
25 | MDW-39263 | Lot01 | GEN2.4 | GEN | Additonal Lighting System at Depot Area | ประธาน | 0 | 0 | 2026-08-01 | 2026-04-01 | 100% | Completed | 2026-05-01 | 100% | Completed | 0 | 0% | 0% | 2026-05-31 | 100% | Completed |  | MDW-39263 | MDW-69287 | MDW-69288
26 | MDW-39290 | Lot01 | GEN2.5 | GEN | Modification Room for PSY at Depot Buildings - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39290 | MDW-69331 | MDW-69332
27 | MDW-39300 | Lot01 | GEN2.6 | GEN | Modification SIG-PSD Office at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39300 | MDW-69351 | MDW-69352
28 | MDW-39301 | Lot01 | GEN2.7 | GEN | Modification Backup CCR Room at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39301 | MDW-69353 | MDW-69354
29 | MDW-39302 | Lot01 | GEN2.8 | GEN | Modification SER at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39302 | MDW-69355 | MDW-69356
30 | MDW-39303 | Lot01 | GEN2.9 | GEN | Modification CER & SCADA Room at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39303 | MDW-69357 | MDW-69358
31 | MDW-39309 | Lot01 | GEN2.10 | GEN | Modification Air Conditioning System at CCR | ประธาน | 0 | 0 | 2026-08-01 | 2026-10-01 | 100% | Completed | 2026-10-31 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 80% | On Schedule | 0 | MDW-39309 | MDW-69369 | MDW-69370
32 | MDW-39312 | Lot01 | GEN2.11 | GEN | Modification Electronic Workshop at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-10-31 | 100% | Completed | 2026-11-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | MDW-39312 | MDW-69375 | MDW-69376
33 | MDW-39313 | Lot01 | GEN2.12 | GEN | Modification Battery Charger Room at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-10-31 | 100% | Completed | 2026-11-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | MDW-39313 | MDW-69377 | MDW-69378
34 | MDW-39314 | Lot01 | GEN2.13 | GEN | Modification Machining Room at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-10-31 | 90% | On Schedule | 2026-11-30 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | MDW-39314 | MDW-69379 | MDW-69380
35 | MDW-39315 | Lot01 | GEN2.14 | GEN | Modification Electronic Workshop, Battery Charger and Machining Room at Main Workshop - Civil & AR | สหชาติ | 0 | 0 | 2026-08-01 | 2026-10-31 | 70% | On Schedule | 2026-11-30 | 90% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | MDW-39315 | MDW-69383 | MDW-69384
36 | MDW-39297 | Lot01 | GEN2.15 | GEN | Training Room at Ratchada Station (Part 2) | สหชาติ | 0 | 0 | 2026-08-01 | 2026-08-01 | 0% | Late | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39297 | MDW-69345 | MDW-69346
37 | MDW-39291 | Lot01 | GEN2.16 | GEN | Conductor Rail Arrangement Modification at Main Line East Section | กำพล | 0 | 0 | 2026-08-01 | 2026-09-30 | 100% | Completed | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 90% | On Schedule | 0 | MDW-39291 | MDW-69333 | MDW-69334
38 | MDW-39292 | Lot01 | GEN2.17 | GEN | Conductor Rail Arrangement Modification at Depot | กำพล | 0 | 0 | 2026-08-01 | 2026-09-30 | 100% | Completed | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 90% | On Schedule | 0 | MDW-39292 | MDW-69335 | MDW-69336
39 | MDW-39295 | Lot01 | GEN2.18 | GEN | Dangerous Goods Building in Depot - Civil & AR | สหชาติ | 0 | 0 | 2026-08-01 | 2026-01-27 | 100% | Completed | 2026-02-27 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed |  | MDW-39295 | MDW-69341 | MDW-69342
40 | MDW-39296 | Lot01 | GEN2.19 | GEN | Dangerous Goods Building in Depot - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2025-12-13 | 100% | Completed | 2026-01-28 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed |  | MDW-39296 | MDW-69343 | MDW-69344
41 | MDW-39308 | Lot01 | GEN2.20 | GEN | Additional Locking Devices for Main Line Tandem Turnouts 2007, 2010 & 2013 and Depot Turnout D16 | กำพล | 0 | 0 | 2026-08-01 | 2026-11-30 | 50% | On Schedule | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | MDW-39308 | MDW-69367 | MDW-69368
42 | MDW-39200-31 | Lot01 | GEN3 | GEN | Cable Containment Modification | - | 0 | 0 | 2025-05-28 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39200
43 | - | Lot01 | GEN4 | GEN | Training Room and Workshop Room | - | 0 | 0 | 2026-04-01 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
44 | MDW-39242 | Lot01 | GEN4.0 | GEN | Modification Works for Training Room at Ratchada Station | ประธาน | 0 | 0 | 2026-04-01 | 2025-12-30 | 100% | Completed | 2026-01-31 | 100% | Completed | 0 | 0% | 0% | 2026-03-31 | 100% | Completed |  | MDW-39242 | MDW-69251 | MDW-69252
45 | MDW-39244 | Lot01 | GEN4.1 | GEN | AFC Training Room Modification - Civil & AR | สหชาติ | 0 | 0 | 2026-08-21 | 2026-09-30 | 10% | Late | 2026-10-15 | 100% | Completed | 0 | 0% | 0% | 2026-11-15 | 0% | On Schedule | อยู่ระหว่างจัดทำแบบก่อสร้าง | MDW-39244 | MDW-69255 | MDW-69256
46 | MDW-39245 | Lot01 | GEN4.2 | GEN | AFC Training Room Modification - Building Services | ประธาน | 0 | 0 | 2026-08-21 | 2025-12-30 | 100% | Completed | 2026-01-31 | 100% | Completed | 0 | 0% | 0% | 2026-03-31 | 100% | Completed |  | MDW-39245 | MDW-69257 | MDW-69258
47 | MDW-39235 | Lot01 | GEN5 | GEN | Raised Floor | สหชาติ | 0 | 0 | 2026-06-01 | 2025-05-15 | 100% | Completed | 2024-12-14 | 100% | Completed | 2025-08-04 | 100% | Completed | 2025-12-28 | 100% | Completed |  | MDW-39235 | MDW-69237 | MDW-69238
48 | MDW-39271 | Lot01 | GEN6 | GEN | Wayside Cable Containment in Depot | - | 0 | Depot | 2026-02-22 | 2025-05-15 | 100% | Completed | 2024-12-14 | 100% | Completed | 2025-08-04 | 100% | Completed | 2025-12-28 | 100% | Completed |  | MDW-39271 | MDW-69297 | MDW-69298
49 | MDW-39269 | Lot01 | GEN6.1 | GEN | PSY Wayside Cable Containment for 24 Kv Cable under the Depot slab | ประธาน | 0 | Depot | 2026-02-22 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39269 | MDW-69293 | MDW-69294
50 | MDW-39270 | Lot01 | GEN6.2 | GEN | COM/SIG Wayside Cable Containment in the Depot | มนตรี/ประธาน | 0 | Depot | 2026-02-22 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39270 | MDW-69295 | MDW-69296
51 | - | Lot01 | GEN7 | GEN | Dangerous Waste Storage Building in Depot | - | 0 | Depot | 2026-09-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
52 | DWE-39024 | Lot01 | GEN7.1 | GEN | Dangerous Waste Storage Building in Depot - Civil & AR | สหชาติ | 0 | Depot | 2026-09-20 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed |  | DWE-39024 | DWE-69024 | DWE-69124
53 | DWE-39025 | Lot01 | GEN7.2 | GEN | Dangerous Waste Storage Building in Depot - Building service | ประธาน | 0 | Depot | 2026-09-20 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed | 0 | 0% | 0% | 2026-06-30 | 100% | Completed |  | DWE-39025 | DWE-69025 | DWE-69125
54 | - | Lot01 | GEN8 | GEN | General Waste Storage Building in Depot | - | 0 | Depot | 2026-09-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
55 | DWE-39026 | Lot01 | GEN8.1 | GEN | General Waste Storage Building in Depot - Civil & AR | สหชาติ | 0 | Depot | 2026-09-20 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed |  | DWE-39026 | DWE-69026 | DWE-69126
56 | DWE-39025 | Lot01 | GEN8.2 | GEN | General Waste Storage Building in Depot - Building service | ประธาน | 0 | Depot | 2026-09-20 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed | 0 | 0% | 0% | 2026-06-30 | 100% | Completed |  | DWE-39025 | DWE-69025 | DWE-69125
57 | DWE-39021 | Lot01 | GEN9 | GEN | Operation Support Equipment | สมศักดิ์ | 0 | Depot | 2026-08-21 | 2025-03-02 | 100% | Completed | 2025-11-02 | 100% | Completed | 2026-11-16 | 90% | On Schedule | 0 | 0 | 0 |  | DWE-39021 | DWE-69021 | DWE-69121
58 | GRS-39001-40 | Lot01 | GEN10.1 | GEN | Graphic and Signage Station | สหชาติ | 0 | 0 | 2026-08-21 | 2026-06-30 | 100% | Completed | 2026-05-31 | 95% | Late | 2027-01-31 | 76% | On Schedule | 2027-02-28 | 34% | On Schedule | GRS | GRS-39001 | GRS-69001 | GRS-69002
59 | GRS-39001-40 | Lot01 | GEN10.2 | GEN | Graphic and Signage Mainline & IVS,VS | สหชาติ | 0 | 0 | 2026-08-21 | 2026-06-15 | 79% | Late | 2026-05-31 | 95% | Late | 2026-07-31 | 0% | Late | 2026-07-31 | 0% | Late | GRS | GRS-39001 | GRS-69001 | GRS-69002
60 | GRS-39001-40 | Lot01 | GEN10.3 | GEN | Graphic and Signage Depot | สหชาติ | 0 | 0 | 2026-08-21 | 2026-08-15 | 90% | Late | 2026-07-31 | 93% | Late | 2026-06-30 | 56% | Late | 2026-06-30 | 19% | Late | GRS | GRS-39001 | GRS-69001 | GRS-69002
61 | MDW-39289 | Lot01 | GEN11 | GEN | Earthing and Bonding Modification | ประธาน | 0 | 0 | 2026-03-01 | 2025-01-31 | 100% | Completed | 2025-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-02-28 | 100% | Completed |  | MDW-39289 | MDW-69329 | MDW-69330
62 | - | Lot01 | GEN12 | GEN | Mainline Cable Trough Modification on East Section | - | 0 | 0 | 2026-06-22 | 2025-10-31 | 100% | Completed | 2025-11-30 | 100% | Completed | 2025-12-30 | 100% | Completed | 2026-03-30 | 100% | Completed |  |  | 0 | 0
63 | MDW-39233 | Lot01 | GEN12.1 | GEN | Main Line Cable Trough Modification (PSY) | มนต์ชัย | 0 | Depot | 2026-06-22 | 2025-10-31 | 100% | Completed | 2025-11-30 | 100% | Completed | 2025-12-30 | 100% | Completed | 2026-03-30 | 100% | Completed |  | MDW-39233
64 | MDW-39234 | Lot01 | GEN12.2 | GEN | Main Line Cable Trough Modification (SIG/COM) | มนตรี | 0 | 0 | 2026-06-22 | 2025-10-31 | 100% | Completed | 2025-11-30 | 100% | Completed | 2025-12-30 | 100% | Completed | 2026-03-30 | 100% | Completed |  | MDW-39234 | MDW-69234 | MDW-69236
65 | MDW-39236 | Lot01 | GEN13 | GEN | Bird Protection System | สหชาติ | 0 | 0 | 2026-11-19 | 2025-06-30 | 100% | Completed | 2025-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-01-26 | 100% | Completed |  | MDW-39236 | MDW-69239 | MDW-69240
66 | - | Lot01 | GEN14 | GEN | Train Crew Office at Thailand Cultural Centre Station | สหชาติ | 0 | 0 | 2026-08-21 | 2025-09-30 | 100% | Completed | 2026-02-27 | 100% | Completed | 0 | 0% | 0% | 2026-05-31 | 100% | Completed |  |  | 0 | 0
67 | MDW-39240 | Lot01 | GEN14.1 | GEN | Driver Train Simulation Room and Train Crew Office at OR18 - Civil & AR | สหชาติ | 0 | Depot | 2026-08-21 | 2025-09-30 | 100% | Completed | 2026-02-28 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed |  | MDW-39240 | MDW-69247 | MDW-69248
68 | MDW-39241 | Lot01 | GEN14.2 | GEN | Driver Train Simulation Room and Train Crew Office at OR18 - Building Services | ประธาน | 0 | 0 | 2026-08-21 | 2025-09-30 | 100% | Completed | 2026-02-28 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed |  | MDW-39241 | MDW-69249 | MDW-69250
69 | MDW-39239 | Lot01 | GEN15 | GEN | Access Panel Closeout for Traction Substation Room in Main Workshop | สหชาติ | 0 | 0 | 2026-03-24 | 2026-01-30 | 100% | Completed | 2026-03-01 | 100% | Completed | 0 | 0% | 0% | 2026-03-31 | 100% | Completed |  | MDW-39239 | MDW-69245 | MDW-69246
70 | MDW-39232 | Lot01 | GEN16 | GEN | Level Crossing at Turnout | กำพล | 0 | 0 | 2026-08-21 | 2026-09-30 | 100% | Completed | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-11-15 | 46% | On Schedule | 0 | MDW-39232 | MDW-69232 | MDW-69233
71 | MDW-39232 | Lot01 | GEN17 | GEN | Track Slab Crossing | ชฎิล/กำพล | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39232 | MDW-69232 | MDW-69233
72 | MDW-39243 | Lot01 | GEN18 | GEN | Eye Adaptation Lighting (Lighting at Tunnel to Expose) | ประธาน | 0 | 0 | 2026-11-19 | 2025-09-30 | 100% | Completed | 2025-10-30 | 100% | Completed | 0 | 0% | 0% | 2026-04-13 | 100% | Completed |  | MDW-39243 | MDW-69253 | MDW-69254
73 | - | Lot01 | GEN19 | GEN | Train Simulation Room and AFC Training Room | - | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
74 | MDW-39244 | Lot01 | GEN19.1 | GEN | Modification AFC Training Center at OR19 - Civil & AR | สหชาติ | 0 | 0 | 2026-11-30 | 2026-09-30 | 100% | Completed | 2026-10-31 | 58% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | Progress Cut&Cover OR22 : 95% | MDW-39244 | MDW-69255 | MDW-69256
75 | MDW-39245 | Lot01 | GEN19.2 | GEN | Modification AFC Training Center at OR19 - Building Services | ประธาน | บัณฑิต | 0 | 2026-11-30 | 2026-09-30 | 100% | Completed | 2026-10-31 | 100% | Completed | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 0 | MDW-39245 | MDW-69257 | MDW-69258
76 | - | Lot01 | GEN20 | GEN | Dormitory Cable Containments (if any) | - | 0 | 0 | - | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
77 |  | Lot01 | GEN21 | GEN | Project Information Management System (PIMS) | บัณฑิต | 0 | 0 | 2024-09-30 | 2024-08-10 | 100% | Completed | 2024-08-15 | 100% | Completed | 0 | 0% | 0% | 2024-09-04 | 100% | Completed
78 | MDW-39237 | Lot01 | GEN22 | GEN | Central BEMS for the MRT Orange Line System | บัณฑิต | 0 | 0 | 2026-08-21 | 2026-04-30 | 0% | Late | 2026-06-30 | 0% | Late | 0 | 0% | 0% | 2026-08-15 | 0% | Late | PPR Oct-26 กำลังเปรียบเทียบ Spec | MDW-39237 | MDW-69241 | MDW-69242
79 |  | Lot01 | GEN23 | GEN | Asset Information | บัณฑิต | 0 | 0 | 2026-11-19 | 0 | 0% | 0% | 2026-08-30 | 100% | Completed | 0 | 0% | 0% | 0 | 0 | 0
80 | MDW-39282 | Lot01 | PSD1 | PSD | Holes for PSD Cable Wiring | กำพล | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39282 | MDW-69315 | MDW-69316
81 | MDW-39004 | Lot01 | PSD2 | PSD | Rubber Gap Fillers on Platform Edge | กำพล | 0 | 0 | 2026-08-21 | 2025-07-30 | 100% | Completed | 2026-01-31 | 100% | Completed | 0 | 0% | 0% | 2026-08-31 | 40% | Late | แผนเข้าติดตั้ง 1/10/26-30/11/26 | MDW-39004 | MDW-69007 | MDW-69008
82 | MDW-39280 | Lot01 | PSD3 | PSD | Platform Finishing | กำพล | 0 | 0 | 2026-08-21 | 2025-07-30 | 100% | Completed | 2025-09-16 | 100% | Completed | 0 | 0% | 0% | 2026-01-07 | 100% | Completed |  | MDW-39280 | MDW-69311 | MDW-69312
83 | MDW-39281 | Lot01 | PSD4 | PSD | Cladding Barrier between EWD and Station Structure | กำพล | 0 | 0 | 2026-08-21 | 2026-02-28 | 100% | Completed | 2026-03-15 | 100% | Completed | 0 | 0% | 0% | 2026-08-15 | 100% | Completed |  | MDW-39281 | MDW-69313 | MDW-69314
84 | - | Lot01 | AFC1 | AFC | Park and Ride System | บัณฑิต/สหชาติ | 0 | 0 | 2026-10-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
85 | MDW-39276 | Lot01 | AFC2 | AFC | Ticket Issuing Machine (TIM) Wall Opening and Closing | สหชาติ | 0 | 0 | 2026-09-20 | 2026-01-30 | 100% | Completed | 2026-03-15 | 50% | Late | 0 | 0% | 0% | 2026-07-13 | 100% | Completed |  | MDW-39276 | MDW-69303 | MDW-69304
86 | MDW-39279 | Lot01 | AFC3 | AFC | Balustrade Modification Along AFC Gate Line | สหชาติ | 0 | 0 | 2026-09-20 | 2026-06-30 | 10% | Late | 2026-08-15 | 50% | Late | 0 | 0% | 0% | 2026-11-06 | 0% | On Schedule | จัดเตรียมแบบ ออกPPR Oct-26 | MDW-39279 | MDW-69309 | MDW-69310
87 | MDW-39278 | Lot01 | AFC4 | AFC | Underfloor Embedded Duct Modification for AFC Gates Line | สหชาติ | 0 | Depot | 2026-09-20 | 2026-01-30 | 100% | Completed | 2026-04-02 | 67% | Late | 0 | 0% | 0% | 2026-10-09 | 81% | Late | 0 | MDW-39278 | MDW-69307 | MDW-69308
88 | MDW-39002 | Lot01 | SIG1 | SIG | Test Track Shelters and Test Track Building | สหชาติ | 0 | 0 | 2026-06-22 | 2025-11-22 | 100% | Completed | 2026-01-18 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-04-15 | 100% | Completed |  | MDW-39002 | MDW-69003 | MDW-69004
89 | MDW-39293 | Lot01 | SIG2 | SIG | Rearrangement of track crossing walkway at stabling yard to consistent with the layout of 4-car train parking | กำพล | 0 | Depot | 2026-06-22 | 2025-11-30 | 100% | Completed | 2025-12-30 | 100% | Completed | 0 | 0% | 0% | 2026-03-30 | 100% | Completed |  | MDW-39293 | MDW-69337 | MDW-69338
90 | MDW-39288 | Lot01 | SIG3 | SIG | Point Machine Foundation Construction | กำพล | 0 | 0 | 2026-08-21 | 2025-11-21 | 100% | Completed | 2025-12-30 | 100% | Completed | 0 | 0% | 0% | 2026-03-19 | 100% | Completed |  | MDW-39288 | MDW-69327 | MDW-69328
91 | MDW-39001 | Lot01 | SIG4 | SIG | Modification of Depot Track Route Line to Stabling Yard | สู่โชค | 0 | Depot | 2026-06-22 | 2025-10-30 | 100% | Completed | 2025-11-29 | 100% | Completed | 0 | 0% | 0% | 2026-05-28 | 95% | Late | คงเหลือเก็บงาน Progress by ช.ธนัท | MDW-39001 | MDW-69001 | MDW-69002
92 | MDW-39287 | Lot01 | SIG5 | SIG | Strobe Light at Buffer Stops | ประธาน | 0 | Depot | 2026-08-21 | 2026-05-30 | 100% | Completed | 2026-06-29 | 100% | Completed | 0 | 0% | 0% | 2026-08-28 | 100% | Completed |  | MDW-39287 | MDW-69323 | MDW-69324
93 | DWE-39016 | Lot01 | DWE1 | DWE | Diesel Fuel Storage Tank for Maintenance Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-01-16 | 100% | Completed | 2026-06-30 | 100% | Completed | 2026-07-31 | 100% | Completed |  | DWE-39016 | DWE-69016 | DWE-69116
94 | DWE-39011 | Lot01 | DWE2 | DWE | Movable Height Maintenance Platform Vehicle (Boom Lift) | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-08-06 | 100% | Completed | 2025-12-31 | 100% | Completed | 2026-06-30 | 100% | Completed |  | DWE-39011 | DWE-69011 | DWE-69111
95 | DWE-39012 | Lot01 | DWE3 | DWE | Fork Lift Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-03-31 | 100% | Completed | 2026-06-01 | 100% | Completed | 2026-06-30 | 100% | Completed |  | DWE-39012 | DWE-69012 | DWE-69112
96 | DWE-39015 | Lot01 | DWE4 | DWE | Compressed Air System and Portable Air Compressor for Depot | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-01-10 | 100% | Completed | 2026-02-15 | 100% | Completed | 2026-09-19 | 0% | Late | Forecast Install 1/11-30-11/26 | DWE-39015 | DWE-69015 | DWE-69115
97 | DWE-39017 | Lot01 | DWE5 | DWE | Pallet Storage Shelves in Hazardous Storage | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-12-16 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-05-31 | 100% | Completed |  | DWE-39017 | DWE-69017 | DWE-69117
98 | DWE-39017 | Lot01 | DWE6 | DWE | Pallet Storage in Main Storage Room | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-12-16 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-05-31 | 100% | Completed |  | DWE-39017 | DWE-69017 | DWE-69117
99 | DWE-39017 | Lot01 | DWE7 | DWE | Two-Tier Shelf | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-12-16 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-05-31 | 100% | Completed |  | DWE-39017 | DWE-69017 | DWE-69117
100 | DWE-39017 | Lot01 | DWE8 | DWE | Tool Storage | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-12-16 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-05-31 | 100% | Completed |  | DWE-39017 | DWE-69017 | DWE-69117
101 | DWE-39018 | Lot01 | DWE9 | DWE | Repair Equipment | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-07-31 | 50% | Late | 2026-10-30 | 70% | On Schedule | 2027-03-03 | 0% | On Schedule | คงเหลือจัดส่งอุปกรณ์ | DWE-39018 | DWE-69018 | DWE-69118
102 | DWE-39020 | Lot01 | DWE10 | DWE | Oil & Grease Disposal | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-01-16 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-03-31 | 100% | Completed |  | DWE-39020 | DWE-69020 | DWE-69120
103 | DWE-39020 | Lot01 | DWE11 | DWE | Grease Dispensers | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-01-16 | 100% | Completed | 2026-04-28 | 100% | Completed | 2026-05-25 | 100% | Completed |  | DWE-39020 | DWE-69020 | DWE-69120
104 | DWE-39020 | Lot01 | DWE12 | DWE | Waste Disposal | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-01-16 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-03-31 | 100% | Completed |  | DWE-39020 | DWE-69020 | DWE-69120
105 | MDW-39305 | Lot01 | DWE13 | DWE | Safety Provision for Maintenance Pits | สหชาติ | 0 | Depot | 2026-09-20 | 2025-11-30 | 100% | Completed | 2026-04-29 | 100% | Completed | 0 | 0% | 0% | 2026-07-29 | 70% | Late | งาน Handrail ที่ Pits Wheel Reprofling Plant ติดตั้งแล้วเหลืองานเก็บสี | MDW-39305 | MDW-69361 | MDW-69362
106 | DWE-39xxx | Lot01 | DWE14 | DWE | Pit Drainage System in Main Workshop | สมศักดิ์ | 0 | Depot | 2026-09-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39xxx | MDW-69361 | MDW-69362
107 | DWE-39023 | Lot01 | DWE15 | DWE | Provision of Civil Works and Building Services to support Train Washing Equipment | สหชาติ | 0 | Depot | 2026-08-01 | 2025-11-30 | 100% | Completed | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-05-31 | 100% | Completed |  | DWE-39023 | DWE-69023 | DWE-69123
108 | DWE-39013 | Lot01 | DWE16 | DWE | Overhead Traveling Crane | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-04-30 | 100% | Completed | 2026-03-20 | 100% | Completed | 0 | 0 | 0 |  | DWE-39013 | DWE-69013 | DWE-69113-513
109 | DWE-39009 | Lot01 | DWE17 | DWE | Vehicle Inspection and Servicing Facilities | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-12-18 | 100% | Completed | 2026-09-07 | 100% | Completed | 0 | 0 | 0 |  | DWE-39009 | DWE-69009 | DWE-69109
110 | DWE-39014 | Lot01 | DWE18 | DWE | Permanent Way Maintenance Facility | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-04-30 | 100% | Completed | 2027-02-28 | 100% | Completed | 2027-01-15 | 70% | On Schedule | 0 | 0 | 0 |  | DWE-39014 | DWE-69014 | DWE-69114
111 | - | Lot01 | DWE19 | DWE | Permanent Way Vehicles | สมศักดิ์ | 0 | Depot | 2026-09-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
112 | DWE-39001 | Lot01 | DWE19.1 | DWE | Shunting Locomotive | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-12-18 | 100% | Completed | 2026-12-15 | 50% | On Schedule | 0 | 0 | 0 |  | DWE-39001 | DWE-69001 | DWE-69101
113 | DWE-39002 | Lot01 | DWE19.2 | DWE | Tunnel Inspection and Cleaning Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 0% | Late | 2025-12-18 | 100% | Completed | 2026-12-30 | 40% | On Schedule | 0 | 0 | 0 |  | DWE-39002 | DWE-69002 | DWE-69102
114 | DWE-39003 | Lot01 | DWE19.3 | DWE | Hi/Rail Maintenance Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-12-18 | 100% | Completed | 2026-11-30 | 55% | On Schedule | 0 | 0 | 0 |  | DWE-39003 | DWE-69003 | DWE-69103
115 | DWE-39004 | Lot01 | DWE19.4 | DWE | Flat wagon | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-12-18 | 100% | Completed | 2026-10-30 | 68% | On Schedule | 0 | 0 | 0 |  | DWE-39004 | DWE-69004 | DWE-69104
116 | DWE-39005 | Lot01 | DWE19.5 | DWE | Re-railing Equipment | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-11-10 | 100% | Completed | 2026-07-15 | 90% | Late | 0 | 0 | 0 |  | DWE-39005 | DWE-69005 | DWE-69105
117 | DWE-39006 | Lot01 | DWE19.6 | DWE | Self-Propelled Rail Based Inspection Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-12-18 | 100% | Completed | 2026-11-03 | 55% | On Schedule | 0 | 0 | 0 |  | DWE-39006 | DWE-69006 | DWE-69106
118 | DWE-39007 | Lot01 | DWE19.7 | DWE | Rail Head Grinding Machine Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 0% | Late | 2025-12-18 | 100% | Completed | 2027-07-31 | 0% | On Schedule | 0 | 0 | 0 |  | DWE-39007 | DWE-69007 | DWE-69107
119 | DWE-39008 | Lot01 | DWE19.8 | DWE | Multi Measuring Rail Vehicle | สมศักดิ์ | 0 | 0 | 2026-09-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39008 | DWE-69008 | DWE-69108
120 | DWE-39010 | Lot01 | DWE19.9 | DWE | High Work Inspection Vehicle | สมศักดิ์ | 0 | 0 | 2026-09-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39010
121 | - | Lot01 | DWE20 | DWE | Building Maintenance Vehicle | - | 0 | 0 | 2026-09-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
122 | EPS-39001 | Lot01 | PSY1 | PSY | Diesel Fuel Storage Tanks for Power Generators | สมศักดิ์ | 0 | 0 | 2026-03-24 | 2026-01-16 | 100% | Completed | 2026-03-31 | 100% | Completed | 2026-03-31 | 100% | Completed | 2026-06-30 | 75% | Late | คงเหลืองานเดินท่อและ Pump น้ำมัน | EPS-39001 | EPS-69001 | EPS-69002
123 | PSY-39001-9 | Lot01 | PSY2 | PSY | GIS and BSS Building and Other Facilities | สหชาติ | 0 | 0 | 2026-03-24 | 2024-08-29 | 100% | Completed | 2024-09-28 | 69% | Late | 0 | 0% | 0% | 2025-12-04 | 100% | Completed |  | PSY-39001 | PSY-69001 | PSY-69002
124 | PSY-39011 | Lot01 | PSY3 | PSY | Steel Grating Raised Floor for EE Panel | สหชาติ | 0 | 0 | 2026-03-24 | 2024-09-30 | 100% | Completed | 2024-10-30 | 75% | Late | 0 | 0% | 0% | 2025-07-14 | 100% | Completed |  | PSY-39011 | PSY-69015 | PSY-69016
125 | - | Lot01 | PSY4 | PSY | Trapping Box between PSY Service Sub Station (SSS) and Low Volt (LV) System | - | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
126 | SCA-39200 | Lot01 | SCA1 | SCA | Modification of BEMS to receive PSD Signal on East Section | ธารทิพย์ | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | SCA-39200 | SCA-69200 | SCA-69201
127 | - | Lot01 | SCA2 | SCA | Modification of Escalator Interface Point with CCTV and SCADA, East Section | - | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
128 | - | Lot01 | SCA3 | SCA | Magnetic of Fire Alarm System Interface Point with CCTV and SCADA | - | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
129 | SCA-39203 | Lot01 | SCA4 | SCA | Add/Modify Civil Scada Hardwire for all Station | ประธาน/ธารทิพย์ | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | SCA-39203 | SCA-69206 | SCA-69207
130 | COM-39200 | Lot01 | COM1 | COM | Magnetic Door Lock | มนตรี | 0 | 0 | 2026-08-21 | 2025-06-30 | 100% | Completed | 2026-05-15 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 27.25% | On Schedule | กำลังดำเนินการ Progress by CIP | COM-39200 | COM-69200 | COM-69201
131 | MDW-39283 | Lot01 | COM2 | COM | Intercom System in Cash Handling Room (if require) | บัณฑิต | 0 | 0 | 2026-12-19 | 2025-09-30 | 100% | Completed | 2026-06-30 | 50% | Late | 0 | 0% | 0% | 2026-10-31 | 0% | On Schedule | รอพื้นที่เข้าติดตั้ง | MDW-39283 | MDW-69317 | MDW-69318
132 | COM-39001 | Lot01 | COM3 | COM | Walk-Through Metal Detector System (WTMD), 1 per entrance | มนตรี | 0 | 0 | 2026-11-19 | 2025-08-31 | 0% | Late | 2026-06-30 | 0% | Late | 0 | 0% | 0% | 2027-02-28 | 0% | On Schedule | รอออก PPR อยู่ระหว่างการตรวจสอบสินค้า | COM-39001 | COM-69001 | COM-69002
133 | MDW-39284 | Lot01 | COM4 | COM | Traveling Cable in all Lifts | มนตรี | 0 | 0 | - | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39284 | MDW-69319 | MDW-69320
134 | MDW-39304 | Lot01 | COM5 | COM | MEA Radio | ประธาน | 0 | 0 | 2026-09-20 | 2026-01-30 | 100% | Completed | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-06-30 | 95% | Late | รอเฟอร์นิเจอร์ Fore cast Dec-26 | MDW-39304 | COM-69202 | COM-69203
135 | COM-39004 | Lot01 | COM6 | COM | Main Cable Containment for M&E Dedicated communication link to MRTA Head Quarter | มนตรี | 0 | 0 | 2026-09-20 | 2026-01-31 | 100% | Completed | 2026-02-28 | 100% | Completed | 0 | 0% | 0% | 2026-08-31 | 75% | Late | Fore cast Oct-26 | COM-39004 | COM-69005 | COM-69006
136 | AFC-39001 | Lot01 | COM7 | COM | Mini Paging in Ticket Office | บัณฑิต | 0 | 0 | 2026-12-19 | 2025-09-10 | 100% | Completed | 2026-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 0% | Late | ของมาแล้ว รอพื้นที่เข้าติดตั้ง | AFC-39002 | AFC-69003 | AFC-69004
137 | MDW-39285 | Lot01 | COM8 | COM | Provision of Cable Containment between OCC ORL and OCC BL | มนตรี | 0 | 0 | 2026-07-22 | 0 | 0% | 0% | 0% | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39285
138 | COM-39005 | Lot01 | COM9 | COM | Power Distribution for M&E Systems at MRTA Head Quarter | มนตรี | 0 | 0 | 2026-09-20 | 2026-03-31 | 100% | Completed | 2026-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-08-31 | 100% | Completed |  | COM-39005 | COM-69007 | COM-69008
139 | COM-39205 | Lot01 | COM10 | COM | Underground Cable Containment at Public Areas (if require) | มนตรี | 0 | 0 | 2026-08-21 | 2026-04-30 | 100% | Completed | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 100% | Completed |  | MDW-39205 | MDW-69200 | MDW-69205
140 | - | Lot01 | COM11 | COM | Intercom at Ticket Issuing Machine | บัณฑิต | 0 | Depot | - | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
141 | RST-39004,8 | Lot01 | RST1 | RST | Driver Training Simulator | ธัญวิทย์ | 0 | Depot | 2026-09-20 | 2025-05-30 | 100% | Completed | 2025-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 81% | On Schedule | 0 | RST-39004,8
142 | MDW-39500 | Lot02 | MO-CK1.1 | MO-CK | Store Modification Works at Main Workshop - Civil&AR | สหชาติ | 0 | Depot | 2026-06-03 | 2026-02-27 | 100% | Completed | 2026-03-30 | 100% | Completed | 0 | 0% | 0% | 2026-05-31 | 100% | Completed |  | MDW-39500 | MDW-69500 | MDW-69501
143 | MDW-39501 | Lot02 | MO-CK1.2 | MO-CK | Store Modification Works at Main Workshop - Building Services | ประธาน | 0 | Depot | 2026-06-04 | 2026-02-12 | 100% | Completed | 2026-03-30 | 100% | Completed | 0 | 0% | 0% | 2026-05-28 | 100% | Completed |  | MDW-39501 | MDW-69502 | MDW-69503
144 | MDW-39503 | Lot02 | MO-CK2 | MO-CK | New MMC at Admin Building - Civil&AR | สหชาติ | 0 | Depot | 2026-08-03 | 2026-04-14 | 100% | Completed | 2026-05-15 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed |  | MDW-39503 | MDW-69506 | MDW-69507
145 | MDW-39504 | Lot02 | MO-CK3 | MO-CK | Move or link Workstation and control panel to MMC room at admin C 2nd floor | ประธาน | 0 | Depot | 2026-08-02 | 2026-02-28 | 100% | Completed | 2026-04-15 | 100% | Completed | 0 | 0% | 0% | 2026-08-31 | 90% | Late | Fore cast Oct-26 | MDW-39504 | MDW-69508 | MDW-69509
146 | MDW-39543 | Lot02 | MO-CK4 | MO-CK | Bird & Rain Protection for Open space Admin C | สหชาติ | 0 | Depot | 2026-08-01 | 2026-04-29 | 100% | Completed | 2026-05-30 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed |  | MDW-39543 | MDW-69586 | MDW-69587
147 | MDW-39547 | Lot02 | MO-CK5 | MO-CK | Relocate door in front of toilet and build partition wall to conceal the view in side of toilet | สหชาติ | 0 | Depot | 2026-08-02 | 2026-05-14 | 100% | Completed | 2026-06-14 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed |  | MDW-39547 | MDW-69594 | MDW-69595
148 | MDW-39547 | Lot02 | MO-CK6 | MO-CK | Modify Lockset the emergency door to be used for passage between the 2nd and 3rd floors inside the building. | สหชาติ | 0 | Depot | 2026-08-03 | 2026-04-29 | 100% | Completed | 2026-06-14 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed |  | MDW-39547 | MDW-69594 | MDW-69595
149 | MDW-39556 | Lot02 | MO-CK7 | MO-CK | Addition small power for lounge and pantry room at 2nd floor and Hall and observation room at 3nd floor | ประธาน | 0 | Depot | 2026-08-04 | 2026-05-14 | 100% | Completed | 2026-06-14 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed |  | MDW-39556 | MDW-69612 | MDW-69613
150 | MDW-39548 | Lot02 | MO-CK8 | MO-CK | Air Condition for using store room to be pantry room. 2nd floor | ประธาน | 0 | Depot | 2026-08-05 | 2026-04-29 | 100% | Completed | 2026-06-14 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed |  | MDW-39548 | MDW-69596 | MDW-69597
151 | MDW-39552 | Lot02 | MO-CK9 | MO-CK | Walk Way Hand rail high 90 cm 1 side (144 m. x 7 route) | สหชาติ | 0 | Depot | 2026-10-01 | 2026-05-30 | 100% | Completed | 2026-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 98.77% | Late | คงเหลืองานคอนกรีตทางเดินข้ามราง | MDW-39552 | MDW-69604 | MDW-69605
152 | MDW-39544 | Lot02 | MO-CK10 | MO-CK | Barbed wire fence Viaduct CE CW | บัณฑิต/สหชาติ | พี่ต่อ | Depot | 2027-01-01 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39544 | MDW-69588 | MDW-69589
153 | MDW-39545 | Lot02 | MO-CK11 | MO-CK | Chain Link at Cut & Cover 600m. | สหชาติ | พรพรหม | Depot | 2026-06-01 | 2026-02-27 | 100% | Completed | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-08-31 | 100% | Completed |  | MDW-39545 | MDW-69590 | MDW-69591
154 | MDW-39546 | Lot02 | MO-CK12 | MO-CK | Chain Link under slab high 1.70 m | สหชาติ | 0 | 0 | 2027-01-01 | 2026-06-30 | 100% | Completed | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 67.27% | On Schedule | เริ่มติดตั้ง Chainlink แล้ว | MDW-39546 | MDW-69592 | MDW-69593
155 | MDW-39550 | Lot02 | MO-CK13.1 | MO-CK | Satellite Store at OR21 - Civil & AR | สหชาติ | 0 | 0 | 2027-01-02 | 2026-08-30 | 100% | Completed | 2026-10-15 | 0% | Late | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | MDW-39550 | MDW-69600 | MDW-695601
156 | MDW-39549 | Lot02 | MO-CK13.2 | MO-CK | Maintenance Room and Satellite Store at Stations - Building Services | ประธาน | 0 | 0 | 2027-01-03 | 2026-08-30 | 100% | Completed | 2026-10-15 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 80% | On Schedule | 0 | MDW-39549 | MDW-69598 | MDW-69599
157 | MDW-39551 | Lot02 | MO-CK14 | MO-CK | Modify Cleaner room at OR29 to be Train crew Standby office with facility system | ประธาน | 0 | Depot | 2026-07-01 | 2026-03-14 | 100% | Completed | 2026-04-29 | 100% | Completed | 0 | 0% | 0% | 2026-06-30 | 95% | Late | 0 | MDW-39551 | MDW-69602 | MDW-69603
158 | MDW-39295 | Lot02 | MO-CK15.1 | MO-CK | Epoxy Floor Installation and Curb Installation at the Entrance - Civil & AR | สหชาติ | 0 | Depot | 2026-05-01 | 2026-01-27 | 100% | Completed | 2026-02-27 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed |  | MDW-39295 | MDW-69341 | MDW-69342
159 | MDW-39296 | Lot02 | MO-CK15.2 | MO-CK | Change Electrical Equipment to be Explosion-proof type - Building Services | ประธาน | 0 | Depot | 2026-05-01 | 2025-12-13 | 100% | Completed | 2026-01-28 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 90% | Late | Fore cast Nov-26 | MDW-39296 | MDW-69343 | MDW-69344
160 | DWE-39024 | Lot02 | MO-CK16 | MO-CK | Dangerous waste Storage 30 x 5 m. =10 room | สหชาติ | 0 | Depot | 2026-05-01 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed |  | DWE-39024 | DWE-69024 | DWE-69124
161 | 0 | Lot02 | MO-CK17 | MO-CK | Safety Sign all Depot Area building | สหชาติ | 0 | Depot | 2026-05-01 | 2025-11-28 | 100% | Completed | 2026-06-15 | 100% | Completed | 2026-09-20 | 27% | Late | 2026-10-15 | 0% | Late | GRS |  | 0 | 0
162 | 0 | Lot02 | MO-CK18 | MO-CK | Emergency escape route map | สหชาติ | 0 | Depot | 2027-01-01 | 2026-09-30 | 0% | Late | 2026-10-30 | 50% | On Schedule | 2026-12-31 | 0% | On Schedule | 2026-12-31 | 0% | On Schedule | GRS |  | 0 | 0
163 | 0 | Lot02 | MO-CK19 | MO-CK | Traffic Line Marking (Thermoplastic Paint) | สหชาติ | 0 | Depot | 2026-05-01 | 2026-04-30 | 100% | Completed | 2026-06-15 | 100% | Completed | 2026-10-15 | 100% | Completed | 2026-10-15 | 25% | Late | GRS |  | 0 | 0
164 | 0 | Lot02 | MO-CK20 | MO-CK | Emergency Car Parking location Painting in front of MWS | สหชาติ | 0 | Depot | 2026-05-01 | 2026-04-30 | 100% | Completed | 2026-06-15 | 100% | Completed | 2026-10-15 | 0% | Late | 2026-10-15 | 0% | Late | GRS |  | 0 | 0
165 | GRS-39022 | Lot02 | MO-CK21 | MO-CK | Safety Line painting in MWS, Stabling Area, P-way, Track | สหชาติ | 0 | Depot | 2027-01-01 | 2026-06-01 | 100% | Completed | 2026-08-01 | 100% | Completed | 2026-10-15 | 100% | Completed | 2026-12-31 | 81% | On Schedule | GRS | GRS-39022 | GRS-69001 | GRS-69022
166 | 0 | Lot02 | MO-CK22 | MO-CK | Fire escape stairs level signs in the Depot, VS and IVS areas | สหชาติ | 0 | Depot | 2027-01-01 | 2026-09-30 | 50% | Late | 2026-10-31 | 0% | On Schedule | 2026-10-20 | 0% | Late | 2026-12-31 | 0% | On Schedule | GRS |  | 0 | 0
167 | DWE-39026 | Lot02 | MO-CK23 | MO-CK | General waste Storage 22 x 5 m | สหชาติ | 0 | Depot | 2026-05-01 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed |  | DWE-39026 | DWE-69026 | DWE-69126
168 | 0 | Lot02 | MO-CK24 | MO-CK | Modify Traffic paint and traffic sign | สหชาติ | 0 | 0 | 2026-05-01 | 2026-04-30 | 100% | Completed | 2026-06-15 | 100% | Completed | 2026-10-15 | 64% | Late | 2026-10-15 | 13% | Late | GRS |  | 0 | 0
169 | 0 | Lot02 | MO-CK25 | MO-CK | Station Area sign 28 stations | สหชาติ | 0 | 0 | 2026-05-01 | 2026-06-15 | 80% | Late | 2026-06-30 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-12-20 | 0% | On Schedule | GRS |  | 0 | 0
170 |  | Lot02 | MO-CK26 | MO-CK | Safety and warning signage for lift and escalator at all station | สหชาติ | 0 | Depot | 2027-01-01 | 2026-06-16 | 100% | Completed | 2026-07-17 | 100% | Completed | 2027-01-31 | 76% | On Schedule | 2027-02-28 | 26% | On Schedule | GRS
171 | MDW-39532 | Lot02 | MO-CK27 | MO-CK | Spike fence for Depot slab | สหชาติ | 0 | Depot | 2027-01-01 | 2026-07-31 | 70% | Late | 2026-08-31 | 0% | Late | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | อยู่ระหว่างส่งขออนุมัติแบบรอ Approve | MDW-39532 | MDW-69564 | MDW-69565
172 | 0 | Lot02 | MO-CK28 | MO-CK | Bird net and Flashing at MWS and Skywalk to Stabling yard | สหชาติ | 0 | 0 | 2026-05-01 |  |  | 0% |  |  | 0% | 0 | 0% | 0% |  |  | 0 |  |  | 0 | 0
173 | MDW-39541 | Lot02 | MO-CK29 | MO-CK | Fire Alarm Manual Call Point signage at all elevated station | สหชาติ | 0 | 0 | 2027-01-01 |  |  | 0% | 2026-07-30 | 100% | Completed | 0 | 0% | 0% |  |  | 0 |  | MDW-39541 | MDW-69582 | MDW-69583
174 | 0 | Lot02 | MO-CK30 | MO-CK | Lighting for sealed space under stairs and behind lift shaft at underground station | ประธาน | 0 | 0 | 2027-01-01 | 2026-10-14 | 0% | Late | 2026-11-14 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | ไฟส่องสว่างสำหรับพื้นที่ปิดใต้บันไดและด้านหลังช่องลิฟต์ที่สถานีรถไฟใต้ดิน |  | 0 | 0
175 | 0 | Lot02 | MO-CK31 | MO-CK | Modify the access door of sealed space (under-stairs room) with a Sump Pump or ESPS cabinet | สหชาติ | 0 | 0 | 2027-01-01 | 2026-07-16 | 0% | Late | 2026-08-16 | 0% | Late | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 |  | 0 | 0
176 | 0 | Lot02 | MO-CK32 | MO-CK | Lighting to the sealed space (under-stairs room) with a Sump Pump or ESPS cabinet | ประธาน | 0 | Depot | 2027-01-01 | 2026-11-03 | 0% | On Schedule | 2026-12-04 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | ซื้อสปอร์ตไลท์+แบต จำนวน 4 ชุด แทนการลากสายไฟ |  | 0 | 0
177 | 0 | Lot02 | MO-CK33 | MO-CK | Additional lighting in areas where the lux level does not meet occupational health standards | ประธาน | 0 | Depot | 2027-01-01 | 2026-09-14 | 100% | Completed | 2026-10-15 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 95% | On Schedule | 0 |  | 0 | 0
178 | 0 | Lot02 | MO-CK34 | MO-CK | Provide and install confined space signage for Station and Depot | สหชาติ | 0 | 0 | 2027-01-01 | 2026-08-15 | 100% | Completed | 2026-09-15 | 100% | Completed | 2027-01-31 | 76% | On Schedule | 2027-02-28 | 26% | On Schedule | GRS |  | 0 | 0
179 |  | Lot02 | MO-CK35 | MO-CK | Build room for Train crew main office at OR18 with office area, resting area, meeting room, pantry, toilet and locker room | สหชาติ/บัณฑิต/ประธาน | 0 | Depot | - |  |  | 0% |  |  | 0% | 0 | 0% | 0% |  |  | 0
180 |  | Lot02 | MO-CK36 | MO-CK | Dormitory Cable Containments (if any) | มนตรี | 0 | Depot | - |  |  | 0% |  |  | 0% | 0 | 0% | 0% |  |  | 0
181 | 0 | Lot02 | MO-CK37 | MO-CK | Provide Raise floor and building Service in Training &Simulator (OCC Admin) | สหชาติ | 0 | Depot | - | 0% | 0% | 0% |  |  |  | 0 | 0% | 0% |  |  | 0 |  |  | 0 | 0
182 |  | Lot02 | MO-CK38 | MO-CK | Add N2 in Playback and Training Room and Backup Control Room | บุญประเสริฐ | 0 | Depot | - |  |  | 0% |  |  | 0% | 0 | 0% | 0% |  |  | 0
183 | MDW-39505 | Lot02 | MO-BEM1.1 | MO-BEM | Walkway from Main Work Shop to Stabling Area - Civil & AR | สหชาติ | 0 | Depot | 2026-08-02 | 2026-04-28 | 100% | Completed | 2026-05-29 | 92% | Late | 0 | 0% | 0% | 2026-09-30 | 93% | Late | คงเหลืองานมุงหลังคา Metal sheet | MDW-39505 | MDW-69510 | MDW-69511
184 | MDW-39506 | Lot02 | MO-BEM1.2 | MO-BEM | Walkway from Main Work Shop to Stabling Area - Building Services | ประธาน | 0 | Depot | 2026-08-02 | 2026-04-28 | 100% | Completed | 2026-05-29 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 0% | Late | รองานหลังคา CIV Oct-26 | MDW-39506 | MDW-69512 | MDW-69513
185 | MDW-39507 | Lot02 | MO-BEM2 | MO-BEM | High Roof at Main Work Shop Entrance and Store | สหชาติ | 0 | Depot | 2026-08-01 | 2026-02-13 | 100% | Completed | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed |  | MDW-39507 | MDW-69514 | MDW-69515
186 | MDW-39509 | Lot02 | MO-BEM3 | MO-BEM | High Roof at the entrance and exit of the under floor wheel lathe | สหชาติ | 0 | Depot | 2026-08-04 | 2026-02-13 | 100% | Completed | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed |  | MDW-39509 | MDW-69518
187 | MDW-39511 | Lot02 | MO-BEM4.1 | MO-BEM | Maintenance Office Rooms at Main Workshop - Civil & AR | สหชาติ | 0 | Depot | 2026-07-03 | 2026-04-13 | 100% | Completed | 2026-05-14 | 100% | Completed | 0 | 0% | 0% | 2026-06-30 | 100% | Completed |  | MDW-39511 | MDW-69522 | MDW-69523
188 | MDW-39512 | Lot02 | MO-BEM4.2 | MO-BEM | Maintenance Office Rooms at Main Workshop - Building Services | ประธาน | 0 | Depot | 2026-07-04 | 2026-04-13 | 100% | Completed | 2026-05-14 | 100% | Completed | 0 | 0% | 0% | 2026-06-30 | 100% | Completed |  | MDW-39512 | MDW-69524 | MDW-69525
189 | MDW-39513 | Lot02 | MO-BEM5 | MO-BEM | Install Concrete car barrier along the walkway in front of MWS building | สหชาติ | 0 | Depot | 2027-01-01 | 2026-10-14 | 100% | Completed | 2026-11-14 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 100% | Completed |  | MDW-39513 | MDW-69526 | MDW-69527
190 | 0 | Lot02 | MO-BEM6 | MO-BEM | Handrail on top of the water tank on the rooftop of the Admin Building | สหชาติ | 0 | Depot | 2027-01-01 | 2026-10-19 | 100% | Completed | 2026-11-19 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 |  | 0 | 0
191 | 0 | Lot02 | MO-BEM7 | MO-BEM | Modify maintenance service door to the roof building to easier access while maintaining safe operational standards | สหชาติ | 0 | Depot | 2027-01-01 | 2026-10-19 | 50% | Late | 2026-11-19 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 |  | 0 | 0
192 | MDW-39536 | Lot02 | MO-BEM8 | MO-BEM | Company logo and Central Control Room sign in CCR room. | สหชาติ | 0 | Depot | 2026-05-01 | 2026-01-27 | 100% | Completed | 2026-03-14 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed |  | MDW-39536 | MDW-69572 | MDW-69573
193 | MDW-39536 | Lot02 | MO-BEM9 | MO-BEM | Soundproof insulation on the wall and structure and equipment in the CCR room. | สหชาติ | 0 | Depot | 2026-05-01 | 2026-01-12 | 100% | Completed | 2026-02-27 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed |  | MDW-39536 | MDW-69572 | MDW-69573
194 | MDW-39526 | Lot02 | MO-BEM10 | MO-BEM | Relocate Fire Hose Cabinet to be outside of the clearance gauge zone 17 set | ประธาน | 0 | Depot | 2026-05-01 | 2026-01-12 | 100% | Completed | 2026-02-27 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed |  | MDW-39526 | MDW-69552 | MDW-69553
195 | MDW-39528 | Lot02 | MO-BEM11.1 | MO-BEM | Washing Area in Cleaning Staff Room at Stabling Yard - Civil & AR | สหชาติ | 0 | Depot | 2026-08-03 | 2026-06-03 | 100% | Completed | 2026-07-04 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed |  | MDW-39528 | MDW-69556 | MDW-69557
196 | MDW-39529 | Lot02 | MO-BEM11.2 | MO-BEM | Washing Area in Cleaning Staff Room at Stabling Yard - Building Services | ประธาน | 0 | Depot | 2026-08-04 | 2026-04-14 | 100% | Completed | 2026-05-30 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed |  | MDW-39529 | MDW-69558 | MDW-69559
197 | MDW-39522 | Lot02 | MO-BEM12 | MO-BEM | Rain protection for Water treatment Building | สหชาติ | 0 | Depot | 2026-08-05 | 2026-04-29 | 100% | Completed | 2026-05-30 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed |  | MDW-39522 | MDW-69544 | MDW-69545
198 | MDW-39522 | Lot02 | MO-BEM13.1 | MO-BEM | Zero Discharge Water treatment in Depot - Civil & AR | สหชาติ | 0 | Depot | 2027-01-01 | 2026-08-15 | 100% | Completed | 2026-09-30 | 75% | Late | 0 | 0% | 0% | 2026-12-31 | 63% | On Schedule | คงเหลืองานประกอบและติดตั้งโครงหลงัคา | MDW-39522 | MDW-69544 | MDW-69545
199 | MDW-39530 | Lot02 | MO-BEM13.2 | MO-BEM | Zero Discharge Water treatment in Depot - Building Services | ประธาน | 0 | Depot | 2027-01-01 | 2026-08-15 | 100% | Completed | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 50% | On Schedule | 0 | MDW-39530 | MDW-69560 | MDW-69561
200 | MDW-39516 | Lot02 | MO-BEM14.1 | MO-BEM | Modification Works : Walkway Bridge between BL Depot and ORL Depot - Civil & AR | สหชาติ | 0 | Depot | 2026-08-02 | 2026-02-28 | 100% | Completed | 2026-06-15 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 95% | Late | คงเหลืองานติดตั้งสะพานและปรับพื้นที่ถนน | MDW-39516 | MDW-69532 | MDW-69533
201 | MDW-39517 | Lot02 | MO-BEM14.2 | MO-BEM | Modification Works : Walkway Bridge between BL Depot and ORL Depot - Building Services | ประธาน | 0 | Depot | 2026-08-03 | 2026-01-14 | 100% | Completed | 2026-03-01 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 10% | Late | รองานหลังคา CIV Oct-26 | MDW-39517 | MDW-69534 | MDW-69535
202 | MDW-39514 | Lot02 | MO-BEM15.1 | MO-BEM | Roof for cars parking lots area (184 car)t - Civil & AR | สหชาติ | 0 | Depot | 2026-08-03 | 2026-02-28 | 100% | Completed | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed |  | MDW-39514 | MDW-69528 | MDW-69529
203 | MDW-39515 | Lot02 | MO-BEM15.2 | MO-BEM | Roof for cars parking lots area (184 car) - Building Services | ประธาน | 0 | Depot | 2026-08-03 | 2026-02-28 | 100% | Completed | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed |  | MDW-39515 | MDW-69530 | MDW-69531
204 | MDW-39519 | Lot02 | MO-BEM16 | MO-BEM | Walkway roof and High roof across the road from Admin ORL to Depot slap | สหชาติ | 0 | Depot | 2026-08-01 | 2026-06-15 | 100% | Completed | 2026-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-10-31 | 57% | On Schedule | คงเหลืองานโครงเหล็ก หลังคา และ Composite | MDW-39519 | MDW-69538 | MDW-69539
205 | MDW-39519 | Lot02 | MO-BEM17 | MO-BEM | Walkway roof to car park in front of admin ORL(3x5m.) | สหชาติ | 0 | Depot | 2026-08-01 | 2026-06-15 | 100% | Completed | 2026-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-10-31 | 70% | On Schedule | คงเหลืองานโครงหลังคาและมุงหลังคา | MDW-39519 | MDW-69538 | MDW-69539
206 | MDW-39519 | Lot02 | MO-BEM18 | MO-BEM | Walkway roof over the footpath near depot slab (1.50 m. x 290 m.) and stair up to depot slap. | สหชาติ | 0 | Depot | 2026-08-01 | 2026-06-15 | 100% | Completed | 2026-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-10-31 | 0% | On Schedule | รอ BEM สรุปว่ายกเลิกหรือทำ | MDW-39519 | MDW-69538 | MDW-69539
207 | MDW-39557 | Lot02 | MO-BEM19 | MO-BEM | Install Chain Link fence to enclose parking area | สหชาติ | 0 | Depot | 2026-10-01 | 2026-06-29 | 100% | Completed | 2026-07-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 0% | Late | 0 | MDW-39557 | MDW-69614 | MDW-69615
208 | MDW-39523 | Lot02 | MO-BEM20 | MO-BEM | Hose bib 1/2" 4 sets for Tree around Admin area | ประธาน | 0 | Depot | 2026-06-01 | 2026-04-23 | 100% | Completed | 2026-06-08 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed |  | MDW-39523 | MDW-69546 | MDW-69547
209 | - | Lot02 | MO-BEM21 | MO-BEM | Relocate Security Guard Box at Front Gate and Install Roof 3x5m. | สหชาติ | 0 | Depot | 2027-01-03 | 2026-07-31 | 100% | Completed | 2026-09-30 | 75% | Late | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule |  |  | 0 | 0
210 | MDW-39534 | Lot02 | MO-BEM21.1 | MO-BEM | Modification Works : Security Guard Box at ORL Depot Entrance - Civil & AR | สหชาติ | 0 | Depot | 2027-01-02 | 2026-07-31 | 100% | Completed | 2026-09-30 | 67% | Late | 0 | 0% | 0% | 2026-12-31 | 100% | Completed |  | MDW-39534 | MDW-69568 | MDW-69569
211 | MDW-39535 | Lot02 | MO-BEM21.2 | MO-BEM | Modification Works : Security Guard Box at ORL Depot Entrance - Building Services | ประธาน | 0 | Depot | 2027-01-03 | 2026-07-31 | 100% | Completed | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 50% | On Schedule |  | MDW-39535 | MDW-69570 | MDW-69571
212 | MDW-39532 | Lot02 | MO-BEM22 | MO-BEM | Addition Spike fence for MRTA fence and Chain link at Klong Chourdyai 400m. | สหชาติ | 0 | Depot | 2027-01-01 | 2026-08-30 | 70% | Late | 2026-09-30 | 0% | Late | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule |  | MDW-39532 | MDW-69564 | MDW-69565
213 | MDW-39527 | Lot02 | MO-BEM23 | MO-BEM | Hand sink with eye wash station | ประธาน | พี่ต่อ | Depot | 2027-01-01 | 2026-08-30 | 100% | Completed | 2026-10-15 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 100% | Completed |  | MDW-39527 | MDW-69554 | MDW-69555
214 | MDW-39531 | Lot02 | MO-BEM24 | MO-BEM | Guard rail protection for Fire Hose Cabinet 8 set | สหชาติ | 0 | Depot | 2026-06-01 | 2026-03-14 | 100% | Completed | 2026-04-14 | 100% | Completed | 0 | 0% | 0% | 2026-08-15 | 100% | Completed |  | MDW-39531 | MDW-69562 | MDW-69563
215 | MDW-39557 | Lot02 | MO-BEM25.1 | MO-BEM | Chain Link Fence to divide controlled areas on Depot slab 3 m.x 485 m. - Civil & AR | สหชาติ | 0 | Depot | 2026-10-01 | 2026-06-14 | 100% | Completed | 2026-07-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 0% | Late |  | MDW-39557 | MDW-69614 | MDW-69615
216 | MDW-39520 | Lot02 | MO-BEM25.2 | MO-BEM | Chain Link Fence to divide controlled areas on Depot slab 3 m.x 485 m.- Building Services | ประธาน | 0 | Depot | 2026-10-01 | 2026-06-14 | 100% | Completed | 2026-07-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 0% | Late |  | MDW-39520 | MDW-69540 | MDW-69541
217 | MDW-39518 | Lot02 | MO-BEM26 | MO-BEM | Street Lighting system area between MRTA Fence and Depot slab | ประธาน | 0 | Depot | 2026-08-01 | 2026-04-14 | 50% | Late | 2026-05-15 | 0% | Late | 0 | 0% | 0% | 2026-07-31 | 0% | Late |  | MDW-39518 | MDW-69536 | MDW-69537
218 | - | Lot02 | MO-BEM27 | MO-BEM | Compacted gravel walkway along the Test Track OR-BL 1.2 m. | สหชาติ | พรพรหม | Depot | 2027-01-01 | 2026-08-30 | 100% | Completed | 2026-09-30 | 0% | Late | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule |  |  | 0 | 0
219 | MDW-39524 | Lot02 | MO-BEM28.1 | MO-BEM | Walkway under Depot Slab for Maintenance Service - Civil & AR | สหชาติ | 0 | Depot | 2027-01-02 | 2026-09-14 | 100% | Completed | 2026-10-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 100% | Completed |  | MDW-39524 | MDW-69548 | MDW-69549
220 | MDW-39525 | Lot02 | MO-BEM28.2 | MO-BEM | Walkway under Depot Slab for Maintenance Service - Building Services | ประธาน | 0 | Depot | 2027-01-03 | 2026-09-14 | 100% | Completed | 2026-10-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 50% | On Schedule |  | MDW-39525 | MDW-69550 | MDW-69551
221 | MDW-39521 | Lot02 | MO-BEM29 | MO-BEM | Walkway Bridge across the canal for Depot area inspection patrols 3 location | สหชาติ | 0 | Depot | 2027-01-01 | 2026-08-15 | 100% | Completed | 2026-09-30 | 67% | Late | 0 | 0% | 0% | 2026-12-31 | 95% | On Schedule |  | MDW-39521 | MDW-69542 | MDW-69543
222 | - | Lot02 | MO-BEM30 | MO-BEM | Cut down trees between Depot BL+ORL and MRTA Fence | สหชาติ | 0 | Depot | 2027-01-01 | 2026-10-29 | 0% | Late | 2026-11-29 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule |  |  | 0 | 0
223 | 0 | Lot02 | MO-BEM31 | MO-BEM | Provide facility system and interface to MMC room (Fire Alarm / CCTV / VMS / TEL / CASS / Radio / PA) | บัณฑิต | 0 | Depot | 2026-10-01 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
224 | - | Lot02 | MO-BEM32 | MO-BEM | Stainless Guard rail balustrade for waiting area | สหชาติ | 0 | Depot | 2026-05-01 |  |  | 0% |  |  | 0% | 0 | 0% | 0% |  |  | 0 |  |  | 0 | 0
225 | - | Lot02 | MO-BEM33 | MO-BEM | Concrete walkway 2 x 80 m. For fire escape route | สหชาติ | 0 | Depot | 2026-05-01 |  |  | 0% |  |  | 0% | 0 | 0% | 0% |  |  | 0 |  |  | 0 | 0
226 | - | Lot02 | MO-BEM34 | MO-BEM | Access Gate (Full Height Turnstile) at 1st floor admin ORL | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule |  |  | 0 | 0
227 | - | Lot02 | MO-BEM35 | MO-BEM | Access Gate (Tripod with Swing Gate) at MWS Entrance | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule |  |  | 0 | 0
228 | - | Lot02 | MO-BEM36 | MO-BEM | Access Gate (Tripod with Swing Gate) at Admin 2nd floor connect to OCC | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule |  |  | 0 | 0
229 | - | Lot02 | MO-BEM37 | MO-BEM | Access Gate (Tripod with Swing Gate) on Klong Chourdyai bridge | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule |  |  | 0 | 0
230 | - | Lot02 | MO-BEM38 | MO-BEM | Access Gate (Tripod with roof covering) at parking lot OCC | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule |  |  | 0 | 0
231 | - | Lot02 | MO-BEM39 | MO-BEM | Access Gate (Tripod with roof covering) at Stair up to Depot slab | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule |  |  | 0 | 0
232 | - | Lot02 | MO-BEM40 | MO-BEM | Access Control (2 Factors, Card + Finger Print) at High Security rooms - CCR/PTR/Store | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule |  |  | 0 | 0
233 | - | Lot02 | MO-BEM41 | MO-BEM | Link CCTV Landscape of all depot ORL area for MMC BL monitoring. | บัณฑิต | 0 | 0 | 2027-01-01 | 2026-11-28 | 0% | On Schedule | 2026-11-29 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule |  |  | 0 | 0
234 | - | Lot02 | MO-BEM42 | MO-BEM | Fire Suppression Control Panel Cover which located in tunnel | สู่โชค | 0 | 0 | 2027-01-01 |  |  | 0% |  |  | 0% | 0 | 0% | 0% |  |  | 0 |  |  | 0 | 0
235 | MDW-39537 | Lot02 | MO-BEM43 | MO-BEM | Handrails for ladder at IVS and Vent buildings | สหชาติ | 0 | 0 | 2026-09-01 | 2026-03-31 | 70% | Late | 2026-05-01 | 0% | Late | 0 | 0% | 0% | 2026-08-31 | 0% | Late |  | MDW-39537 | MDW-69574 | MDW-69575
236 | MDW-39538 | Lot02 | MO-BEM44 | MO-BEM | Escalator Anti-Slide device for all station. | สหชาติ | 0 | 0 | 2026-09-01 | 2026-05-30 | 100% | Completed | 2026-06-30 | 100% | Completed | 2027-01-31 | 100% | Completed | 2027-02-28 | 70% | On Schedule |  | MDW-39538 | MDW-69576 | MDW-69577
237 | MDW-39539 | Lot02 | MO-BEM45 | MO-BEM | Roof for control panel on vent building | สหชาติ | 0 | 0 | 2027-01-01 | 2026-09-14 | 70% | Late | 2026-10-30 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule |  | MDW-39539 | MDW-69578 | MDW-69579
238 | MDW-39553 | Lot02 | MO-BEM46 | MO-BEM | Provide Standing plate or ladder to access the Fire Valve in at Omega points for all underground stations. | สหชาติ | 0 | Depot | 2027-01-01 | 2026-09-14 | 0% | Late | 2026-10-30 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule |  | MDW-39553 | MDW-69606 | MDW-69607
239 | MDW-39540 | Lot02 | MO-BEM47 | MO-BEM | Water drop protection above UPS cabinet at station and Depot | สหชาติ | 0 | 0 | 2027-01-01 | 2026-09-14 | 0% | Late | 2026-10-30 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule |  | MDW-39540 | MDW-69580 | MDW-69581
240 | MDW-39541 | Lot02 | MO-BEM48 | MO-BEM | Fire alarm manual call point cover in public area at all station | ประธาน | 0 | 0 | 2027-01-01 | 2026-09-14 | 50% | Late | 2026-10-30 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule |  | MDW-39541 | MDW-69582 | MDW-69583
241 | MDW-39542 | Lot02 | MO-BEM49 | MO-BEM | Emergency stop button cover for escalator at all station. | สหชาติ | 0 | 0 | 2027-01-01 | 2026-09-14 | 0% | Late | 2026-10-30 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule |  | MDW-39542 | MDW-69584 | MDW-69585
242 | 0 | Lot02 | MO-BEM50 | MO-BEM | Modify maintenance service door to the roof of OR13 vent building to easier access while maintaining safe operational standards | สู่โชค | 0 | Depot | 2027-01-01 | 2026-10-29 | 0% | Late | 2026-10-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule |  |  | 0 | 0
243 | MDW-39514 | Lot02 | MO-BEM51 | MO-BEM | Modify existing car park to be 220 motorcycle parking lots including floor painting and parking roof | สหชาติ | 0 | Depot | 2026-08-01 | 2026-01-29 | 100% | Completed | 2026-03-16 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed |  | MDW-39514 | MDW-69528 | MDW-69529
244 | MDW-39534 | Lot02 | MO-BEM52 | MO-BEM | Modify the sidewalk for temporary parking at entrance | สหชาติ | 0 | Depot | 2027-01-01 | 2026-07-31 | 100% | Completed | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 100% | Completed |  | MDW-39534 | MDW-69568 | MDW-69569
245 | MDW-39554 | Lot02 | MO-BEM53.1 | MO-BEM | Modification Works : Security Guard Box at OCC Parking Area - Civil & AR | สหชาติ | 0 | Depot | 2027-01-02 | 2026-09-14 | 100% | Completed | 2026-10-31 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule |  | MDW-39554 | MDW-69608 | MDW-69609
246 | MDW-39555 | Lot02 | MO-BEM53.2 | MO-BEM | Modification Works : Security Guard Box at OCC Parking Area - Building Services | ประธาน | 0 | 0 | 2027-01-02 | 2026-09-14 | 100% | Completed | 2026-10-31 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 50% | On Schedule |  | MDW-39555 | MDW-69610 | MDW-69611
247 | NoDrawing | Lot02 | MO-BEM54 | MO-BEM | Strengthen the Maintenance Walkway of the TEF fan | สหชาติ | 0 | 0 | 2027-01-01 | 2026-07-16 | 100% | Completed | 2026-08-16 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule |  |  | 0 | 0
Lot 1 Construction/Installation
[26 empty] | CK Pesonsible Person | Total | Completed | Late | On Schedule
[26 empty] | สหชาติ | 29 | 19 | 4 | 6
[26 empty] | ประธาน | 37 | 25 | 5 | 7
[26 empty] | สมศักดิ์ | 13 | 10 | 2 | 1
[26 empty] | กำพล | 9 | 4 | 1 | 4
[26 empty] | บัณฑิต | 4 | 1 | 2 | 1
[26 empty] | สู่โชค | 1 | 0 | 1 | 0
[26 empty] | ธัญวิทย์ | 1 | 0 | 0 | 1
[26 empty] | มนตรี | 6 | 3 | 1 | 2
[26 empty] | มนต์ชัย | 1 | 1 | 0 | 0
[26 empty] | - | 2 | 2 | 0 | 0
Lot 2 Construction/Installation
[26 empty] | CK Pesonsible Person | Total | Completed | Late | On Schedule
[26 empty] | สหชาติ | 61 | 23 | 10 | 28
[26 empty] | ประธาน | 25 | 9 | 7 | 9
[26 empty] | บัณฑิต | 8 | 0 | 0 | 8
[26 empty] | สู่โชค | 1 | 0 | 0 | 1

## T&C (hidden)
T&C
No. | Design Submission | Lot No. | Code | System | Activity Name | CK Responsible Person |  | Location | Expected Completion Month | Design (PLAN) | Design (%) | Design (Status) | Procurement (PLAN) | Procurement (%) | Procurement (Status) | Manufacturing / Delivery Process (PLAN) | Manufacturing / Delivery Process (%) | Manufacturing / Delivery (Status) | Construction /Installation (PLAN) | Construction /Installation (%) | Construction /Installation (Status) | T&C (PLAN) | T&C (%) | T&C (Status) | Note | Design Submission | Procedure No. | Test Report No.
1 | MDW-39246-60 | Lot01 | GEN1 | GEN | Rooms and Building Service Systems Modification in Stations Area | - | 0 | 0 | 2026-08-01 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39246 | MDW-69259 | MDW-69260
2 | MDW-39246 | Lot01 | GEN1.1 | GEN | Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR13 - OR17 | ประธาน | 0 | 0 | 2026-08-01 | 2026-01-30 | 100% | Completed | 2026-03-01 | 100% | Completed | 0 | 0% | 0% | 2026-03-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39246 | MDW-69259 | MDW-69260
3 | MDW-39247 | Lot01 | GEN1.2 | GEN | Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR18 - OR22 | ประธาน | 0 | 0 | 2026-08-01 | 2025-12-30 | 100% | Completed | 2026-01-29 | 100% | Completed | 0 | 0% | 0% | 2026-02-28 | 100% | Completed | 0 | 0 | 0 |  | MDW-39247 | MDW-69259 | MDW-69261
4 | MDW-39248 | Lot01 | GEN1.3 | GEN | Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR23 - OR29 | ประธาน | 0 | 0 | 2026-08-01 | 2026-01-30 | 100% | Completed | 2026-03-01 | 100% | Completed | 0 | 0% | 0% | 2026-03-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39248 | MDW-69259 | MDW-69262
5 | MDW-39252 | Lot01 | GEN1.4 | GEN | Modification of Fire Suppression System (N2) in Commerial Room at OR14 | ประธาน | 0 | 0 | 2026-08-01 | 2025-12-30 | 100% | Completed | 2026-01-29 | 100% | Completed | 0 | 0% | 0% | 2026-02-28 | 100% | Completed | 0 | 0 | 0 |  | MDW-39252 | MDW-69269 | MDW-69270
6 | MDW-39253 | Lot01 | GEN1.5 | GEN | Modification of Civil Work in Telecommunication Room at OR14 | สหชาติ | 0 | 0 | 2026-08-01 | 2025-12-30 | 100% | Completed | 2026-01-29 | 100% | Completed | 0 | 0% | 0% | 2026-02-28 | 100% | Completed | 0 | 0 | 0 |  | MDW-39253 | MDW-69271 | MDW-69272
7 | MDW-39254 | Lot01 | GEN1.6 | GEN | Modification in Staff Mess Room at OR13-OR17 | ประธาน | 0 | 0 | 2026-08-01 | 2026-01-30 | 100% | Completed | 2026-03-01 | 100% | Completed | 0 | 0% | 0% | 2026-03-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39254 | MDW-69273 | MDW-69274
8 | MDW-39255 | Lot01 | GEN1.7 | GEN | Modification in Staff Mess Room at OR18-OR22 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39255 | MDW-69273 | MDW-69275
9 | MDW-39256 | Lot01 | GEN1.8 | GEN | Modification in Staff Mess Room at OR23-OR29 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39256 | MDW-69273 | MDW-69276
10 | MDW-39257 | Lot01 | GEN1.9 | GEN | Modification of Air Conditioning in CER and SER at OR13-OR19 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 99% | Late | 0 | 0 | 0 |  | MDW-39257 | MDW-69277 | MDW-69278
11 | MDW-39258 | Lot01 | GEN1.10 | GEN | Modification of Air Conditioning in CER and SER at OR20-OR22 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 99% | Late | 0 | 0 | 0 |  | MDW-39258 | MDW-69277 | MDW-69279
12 | MDW-39259 | Lot01 | GEN1.11 | GEN | Modification of Air Conditioning in CER and SER at OR23-OR29 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 99% | Late | 0 | 0 | 0 |  | MDW-39259 | MDW-69277 | MDW-69280
13 | MDW-39272 | Lot01 | GEN1.12 | GEN | Modification of New M&E Room at IVS15 - IVS17 Civil & AR | สหชาติ | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39272 | MDW-69299 | MDW-69300
14 | MDW-39273 | Lot01 | GEN1.13 | GEN | Modification of New M&E UPS Room at IVS15-IVS17 - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 99% | Late | 0 | 0 | 0 |  | MDW-39273 | MDW-69301 | MDW-69302
15 | MDW-39294 | Lot01 | GEN1.14 | GEN | Provision of Architectural Work in new M&E UPS room at OR23 | สหชาติ | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39294 | MDW-69339 | MDW-69340
16 | MDW-39299 | Lot01 | GEN1.15 | GEN | Provision of Air Conditioning System in Commercial Room at OR13-OR19 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39299 | MDW-69349 | MDW-69350
17 | MDW-39306 | Lot01 | GEN1.16 | GEN | Modification CER and First Aid Room at OR14 - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39306 | MDW-69363 | MDW-69364
18 | MDW-39307 | Lot01 | GEN1.17 | GEN | Additional Fence at Back of House OR13 - OR22 and IVS East Section | สหชาติ | 0 | 0 | 2026-08-01 | 2026-09-30 | 100% | Completed | 2026-10-31 | 50% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0 | 0 |  | MDW-39307 | MDW-69365 | MDW-69366
19 | MDW-39249 | Lot01 | GEN1.18 | GEN | SOR Counter and Workstation Hanging Support Installation on East Section | สหชาติ | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39249 | MDW-69263 | MDW-69264
20 | MDW-39250 | Lot01 | GEN1.19 | GEN | Ticket Office Modification on East Section | สหชาติ | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39250 | MDW-69265 | MDW-69266
21 | MDW-39261 | Lot01 | GEN2 | GEN | Rooms and Building Service Systems Modification in Depot Area | - | 0 | Depot | 2026-08-01 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39261 | MDW-69283 | MDW-69284
22 | MDW-39260 | Lot01 | GEN2.1 | GEN | Modification of Air Conditioning in M&E Room at OCC Building | ประธาน | 0 | 0 | 2026-08-01 | 2025-12-30 | 100% | Completed | 2026-01-29 | 100% | Completed | 0 | 0% | 0% | 2026-02-28 | 100% | Completed | 0 | 0 | 0 |  | MDW-39260 | MDW-69281 | MDW-69282
23 | MDW-39261 | Lot01 | GEN2.2 | GEN | Provision of UPS for MDB Control at Main Workshop, OCC Building, Admin Building, Stabling Yard and Train Washing Plant | ประธาน | 0 | 0 | 2026-08-01 | 2026-09-01 | 100% | Completed | 2026-10-01 | 100% | Completed | 0 | 0% | 0% | 2026-10-31 | 90% | On Schedule | 0 | 0 | 0 |  | MDW-39261 | MDW-69283 | MDW-69284
24 | MDW-39262 | Lot01 | GEN2.3 | GEN | Provision of Redundant MDB at OCC Building, Admin Building and Canteen | ประธาน | 0 | 0 | 2026-08-01 | 2026-09-01 | 100% | Completed | 2026-10-01 | 100% | Completed | 0 | 0% | 0% | 2026-10-31 | 95% | On Schedule | 0 | 0 | 0 |  | MDW-39262 | MDW-69285 | MDW-69286
25 | MDW-39263 | Lot01 | GEN2.4 | GEN | Additonal Lighting System at Depot Area | ประธาน | 0 | 0 | 2026-08-01 | 2026-04-01 | 100% | Completed | 2026-05-01 | 100% | Completed | 0 | 0% | 0% | 2026-05-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39263 | MDW-69287 | MDW-69288
26 | MDW-39290 | Lot01 | GEN2.5 | GEN | Modification Room for PSY at Depot Buildings - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39290 | MDW-69331 | MDW-69332
27 | MDW-39300 | Lot01 | GEN2.6 | GEN | Modification SIG-PSD Office at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39300 | MDW-69351 | MDW-69352
28 | MDW-39301 | Lot01 | GEN2.7 | GEN | Modification Backup CCR Room at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39301 | MDW-69353 | MDW-69354
29 | MDW-39302 | Lot01 | GEN2.8 | GEN | Modification SER at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39302 | MDW-69355 | MDW-69356
30 | MDW-39303 | Lot01 | GEN2.9 | GEN | Modification CER & SCADA Room at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39303 | MDW-69357 | MDW-69358
31 | MDW-39309 | Lot01 | GEN2.10 | GEN | Modification Air Conditioning System at CCR | ประธาน | 0 | 0 | 2026-08-01 | 2026-10-01 | 100% | Completed | 2026-10-31 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 80% | On Schedule | 0 | 0 | 0 |  | MDW-39309 | MDW-69369 | MDW-69370
32 | MDW-39312 | Lot01 | GEN2.11 | GEN | Modification Electronic Workshop at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-10-31 | 100% | Completed | 2026-11-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0 | 0 |  | MDW-39312 | MDW-69375 | MDW-69376
33 | MDW-39313 | Lot01 | GEN2.12 | GEN | Modification Battery Charger Room at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-10-31 | 100% | Completed | 2026-11-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0 | 0 |  | MDW-39313 | MDW-69377 | MDW-69378
34 | MDW-39314 | Lot01 | GEN2.13 | GEN | Modification Machining Room at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-10-31 | 90% | On Schedule | 2026-11-30 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0 | 0 |  | MDW-39314 | MDW-69379 | MDW-69380
35 | MDW-39315 | Lot01 | GEN2.14 | GEN | Modification Electronic Workshop, Battery Charger and Machining Room at Main Workshop - Civil & AR | สหชาติ | 0 | 0 | 2026-08-01 | 2026-10-31 | 70% | On Schedule | 2026-11-30 | 90% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0 | 0 |  | MDW-39315 | MDW-69383 | MDW-69384
36 | MDW-39297 | Lot01 | GEN2.15 | GEN | Training Room at Ratchada Station (Part 2) | สหชาติ | 0 | 0 | 2026-08-01 | 2026-08-01 | 0% | Late | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39297 | MDW-69345 | MDW-69346
37 | MDW-39291 | Lot01 | GEN2.16 | GEN | Conductor Rail Arrangement Modification at Main Line East Section | กำพล | 0 | 0 | 2026-08-01 | 2026-09-30 | 100% | Completed | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 90% | On Schedule | 0 | 0 | 0 |  | MDW-39291 | MDW-69333 | MDW-69334
38 | MDW-39292 | Lot01 | GEN2.17 | GEN | Conductor Rail Arrangement Modification at Depot | กำพล | 0 | 0 | 2026-08-01 | 2026-09-30 | 100% | Completed | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 90% | On Schedule | 0 | 0 | 0 |  | MDW-39292 | MDW-69335 | MDW-69336
39 | MDW-39295 | Lot01 | GEN2.18 | GEN | Dangerous Goods Building in Depot - Civil & AR | สหชาติ | 0 | 0 | 2026-08-01 | 2026-01-27 | 100% | Completed | 2026-02-27 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39295 | MDW-69341 | MDW-69342
40 | MDW-39296 | Lot01 | GEN2.19 | GEN | Dangerous Goods Building in Depot - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2025-12-13 | 100% | Completed | 2026-01-28 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39296 | MDW-69343 | MDW-69344
41 | MDW-39308 | Lot01 | GEN2.20 | GEN | Additional Locking Devices for Main Line Tandem Turnouts 2007, 2010 & 2013 and Depot Turnout D16 | กำพล | 0 | 0 | 2026-08-01 | 2026-11-30 | 50% | On Schedule | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0 | 0 |  | MDW-39308 | MDW-69367 | MDW-69368
42 | MDW-39200-31 | Lot01 | GEN3 | GEN | Cable Containment Modification | - | 0 | 0 | 2025-05-28 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39200
43 | - | Lot01 | GEN4 | GEN | Training Room and Workshop Room | - | 0 | 0 | 2026-04-01 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
44 | MDW-39242 | Lot01 | GEN4.0 | GEN | Modification Works for Training Room at Ratchada Station | ประธาน | 0 | 0 | 2026-04-01 | 2025-12-30 | 100% | Completed | 2026-01-31 | 100% | Completed | 0 | 0% | 0% | 2026-03-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39242 | MDW-69251 | MDW-69252
45 | MDW-39244 | Lot01 | GEN4.1 | GEN | AFC Training Room Modification - Civil & AR | สหชาติ | 0 | 0 | 2026-08-21 | 2026-09-30 | 10% | Late | 2026-10-15 | 100% | Completed | 0 | 0% | 0% | 2026-11-15 | 0% | On Schedule | 0 | 0 | 0 |  | MDW-39244 | MDW-69255 | MDW-69256
46 | MDW-39245 | Lot01 | GEN4.2 | GEN | AFC Training Room Modification - Building Services | ประธาน | 0 | 0 | 2026-08-21 | 2025-12-30 | 100% | Completed | 2026-01-31 | 100% | Completed | 0 | 0% | 0% | 2026-03-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39245 | MDW-69257 | MDW-69258
47 | MDW-39235 | Lot01 | GEN5 | GEN | Raised Floor | สหชาติ | 0 | 0 | 2026-06-01 | 2025-05-15 | 100% | Completed | 2024-12-14 | 100% | Completed | 2025-08-04 | 100% | Completed | 2025-12-28 | 100% | Completed | 0 | 0 | 0 |  | MDW-39235 | MDW-69237 | MDW-69238
48 | MDW-39271 | Lot01 | GEN6 | GEN | Wayside Cable Containment in Depot | - | 0 | Depot | 2026-02-22 | 2025-05-15 | 100% | Completed | 2024-12-14 | 100% | Completed | 2025-08-04 | 100% | Completed | 2025-12-28 | 100% | Completed | 0 | 0 | 0 |  | MDW-39271 | MDW-69297 | MDW-69298
49 | MDW-39269 | Lot01 | GEN6.1 | GEN | PSY Wayside Cable Containment for 24 Kv Cable under the Depot slab | ประธาน | 0 | Depot | 2026-02-22 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39269 | MDW-69293 | MDW-69294
50 | MDW-39270 | Lot01 | GEN6.2 | GEN | COM/SIG Wayside Cable Containment in the Depot | มนตรี/ประธาน | 0 | Depot | 2026-02-22 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39270 | MDW-69295 | MDW-69296
51 | - | Lot01 | GEN7 | GEN | Dangerous Waste Storage Building in Depot | - | 0 | Depot | 2026-09-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
52 | DWE-39024 | Lot01 | GEN7.1 | GEN | Dangerous Waste Storage Building in Depot - Civil & AR | สหชาติ | 0 | Depot | 2026-09-20 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0 | 0 |  | DWE-39024 | DWE-69024 | DWE-69124
53 | DWE-39025 | Lot01 | GEN7.2 | GEN | Dangerous Waste Storage Building in Depot - Building service | ประธาน | 0 | Depot | 2026-09-20 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed | 0 | 0% | 0% | 2026-06-30 | 100% | Completed | 0 | 0 | 0 |  | DWE-39025 | DWE-69025 | DWE-69125
54 | - | Lot01 | GEN8 | GEN | General Waste Storage Building in Depot | - | 0 | Depot | 2026-09-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
55 | DWE-39026 | Lot01 | GEN8.1 | GEN | General Waste Storage Building in Depot - Civil & AR | สหชาติ | 0 | Depot | 2026-09-20 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0 | 0 |  | DWE-39026 | DWE-69026 | DWE-69126
56 | DWE-39025 | Lot01 | GEN8.2 | GEN | General Waste Storage Building in Depot - Building service | ประธาน | 0 | Depot | 2026-09-20 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed | 0 | 0% | 0% | 2026-06-30 | 100% | Completed | 0 | 0 | 0 |  | DWE-39025 | DWE-69025 | DWE-69125
57 | DWE-39021 | Lot01 | GEN9 | GEN | Operation Support Equipment | สมศักดิ์ | 0 | Depot | 2026-08-21 | 2025-03-02 | 100% | Completed | 2025-11-02 | 100% | Completed | 2026-11-16 | 90% | On Schedule | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39021 | DWE-69021 | DWE-69121
58 | GRS-39001-40 | Lot01 | GEN10.1 | GEN | Graphic and Signage Station | สหชาติ | 0 | 0 | 2026-08-21 | 2026-06-30 | 100% | Completed | 2026-05-31 | 95% | Late | 2027-01-31 | 76% | On Schedule | 2027-02-28 | 34% | On Schedule | 0 | 0 | 0 |  | GRS-39001 | GRS-69001 | GRS-69002
59 | GRS-39001-40 | Lot01 | GEN10.2 | GEN | Graphic and Signage Mainline & IVS,VS | สหชาติ | 0 | 0 | 2026-08-21 | 2026-06-15 | 79% | Late | 2026-05-31 | 95% | Late | 2026-07-31 | 0% | Late | 2026-07-31 | 0% | Late | 0 | 0 | 0 |  | GRS-39001 | GRS-69001 | GRS-69002
60 | GRS-39001-40 | Lot01 | GEN10.3 | GEN | Graphic and Signage Depot | สหชาติ | 0 | 0 | 2026-08-21 | 2026-08-15 | 90% | Late | 2026-07-31 | 93% | Late | 2026-06-30 | 56% | Late | 2026-06-30 | 19% | Late | 0 | 0 | 0 |  | GRS-39001 | GRS-69001 | GRS-69002
61 | MDW-39289 | Lot01 | GEN11 | GEN | Earthing and Bonding Modification | ประธาน | 0 | 0 | 2026-03-01 | 2025-01-31 | 100% | Completed | 2025-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-02-28 | 100% | Completed | 2026-03-30 | 100% | Completed |  | MDW-39289 | MDW-69329 | MDW-69330
62 | - | Lot01 | GEN12 | GEN | Mainline Cable Trough Modification on East Section | - | 0 | 0 | 2026-06-22 | 2025-10-31 | 100% | Completed | 2025-11-30 | 100% | Completed | 2025-12-30 | 100% | Completed | 2026-03-30 | 100% | Completed | 0 | 0 | 0 |  |  | 0 | 0
63 | MDW-39233 | Lot01 | GEN12.1 | GEN | Main Line Cable Trough Modification (PSY) | มนต์ชัย | 0 | Depot | 2026-06-22 | 2025-10-31 | 100% | Completed | 2025-11-30 | 100% | Completed | 2025-12-30 | 100% | Completed | 2026-03-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39233
64 | MDW-39234 | Lot01 | GEN12.2 | GEN | Main Line Cable Trough Modification (SIG/COM) | มนตรี | 0 | 0 | 2026-06-22 | 2025-10-31 | 100% | Completed | 2025-11-30 | 100% | Completed | 2025-12-30 | 100% | Completed | 2026-03-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39234 | MDW-69234 | MDW-69236
65 | MDW-39236 | Lot01 | GEN13 | GEN | Bird Protection System | สหชาติ | 0 | 0 | 2026-11-19 | 2025-06-30 | 100% | Completed | 2025-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-01-26 | 100% | Completed | 0 | 0 | 0 |  | MDW-39236 | MDW-69239 | MDW-69240
66 | - | Lot01 | GEN14 | GEN | Train Crew Office at Thailand Cultural Centre Station | สหชาติ | 0 | 0 | 2026-08-21 | 2025-09-30 | 100% | Completed | 2026-02-27 | 100% | Completed | 0 | 0% | 0% | 2026-05-31 | 100% | Completed | 0 | 0 | 0 |  |  | 0 | 0
67 | MDW-39240 | Lot01 | GEN14.1 | GEN | Driver Train Simulation Room and Train Crew Office at OR18 - Civil & AR | สหชาติ | 0 | Depot | 2026-08-21 | 2025-09-30 | 100% | Completed | 2026-02-28 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39240 | MDW-69247 | MDW-69248
68 | MDW-39241 | Lot01 | GEN14.2 | GEN | Driver Train Simulation Room and Train Crew Office at OR18 - Building Services | ประธาน | 0 | 0 | 2026-08-21 | 2025-09-30 | 100% | Completed | 2026-02-28 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39241 | MDW-69249 | MDW-69250
69 | MDW-39239 | Lot01 | GEN15 | GEN | Access Panel Closeout for Traction Substation Room in Main Workshop | สหชาติ | 0 | 0 | 2026-03-24 | 2026-01-30 | 100% | Completed | 2026-03-01 | 100% | Completed | 0 | 0% | 0% | 2026-03-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39239 | MDW-69245 | MDW-69246
70 | MDW-39232 | Lot01 | GEN16 | GEN | Level Crossing at Turnout | กำพล | 0 | 0 | 2026-08-21 | 2026-09-30 | 100% | Completed | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-11-15 | 46% | On Schedule | 0 | 0 | 0 |  | MDW-39232 | MDW-69232 | MDW-69233
71 | MDW-39232 | Lot01 | GEN17 | GEN | Track Slab Crossing | ชฎิล/กำพล | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39232 | MDW-69232 | MDW-69233
72 | MDW-39243 | Lot01 | GEN18 | GEN | Eye Adaptation Lighting (Lighting at Tunnel to Expose) | ประธาน | 0 | 0 | 2026-11-19 | 2025-09-30 | 100% | Completed | 2025-10-30 | 100% | Completed | 0 | 0% | 0% | 2026-04-13 | 100% | Completed | 0 | 0 | 0 |  | MDW-39243 | MDW-69253 | MDW-69254
73 | - | Lot01 | GEN19 | GEN | Train Simulation Room and AFC Training Room | - | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
74 | MDW-39244 | Lot01 | GEN19.1 | GEN | Modification AFC Training Center at OR19 - Civil & AR | สหชาติ | 0 | 0 | 2026-11-30 | 2026-09-30 | 100% | Completed | 2026-10-31 | 58% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 0 | 0 | 0 |  | MDW-39244 | MDW-69255 | MDW-69256
75 | MDW-39245 | Lot01 | GEN19.2 | GEN | Modification AFC Training Center at OR19 - Building Services | ประธาน | บัณฑิต | 0 | 2026-11-30 | 2026-09-30 | 100% | Completed | 2026-10-31 | 100% | Completed | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 0 | 0 | 0 |  | MDW-39245 | MDW-69257 | MDW-69258
76 | - | Lot01 | GEN20 | GEN | Dormitory Cable Containments (if any) | - | 0 | 0 | - | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
77 |  | Lot01 | GEN21 | GEN | Project Information Management System (PIMS) | บัณฑิต | 0 | 0 | 2024-09-30 | 2024-08-10 | 100% | Completed | 2024-08-15 | 100% | Completed | 0 | 0% | 0% | 2024-09-04 | 100% | Completed | 2024-09-14 | 100% | Completed
78 | MDW-39237 | Lot01 | GEN22 | GEN | Central BEMS for the MRT Orange Line System | บัณฑิต | 0 | 0 | 2026-08-21 | 2026-04-30 | 0% | Late | 2026-06-30 | 0% | Late | 0 | 0% | 0% | 2026-08-15 | 0% | Late | 2026-08-31 | 0% | Late | PPR Oct-26 กำลังเปรียบเทียบ Spec | MDW-39237 | MDW-69241 | MDW-69242
79 |  | Lot01 | GEN23 | GEN | Asset Information | บัณฑิต | 0 | 0 | 2026-11-19 | 0 | 0% | 0% | 2026-08-30 | 100% | Completed | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0
80 | MDW-39282 | Lot01 | PSD1 | PSD | Holes for PSD Cable Wiring | กำพล | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39282 | MDW-69315 | MDW-69316
81 | MDW-39004 | Lot01 | PSD2 | PSD | Rubber Gap Fillers on Platform Edge | กำพล | 0 | 0 | 2026-08-21 | 2025-07-30 | 100% | Completed | 2026-01-31 | 100% | Completed | 0 | 0% | 0% | 2026-08-31 | 40% | Late | 0 | 0 | 0 |  | MDW-39004 | MDW-69007 | MDW-69008
82 | MDW-39280 | Lot01 | PSD3 | PSD | Platform Finishing | กำพล | 0 | 0 | 2026-08-21 | 2025-07-30 | 100% | Completed | 2025-09-16 | 100% | Completed | 0 | 0% | 0% | 2026-01-07 | 100% | Completed | 0 | 0 | 0 |  | MDW-39280 | MDW-69311 | MDW-69312
83 | MDW-39281 | Lot01 | PSD4 | PSD | Cladding Barrier between EWD and Station Structure | กำพล | 0 | 0 | 2026-08-21 | 2026-02-28 | 100% | Completed | 2026-03-15 | 100% | Completed | 0 | 0% | 0% | 2026-08-15 | 100% | Completed | 0 | 0 | 0 |  | MDW-39281 | MDW-69313 | MDW-69314
84 | - | Lot01 | AFC1 | AFC | Park and Ride System | บัณฑิต/สหชาติ | 0 | 0 | 2026-10-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
85 | MDW-39276 | Lot01 | AFC2 | AFC | Ticket Issuing Machine (TIM) Wall Opening and Closing | สหชาติ | 0 | 0 | 2026-09-20 | 2026-01-30 | 100% | Completed | 2026-03-15 | 50% | Late | 0 | 0% | 0% | 2026-07-13 | 100% | Completed | 0 | 0 | 0 |  | MDW-39276 | MDW-69303 | MDW-69304
86 | MDW-39279 | Lot01 | AFC3 | AFC | Balustrade Modification Along AFC Gate Line | สหชาติ | 0 | 0 | 2026-09-20 | 2026-06-30 | 10% | Late | 2026-08-15 | 50% | Late | 0 | 0% | 0% | 2026-11-06 | 0% | On Schedule | 0 | 0 | 0 |  | MDW-39279 | MDW-69309 | MDW-69310
87 | MDW-39278 | Lot01 | AFC4 | AFC | Underfloor Embedded Duct Modification for AFC Gates Line | สหชาติ | 0 | Depot | 2026-09-20 | 2026-01-30 | 100% | Completed | 2026-04-02 | 67% | Late | 0 | 0% | 0% | 2026-10-09 | 81% | Late | 0 | 0 | 0 |  | MDW-39278 | MDW-69307 | MDW-69308
88 | MDW-39002 | Lot01 | SIG1 | SIG | Test Track Shelters and Test Track Building | สหชาติ | 0 | 0 | 2026-06-22 | 2025-11-22 | 100% | Completed | 2026-01-18 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-04-15 | 100% | Completed | 0 | 0 | 0 |  | MDW-39002 | MDW-69003 | MDW-69004
89 | MDW-39293 | Lot01 | SIG2 | SIG | Rearrangement of track crossing walkway at stabling yard to consistent with the layout of 4-car train parking | กำพล | 0 | Depot | 2026-06-22 | 2025-11-30 | 100% | Completed | 2025-12-30 | 100% | Completed | 0 | 0% | 0% | 2026-03-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39293 | MDW-69337 | MDW-69338
90 | MDW-39288 | Lot01 | SIG3 | SIG | Point Machine Foundation Construction | กำพล | 0 | 0 | 2026-08-21 | 2025-11-21 | 100% | Completed | 2025-12-30 | 100% | Completed | 0 | 0% | 0% | 2026-03-19 | 100% | Completed | 0 | 0 | 0 |  | MDW-39288 | MDW-69327 | MDW-69328
91 | MDW-39001 | Lot01 | SIG4 | SIG | Modification of Depot Track Route Line to Stabling Yard | สู่โชค | 0 | Depot | 2026-06-22 | 2025-10-30 | 100% | Completed | 2025-11-29 | 100% | Completed | 0 | 0% | 0% | 2026-05-28 | 95% | Late | 0 | 0 | 0 |  | MDW-39001 | MDW-69001 | MDW-69002
92 | MDW-39287 | Lot01 | SIG5 | SIG | Strobe Light at Buffer Stops | ประธาน | 0 | Depot | 2026-08-21 | 2026-05-30 | 100% | Completed | 2026-06-29 | 100% | Completed | 0 | 0% | 0% | 2026-08-28 | 100% | Completed | 0 | 0 | 0 |  | MDW-39287 | MDW-69323 | MDW-69324
93 | DWE-39016 | Lot01 | DWE1 | DWE | Diesel Fuel Storage Tank for Maintenance Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-01-16 | 100% | Completed | 2026-06-30 | 100% | Completed | 2026-07-31 | 100% | Completed | 2026-08-09 | 0% | Late | Test ช่วงต้น Nov-26 | DWE-39016 | DWE-69016 | DWE-69116
94 | DWE-39011 | Lot01 | DWE2 | DWE | Movable Height Maintenance Platform Vehicle (Boom Lift) | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-08-06 | 100% | Completed | 2025-12-31 | 100% | Completed | 2026-06-30 | 100% | Completed | 2026-07-09 | 0% | Late | Test 9-15/11/26 | DWE-39011 | DWE-69011 | DWE-69111
95 | DWE-39012 | Lot01 | DWE3 | DWE | Fork Lift Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-03-31 | 100% | Completed | 2026-06-01 | 100% | Completed | 2026-06-30 | 100% | Completed | 2026-07-30 | 0% | Late | Test 9-15/11/26 | DWE-39012 | DWE-69012 | DWE-69112
96 | DWE-39015 | Lot01 | DWE4 | DWE | Compressed Air System and Portable Air Compressor for Depot | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-01-10 | 100% | Completed | 2026-02-15 | 100% | Completed | 2026-09-19 | 0% | Late | 2026-09-29 | 0% | Late | Forecast Install 1/11-30-11/26 | DWE-39015 | DWE-69015 | DWE-69115
97 | DWE-39017 | Lot01 | DWE5 | DWE | Pallet Storage Shelves in Hazardous Storage | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-12-16 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-05-31 | 100% | Completed | 2026-06-05 | 0% | Late | Test 26-30/10/26 | DWE-39017 | DWE-69017 | DWE-69117
98 | DWE-39017 | Lot01 | DWE6 | DWE | Pallet Storage in Main Storage Room | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-12-16 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-05-31 | 100% | Completed | 2026-06-05 | 0% | Late | Test 26-30/10/26 | DWE-39017 | DWE-69017 | DWE-69117
99 | DWE-39017 | Lot01 | DWE7 | DWE | Two-Tier Shelf | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-12-16 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-05-31 | 100% | Completed | 2026-06-05 | 0% | Late | Test 26-30/10/26 | DWE-39017 | DWE-69017 | DWE-69117
100 | DWE-39017 | Lot01 | DWE8 | DWE | Tool Storage | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-12-16 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-05-31 | 100% | Completed | 2026-06-05 | 0% | Late | Test 26-30/10/26 | DWE-39017 | DWE-69017 | DWE-69117
101 | DWE-39018 | Lot01 | DWE9 | DWE | Repair Equipment | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-07-31 | 50% | Late | 2026-10-30 | 70% | On Schedule | 2027-03-03 | 0% | On Schedule | 2027-04-02 | 0% | On Schedule | คงเหลือจัดส่งอุปกรณ์ | DWE-39018 | DWE-69018 | DWE-69118
102 | DWE-39020 | Lot01 | DWE10 | DWE | Oil & Grease Disposal | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-01-16 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-03-31 | 100% | Completed | 2026-07-05 | 0% | Late | Test 9-15/11/26 | DWE-39020 | DWE-69020 | DWE-69120
103 | DWE-39020 | Lot01 | DWE11 | DWE | Grease Dispensers | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-01-16 | 100% | Completed | 2026-04-28 | 100% | Completed | 2026-05-25 | 100% | Completed | 2026-07-05 | 0% | Late | Test 9-15/11/26 | DWE-39020 | DWE-69020 | DWE-69120
104 | DWE-39020 | Lot01 | DWE12 | DWE | Waste Disposal | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-01-16 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-03-31 | 100% | Completed | 2026-07-05 | 0% | Late | Test 9-15/11/26 | DWE-39020 | DWE-69020 | DWE-69120
105 | MDW-39305 | Lot01 | DWE13 | DWE | Safety Provision for Maintenance Pits | สหชาติ | 0 | Depot | 2026-09-20 | 2025-11-30 | 100% | Completed | 2026-04-29 | 100% | Completed | 0 | 0% | 0% | 2026-07-29 | 70% | Late | 0 | 0 | 0 |  | MDW-39305 | MDW-69361 | MDW-69362
106 | DWE-39xxx | Lot01 | DWE14 | DWE | Pit Drainage System in Main Workshop | สมศักดิ์ | 0 | Depot | 2026-09-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39xxx | MDW-69361 | MDW-69362
107 | DWE-39023 | Lot01 | DWE15 | DWE | Provision of Civil Works and Building Services to support Train Washing Equipment | สหชาติ | 0 | Depot | 2026-08-01 | 2025-11-30 | 100% | Completed | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-05-31 | 100% | Completed | 0 | 0 | 0 |  | DWE-39023 | DWE-69023 | DWE-69123
108 | DWE-39013 | Lot01 | DWE16 | DWE | Overhead Traveling Crane | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-04-30 | 100% | Completed | 2026-03-20 | 100% | Completed | 0 | 0% | 0% | 2026-04-04 | 100% | Completed |  | DWE-39013 | DWE-69013 | DWE-69113-513
109 | DWE-39009 | Lot01 | DWE17 | DWE | Vehicle Inspection and Servicing Facilities | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-12-18 | 100% | Completed | 2026-09-07 | 100% | Completed | 0 | 0% | 0% | 2026-10-01 | 0% | Late | Test 9-15/11/26 | DWE-39009 | DWE-69009 | DWE-69109
110 | DWE-39014 | Lot01 | DWE18 | DWE | Permanent Way Maintenance Facility | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-04-30 | 100% | Completed | 2027-02-28 | 100% | Completed | 2027-01-15 | 70% | On Schedule | 0 | 0% | 0% | 2027-03-30 | 0% | On Schedule | Test 18-30/1/27 | DWE-39014 | DWE-69014 | DWE-69114
111 | - | Lot01 | DWE19 | DWE | Permanent Way Vehicles | สมศักดิ์ | 0 | Depot | 2026-09-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
112 | DWE-39001 | Lot01 | DWE19.1 | DWE | Shunting Locomotive | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-12-18 | 100% | Completed | 2026-12-15 | 50% | On Schedule | 0 | 0% | 0% | 2026-12-30 | 0% | On Schedule | Delivery to Thailand Feb-27 | DWE-39001 | DWE-69001 | DWE-69101
113 | DWE-39002 | Lot01 | DWE19.2 | DWE | Tunnel Inspection and Cleaning Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 0% | Late | 2025-12-18 | 100% | Completed | 2026-12-30 | 40% | On Schedule | 0 | 0% | 0% | 2026-10-11 | 0% | Late | Delivery to Thailand Feb-27 | DWE-39002 | DWE-69002 | DWE-69102
114 | DWE-39003 | Lot01 | DWE19.3 | DWE | Hi/Rail Maintenance Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-12-18 | 100% | Completed | 2026-11-30 | 55% | On Schedule | 0 | 0% | 0% | 2026-12-16 | 0% | On Schedule | Delivery to Thailand Dec-26 | DWE-39003 | DWE-69003 | DWE-69103
115 | DWE-39004 | Lot01 | DWE19.4 | DWE | Flat wagon | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-12-18 | 100% | Completed | 2026-10-30 | 68% | On Schedule | 0 | 0% | 0% | 2026-08-11 | 0% | Late | Delivery to Thailand Dec-26 | DWE-39004 | DWE-69004 | DWE-69104
116 | DWE-39005 | Lot01 | DWE19.5 | DWE | Re-railing Equipment | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-11-10 | 100% | Completed | 2026-07-15 | 90% | Late | 0 | 0% | 0% | 2026-08-31 | 0% | Late | Test 16-22/11/26 | DWE-39005 | DWE-69005 | DWE-69105
117 | DWE-39006 | Lot01 | DWE19.6 | DWE | Self-Propelled Rail Based Inspection Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-12-18 | 100% | Completed | 2026-11-03 | 55% | On Schedule | 0 | 0% | 0% | 2026-12-16 | 0% | On Schedule | Delivery to Thailand Dec-26 | DWE-39006 | DWE-69006 | DWE-69106
118 | DWE-39007 | Lot01 | DWE19.7 | DWE | Rail Head Grinding Machine Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 0% | Late | 2025-12-18 | 100% | Completed | 2027-07-31 | 0% | On Schedule | 0 | 0% | 0% | 2027-08-31 | 0% | On Schedule | 0 | DWE-39007 | DWE-69007 | DWE-69107
119 | DWE-39008 | Lot01 | DWE19.8 | DWE | Multi Measuring Rail Vehicle | สมศักดิ์ | 0 | 0 | 2026-09-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39008 | DWE-69008 | DWE-69108
120 | DWE-39010 | Lot01 | DWE19.9 | DWE | High Work Inspection Vehicle | สมศักดิ์ | 0 | 0 | 2026-09-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39010
121 | - | Lot01 | DWE20 | DWE | Building Maintenance Vehicle | - | 0 | 0 | 2026-09-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
122 | EPS-39001 | Lot01 | PSY1 | PSY | Diesel Fuel Storage Tanks for Power Generators | สมศักดิ์ | 0 | 0 | 2026-03-24 | 2026-01-16 | 100% | Completed | 2026-03-31 | 100% | Completed | 2026-03-31 | 100% | Completed | 2026-06-30 | 75% | Late | 2026-07-10 | 0% | Late | คงเหลืองานเดินท่อและ Pump น้ำมัน | EPS-39001 | EPS-69001 | EPS-69002
123 | PSY-39001-9 | Lot01 | PSY2 | PSY | GIS and BSS Building and Other Facilities | สหชาติ | 0 | 0 | 2026-03-24 | 2024-08-29 | 100% | Completed | 2024-09-28 | 69% | Late | 0 | 0% | 0% | 2025-12-04 | 100% | Completed | 0 | 0 | 0 |  | PSY-39001 | PSY-69001 | PSY-69002
124 | PSY-39011 | Lot01 | PSY3 | PSY | Steel Grating Raised Floor for EE Panel | สหชาติ | 0 | 0 | 2026-03-24 | 2024-09-30 | 100% | Completed | 2024-10-30 | 75% | Late | 0 | 0% | 0% | 2025-07-14 | 100% | Completed | 0 | 0 | 0 |  | PSY-39011 | PSY-69015 | PSY-69016
125 | - | Lot01 | PSY4 | PSY | Trapping Box between PSY Service Sub Station (SSS) and Low Volt (LV) System | - | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
126 | SCA-39200 | Lot01 | SCA1 | SCA | Modification of BEMS to receive PSD Signal on East Section | ธารทิพย์ | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | SCA-39200 | SCA-69200 | SCA-69201
127 | - | Lot01 | SCA2 | SCA | Modification of Escalator Interface Point with CCTV and SCADA, East Section | - | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
128 | - | Lot01 | SCA3 | SCA | Magnetic of Fire Alarm System Interface Point with CCTV and SCADA | - | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
129 | SCA-39203 | Lot01 | SCA4 | SCA | Add/Modify Civil Scada Hardwire for all Station | ประธาน/ธารทิพย์ | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | SCA-39203 | SCA-69206 | SCA-69207
130 | COM-39200 | Lot01 | COM1 | COM | Magnetic Door Lock | มนตรี | 0 | 0 | 2026-08-21 | 2025-06-30 | 100% | Completed | 2026-05-15 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 27.25% | On Schedule | 0 | 0 | 0 |  | COM-39200 | COM-69200 | COM-69201
131 | MDW-39283 | Lot01 | COM2 | COM | Intercom System in Cash Handling Room (if require) | บัณฑิต | 0 | 0 | 2026-12-19 | 2025-09-30 | 100% | Completed | 2026-06-30 | 50% | Late | 0 | 0% | 0% | 2026-10-31 | 0% | On Schedule | 2026-12-30 | 0% | On Schedule | รอพื้นที่เข้าติดตั้ง | MDW-39283 | MDW-69317 | MDW-69318
132 | COM-39001 | Lot01 | COM3 | COM | Walk-Through Metal Detector System (WTMD), 1 per entrance | มนตรี | 0 | 0 | 2026-11-19 | 2025-08-31 | 0% | Late | 2026-06-30 | 0% | Late | 0 | 0% | 0% | 2027-02-28 | 0% | On Schedule | 0 | 0 | 0 |  | COM-39001 | COM-69001 | COM-69002
133 | MDW-39284 | Lot01 | COM4 | COM | Traveling Cable in all Lifts | มนตรี | 0 | 0 | - | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39284 | MDW-69319 | MDW-69320
134 | MDW-39304 | Lot01 | COM5 | COM | MEA Radio | ประธาน | 0 | 0 | 2026-09-20 | 2026-01-30 | 100% | Completed | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-06-30 | 95% | Late | 2026-09-30 | 0% | Late | รอเฟอร์นิเจอร์ Fore cast Dec-26 | MDW-39304 | COM-69202 | COM-69203
135 | COM-39004 | Lot01 | COM6 | COM | Main Cable Containment for M&E Dedicated communication link to MRTA Head Quarter | มนตรี | 0 | 0 | 2026-09-20 | 2026-01-31 | 100% | Completed | 2026-02-28 | 100% | Completed | 0 | 0% | 0% | 2026-08-31 | 75% | Late | 0 | 0 | 0 |  | COM-39004 | COM-69005 | COM-69006
136 | AFC-39001 | Lot01 | COM7 | COM | Mini Paging in Ticket Office | บัณฑิต | 0 | 0 | 2026-12-19 | 2025-09-10 | 100% | Completed | 2026-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 0% | Late | 2026-11-30 | 0% | On Schedule | ของมาแล้ว รอพื้นที่เข้าติดตั้ง | AFC-39002 | AFC-69003 | AFC-69004
137 | MDW-39285 | Lot01 | COM8 | COM | Provision of Cable Containment between OCC ORL and OCC BL | มนตรี | 0 | 0 | 2026-07-22 | 0 | 0% | 0% | 0% | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39285
138 | COM-39005 | Lot01 | COM9 | COM | Power Distribution for M&E Systems at MRTA Head Quarter | มนตรี | 0 | 0 | 2026-09-20 | 2026-03-31 | 100% | Completed | 2026-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-08-31 | 100% | Completed | 0 | 0 | 0 |  | COM-39005 | COM-69007 | COM-69008
139 | COM-39205 | Lot01 | COM10 | COM | Underground Cable Containment at Public Areas (if require) | มนตรี | 0 | 0 | 2026-08-21 | 2026-04-30 | 100% | Completed | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39205 | MDW-69200 | MDW-69205
140 | - | Lot01 | COM11 | COM | Intercom at Ticket Issuing Machine | บัณฑิต | 0 | Depot | - | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
141 | RST-39004,8 | Lot01 | RST1 | RST | Driver Training Simulator | ธัญวิทย์ | 0 | Depot | 2026-09-20 | 2025-05-30 | 100% | Completed | 2025-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 81% | On Schedule | 0 | 0 | 0 |  | RST-39004,8
142 | MDW-39500 | Lot02 | MO-CK1.1 | MO-CK | Store Modification Works at Main Workshop - Civil&AR | สหชาติ | 0 | Depot | 2026-06-03 | 2026-02-27 | 100% | Completed | 2026-03-30 | 100% | Completed | 0 | 0% | 0% | 2026-05-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39500 | MDW-69500 | MDW-69501
143 | MDW-39501 | Lot02 | MO-CK1.2 | MO-CK | Store Modification Works at Main Workshop - Building Services | ประธาน | 0 | Depot | 2026-06-04 | 2026-02-12 | 100% | Completed | 2026-03-30 | 100% | Completed | 0 | 0% | 0% | 2026-05-28 | 100% | Completed | 0 | 0 | 0 |  | MDW-39501 | MDW-69502 | MDW-69503
144 | MDW-39503 | Lot02 | MO-CK2 | MO-CK | New MMC at Admin Building - Civil&AR | สหชาติ | 0 | Depot | 2026-08-03 | 2026-04-14 | 100% | Completed | 2026-05-15 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39503 | MDW-69506 | MDW-69507
145 | MDW-39504 | Lot02 | MO-CK3 | MO-CK | Move or link Workstation and control panel to MMC room at admin C 2nd floor | ประธาน | 0 | Depot | 2026-08-02 | 2026-02-28 | 100% | Completed | 2026-04-15 | 100% | Completed | 0 | 0% | 0% | 2026-08-31 | 90% | Late | 0 | 0 | 0 |  | MDW-39504 | MDW-69508 | MDW-69509
146 | MDW-39543 | Lot02 | MO-CK4 | MO-CK | Bird & Rain Protection for Open space Admin C | สหชาติ | 0 | Depot | 2026-08-01 | 2026-04-29 | 100% | Completed | 2026-05-30 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39543 | MDW-69586 | MDW-69587
147 | MDW-39547 | Lot02 | MO-CK5 | MO-CK | Relocate door in front of toilet and build partition wall to conceal the view in side of toilet | สหชาติ | 0 | Depot | 2026-08-02 | 2026-05-14 | 100% | Completed | 2026-06-14 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39547 | MDW-69594 | MDW-69595
148 | MDW-39547 | Lot02 | MO-CK6 | MO-CK | Modify Lockset the emergency door to be used for passage between the 2nd and 3rd floors inside the building. | สหชาติ | 0 | Depot | 2026-08-03 | 2026-04-29 | 100% | Completed | 2026-06-14 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39547 | MDW-69594 | MDW-69595
149 | MDW-39556 | Lot02 | MO-CK7 | MO-CK | Addition small power for lounge and pantry room at 2nd floor and Hall and observation room at 3nd floor | ประธาน | 0 | Depot | 2026-08-04 | 2026-05-14 | 100% | Completed | 2026-06-14 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39556 | MDW-69612 | MDW-69613
150 | MDW-39548 | Lot02 | MO-CK8 | MO-CK | Air Condition for using store room to be pantry room. 2nd floor | ประธาน | 0 | Depot | 2026-08-05 | 2026-04-29 | 100% | Completed | 2026-06-14 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39548 | MDW-69596 | MDW-69597
151 | MDW-39552 | Lot02 | MO-CK9 | MO-CK | Walk Way Hand rail high 90 cm 1 side (144 m. x 7 route) | สหชาติ | 0 | Depot | 2026-10-01 | 2026-05-30 | 100% | Completed | 2026-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 98.77% | Late | 0 | 0 | 0 |  | MDW-39552 | MDW-69604 | MDW-69605
152 | MDW-39544 | Lot02 | MO-CK10 | MO-CK | Barbed wire fence Viaduct CE CW | บัณฑิต/สหชาติ | พี่ต่อ | Depot | 2027-01-01 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39544 | MDW-69588 | MDW-69589
153 | MDW-39545 | Lot02 | MO-CK11 | MO-CK | Chain Link at Cut & Cover 600m. | สหชาติ | พรพรหม | Depot | 2026-06-01 | 2026-02-27 | 100% | Completed | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-08-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39545 | MDW-69590 | MDW-69591
154 | MDW-39546 | Lot02 | MO-CK12 | MO-CK | Chain Link under slab high 1.70 m | สหชาติ | 0 | 0 | 2027-01-01 | 2026-06-30 | 100% | Completed | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 67.27% | On Schedule | 0 | 0 | 0 |  | MDW-39546 | MDW-69592 | MDW-69593
155 | MDW-39550 | Lot02 | MO-CK13.1 | MO-CK | Satellite Store at OR21 - Civil & AR | สหชาติ | 0 | 0 | 2027-01-02 | 2026-08-30 | 100% | Completed | 2026-10-15 | 0% | Late | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0 | 0 |  | MDW-39550 | MDW-69600 | MDW-695601
156 | MDW-39549 | Lot02 | MO-CK13.2 | MO-CK | Maintenance Room and Satellite Store at Stations - Building Services | ประธาน | 0 | 0 | 2027-01-03 | 2026-08-30 | 100% | Completed | 2026-10-15 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 80% | On Schedule | 0 | 0 | 0 |  | MDW-39549 | MDW-69598 | MDW-69599
157 | MDW-39551 | Lot02 | MO-CK14 | MO-CK | Modify Cleaner room at OR29 to be Train crew Standby office with facility system | ประธาน | 0 | Depot | 2026-07-01 | 2026-03-14 | 100% | Completed | 2026-04-29 | 100% | Completed | 0 | 0% | 0% | 2026-06-30 | 95% | Late | 0 | 0 | 0 |  | MDW-39551 | MDW-69602 | MDW-69603
158 | MDW-39295 | Lot02 | MO-CK15.1 | MO-CK | Epoxy Floor Installation and Curb Installation at the Entrance - Civil & AR | สหชาติ | 0 | Depot | 2026-05-01 | 2026-01-27 | 100% | Completed | 2026-02-27 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39295 | MDW-69341 | MDW-69342
159 | MDW-39296 | Lot02 | MO-CK15.2 | MO-CK | Change Electrical Equipment to be Explosion-proof type - Building Services | ประธาน | 0 | Depot | 2026-05-01 | 2025-12-13 | 100% | Completed | 2026-01-28 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 90% | Late | 0 | 0 | 0 |  | MDW-39296 | MDW-69343 | MDW-69344
160 | DWE-39024 | Lot02 | MO-CK16 | MO-CK | Dangerous waste Storage 30 x 5 m. =10 room | สหชาติ | 0 | Depot | 2026-05-01 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0 | 0 |  | DWE-39024 | DWE-69024 | DWE-69124
161 | 0 | Lot02 | MO-CK17 | MO-CK | Safety Sign all Depot Area building | สหชาติ | 0 | Depot | 2026-05-01 | 2025-11-28 | 100% | Completed | 2026-06-15 | 100% | Completed | 2026-09-20 | 27% | Late | 2026-10-15 | 0% | Late | 0 | 0 | 0 |  |  | 0 | 0
162 | 0 | Lot02 | MO-CK18 | MO-CK | Emergency escape route map | สหชาติ | 0 | Depot | 2027-01-01 | 2026-09-30 | 0% | Late | 2026-10-30 | 50% | On Schedule | 2026-12-31 | 0% | On Schedule | 2026-12-31 | 0% | On Schedule | 0 | 0 | 0 |  |  | 0 | 0
163 | 0 | Lot02 | MO-CK19 | MO-CK | Traffic Line Marking (Thermoplastic Paint) | สหชาติ | 0 | Depot | 2026-05-01 | 2026-04-30 | 100% | Completed | 2026-06-15 | 100% | Completed | 2026-10-15 | 100% | Completed | 2026-10-15 | 25% | Late | 0 | 0 | 0 |  |  | 0 | 0
164 | 0 | Lot02 | MO-CK20 | MO-CK | Emergency Car Parking location Painting in front of MWS | สหชาติ | 0 | Depot | 2026-05-01 | 2026-04-30 | 100% | Completed | 2026-06-15 | 100% | Completed | 2026-10-15 | 0% | Late | 2026-10-15 | 0% | Late | 0 | 0 | 0 |  |  | 0 | 0
165 | GRS-39022 | Lot02 | MO-CK21 | MO-CK | Safety Line painting in MWS, Stabling Area, P-way, Track | สหชาติ | 0 | Depot | 2027-01-01 | 2026-06-01 | 100% | Completed | 2026-08-01 | 100% | Completed | 2026-10-15 | 100% | Completed | 2026-12-31 | 81% | On Schedule | 0 | 0 | 0 |  | GRS-39022 | GRS-69001 | GRS-69022
166 | 0 | Lot02 | MO-CK22 | MO-CK | Fire escape stairs level signs in the Depot, VS and IVS areas | สหชาติ | 0 | Depot | 2027-01-01 | 2026-09-30 | 50% | Late | 2026-10-31 | 0% | On Schedule | 2026-10-20 | 0% | Late | 2026-12-31 | 0% | On Schedule | 0 | 0 | 0 |  |  | 0 | 0
167 | DWE-39026 | Lot02 | MO-CK23 | MO-CK | General waste Storage 22 x 5 m | สหชาติ | 0 | Depot | 2026-05-01 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0 | 0 |  | DWE-39026 | DWE-69026 | DWE-69126
168 | 0 | Lot02 | MO-CK24 | MO-CK | Modify Traffic paint and traffic sign | สหชาติ | 0 | 0 | 2026-05-01 | 2026-04-30 | 100% | Completed | 2026-06-15 | 100% | Completed | 2026-10-15 | 64% | Late | 2026-10-15 | 13% | Late | 0 | 0 | 0 |  |  | 0 | 0
169 | 0 | Lot02 | MO-CK25 | MO-CK | Station Area sign 28 stations | สหชาติ | 0 | 0 | 2026-05-01 | 2026-06-15 | 80% | Late | 2026-06-30 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-12-20 | 0% | On Schedule | 0 | 0 | 0 |  |  | 0 | 0
170 |  | Lot02 | MO-CK26 | MO-CK | Safety and warning signage for lift and escalator at all station | สหชาติ | 0 | Depot | 2027-01-01 | 2026-06-16 | 100% | Completed | 2026-07-17 | 100% | Completed | 2027-01-31 | 76% | On Schedule | 2027-02-28 | 26% | On Schedule | 0 | 0 | 0
171 | MDW-39532 | Lot02 | MO-CK27 | MO-CK | Spike fence for Depot slab | สหชาติ | 0 | Depot | 2027-01-01 | 2026-07-31 | 70% | Late | 2026-08-31 | 0% | Late | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0 | 0 |  | MDW-39532 | MDW-69564 | MDW-69565
172 | 0 | Lot02 | MO-CK28 | MO-CK | Bird net and Flashing at MWS and Skywalk to Stabling yard | สหชาติ | 0 | 0 | 2026-05-01 |  |  | 0% |  |  | 0% | 0 | 0% | 0% |  |  | 0% | 0 | 0 | 0 |  |  | 0 | 0
173 | MDW-39541 | Lot02 | MO-CK29 | MO-CK | Fire Alarm Manual Call Point signage at all elevated station | สหชาติ | 0 | 0 | 2027-01-01 |  |  | 0% | 2026-07-30 | 100% | Completed | 0 | 0% | 0% |  |  | 0% | 0 | 0 | 0 |  | MDW-39541 | MDW-69582 | MDW-69583
174 | 0 | Lot02 | MO-CK30 | MO-CK | Lighting for sealed space under stairs and behind lift shaft at underground station | ประธาน | 0 | 0 | 2027-01-01 | 2026-10-14 | 0% | Late | 2026-11-14 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0 | 0 |  |  | 0 | 0
175 | 0 | Lot02 | MO-CK31 | MO-CK | Modify the access door of sealed space (under-stairs room) with a Sump Pump or ESPS cabinet | สหชาติ | 0 | 0 | 2027-01-01 | 2026-07-16 | 0% | Late | 2026-08-16 | 0% | Late | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0 | 0 |  |  | 0 | 0
176 | 0 | Lot02 | MO-CK32 | MO-CK | Lighting to the sealed space (under-stairs room) with a Sump Pump or ESPS cabinet | ประธาน | 0 | Depot | 2027-01-01 | 2026-11-03 | 0% | On Schedule | 2026-12-04 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0 | 0 |  |  | 0 | 0
177 | 0 | Lot02 | MO-CK33 | MO-CK | Additional lighting in areas where the lux level does not meet occupational health standards | ประธาน | 0 | Depot | 2027-01-01 | 2026-09-14 | 100% | Completed | 2026-10-15 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 95% | On Schedule | 0 | 0 | 0 |  |  | 0 | 0
178 | 0 | Lot02 | MO-CK34 | MO-CK | Provide and install confined space signage for Station and Depot | สหชาติ | 0 | 0 | 2027-01-01 | 2026-08-15 | 100% | Completed | 2026-09-15 | 100% | Completed | 2027-01-31 | 76% | On Schedule | 2027-02-28 | 26% | On Schedule | 0 | 0 | 0 |  |  | 0 | 0
179 |  | Lot02 | MO-CK35 | MO-CK | Build room for Train crew main office at OR18 with office area, resting area, meeting room, pantry, toilet and locker room | สหชาติ/บัณฑิต/ประธาน | 0 | Depot | - |  |  | 0% |  |  | 0% | 0 | 0% | 0% |  |  | 0% | 0 | 0 | 0
180 |  | Lot02 | MO-CK36 | MO-CK | Dormitory Cable Containments (if any) | มนตรี | 0 | Depot | - |  |  | 0% |  |  | 0% | 0 | 0% | 0% |  |  | 0% | 0 | 0 | 0
181 | 0 | Lot02 | MO-CK37 | MO-CK | Provide Raise floor and building Service in Training &Simulator (OCC Admin) | สหชาติ | 0 | Depot | - | 0% | 0% | 0% |  |  |  | 0 | 0% | 0% |  |  | 0% | 0 | 0 | 0 |  |  | 0 | 0
182 |  | Lot02 | MO-CK38 | MO-CK | Add N2 in Playback and Training Room and Backup Control Room | บุญประเสริฐ | 0 | Depot | - |  |  | 0% |  |  | 0% | 0 | 0% | 0% |  |  | 0% | 0 | 0 | 0
183 | MDW-39505 | Lot02 | MO-BEM1.1 | MO-BEM | Walkway from Main Work Shop to Stabling Area - Civil & AR | สหชาติ | 0 | Depot | 2026-08-02 | 2026-04-28 | 100% | Completed | 2026-05-29 | 92% | Late | 0 | 0% | 0% | 2026-09-30 | 93% | Late | 0 | 0 | 0 |  | MDW-39505 | MDW-69510 | MDW-69511
184 | MDW-39506 | Lot02 | MO-BEM1.2 | MO-BEM | Walkway from Main Work Shop to Stabling Area - Building Services | ประธาน | 0 | Depot | 2026-08-02 | 2026-04-28 | 100% | Completed | 2026-05-29 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 0% | Late | 0 | 0 | 0 |  | MDW-39506 | MDW-69512 | MDW-69513
185 | MDW-39507 | Lot02 | MO-BEM2 | MO-BEM | High Roof at Main Work Shop Entrance and Store | สหชาติ | 0 | Depot | 2026-08-01 | 2026-02-13 | 100% | Completed | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39507 | MDW-69514 | MDW-69515
186 | MDW-39509 | Lot02 | MO-BEM3 | MO-BEM | High Roof at the entrance and exit of the under floor wheel lathe | สหชาติ | 0 | Depot | 2026-08-04 | 2026-02-13 | 100% | Completed | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39509 | MDW-69518
187 | MDW-39511 | Lot02 | MO-BEM4.1 | MO-BEM | Maintenance Office Rooms at Main Workshop - Civil & AR | สหชาติ | 0 | Depot | 2026-07-03 | 2026-04-13 | 100% | Completed | 2026-05-14 | 100% | Completed | 0 | 0% | 0% | 2026-06-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39511 | MDW-69522 | MDW-69523
188 | MDW-39512 | Lot02 | MO-BEM4.2 | MO-BEM | Maintenance Office Rooms at Main Workshop - Building Services | ประธาน | 0 | Depot | 2026-07-04 | 2026-04-13 | 100% | Completed | 2026-05-14 | 100% | Completed | 0 | 0% | 0% | 2026-06-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39512 | MDW-69524 | MDW-69525
189 | MDW-39513 | Lot02 | MO-BEM5 | MO-BEM | Install Concrete car barrier along the walkway in front of MWS building | สหชาติ | 0 | Depot | 2027-01-01 | 2026-10-14 | 100% | Completed | 2026-11-14 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39513 | MDW-69526 | MDW-69527
190 | 0 | Lot02 | MO-BEM6 | MO-BEM | Handrail on top of the water tank on the rooftop of the Admin Building | สหชาติ | 0 | Depot | 2027-01-01 | 2026-10-19 | 100% | Completed | 2026-11-19 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0 | 0 |  |  | 0 | 0
191 | 0 | Lot02 | MO-BEM7 | MO-BEM | Modify maintenance service door to the roof building to easier access while maintaining safe operational standards | สหชาติ | 0 | Depot | 2027-01-01 | 2026-10-19 | 50% | Late | 2026-11-19 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0 | 0 |  |  | 0 | 0
192 | MDW-39536 | Lot02 | MO-BEM8 | MO-BEM | Company logo and Central Control Room sign in CCR room. | สหชาติ | 0 | Depot | 2026-05-01 | 2026-01-27 | 100% | Completed | 2026-03-14 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39536 | MDW-69572 | MDW-69573
193 | MDW-39536 | Lot02 | MO-BEM9 | MO-BEM | Soundproof insulation on the wall and structure and equipment in the CCR room. | สหชาติ | 0 | Depot | 2026-05-01 | 2026-01-12 | 100% | Completed | 2026-02-27 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39536 | MDW-69572 | MDW-69573
194 | MDW-39526 | Lot02 | MO-BEM10 | MO-BEM | Relocate Fire Hose Cabinet to be outside of the clearance gauge zone 17 set | ประธาน | 0 | Depot | 2026-05-01 | 2026-01-12 | 100% | Completed | 2026-02-27 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39526 | MDW-69552 | MDW-69553
195 | MDW-39528 | Lot02 | MO-BEM11.1 | MO-BEM | Washing Area in Cleaning Staff Room at Stabling Yard - Civil & AR | สหชาติ | 0 | Depot | 2026-08-03 | 2026-06-03 | 100% | Completed | 2026-07-04 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39528 | MDW-69556 | MDW-69557
196 | MDW-39529 | Lot02 | MO-BEM11.2 | MO-BEM | Washing Area in Cleaning Staff Room at Stabling Yard - Building Services | ประธาน | 0 | Depot | 2026-08-04 | 2026-04-14 | 100% | Completed | 2026-05-30 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39529 | MDW-69558 | MDW-69559
197 | MDW-39522 | Lot02 | MO-BEM12 | MO-BEM | Rain protection for Water treatment Building | สหชาติ | 0 | Depot | 2026-08-05 | 2026-04-29 | 100% | Completed | 2026-05-30 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39522 | MDW-69544 | MDW-69545
198 | MDW-39522 | Lot02 | MO-BEM13.1 | MO-BEM | Zero Discharge Water treatment in Depot - Civil & AR | สหชาติ | 0 | Depot | 2027-01-01 | 2026-08-15 | 100% | Completed | 2026-09-30 | 75% | Late | 0 | 0% | 0% | 2026-12-31 | 63% | On Schedule | 0 | 0 | 0 |  | MDW-39522 | MDW-69544 | MDW-69545
199 | MDW-39530 | Lot02 | MO-BEM13.2 | MO-BEM | Zero Discharge Water treatment in Depot - Building Services | ประธาน | 0 | Depot | 2027-01-01 | 2026-08-15 | 100% | Completed | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 50% | On Schedule | 0 | 0 | 0 |  | MDW-39530 | MDW-69560 | MDW-69561
200 | MDW-39516 | Lot02 | MO-BEM14.1 | MO-BEM | Modification Works : Walkway Bridge between BL Depot and ORL Depot - Civil & AR | สหชาติ | 0 | Depot | 2026-08-02 | 2026-02-28 | 100% | Completed | 2026-06-15 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 95% | Late | 0 | 0 | 0 |  | MDW-39516 | MDW-69532 | MDW-69533
201 | MDW-39517 | Lot02 | MO-BEM14.2 | MO-BEM | Modification Works : Walkway Bridge between BL Depot and ORL Depot - Building Services | ประธาน | 0 | Depot | 2026-08-03 | 2026-01-14 | 100% | Completed | 2026-03-01 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 10% | Late | 0 | 0 | 0 |  | MDW-39517 | MDW-69534 | MDW-69535
202 | MDW-39514 | Lot02 | MO-BEM15.1 | MO-BEM | Roof for cars parking lots area (184 car)t - Civil & AR | สหชาติ | 0 | Depot | 2026-08-03 | 2026-02-28 | 100% | Completed | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39514 | MDW-69528 | MDW-69529
203 | MDW-39515 | Lot02 | MO-BEM15.2 | MO-BEM | Roof for cars parking lots area (184 car) - Building Services | ประธาน | 0 | Depot | 2026-08-03 | 2026-02-28 | 100% | Completed | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39515 | MDW-69530 | MDW-69531
204 | MDW-39519 | Lot02 | MO-BEM16 | MO-BEM | Walkway roof and High roof across the road from Admin ORL to Depot slap | สหชาติ | 0 | Depot | 2026-08-01 | 2026-06-15 | 100% | Completed | 2026-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-10-31 | 57% | On Schedule | 0 | 0 | 0 |  | MDW-39519 | MDW-69538 | MDW-69539
205 | MDW-39519 | Lot02 | MO-BEM17 | MO-BEM | Walkway roof to car park in front of admin ORL(3x5m.) | สหชาติ | 0 | Depot | 2026-08-01 | 2026-06-15 | 100% | Completed | 2026-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-10-31 | 70% | On Schedule | 0 | 0 | 0 |  | MDW-39519 | MDW-69538 | MDW-69539
206 | MDW-39519 | Lot02 | MO-BEM18 | MO-BEM | Walkway roof over the footpath near depot slab (1.50 m. x 290 m.) and stair up to depot slap. | สหชาติ | 0 | Depot | 2026-08-01 | 2026-06-15 | 100% | Completed | 2026-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-10-31 | 0% | On Schedule | 0 | 0 | 0 |  | MDW-39519 | MDW-69538 | MDW-69539
207 | MDW-39557 | Lot02 | MO-BEM19 | MO-BEM | Install Chain Link fence to enclose parking area | สหชาติ | 0 | Depot | 2026-10-01 | 2026-06-29 | 100% | Completed | 2026-07-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 0% | Late | 0 | 0 | 0 |  | MDW-39557 | MDW-69614 | MDW-69615
208 | MDW-39523 | Lot02 | MO-BEM20 | MO-BEM | Hose bib 1/2" 4 sets for Tree around Admin area | ประธาน | 0 | Depot | 2026-06-01 | 2026-04-23 | 100% | Completed | 2026-06-08 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39523 | MDW-69546 | MDW-69547
209 | - | Lot02 | MO-BEM21 | MO-BEM | Relocate Security Guard Box at Front Gate and Install Roof 3x5m. | สหชาติ | 0 | Depot | 2027-01-03 | 2026-07-31 | 100% | Completed | 2026-09-30 | 75% | Late | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0 | 0 |  |  | 0 | 0
210 | MDW-39534 | Lot02 | MO-BEM21.1 | MO-BEM | Modification Works : Security Guard Box at ORL Depot Entrance - Civil & AR | สหชาติ | 0 | Depot | 2027-01-02 | 2026-07-31 | 100% | Completed | 2026-09-30 | 67% | Late | 0 | 0% | 0% | 2026-12-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39534 | MDW-69568 | MDW-69569
211 | MDW-39535 | Lot02 | MO-BEM21.2 | MO-BEM | Modification Works : Security Guard Box at ORL Depot Entrance - Building Services | ประธาน | 0 | Depot | 2027-01-03 | 2026-07-31 | 100% | Completed | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 50% | On Schedule | 0 | 0 | 0 |  | MDW-39535 | MDW-69570 | MDW-69571
212 | MDW-39532 | Lot02 | MO-BEM22 | MO-BEM | Addition Spike fence for MRTA fence and Chain link at Klong Chourdyai 400m. | สหชาติ | 0 | Depot | 2027-01-01 | 2026-08-30 | 70% | Late | 2026-09-30 | 0% | Late | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0 | 0 |  | MDW-39532 | MDW-69564 | MDW-69565
213 | MDW-39527 | Lot02 | MO-BEM23 | MO-BEM | Hand sink with eye wash station | ประธาน | พี่ต่อ | Depot | 2027-01-01 | 2026-08-30 | 100% | Completed | 2026-10-15 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39527 | MDW-69554 | MDW-69555
214 | MDW-39531 | Lot02 | MO-BEM24 | MO-BEM | Guard rail protection for Fire Hose Cabinet 8 set | สหชาติ | 0 | Depot | 2026-06-01 | 2026-03-14 | 100% | Completed | 2026-04-14 | 100% | Completed | 0 | 0% | 0% | 2026-08-15 | 100% | Completed | 0 | 0 | 0 |  | MDW-39531 | MDW-69562 | MDW-69563
215 | MDW-39557 | Lot02 | MO-BEM25.1 | MO-BEM | Chain Link Fence to divide controlled areas on Depot slab 3 m.x 485 m. - Civil & AR | สหชาติ | 0 | Depot | 2026-10-01 | 2026-06-14 | 100% | Completed | 2026-07-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 0% | Late | 0 | 0 | 0 |  | MDW-39557 | MDW-69614 | MDW-69615
216 | MDW-39520 | Lot02 | MO-BEM25.2 | MO-BEM | Chain Link Fence to divide controlled areas on Depot slab 3 m.x 485 m.- Building Services | ประธาน | 0 | Depot | 2026-10-01 | 2026-06-14 | 100% | Completed | 2026-07-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 0% | Late | 0 | 0 | 0 |  | MDW-39520 | MDW-69540 | MDW-69541
217 | MDW-39518 | Lot02 | MO-BEM26 | MO-BEM | Street Lighting system area between MRTA Fence and Depot slab | ประธาน | 0 | Depot | 2026-08-01 | 2026-04-14 | 50% | Late | 2026-05-15 | 0% | Late | 0 | 0% | 0% | 2026-07-31 | 0% | Late | 0 | 0 | 0 |  | MDW-39518 | MDW-69536 | MDW-69537
218 | - | Lot02 | MO-BEM27 | MO-BEM | Compacted gravel walkway along the Test Track OR-BL 1.2 m. | สหชาติ | พรพรหม | Depot | 2027-01-01 | 2026-08-30 | 100% | Completed | 2026-09-30 | 0% | Late | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0 | 0 |  |  | 0 | 0
219 | MDW-39524 | Lot02 | MO-BEM28.1 | MO-BEM | Walkway under Depot Slab for Maintenance Service - Civil & AR | สหชาติ | 0 | Depot | 2027-01-02 | 2026-09-14 | 100% | Completed | 2026-10-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39524 | MDW-69548 | MDW-69549
220 | MDW-39525 | Lot02 | MO-BEM28.2 | MO-BEM | Walkway under Depot Slab for Maintenance Service - Building Services | ประธาน | 0 | Depot | 2027-01-03 | 2026-09-14 | 100% | Completed | 2026-10-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 50% | On Schedule | 0 | 0 | 0 |  | MDW-39525 | MDW-69550 | MDW-69551
221 | MDW-39521 | Lot02 | MO-BEM29 | MO-BEM | Walkway Bridge across the canal for Depot area inspection patrols 3 location | สหชาติ | 0 | Depot | 2027-01-01 | 2026-08-15 | 100% | Completed | 2026-09-30 | 67% | Late | 0 | 0% | 0% | 2026-12-31 | 95% | On Schedule | 0 | 0 | 0 |  | MDW-39521 | MDW-69542 | MDW-69543
222 | - | Lot02 | MO-BEM30 | MO-BEM | Cut down trees between Depot BL+ORL and MRTA Fence | สหชาติ | 0 | Depot | 2027-01-01 | 2026-10-29 | 0% | Late | 2026-11-29 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0 | 0 |  |  | 0 | 0
223 | 0 | Lot02 | MO-BEM31 | MO-BEM | Provide facility system and interface to MMC room (Fire Alarm / CCTV / VMS / TEL / CASS / Radio / PA) | บัณฑิต | 0 | Depot | 2026-10-01 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
224 | - | Lot02 | MO-BEM32 | MO-BEM | Stainless Guard rail balustrade for waiting area | สหชาติ | 0 | Depot | 2026-05-01 |  |  | 0% |  |  | 0% | 0 | 0% | 0% |  |  | 0% | 0 | 0 | 0 |  |  | 0 | 0
225 | - | Lot02 | MO-BEM33 | MO-BEM | Concrete walkway 2 x 80 m. For fire escape route | สหชาติ | 0 | Depot | 2026-05-01 |  |  | 0% |  |  | 0% | 0 | 0% | 0% |  |  | 0% | 0 | 0 | 0 |  |  | 0 | 0
226 | - | Lot02 | MO-BEM34 | MO-BEM | Access Gate (Full Height Turnstile) at 1st floor admin ORL | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0 | 0 |  |  | 0 | 0
227 | - | Lot02 | MO-BEM35 | MO-BEM | Access Gate (Tripod with Swing Gate) at MWS Entrance | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0 | 0 |  |  | 0 | 0
228 | - | Lot02 | MO-BEM36 | MO-BEM | Access Gate (Tripod with Swing Gate) at Admin 2nd floor connect to OCC | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0 | 0 |  |  | 0 | 0
229 | - | Lot02 | MO-BEM37 | MO-BEM | Access Gate (Tripod with Swing Gate) on Klong Chourdyai bridge | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0 | 0 |  |  | 0 | 0
230 | - | Lot02 | MO-BEM38 | MO-BEM | Access Gate (Tripod with roof covering) at parking lot OCC | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0 | 0 |  |  | 0 | 0
231 | - | Lot02 | MO-BEM39 | MO-BEM | Access Gate (Tripod with roof covering) at Stair up to Depot slab | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0 | 0 |  |  | 0 | 0
232 | - | Lot02 | MO-BEM40 | MO-BEM | Access Control (2 Factors, Card + Finger Print) at High Security rooms - CCR/PTR/Store | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0 | 0 |  |  | 0 | 0
233 | - | Lot02 | MO-BEM41 | MO-BEM | Link CCTV Landscape of all depot ORL area for MMC BL monitoring. | บัณฑิต | 0 | 0 | 2027-01-01 | 2026-11-28 | 0% | On Schedule | 2026-11-29 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0 | 0 |  |  | 0 | 0
234 | - | Lot02 | MO-BEM42 | MO-BEM | Fire Suppression Control Panel Cover which located in tunnel | สู่โชค | 0 | 0 | 2027-01-01 |  |  | 0% |  |  | 0% | 0 | 0% | 0% |  |  | 0% | 0 | 0 | 0 |  |  | 0 | 0
235 | MDW-39537 | Lot02 | MO-BEM43 | MO-BEM | Handrails for ladder at IVS and Vent buildings | สหชาติ | 0 | 0 | 2026-09-01 | 2026-03-31 | 70% | Late | 2026-05-01 | 0% | Late | 0 | 0% | 0% | 2026-08-31 | 0% | Late | 0 | 0 | 0 |  | MDW-39537 | MDW-69574 | MDW-69575
236 | MDW-39538 | Lot02 | MO-BEM44 | MO-BEM | Escalator Anti-Slide device for all station. | สหชาติ | 0 | 0 | 2026-09-01 | 2026-05-30 | 100% | Completed | 2026-06-30 | 100% | Completed | 2027-01-31 | 100% | Completed | 2027-02-28 | 70% | On Schedule | 0 | 0 | 0 |  | MDW-39538 | MDW-69576 | MDW-69577
237 | MDW-39539 | Lot02 | MO-BEM45 | MO-BEM | Roof for control panel on vent building | สหชาติ | 0 | 0 | 2027-01-01 | 2026-09-14 | 70% | Late | 2026-10-30 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0 | 0 |  | MDW-39539 | MDW-69578 | MDW-69579
238 | MDW-39553 | Lot02 | MO-BEM46 | MO-BEM | Provide Standing plate or ladder to access the Fire Valve in at Omega points for all underground stations. | สหชาติ | 0 | Depot | 2027-01-01 | 2026-09-14 | 0% | Late | 2026-10-30 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0 | 0 |  | MDW-39553 | MDW-69606 | MDW-69607
239 | MDW-39540 | Lot02 | MO-BEM47 | MO-BEM | Water drop protection above UPS cabinet at station and Depot | สหชาติ | 0 | 0 | 2027-01-01 | 2026-09-14 | 0% | Late | 2026-10-30 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0 | 0 |  | MDW-39540 | MDW-69580 | MDW-69581
240 | MDW-39541 | Lot02 | MO-BEM48 | MO-BEM | Fire alarm manual call point cover in public area at all station | ประธาน | 0 | 0 | 2027-01-01 | 2026-09-14 | 50% | Late | 2026-10-30 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0 | 0 |  | MDW-39541 | MDW-69582 | MDW-69583
241 | MDW-39542 | Lot02 | MO-BEM49 | MO-BEM | Emergency stop button cover for escalator at all station. | สหชาติ | 0 | 0 | 2027-01-01 | 2026-09-14 | 0% | Late | 2026-10-30 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0 | 0 |  | MDW-39542 | MDW-69584 | MDW-69585
242 | 0 | Lot02 | MO-BEM50 | MO-BEM | Modify maintenance service door to the roof of OR13 vent building to easier access while maintaining safe operational standards | สู่โชค | 0 | Depot | 2027-01-01 | 2026-10-29 | 0% | Late | 2026-10-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0 | 0 |  |  | 0 | 0
243 | MDW-39514 | Lot02 | MO-BEM51 | MO-BEM | Modify existing car park to be 220 motorcycle parking lots including floor painting and parking roof | สหชาติ | 0 | Depot | 2026-08-01 | 2026-01-29 | 100% | Completed | 2026-03-16 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39514 | MDW-69528 | MDW-69529
244 | MDW-39534 | Lot02 | MO-BEM52 | MO-BEM | Modify the sidewalk for temporary parking at entrance | สหชาติ | 0 | Depot | 2027-01-01 | 2026-07-31 | 100% | Completed | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 100% | Completed | 0 | 0 | 0 |  | MDW-39534 | MDW-69568 | MDW-69569
245 | MDW-39554 | Lot02 | MO-BEM53.1 | MO-BEM | Modification Works : Security Guard Box at OCC Parking Area - Civil & AR | สหชาติ | 0 | Depot | 2027-01-02 | 2026-09-14 | 100% | Completed | 2026-10-31 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0 | 0 |  | MDW-39554 | MDW-69608 | MDW-69609
246 | MDW-39555 | Lot02 | MO-BEM53.2 | MO-BEM | Modification Works : Security Guard Box at OCC Parking Area - Building Services | ประธาน | 0 | 0 | 2027-01-02 | 2026-09-14 | 100% | Completed | 2026-10-31 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 50% | On Schedule | 0 | 0 | 0 |  | MDW-39555 | MDW-69610 | MDW-69611
247 | NoDrawing | Lot02 | MO-BEM54 | MO-BEM | Strengthen the Maintenance Walkway of the TEF fan | สหชาติ | 0 | 0 | 2027-01-01 | 2026-07-16 | 100% | Completed | 2026-08-16 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0 | 0 |  |  | 0 | 0
Lot 1 T&C
[29 empty] | CK Pesonsible Person | Total | Completed | Late | On Schedule
[29 empty] | ประธาน | 2 | 1 | 1 | 0
[29 empty] | สมศักดิ์ | 23 | 1 | 16 | 6
[29 empty] | บัณฑิต | 4 | 1 | 1 | 2

## Test Procedure (hidden)
Test Procedure
No. | Design Submission | Lot No. | Code | System | Activity Name | CK Responsible Person |  | Location | Expected Completion Month | Design (PLAN) | Design (%) | Design (Status) | Procurement (PLAN) | Procurement (%) | Procurement (Status) | Manufacturing / Delivery Process (PLAN) | Manufacturing / Delivery Process (%) | Manufacturing / Delivery (Status) | Construction /Installation (PLAN) | Construction /Installation (%) | Construction /Installation (Status) | T&C (PLAN) | T&C (%) | T&C (Status) | Test Procedure (PLAN) | Test Procedure (%) | Test Procedure (Status) | Note | Design Submission | Procedure No. | Test Report No.
1 | MDW-39246-60 | Lot01 | GEN1 | GEN | Rooms and Building Service Systems Modification in Stations Area | - | 0 | 0 | 2026-08-01 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39246 | MDW-69259 | MDW-69260
2 | MDW-39246 | Lot01 | GEN1.1 | GEN | Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR13 - OR17 | ประธาน | 0 | 0 | 2026-08-01 | 2026-01-30 | 100% | Completed | 2026-03-01 | 100% | Completed | 0 | 0% | 0% | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39246 | MDW-69259 | MDW-69260
3 | MDW-39247 | Lot01 | GEN1.2 | GEN | Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR18 - OR22 | ประธาน | 0 | 0 | 2026-08-01 | 2025-12-30 | 100% | Completed | 2026-01-29 | 100% | Completed | 0 | 0% | 0% | 2026-02-28 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39247 | MDW-69259 | MDW-69261
4 | MDW-39248 | Lot01 | GEN1.3 | GEN | Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR23 - OR29 | ประธาน | 0 | 0 | 2026-08-01 | 2026-01-30 | 100% | Completed | 2026-03-01 | 100% | Completed | 0 | 0% | 0% | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39248 | MDW-69259 | MDW-69262
5 | MDW-39252 | Lot01 | GEN1.4 | GEN | Modification of Fire Suppression System (N2) in Commerial Room at OR14 | ประธาน | 0 | 0 | 2026-08-01 | 2025-12-30 | 100% | Completed | 2026-01-29 | 100% | Completed | 0 | 0% | 0% | 2026-02-28 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39252 | MDW-69269 | MDW-69270
6 | MDW-39253 | Lot01 | GEN1.5 | GEN | Modification of Civil Work in Telecommunication Room at OR14 | สหชาติ | 0 | 0 | 2026-08-01 | 2025-12-30 | 100% | Completed | 2026-01-29 | 100% | Completed | 0 | 0% | 0% | 2026-02-28 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39253 | MDW-69271 | MDW-69272
7 | MDW-39254 | Lot01 | GEN1.6 | GEN | Modification in Staff Mess Room at OR13-OR17 | ประธาน | 0 | 0 | 2026-08-01 | 2026-01-30 | 100% | Completed | 2026-03-01 | 100% | Completed | 0 | 0% | 0% | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39254 | MDW-69273 | MDW-69274
8 | MDW-39255 | Lot01 | GEN1.7 | GEN | Modification in Staff Mess Room at OR18-OR22 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39255 | MDW-69273 | MDW-69275
9 | MDW-39256 | Lot01 | GEN1.8 | GEN | Modification in Staff Mess Room at OR23-OR29 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39256 | MDW-69273 | MDW-69276
10 | MDW-39257 | Lot01 | GEN1.9 | GEN | Modification of Air Conditioning in CER and SER at OR13-OR19 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 99% | Late | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39257 | MDW-69277 | MDW-69278
11 | MDW-39258 | Lot01 | GEN1.10 | GEN | Modification of Air Conditioning in CER and SER at OR20-OR22 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 99% | Late | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39258 | MDW-69277 | MDW-69279
12 | MDW-39259 | Lot01 | GEN1.11 | GEN | Modification of Air Conditioning in CER and SER at OR23-OR29 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 99% | Late | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39259 | MDW-69277 | MDW-69280
13 | MDW-39272 | Lot01 | GEN1.12 | GEN | Modification of New M&E Room at IVS15 - IVS17 Civil & AR | สหชาติ | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39272 | MDW-69299 | MDW-69300
14 | MDW-39273 | Lot01 | GEN1.13 | GEN | Modification of New M&E UPS Room at IVS15-IVS17 - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 99% | Late | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39273 | MDW-69301 | MDW-69302
15 | MDW-39294 | Lot01 | GEN1.14 | GEN | Provision of Architectural Work in new M&E UPS room at OR23 | สหชาติ | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39294 | MDW-69339 | MDW-69340
16 | MDW-39299 | Lot01 | GEN1.15 | GEN | Provision of Air Conditioning System in Commercial Room at OR13-OR19 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39299 | MDW-69349 | MDW-69350
17 | MDW-39306 | Lot01 | GEN1.16 | GEN | Modification CER and First Aid Room at OR14 - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39306 | MDW-69363 | MDW-69364
18 | MDW-39307 | Lot01 | GEN1.17 | GEN | Additional Fence at Back of House OR13 - OR22 and IVS East Section | สหชาติ | 0 | 0 | 2026-08-01 | 2026-09-30 | 100% | Completed | 2026-10-31 | 50% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39307 | MDW-69365 | MDW-69366
19 | MDW-39249 | Lot01 | GEN1.18 | GEN | SOR Counter and Workstation Hanging Support Installation on East Section | สหชาติ | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39249 | MDW-69263 | MDW-69264
20 | MDW-39250 | Lot01 | GEN1.19 | GEN | Ticket Office Modification on East Section | สหชาติ | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39250 | MDW-69265 | MDW-69266
21 | MDW-39261 | Lot01 | GEN2 | GEN | Rooms and Building Service Systems Modification in Depot Area | - | 0 | Depot | 2026-08-01 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39261 | MDW-69283 | MDW-69284
22 | MDW-39260 | Lot01 | GEN2.1 | GEN | Modification of Air Conditioning in M&E Room at OCC Building | ประธาน | 0 | 0 | 2026-08-01 | 2025-12-30 | 100% | Completed | 2026-01-29 | 100% | Completed | 0 | 0% | 0% | 2026-02-28 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39260 | MDW-69281 | MDW-69282
23 | MDW-39261 | Lot01 | GEN2.2 | GEN | Provision of UPS for MDB Control at Main Workshop, OCC Building, Admin Building, Stabling Yard and Train Washing Plant | ประธาน | 0 | 0 | 2026-08-01 | 2026-09-01 | 100% | Completed | 2026-10-01 | 100% | Completed | 0 | 0% | 0% | 2026-10-31 | 90% | On Schedule | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39261 | MDW-69283 | MDW-69284
24 | MDW-39262 | Lot01 | GEN2.3 | GEN | Provision of Redundant MDB at OCC Building, Admin Building and Canteen | ประธาน | 0 | 0 | 2026-08-01 | 2026-09-01 | 100% | Completed | 2026-10-01 | 100% | Completed | 0 | 0% | 0% | 2026-10-31 | 95% | On Schedule | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39262 | MDW-69285 | MDW-69286
25 | MDW-39263 | Lot01 | GEN2.4 | GEN | Additonal Lighting System at Depot Area | ประธาน | 0 | 0 | 2026-08-01 | 2026-04-01 | 100% | Completed | 2026-05-01 | 100% | Completed | 0 | 0% | 0% | 2026-05-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39263 | MDW-69287 | MDW-69288
26 | MDW-39290 | Lot01 | GEN2.5 | GEN | Modification Room for PSY at Depot Buildings - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39290 | MDW-69331 | MDW-69332
27 | MDW-39300 | Lot01 | GEN2.6 | GEN | Modification SIG-PSD Office at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39300 | MDW-69351 | MDW-69352
28 | MDW-39301 | Lot01 | GEN2.7 | GEN | Modification Backup CCR Room at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39301 | MDW-69353 | MDW-69354
29 | MDW-39302 | Lot01 | GEN2.8 | GEN | Modification SER at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39302 | MDW-69355 | MDW-69356
30 | MDW-39303 | Lot01 | GEN2.9 | GEN | Modification CER & SCADA Room at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39303 | MDW-69357 | MDW-69358
31 | MDW-39309 | Lot01 | GEN2.10 | GEN | Modification Air Conditioning System at CCR | ประธาน | 0 | 0 | 2026-08-01 | 2026-10-01 | 100% | Completed | 2026-10-31 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 80% | On Schedule | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39309 | MDW-69369 | MDW-69370
32 | MDW-39312 | Lot01 | GEN2.11 | GEN | Modification Electronic Workshop at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-10-31 | 100% | Completed | 2026-11-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 0 | MDW-39312 | MDW-69375 | MDW-69376
33 | MDW-39313 | Lot01 | GEN2.12 | GEN | Modification Battery Charger Room at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-10-31 | 100% | Completed | 2026-11-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 0 | MDW-39313 | MDW-69377 | MDW-69378
34 | MDW-39314 | Lot01 | GEN2.13 | GEN | Modification Machining Room at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-10-31 | 90% | On Schedule | 2026-11-30 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 0 | MDW-39314 | MDW-69379 | MDW-69380
35 | MDW-39315 | Lot01 | GEN2.14 | GEN | Modification Electronic Workshop, Battery Charger and Machining Room at Main Workshop - Civil & AR | สหชาติ | 0 | 0 | 2026-08-01 | 2026-10-31 | 70% | On Schedule | 2026-11-30 | 90% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 0 | MDW-39315 | MDW-69383 | MDW-69384
36 | MDW-39297 | Lot01 | GEN2.15 | GEN | Training Room at Ratchada Station (Part 2) | สหชาติ | 0 | 0 | 2026-08-01 | 2026-08-01 | 0% | Late | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 0 | MDW-39297 | MDW-69345 | MDW-69346
37 | MDW-39291 | Lot01 | GEN2.16 | GEN | Conductor Rail Arrangement Modification at Main Line East Section | กำพล | 0 | 0 | 2026-08-01 | 2026-09-30 | 100% | Completed | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 90% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 0 | MDW-39291 | MDW-69333 | MDW-69334
38 | MDW-39292 | Lot01 | GEN2.17 | GEN | Conductor Rail Arrangement Modification at Depot | กำพล | 0 | 0 | 2026-08-01 | 2026-09-30 | 100% | Completed | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 90% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 0 | MDW-39292 | MDW-69335 | MDW-69336
39 | MDW-39295 | Lot01 | GEN2.18 | GEN | Dangerous Goods Building in Depot - Civil & AR | สหชาติ | 0 | 0 | 2026-08-01 | 2026-01-27 | 100% | Completed | 2026-02-27 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed |  | MDW-39295 | MDW-69341 | MDW-69342
40 | MDW-39296 | Lot01 | GEN2.19 | GEN | Dangerous Goods Building in Depot - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2025-12-13 | 100% | Completed | 2026-01-28 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed |  | MDW-39296 | MDW-69343 | MDW-69344
41 | MDW-39308 | Lot01 | GEN2.20 | GEN | Additional Locking Devices for Main Line Tandem Turnouts 2007, 2010 & 2013 and Depot Turnout D16 | กำพล | 0 | 0 | 2026-08-01 | 2026-11-30 | 50% | On Schedule | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 0 | MDW-39308 | MDW-69367 | MDW-69368
42 | MDW-39200-31 | Lot01 | GEN3 | GEN | Cable Containment Modification | - | 0 | 0 | 2025-05-28 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39200
43 | - | Lot01 | GEN4 | GEN | Training Room and Workshop Room | - | 0 | 0 | 2026-04-01 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
44 | MDW-39242 | Lot01 | GEN4.0 | GEN | Modification Works for Training Room at Ratchada Station | ประธาน | 0 | 0 | 2026-04-01 | 2025-12-30 | 100% | Completed | 2026-01-31 | 100% | Completed | 0 | 0% | 0% | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-03-16 | 100% | Completed |  | MDW-39242 | MDW-69251 | MDW-69252
45 | MDW-39244 | Lot01 | GEN4.1 | GEN | AFC Training Room Modification - Civil & AR | สหชาติ | 0 | 0 | 2026-08-21 | 2026-09-30 | 10% | Late | 2026-10-15 | 100% | Completed | 0 | 0% | 0% | 2026-11-15 | 0% | On Schedule | 0 | 0% | 0% | 2026-10-31 | 0% | On Schedule | อยู่ระหว่างจัดทำแบบก่อสร้าง | MDW-39244 | MDW-69255 | MDW-69256
46 | MDW-39245 | Lot01 | GEN4.2 | GEN | AFC Training Room Modification - Building Services | ประธาน | 0 | 0 | 2026-08-21 | 2025-12-30 | 100% | Completed | 2026-01-31 | 100% | Completed | 0 | 0% | 0% | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-03-24 | 100% | Completed |  | MDW-39245 | MDW-69257 | MDW-69258
47 | MDW-39235 | Lot01 | GEN5 | GEN | Raised Floor | สหชาติ | 0 | 0 | 2026-06-01 | 2025-05-15 | 100% | Completed | 2024-12-14 | 100% | Completed | 2025-08-04 | 100% | Completed | 2025-12-28 | 100% | Completed | 0 | 0% | 0% | 2025-11-28 | 100% | Completed |  | MDW-39235 | MDW-69237 | MDW-69238
48 | MDW-39271 | Lot01 | GEN6 | GEN | Wayside Cable Containment in Depot | - | 0 | Depot | 2026-02-22 | 2025-05-15 | 100% | Completed | 2024-12-14 | 100% | Completed | 2025-08-04 | 100% | Completed | 2025-12-28 | 100% | Completed | 0 | 0% | 0% | 2026-08-26 | 100% | Completed |  | MDW-39271 | MDW-69297 | MDW-69298
49 | MDW-39269 | Lot01 | GEN6.1 | GEN | PSY Wayside Cable Containment for 24 Kv Cable under the Depot slab | ประธาน | 0 | Depot | 2026-02-22 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39269 | MDW-69293 | MDW-69294
50 | MDW-39270 | Lot01 | GEN6.2 | GEN | COM/SIG Wayside Cable Containment in the Depot | มนตรี/ประธาน | 0 | Depot | 2026-02-22 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39270 | MDW-69295 | MDW-69296
51 | - | Lot01 | GEN7 | GEN | Dangerous Waste Storage Building in Depot | - | 0 | Depot | 2026-09-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
52 | DWE-39024 | Lot01 | GEN7.1 | GEN | Dangerous Waste Storage Building in Depot - Civil & AR | สหชาติ | 0 | Depot | 2026-09-20 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-07-15 | 100% | Completed |  | DWE-39024 | DWE-69024 | DWE-69124
53 | DWE-39025 | Lot01 | GEN7.2 | GEN | Dangerous Waste Storage Building in Depot - Building service | ประธาน | 0 | Depot | 2026-09-20 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed | 0 | 0% | 0% | 2026-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-04-20 | 100% | Completed |  | DWE-39025 | DWE-69025 | DWE-69125
54 | - | Lot01 | GEN8 | GEN | General Waste Storage Building in Depot | - | 0 | Depot | 2026-09-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
55 | DWE-39026 | Lot01 | GEN8.1 | GEN | General Waste Storage Building in Depot - Civil & AR | สหชาติ | 0 | Depot | 2026-09-20 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-07-15 | 100% | Completed |  | DWE-39026 | DWE-69026 | DWE-69126
56 | DWE-39025 | Lot01 | GEN8.2 | GEN | General Waste Storage Building in Depot - Building service | ประธาน | 0 | Depot | 2026-09-20 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed | 0 | 0% | 0% | 2026-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-04-20 | 100% | Completed |  | DWE-39025 | DWE-69025 | DWE-69125
57 | DWE-39021 | Lot01 | GEN9 | GEN | Operation Support Equipment | สมศักดิ์ | 0 | Depot | 2026-08-21 | 2025-03-02 | 100% | Completed | 2025-11-02 | 100% | Completed | 2026-11-16 | 90% | On Schedule | 0 | 0% | 0% | 0 | 0% | 0% | 2026-10-17 | 0% | Late | คงเหลือจัดส่ง Signal Lamp | DWE-39021 | DWE-69021 | DWE-69121
58 | GRS-39001-40 | Lot01 | GEN10.1 | GEN | Graphic and Signage Station | สหชาติ | 0 | 0 | 2026-08-21 | 2026-06-30 | 100% | Completed | 2026-05-31 | 95% | Late | 2027-01-31 | 76% | On Schedule | 2027-02-28 | 34% | On Schedule | 0 | 0% | 0% | 0 | 0 | 0 |  | GRS-39001 | GRS-69001 | GRS-69002
59 | GRS-39001-40 | Lot01 | GEN10.2 | GEN | Graphic and Signage Mainline & IVS,VS | สหชาติ | 0 | 0 | 2026-08-21 | 2026-06-15 | 79% | Late | 2026-05-31 | 95% | Late | 2026-07-31 | 0% | Late | 2026-07-31 | 0% | Late | 0 | 0% | 0% | 0 | 0 | 0 |  | GRS-39001 | GRS-69001 | GRS-69002
60 | GRS-39001-40 | Lot01 | GEN10.3 | GEN | Graphic and Signage Depot | สหชาติ | 0 | 0 | 2026-08-21 | 2026-08-15 | 90% | Late | 2026-07-31 | 93% | Late | 2026-06-30 | 56% | Late | 2026-06-30 | 19% | Late | 0 | 0% | 0% | 0 | 0 | 0 |  | GRS-39001 | GRS-69001 | GRS-69002
61 | MDW-39289 | Lot01 | GEN11 | GEN | Earthing and Bonding Modification | ประธาน | 0 | 0 | 2026-03-01 | 2025-01-31 | 100% | Completed | 2025-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-02-28 | 100% | Completed | 2026-03-30 | 100% | Completed | 2026-09-23 | 0% | Late | 0 | MDW-39289 | MDW-69329 | MDW-69330
62 | - | Lot01 | GEN12 | GEN | Mainline Cable Trough Modification on East Section | - | 0 | 0 | 2026-06-22 | 2025-10-31 | 100% | Completed | 2025-11-30 | 100% | Completed | 2025-12-30 | 100% | Completed | 2026-03-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 80% | Late | 0 |  | 0 | 0
63 | MDW-39233 | Lot01 | GEN12.1 | GEN | Main Line Cable Trough Modification (PSY) | มนต์ชัย | 0 | Depot | 2026-06-22 | 2025-10-31 | 100% | Completed | 2025-11-30 | 100% | Completed | 2025-12-30 | 100% | Completed | 2026-03-30 | 100% | Completed | 0% | 0% | 0% | 2026-09-30 | 80% | Late | 0 | MDW-39233
64 | MDW-39234 | Lot01 | GEN12.2 | GEN | Main Line Cable Trough Modification (SIG/COM) | มนตรี | 0 | 0 | 2026-06-22 | 2025-10-31 | 100% | Completed | 2025-11-30 | 100% | Completed | 2025-12-30 | 100% | Completed | 2026-03-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 80% | Late | งานจบแล้ว | MDW-39234 | MDW-69234 | MDW-69236
65 | MDW-39236 | Lot01 | GEN13 | GEN | Bird Protection System | สหชาติ | 0 | 0 | 2026-11-19 | 2025-06-30 | 100% | Completed | 2025-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-01-26 | 100% | Completed | 0 | 0% | 0% | 2026-07-15 | 100% | Completed |  | MDW-39236 | MDW-69239 | MDW-69240
66 | - | Lot01 | GEN14 | GEN | Train Crew Office at Thailand Cultural Centre Station | สหชาติ | 0 | 0 | 2026-08-21 | 2025-09-30 | 100% | Completed | 2026-02-27 | 100% | Completed | 0 | 0% | 0% | 2026-05-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-23 | 0% | Late | 0 |  | 0 | 0
67 | MDW-39240 | Lot01 | GEN14.1 | GEN | Driver Train Simulation Room and Train Crew Office at OR18 - Civil & AR | สหชาติ | 0 | Depot | 2026-08-21 | 2025-09-30 | 100% | Completed | 2026-02-28 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-07-15 | 100% | Completed |  | MDW-39240 | MDW-69247 | MDW-69248
68 | MDW-39241 | Lot01 | GEN14.2 | GEN | Driver Train Simulation Room and Train Crew Office at OR18 - Building Services | ประธาน | 0 | 0 | 2026-08-21 | 2025-09-30 | 100% | Completed | 2026-02-28 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-03-12 | 100% | Completed |  | MDW-39241 | MDW-69249 | MDW-69250
69 | MDW-39239 | Lot01 | GEN15 | GEN | Access Panel Closeout for Traction Substation Room in Main Workshop | สหชาติ | 0 | 0 | 2026-03-24 | 2026-01-30 | 100% | Completed | 2026-03-01 | 100% | Completed | 0 | 0% | 0% | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-15 | 100% | Completed |  | MDW-39239 | MDW-69245 | MDW-69246
70 | MDW-39232 | Lot01 | GEN16 | GEN | Level Crossing at Turnout | กำพล | 0 | 0 | 2026-08-21 | 2026-09-30 | 100% | Completed | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-11-15 | 46% | On Schedule | 0 | 0% | 0% |  | 0% | On Schedule | 0 | MDW-39232 | MDW-69232 | MDW-69233
71 | MDW-39232 | Lot01 | GEN17 | GEN | Track Slab Crossing | ชฎิล/กำพล | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39232 | MDW-69232 | MDW-69233
72 | MDW-39243 | Lot01 | GEN18 | GEN | Eye Adaptation Lighting (Lighting at Tunnel to Expose) | ประธาน | 0 | 0 | 2026-11-19 | 2025-09-30 | 100% | Completed | 2025-10-30 | 100% | Completed | 0 | 0% | 0% | 2026-04-13 | 100% | Completed | 0 | 0% | 0% | 2026-02-18 | 100% | Completed |  | MDW-39243 | MDW-69253 | MDW-69254
73 | - | Lot01 | GEN19 | GEN | Train Simulation Room and AFC Training Room | - | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
74 | MDW-39244 | Lot01 | GEN19.1 | GEN | Modification AFC Training Center at OR19 - Civil & AR | สหชาติ | 0 | 0 | 2026-11-30 | 2026-09-30 | 100% | Completed | 2026-10-31 | 58% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 0 | 0% | 0% | 2026-10-31 | 0% | On Schedule | Progress Cut&Cover OR22 : 95% | MDW-39244 | MDW-69255 | MDW-69256
75 | MDW-39245 | Lot01 | GEN19.2 | GEN | Modification AFC Training Center at OR19 - Building Services | ประธาน | บัณฑิต | 0 | 2026-11-30 | 2026-09-30 | 100% | Completed | 2026-10-31 | 100% | Completed | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 0 | 0% | 0% | 2026-10-31 | 0% | On Schedule | 0 | MDW-39245 | MDW-69257 | MDW-69258
76 | - | Lot01 | GEN20 | GEN | Dormitory Cable Containments (if any) | - | 0 | 0 | - | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
77 |  | Lot01 | GEN21 | GEN | Project Information Management System (PIMS) | บัณฑิต | 0 | 0 | 2024-09-30 | 2024-08-10 | 100% | Completed | 2024-08-15 | 100% | Completed | 0 | 0% | 0% | 2024-09-04 | 100% | Completed | 2024-09-14 | 100% | Completed | 2026-09-23 | 0% | Late | งานจบแล้ว
78 | MDW-39237 | Lot01 | GEN22 | GEN | Central BEMS for the MRT Orange Line System | บัณฑิต | 0 | 0 | 2026-08-21 | 2026-04-30 | 0% | Late | 2026-06-30 | 0% | Late | 0 | 0% | 0% | 2026-08-15 | 0% | Late | 2026-08-31 | 0% | Late | 2026-11-30 | 0% | On Schedule | PPR Oct-26 กำลังเปรียบเทียบ Spec | MDW-39237 | MDW-69241 | MDW-69242
79 |  | Lot01 | GEN23 | GEN | Asset Information | บัณฑิต | 0 | 0 | 2026-11-19 | 0 | 0% | 0% | 2026-08-30 | 100% | Completed | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0
80 | MDW-39282 | Lot01 | PSD1 | PSD | Holes for PSD Cable Wiring | กำพล | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39282 | MDW-69315 | MDW-69316
81 | MDW-39004 | Lot01 | PSD2 | PSD | Rubber Gap Fillers on Platform Edge | กำพล | 0 | 0 | 2026-08-21 | 2025-07-30 | 100% | Completed | 2026-01-31 | 100% | Completed | 0 | 0% | 0% | 2026-08-31 | 40% | Late | 0 | 0% | 0% | 2026-09-30 | 25% | Late | แผนเข้าติดตั้ง 1/10/26-30/11/26 | MDW-39004 | MDW-69007 | MDW-69008
82 | MDW-39280 | Lot01 | PSD3 | PSD | Platform Finishing | กำพล | 0 | 0 | 2026-08-21 | 2025-07-30 | 100% | Completed | 2025-09-16 | 100% | Completed | 0 | 0% | 0% | 2026-01-07 | 100% | Completed | 0 | 0% | 0% | 2026-08-17 | 100% | Completed |  | MDW-39280 | MDW-69311 | MDW-69312
83 | MDW-39281 | Lot01 | PSD4 | PSD | Cladding Barrier between EWD and Station Structure | กำพล | 0 | 0 | 2026-08-21 | 2026-02-28 | 100% | Completed | 2026-03-15 | 100% | Completed | 0 | 0% | 0% | 2026-08-15 | 100% | Completed | 0 | 0% | 0% | 2026-09-23 | 0% | Late | 0 | MDW-39281 | MDW-69313 | MDW-69314
84 | - | Lot01 | AFC1 | AFC | Park and Ride System | บัณฑิต/สหชาติ | 0 | 0 | 2026-10-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
85 | MDW-39276 | Lot01 | AFC2 | AFC | Ticket Issuing Machine (TIM) Wall Opening and Closing | สหชาติ | 0 | 0 | 2026-09-20 | 2026-01-30 | 100% | Completed | 2026-03-15 | 50% | Late | 0 | 0% | 0% | 2026-07-13 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 50% | Late | มีแก้ไขตำแหน่ง OR14,17,18,23 | MDW-39276 | MDW-69303 | MDW-69304
86 | MDW-39279 | Lot01 | AFC3 | AFC | Balustrade Modification Along AFC Gate Line | สหชาติ | 0 | 0 | 2026-09-20 | 2026-06-30 | 10% | Late | 2026-08-15 | 50% | Late | 0 | 0% | 0% | 2026-11-06 | 0% | On Schedule | 0 | 0% | 0% | 2026-10-07 | 0% | Late | จัดเตรียมแบบ ออกPPR Oct-26 | MDW-39279 | MDW-69309 | MDW-69310
87 | MDW-39278 | Lot01 | AFC4 | AFC | Underfloor Embedded Duct Modification for AFC Gates Line | สหชาติ | 0 | Depot | 2026-09-20 | 2026-01-30 | 100% | Completed | 2026-04-02 | 67% | Late | 0 | 0% | 0% | 2026-10-09 | 81% | Late | 0 | 0% | 0% | 2026-09-30 | 0% | Late | 0 | MDW-39278 | MDW-69307 | MDW-69308
88 | MDW-39002 | Lot01 | SIG1 | SIG | Test Track Shelters and Test Track Building | สหชาติ | 0 | 0 | 2026-06-22 | 2025-11-22 | 100% | Completed | 2026-01-18 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-04-15 | 100% | Completed | 0 | 0% | 0% | 2026-05-15 | 100% | Completed |  | MDW-39002 | MDW-69003 | MDW-69004
89 | MDW-39293 | Lot01 | SIG2 | SIG | Rearrangement of track crossing walkway at stabling yard to consistent with the layout of 4-car train parking | กำพล | 0 | Depot | 2026-06-22 | 2025-11-30 | 100% | Completed | 2025-12-30 | 100% | Completed | 0 | 0% | 0% | 2026-03-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 50% | Late | 0 | MDW-39293 | MDW-69337 | MDW-69338
90 | MDW-39288 | Lot01 | SIG3 | SIG | Point Machine Foundation Construction | กำพล | 0 | 0 | 2026-08-21 | 2025-11-21 | 100% | Completed | 2025-12-30 | 100% | Completed | 0 | 0% | 0% | 2026-03-19 | 100% | Completed | 0 | 0% | 0% | 2026-09-23 | 25% | Late | 0 | MDW-39288 | MDW-69327 | MDW-69328
91 | MDW-39001 | Lot01 | SIG4 | SIG | Modification of Depot Track Route Line to Stabling Yard | สู่โชค | 0 | Depot | 2026-06-22 | 2025-10-30 | 100% | Completed | 2025-11-29 | 100% | Completed | 0 | 0% | 0% | 2026-05-28 | 95% | Late | 0 | 0% | 0% | 2026-09-30 | 50% | Late | คงเหลือเก็บงาน Progress by ช.ธนัท | MDW-39001 | MDW-69001 | MDW-69002
92 | MDW-39287 | Lot01 | SIG5 | SIG | Strobe Light at Buffer Stops | ประธาน | 0 | Depot | 2026-08-21 | 2026-05-30 | 100% | Completed | 2026-06-29 | 100% | Completed | 0 | 0% | 0% | 2026-08-28 | 100% | Completed | 0 | 0% | 0% | 2026-03-14 | 100% | Completed |  | MDW-39287 | MDW-69323 | MDW-69324
93 | DWE-39016 | Lot01 | DWE1 | DWE | Diesel Fuel Storage Tank for Maintenance Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-01-16 | 100% | Completed | 2026-06-30 | 100% | Completed | 2026-07-31 | 100% | Completed | 2026-08-09 | 0% | Late | 0 | 0 | 0 |  | DWE-39016 | DWE-69016 | DWE-69116
94 | DWE-39011 | Lot01 | DWE2 | DWE | Movable Height Maintenance Platform Vehicle (Boom Lift) | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-08-06 | 100% | Completed | 2025-12-31 | 100% | Completed | 2026-06-30 | 100% | Completed | 2026-07-09 | 0% | Late | 2026-05-22 | 100% | Completed |  | DWE-39011 | DWE-69011 | DWE-69111
95 | DWE-39012 | Lot01 | DWE3 | DWE | Fork Lift Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-03-31 | 100% | Completed | 2026-06-01 | 100% | Completed | 2026-06-30 | 100% | Completed | 2026-07-30 | 0% | Late | 2026-09-30 | 0% | Late | Test 9-15/11/26 | DWE-39012 | DWE-69012 | DWE-69112
96 | DWE-39015 | Lot01 | DWE4 | DWE | Compressed Air System and Portable Air Compressor for Depot | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-01-10 | 100% | Completed | 2026-02-15 | 100% | Completed | 2026-09-19 | 0% | Late | 2026-09-29 | 0% | Late | 0 | 0 | 0 |  | DWE-39015 | DWE-69015 | DWE-69115
97 | DWE-39017 | Lot01 | DWE5 | DWE | Pallet Storage Shelves in Hazardous Storage | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-12-16 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-05-31 | 100% | Completed | 2026-06-05 | 0% | Late | 2026-07-17 | 100% | Completed |  | DWE-39017 | DWE-69017 | DWE-69117
98 | DWE-39017 | Lot01 | DWE6 | DWE | Pallet Storage in Main Storage Room | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-12-16 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-05-31 | 100% | Completed | 2026-06-05 | 0% | Late | 2026-07-17 | 100% | Completed |  | DWE-39017 | DWE-69017 | DWE-69117
99 | DWE-39017 | Lot01 | DWE7 | DWE | Two-Tier Shelf | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-12-16 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-05-31 | 100% | Completed | 2026-06-05 | 0% | Late | 2026-07-17 | 100% | Completed |  | DWE-39017 | DWE-69017 | DWE-69117
100 | DWE-39017 | Lot01 | DWE8 | DWE | Tool Storage | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-12-16 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-05-31 | 100% | Completed | 2026-06-05 | 0% | Late | 2026-07-17 | 100% | Completed |  | DWE-39017 | DWE-69017 | DWE-69117
101 | DWE-39018 | Lot01 | DWE9 | DWE | Repair Equipment | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-07-31 | 50% | Late | 2026-10-30 | 70% | On Schedule | 2027-03-03 | 0% | On Schedule | 2027-04-02 | 0% | On Schedule | 2027-03-03 | 0% | On Schedule | คงเหลือจัดส่งอุปกรณ์ | DWE-39018 | DWE-69018 | DWE-69118
102 | DWE-39020 | Lot01 | DWE10 | DWE | Oil & Grease Disposal | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-01-16 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-03-31 | 100% | Completed | 2026-07-05 | 0% | Late | 2026-09-30 | 0% | Late | Test 9-15/11/26 | DWE-39020 | DWE-69020 | DWE-69120
103 | DWE-39020 | Lot01 | DWE11 | DWE | Grease Dispensers | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-01-16 | 100% | Completed | 2026-04-28 | 100% | Completed | 2026-05-25 | 100% | Completed | 2026-07-05 | 0% | Late | 2026-09-30 | 0% | Late | Test 9-15/11/26 | DWE-39020 | DWE-69020 | DWE-69120
104 | DWE-39020 | Lot01 | DWE12 | DWE | Waste Disposal | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-01-16 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-03-31 | 100% | Completed | 2026-07-05 | 0% | Late | 2026-09-30 | 0% | Late | Test 9-15/11/26 | DWE-39020 | DWE-69020 | DWE-69120
105 | MDW-39305 | Lot01 | DWE13 | DWE | Safety Provision for Maintenance Pits | สหชาติ | 0 | Depot | 2026-09-20 | 2025-11-30 | 100% | Completed | 2026-04-29 | 100% | Completed | 0 | 0% | 0% | 2026-07-29 | 70% | Late | 0 | 0% | 0% | 2026-09-30 | 50% | Late | งาน Handrail ที่ Pits Wheel Reprofling Plant ติดตั้งแล้วเหลืองานเก็บสี | MDW-39305 | MDW-69361 | MDW-69362
106 | DWE-39xxx | Lot01 | DWE14 | DWE | Pit Drainage System in Main Workshop | สมศักดิ์ | 0 | Depot | 2026-09-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39xxx | MDW-69361 | MDW-69362
107 | DWE-39023 | Lot01 | DWE15 | DWE | Provision of Civil Works and Building Services to support Train Washing Equipment | สหชาติ | 0 | Depot | 2026-08-01 | 2025-11-30 | 100% | Completed | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-05-31 | 100% | Completed | 0 | 0% | 0% | 2026-08-31 | 100% | Completed |  | DWE-39023 | DWE-69023 | DWE-69123
108 | DWE-39013 | Lot01 | DWE16 | DWE | Overhead Traveling Crane | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-04-30 | 100% | Completed | 2026-03-20 | 100% | Completed | 0 | 0% | 0% | 2026-04-04 | 100% | Completed | 2026-05-26 | 100% | Completed |  | DWE-39013 | DWE-69013 | DWE-69113-513
109 | DWE-39009 | Lot01 | DWE17 | DWE | Vehicle Inspection and Servicing Facilities | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-12-18 | 100% | Completed | 2026-09-07 | 100% | Completed | 0 | 0% | 0% | 2026-10-01 | 0% | Late | 0 | 0 | 0 |  | DWE-39009 | DWE-69009 | DWE-69109
110 | DWE-39014 | Lot01 | DWE18 | DWE | Permanent Way Maintenance Facility | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-04-30 | 100% | Completed | 2027-02-28 | 100% | Completed | 2027-01-15 | 70% | On Schedule | 0 | 0% | 0% | 2027-03-30 | 0% | On Schedule | 0 | 0 | 0 |  | DWE-39014 | DWE-69014 | DWE-69114
111 | - | Lot01 | DWE19 | DWE | Permanent Way Vehicles | สมศักดิ์ | 0 | Depot | 2026-09-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
112 | DWE-39001 | Lot01 | DWE19.1 | DWE | Shunting Locomotive | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-12-18 | 100% | Completed | 2026-12-15 | 50% | On Schedule | 0 | 0% | 0% | 2026-12-30 | 0% | On Schedule | 0 | 0 | 0 |  | DWE-39001 | DWE-69001 | DWE-69101
113 | DWE-39002 | Lot01 | DWE19.2 | DWE | Tunnel Inspection and Cleaning Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 0% | Late | 2025-12-18 | 100% | Completed | 2026-12-30 | 40% | On Schedule | 0 | 0% | 0% | 2026-10-11 | 0% | Late | 0 | 0 | 0 |  | DWE-39002 | DWE-69002 | DWE-69102
114 | DWE-39003 | Lot01 | DWE19.3 | DWE | Hi/Rail Maintenance Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-12-18 | 100% | Completed | 2026-11-30 | 55% | On Schedule | 0 | 0% | 0% | 2026-12-16 | 0% | On Schedule | 0 | 0 | 0 |  | DWE-39003 | DWE-69003 | DWE-69103
115 | DWE-39004 | Lot01 | DWE19.4 | DWE | Flat wagon | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-12-18 | 100% | Completed | 2026-10-30 | 68% | On Schedule | 0 | 0% | 0% | 2026-08-11 | 0% | Late | 0 | 0 | 0 |  | DWE-39004 | DWE-69004 | DWE-69104
116 | DWE-39005 | Lot01 | DWE19.5 | DWE | Re-railing Equipment | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-11-10 | 100% | Completed | 2026-07-15 | 90% | Late | 0 | 0% | 0% | 2026-08-31 | 0% | Late | 0 | 0 | 0 |  | DWE-39005 | DWE-69005 | DWE-69105
117 | DWE-39006 | Lot01 | DWE19.6 | DWE | Self-Propelled Rail Based Inspection Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-12-18 | 100% | Completed | 2026-11-03 | 55% | On Schedule | 0 | 0% | 0% | 2026-12-16 | 0% | On Schedule | 0 | 0 | 0 |  | DWE-39006 | DWE-69006 | DWE-69106
118 | DWE-39007 | Lot01 | DWE19.7 | DWE | Rail Head Grinding Machine Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 0% | Late | 2025-12-18 | 100% | Completed | 2027-07-31 | 0% | On Schedule | 0 | 0% | 0% | 2027-08-31 | 0% | On Schedule | 0 | 0 | 0 |  | DWE-39007 | DWE-69007 | DWE-69107
119 | DWE-39008 | Lot01 | DWE19.8 | DWE | Multi Measuring Rail Vehicle | สมศักดิ์ | 0 | 0 | 2026-09-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39008 | DWE-69008 | DWE-69108
120 | DWE-39010 | Lot01 | DWE19.9 | DWE | High Work Inspection Vehicle | สมศักดิ์ | 0 | 0 | 2026-09-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39010
121 | - | Lot01 | DWE20 | DWE | Building Maintenance Vehicle | - | 0 | 0 | 2026-09-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
122 | EPS-39001 | Lot01 | PSY1 | PSY | Diesel Fuel Storage Tanks for Power Generators | สมศักดิ์ | 0 | 0 | 2026-03-24 | 2026-01-16 | 100% | Completed | 2026-03-31 | 100% | Completed | 2026-03-31 | 100% | Completed | 2026-06-30 | 75% | Late | 2026-07-10 | 0% | Late | 2026-10-23 | 0% | Late | คงเหลืองานเดินท่อและ Pump น้ำมัน | EPS-39001 | EPS-69001 | EPS-69002
123 | PSY-39001-9 | Lot01 | PSY2 | PSY | GIS and BSS Building and Other Facilities | สหชาติ | 0 | 0 | 2026-03-24 | 2024-08-29 | 100% | Completed | 2024-09-28 | 69% | Late | 0 | 0% | 0% | 2025-12-04 | 100% | Completed | 0 | 0% | 0% | 2026-09-23 | 100% | Completed |  | PSY-39001 | PSY-69001 | PSY-69002
124 | PSY-39011 | Lot01 | PSY3 | PSY | Steel Grating Raised Floor for EE Panel | สหชาติ | 0 | 0 | 2026-03-24 | 2024-09-30 | 100% | Completed | 2024-10-30 | 75% | Late | 0 | 0% | 0% | 2025-07-14 | 100% | Completed | 0 | 0% | 0% | 2026-06-14 | 100% | Completed |  | PSY-39011 | PSY-69015 | PSY-69016
125 | - | Lot01 | PSY4 | PSY | Trapping Box between PSY Service Sub Station (SSS) and Low Volt (LV) System | - | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
126 | SCA-39200 | Lot01 | SCA1 | SCA | Modification of BEMS to receive PSD Signal on East Section | ธารทิพย์ | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | SCA-39200 | SCA-69200 | SCA-69201
127 | - | Lot01 | SCA2 | SCA | Modification of Escalator Interface Point with CCTV and SCADA, East Section | - | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
128 | - | Lot01 | SCA3 | SCA | Magnetic of Fire Alarm System Interface Point with CCTV and SCADA | - | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
129 | SCA-39203 | Lot01 | SCA4 | SCA | Add/Modify Civil Scada Hardwire for all Station | ประธาน/ธารทิพย์ | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | SCA-39203 | SCA-69206 | SCA-69207
130 | COM-39200 | Lot01 | COM1 | COM | Magnetic Door Lock | มนตรี | 0 | 0 | 2026-08-21 | 2025-06-30 | 100% | Completed | 2026-05-15 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 27.25% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | กำลังดำเนินการ Progress by CIP | COM-39200 | COM-69200 | COM-69201
131 | MDW-39283 | Lot01 | COM2 | COM | Intercom System in Cash Handling Room (if require) | บัณฑิต | 0 | 0 | 2026-12-19 | 2025-09-30 | 100% | Completed | 2026-06-30 | 50% | Late | 0 | 0% | 0% | 2026-10-31 | 0% | On Schedule | 2026-12-30 | 0% | On Schedule | 2026-09-30 | 0% | Late | รอพื้นที่เข้าติดตั้ง | MDW-39283 | MDW-69317 | MDW-69318
132 | COM-39001 | Lot01 | COM3 | COM | Walk-Through Metal Detector System (WTMD), 1 per entrance | มนตรี | 0 | 0 | 2026-11-19 | 2025-08-31 | 0% | Late | 2026-06-30 | 0% | Late | 0 | 0% | 0% | 2027-02-28 | 0% | On Schedule | 0 | 0% | 0% | 2027-01-29 | 0% | On Schedule | รอออก PPR อยู่ระหว่างการตรวจสอบสินค้า | COM-39001 | COM-69001 | COM-69002
133 | MDW-39284 | Lot01 | COM4 | COM | Traveling Cable in all Lifts | มนตรี | 0 | 0 | - | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39284 | MDW-69319 | MDW-69320
134 | MDW-39304 | Lot01 | COM5 | COM | MEA Radio | ประธาน | 0 | 0 | 2026-09-20 | 2026-01-30 | 100% | Completed | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-06-30 | 95% | Late | 2026-09-30 | 0% | Late | 2026-09-23 | 0% | Late | รอเฟอร์นิเจอร์ Fore cast Dec-26 | MDW-39304 | COM-69202 | COM-69203
135 | COM-39004 | Lot01 | COM6 | COM | Main Cable Containment for M&E Dedicated communication link to MRTA Head Quarter | มนตรี | 0 | 0 | 2026-09-20 | 2026-01-31 | 100% | Completed | 2026-02-28 | 100% | Completed | 0 | 0% | 0% | 2026-08-31 | 75% | Late | 0 | 0% | 0% | 0 | 0 | 0 |  | COM-39004 | COM-69005 | COM-69006
136 | AFC-39001 | Lot01 | COM7 | COM | Mini Paging in Ticket Office | บัณฑิต | 0 | 0 | 2026-12-19 | 2025-09-10 | 100% | Completed | 2026-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 0% | Late | 2026-11-30 | 0% | On Schedule | 2026-10-31 | 0% | On Schedule | ของมาแล้ว รอพื้นที่เข้าติดตั้ง | AFC-39002 | AFC-69003 | AFC-69004
137 | MDW-39285 | Lot01 | COM8 | COM | Provision of Cable Containment between OCC ORL and OCC BL | มนตรี | 0 | 0 | 2026-07-22 | 0 | 0% | 0% | 0% | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39285
138 | COM-39005 | Lot01 | COM9 | COM | Power Distribution for M&E Systems at MRTA Head Quarter | มนตรี | 0 | 0 | 2026-09-20 | 2026-03-31 | 100% | Completed | 2026-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 0 | 0 | 0 |  | COM-39005 | COM-69007 | COM-69008
139 | COM-39205 | Lot01 | COM10 | COM | Underground Cable Containment at Public Areas (if require) | มนตรี | 0 | 0 | 2026-08-21 | 2026-04-30 | 100% | Completed | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 100% | Completed | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39205 | MDW-69200 | MDW-69205
140 | - | Lot01 | COM11 | COM | Intercom at Ticket Issuing Machine | บัณฑิต | 0 | Depot | - | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
141 | RST-39004,8 | Lot01 | RST1 | RST | Driver Training Simulator | ธัญวิทย์ | 0 | Depot | 2026-09-20 | 2025-05-30 | 100% | Completed | 2025-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 81% | On Schedule | 0 | 0% | 0% | 0 | 0 | 0 |  | RST-39004,8
142 | MDW-39500 | Lot02 | MO-CK1.1 | MO-CK | Store Modification Works at Main Workshop - Civil&AR | สหชาติ | 0 | Depot | 2026-06-03 | 2026-02-27 | 100% | Completed | 2026-03-30 | 100% | Completed | 0 | 0% | 0% | 2026-05-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 50% | Late | 0 | MDW-39500 | MDW-69500 | MDW-69501
143 | MDW-39501 | Lot02 | MO-CK1.2 | MO-CK | Store Modification Works at Main Workshop - Building Services | ประธาน | 0 | Depot | 2026-06-04 | 2026-02-12 | 100% | Completed | 2026-03-30 | 100% | Completed | 0 | 0% | 0% | 2026-05-28 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 0% | Late | รอสรุปตำแหน่ง Power Plug ชาร์จโฟลคลิฟท์ Oct-26 | MDW-39501 | MDW-69502 | MDW-69503
144 | MDW-39503 | Lot02 | MO-CK2 | MO-CK | New MMC at Admin Building - Civil&AR | สหชาติ | 0 | Depot | 2026-08-03 | 2026-04-14 | 100% | Completed | 2026-05-15 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 50% | Late | กำลังทำเอกสาร Test Report | MDW-39503 | MDW-69506 | MDW-69507
145 | MDW-39504 | Lot02 | MO-CK3 | MO-CK | Move or link Workstation and control panel to MMC room at admin C 2nd floor | ประธาน | 0 | Depot | 2026-08-02 | 2026-02-28 | 100% | Completed | 2026-04-15 | 100% | Completed | 0 | 0% | 0% | 2026-08-31 | 90% | Late | 0 | 0% | 0% | 2026-09-30 | 0% | Late | Fore cast Oct-26 | MDW-39504 | MDW-69508 | MDW-69509
146 | MDW-39543 | Lot02 | MO-CK4 | MO-CK | Bird & Rain Protection for Open space Admin C | สหชาติ | 0 | Depot | 2026-08-01 | 2026-04-29 | 100% | Completed | 2026-05-30 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 50% | Late | 0 | MDW-39543 | MDW-69586 | MDW-69587
147 | MDW-39547 | Lot02 | MO-CK5 | MO-CK | Relocate door in front of toilet and build partition wall to conceal the view in side of toilet | สหชาติ | 0 | Depot | 2026-08-02 | 2026-05-14 | 100% | Completed | 2026-06-14 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-15 | 100% | Completed |  | MDW-39547 | MDW-69594 | MDW-69595
148 | MDW-39547 | Lot02 | MO-CK6 | MO-CK | Modify Lockset the emergency door to be used for passage between the 2nd and 3rd floors inside the building. | สหชาติ | 0 | Depot | 2026-08-03 | 2026-04-29 | 100% | Completed | 2026-06-14 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-01 | 100% | Completed |  | MDW-39547 | MDW-69594 | MDW-69595
149 | MDW-39556 | Lot02 | MO-CK7 | MO-CK | Addition small power for lounge and pantry room at 2nd floor and Hall and observation room at 3nd floor | ประธาน | 0 | Depot | 2026-08-04 | 2026-05-14 | 100% | Completed | 2026-06-14 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-05-05 | 100% | Completed |  | MDW-39556 | MDW-69612 | MDW-69613
150 | MDW-39548 | Lot02 | MO-CK8 | MO-CK | Air Condition for using store room to be pantry room. 2nd floor | ประธาน | 0 | Depot | 2026-08-05 | 2026-04-29 | 100% | Completed | 2026-06-14 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-03-24 | 100% | Completed |  | MDW-39548 | MDW-69596 | MDW-69597
151 | MDW-39552 | Lot02 | MO-CK9 | MO-CK | Walk Way Hand rail high 90 cm 1 side (144 m. x 7 route) | สหชาติ | 0 | Depot | 2026-10-01 | 2026-05-30 | 100% | Completed | 2026-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 98.77% | Late | 0 | 0% | 0% | 2026-09-30 | 50% | Late | คงเหลืองานคอนกรีตทางเดินข้ามราง | MDW-39552 | MDW-69604 | MDW-69605
152 | MDW-39544 | Lot02 | MO-CK10 | MO-CK | Barbed wire fence Viaduct CE CW | บัณฑิต/สหชาติ | พี่ต่อ | Depot | 2027-01-01 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39544 | MDW-69588 | MDW-69589
153 | MDW-39545 | Lot02 | MO-CK11 | MO-CK | Chain Link at Cut & Cover 600m. | สหชาติ | พรพรหม | Depot | 2026-06-01 | 2026-02-27 | 100% | Completed | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-08-01 | 100% | Completed |  | MDW-39545 | MDW-69590 | MDW-69591
154 | MDW-39546 | Lot02 | MO-CK12 | MO-CK | Chain Link under slab high 1.70 m | สหชาติ | 0 | 0 | 2027-01-01 | 2026-06-30 | 100% | Completed | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 67.27% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 50% | On Schedule | เริ่มติดตั้ง Chainlink แล้ว | MDW-39546 | MDW-69592 | MDW-69593
155 | MDW-39550 | Lot02 | MO-CK13.1 | MO-CK | Satellite Store at OR21 - Civil & AR | สหชาติ | 0 | 0 | 2027-01-02 | 2026-08-30 | 100% | Completed | 2026-10-15 | 0% | Late | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 100% | Completed |  | MDW-39550 | MDW-69600 | MDW-695601
156 | MDW-39549 | Lot02 | MO-CK13.2 | MO-CK | Maintenance Room and Satellite Store at Stations - Building Services | ประธาน | 0 | 0 | 2027-01-03 | 2026-08-30 | 100% | Completed | 2026-10-15 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 80% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 100% | Completed |  | MDW-39549 | MDW-69598 | MDW-69599
157 | MDW-39551 | Lot02 | MO-CK14 | MO-CK | Modify Cleaner room at OR29 to be Train crew Standby office with facility system | ประธาน | 0 | Depot | 2026-07-01 | 2026-03-14 | 100% | Completed | 2026-04-29 | 100% | Completed | 0 | 0% | 0% | 2026-06-30 | 95% | Late | 0 | 0% | 0% | 2026-09-30 | 100% | Completed |  | MDW-39551 | MDW-69602 | MDW-69603
158 | MDW-39295 | Lot02 | MO-CK15.1 | MO-CK | Epoxy Floor Installation and Curb Installation at the Entrance - Civil & AR | สหชาติ | 0 | Depot | 2026-05-01 | 2026-01-27 | 100% | Completed | 2026-02-27 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 50% | Late | 0 | MDW-39295 | MDW-69341 | MDW-69342
159 | MDW-39296 | Lot02 | MO-CK15.2 | MO-CK | Change Electrical Equipment to be Explosion-proof type - Building Services | ประธาน | 0 | Depot | 2026-05-01 | 2025-12-13 | 100% | Completed | 2026-01-28 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 90% | Late | 0 | 0% | 0% | 2026-09-30 | 0% | Late | Fore cast Nov-26 | MDW-39296 | MDW-69343 | MDW-69344
160 | DWE-39024 | Lot02 | MO-CK16 | MO-CK | Dangerous waste Storage 30 x 5 m. =10 room | สหชาติ | 0 | Depot | 2026-05-01 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-07-15 | 100% | Completed |  | DWE-39024 | DWE-69024 | DWE-69124
161 | 0 | Lot02 | MO-CK17 | MO-CK | Safety Sign all Depot Area building | สหชาติ | 0 | Depot | 2026-05-01 | 2025-11-28 | 100% | Completed | 2026-06-15 | 100% | Completed | 2026-09-20 | 27% | Late | 2026-10-15 | 0% | Late | 0 | 0% | 0% | 0 | 0% | Late | GRS |  | 0 | 0
162 | 0 | Lot02 | MO-CK18 | MO-CK | Emergency escape route map | สหชาติ | 0 | Depot | 2027-01-01 | 2026-09-30 | 0% | Late | 2026-10-30 | 50% | On Schedule | 2026-12-31 | 0% | On Schedule | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | GRS |  | 0 | 0
163 | 0 | Lot02 | MO-CK19 | MO-CK | Traffic Line Marking (Thermoplastic Paint) | สหชาติ | 0 | Depot | 2026-05-01 | 2026-04-30 | 100% | Completed | 2026-06-15 | 100% | Completed | 2026-10-15 | 100% | Completed | 2026-10-15 | 25% | Late | 0 | 0% | 0% | 0 | 0% | Late | GRS |  | 0 | 0
164 | 0 | Lot02 | MO-CK20 | MO-CK | Emergency Car Parking location Painting in front of MWS | สหชาติ | 0 | Depot | 2026-05-01 | 2026-04-30 | 100% | Completed | 2026-06-15 | 100% | Completed | 2026-10-15 | 0% | Late | 2026-10-15 | 0% | Late | 0 | 0% | 0% | 0 | 0% | Late | GRS |  | 0 | 0
165 | GRS-39022 | Lot02 | MO-CK21 | MO-CK | Safety Line painting in MWS, Stabling Area, P-way, Track | สหชาติ | 0 | Depot | 2027-01-01 | 2026-06-01 | 100% | Completed | 2026-08-01 | 100% | Completed | 2026-10-15 | 100% | Completed | 2026-12-31 | 81% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | GRS | GRS-39022 | GRS-69001 | GRS-69022
166 | 0 | Lot02 | MO-CK22 | MO-CK | Fire escape stairs level signs in the Depot, VS and IVS areas | สหชาติ | 0 | Depot | 2027-01-01 | 2026-09-30 | 50% | Late | 2026-10-31 | 0% | On Schedule | 2026-10-20 | 0% | Late | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | GRS |  | 0 | 0
167 | DWE-39026 | Lot02 | MO-CK23 | MO-CK | General waste Storage 22 x 5 m | สหชาติ | 0 | Depot | 2026-05-01 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-07-15 | 100% | Completed |  | DWE-39026 | DWE-69026 | DWE-69126
168 | 0 | Lot02 | MO-CK24 | MO-CK | Modify Traffic paint and traffic sign | สหชาติ | 0 | 0 | 2026-05-01 | 2026-04-30 | 100% | Completed | 2026-06-15 | 100% | Completed | 2026-10-15 | 64% | Late | 2026-10-15 | 13% | Late | 0 | 0% | 0% | 0 | 0% | Late | GRS |  | 0 | 0
169 | 0 | Lot02 | MO-CK25 | MO-CK | Station Area sign 28 stations | สหชาติ | 0 | 0 | 2026-05-01 | 2026-06-15 | 80% | Late | 2026-06-30 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-12-20 | 0% | On Schedule | 0 | 0% | 0% | 0 | 0% | Late | GRS |  | 0 | 0
170 |  | Lot02 | MO-CK26 | MO-CK | Safety and warning signage for lift and escalator at all station | สหชาติ | 0 | Depot | 2027-01-01 | 2026-06-16 | 100% | Completed | 2026-07-17 | 100% | Completed | 2027-01-31 | 76% | On Schedule | 2027-02-28 | 26% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | GRS
171 | MDW-39532 | Lot02 | MO-CK27 | MO-CK | Spike fence for Depot slab | สหชาติ | 0 | Depot | 2027-01-01 | 2026-07-31 | 70% | Late | 2026-08-31 | 0% | Late | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule | อยู่ระหว่างส่งขออนุมัติแบบรอ Approve | MDW-39532 | MDW-69564 | MDW-69565
172 | 0 | Lot02 | MO-CK28 | MO-CK | Bird net and Flashing at MWS and Skywalk to Stabling yard | สหชาติ | 0 | 0 | 2026-05-01 |  |  | 0% |  |  | 0% | 0 | 0% | 0% |  |  | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
173 | MDW-39541 | Lot02 | MO-CK29 | MO-CK | Fire Alarm Manual Call Point signage at all elevated station | สหชาติ | 0 | 0 | 2027-01-01 |  |  | 0% | 2026-07-30 | 100% | Completed | 0 | 0% | 0% |  |  | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39541 | MDW-69582 | MDW-69583
174 | 0 | Lot02 | MO-CK30 | MO-CK | Lighting for sealed space under stairs and behind lift shaft at underground station | ประธาน | 0 | 0 | 2027-01-01 | 2026-10-14 | 0% | Late | 2026-11-14 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | ไฟส่องสว่างสำหรับพื้นที่ปิดใต้บันไดและด้านหลังช่องลิฟต์ที่สถานีรถไฟใต้ดิน |  | 0 | 0
175 | 0 | Lot02 | MO-CK31 | MO-CK | Modify the access door of sealed space (under-stairs room) with a Sump Pump or ESPS cabinet | สหชาติ | 0 | 0 | 2027-01-01 | 2026-07-16 | 0% | Late | 2026-08-16 | 0% | Late | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 0 |  | 0 | 0
176 | 0 | Lot02 | MO-CK32 | MO-CK | Lighting to the sealed space (under-stairs room) with a Sump Pump or ESPS cabinet | ประธาน | 0 | Depot | 2027-01-01 | 2026-11-03 | 0% | On Schedule | 2026-12-04 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | ซื้อสปอร์ตไลท์+แบต จำนวน 4 ชุด แทนการลากสายไฟ |  | 0 | 0
177 | 0 | Lot02 | MO-CK33 | MO-CK | Additional lighting in areas where the lux level does not meet occupational health standards | ประธาน | 0 | Depot | 2027-01-01 | 2026-09-14 | 100% | Completed | 2026-10-15 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 95% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 0 |  | 0 | 0
178 | 0 | Lot02 | MO-CK34 | MO-CK | Provide and install confined space signage for Station and Depot | สหชาติ | 0 | 0 | 2027-01-01 | 2026-08-15 | 100% | Completed | 2026-09-15 | 100% | Completed | 2027-01-31 | 76% | On Schedule | 2027-02-28 | 26% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | GRS |  | 0 | 0
179 |  | Lot02 | MO-CK35 | MO-CK | Build room for Train crew main office at OR18 with office area, resting area, meeting room, pantry, toilet and locker room | สหชาติ/บัณฑิต/ประธาน | 0 | Depot | - |  |  | 0% |  |  | 0% | 0 | 0% | 0% |  |  | 0% | 0 | 0% | 0% | 0 | 0 | 0
180 |  | Lot02 | MO-CK36 | MO-CK | Dormitory Cable Containments (if any) | มนตรี | 0 | Depot | - |  |  | 0% |  |  | 0% | 0 | 0% | 0% |  |  | 0% | 0 | 0% | 0% | 0 | 0 | 0
181 | 0 | Lot02 | MO-CK37 | MO-CK | Provide Raise floor and building Service in Training &Simulator (OCC Admin) | สหชาติ | 0 | Depot | - | 0% | 0% | 0% |  |  |  | 0 | 0% | 0% |  |  | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
182 |  | Lot02 | MO-CK38 | MO-CK | Add N2 in Playback and Training Room and Backup Control Room | บุญประเสริฐ | 0 | Depot | - |  |  | 0% |  |  | 0% | 0 | 0% | 0% |  |  | 0% | 0 | 0% | 0% | 0 | 0 | 0
183 | MDW-39505 | Lot02 | MO-BEM1.1 | MO-BEM | Walkway from Main Work Shop to Stabling Area - Civil & AR | สหชาติ | 0 | Depot | 2026-08-02 | 2026-04-28 | 100% | Completed | 2026-05-29 | 92% | Late | 0 | 0% | 0% | 2026-09-30 | 93% | Late | 0 | 0% | 0% | 2026-08-31 | 100% | Completed |  | MDW-39505 | MDW-69510 | MDW-69511
184 | MDW-39506 | Lot02 | MO-BEM1.2 | MO-BEM | Walkway from Main Work Shop to Stabling Area - Building Services | ประธาน | 0 | Depot | 2026-08-02 | 2026-04-28 | 100% | Completed | 2026-05-29 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 0% | Late | 0 | 0% | 0% | 2026-09-23 | 100% | Completed |  | MDW-39506 | MDW-69512 | MDW-69513
185 | MDW-39507 | Lot02 | MO-BEM2 | MO-BEM | High Roof at Main Work Shop Entrance and Store | สหชาติ | 0 | Depot | 2026-08-01 | 2026-02-13 | 100% | Completed | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-01 | 100% | Completed |  | MDW-39507 | MDW-69514 | MDW-69515
186 | MDW-39509 | Lot02 | MO-BEM3 | MO-BEM | High Roof at the entrance and exit of the under floor wheel lathe | สหชาติ | 0 | Depot | 2026-08-04 | 2026-02-13 | 100% | Completed | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-01 | 100% | Completed |  | MDW-39509 | MDW-69518
187 | MDW-39511 | Lot02 | MO-BEM4.1 | MO-BEM | Maintenance Office Rooms at Main Workshop - Civil & AR | สหชาติ | 0 | Depot | 2026-07-03 | 2026-04-13 | 100% | Completed | 2026-05-14 | 100% | Completed | 0 | 0% | 0% | 2026-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-05-31 | 100% | Completed |  | MDW-39511 | MDW-69522 | MDW-69523
188 | MDW-39512 | Lot02 | MO-BEM4.2 | MO-BEM | Maintenance Office Rooms at Main Workshop - Building Services | ประธาน | 0 | Depot | 2026-07-04 | 2026-04-13 | 100% | Completed | 2026-05-14 | 100% | Completed | 0 | 0% | 0% | 2026-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-23 | 100% | Completed |  | MDW-39512 | MDW-69524 | MDW-69525
189 | MDW-39513 | Lot02 | MO-BEM5 | MO-BEM | Install Concrete car barrier along the walkway in front of MWS building | สหชาติ | 0 | Depot | 2027-01-01 | 2026-10-14 | 100% | Completed | 2026-11-14 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 100% | Completed | 0 | 0% | 0% | 2026-12-01 | 50% | On Schedule | 0 | MDW-39513 | MDW-69526 | MDW-69527
190 | 0 | Lot02 | MO-BEM6 | MO-BEM | Handrail on top of the water tank on the rooftop of the Admin Building | สหชาติ | 0 | Depot | 2027-01-01 | 2026-10-19 | 100% | Completed | 2026-11-19 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 0 |  | 0 | 0
191 | 0 | Lot02 | MO-BEM7 | MO-BEM | Modify maintenance service door to the roof building to easier access while maintaining safe operational standards | สหชาติ | 0 | Depot | 2027-01-01 | 2026-10-19 | 50% | Late | 2026-11-19 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 0 |  | 0 | 0
192 | MDW-39536 | Lot02 | MO-BEM8 | MO-BEM | Company logo and Central Control Room sign in CCR room. | สหชาติ | 0 | Depot | 2026-05-01 | 2026-01-27 | 100% | Completed | 2026-03-14 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 50% | Late | 0 | MDW-39536 | MDW-69572 | MDW-69573
193 | MDW-39536 | Lot02 | MO-BEM9 | MO-BEM | Soundproof insulation on the wall and structure and equipment in the CCR room. | สหชาติ | 0 | Depot | 2026-05-01 | 2026-01-12 | 100% | Completed | 2026-02-27 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 50% | Late | 0 | MDW-39536 | MDW-69572 | MDW-69573
194 | MDW-39526 | Lot02 | MO-BEM10 | MO-BEM | Relocate Fire Hose Cabinet to be outside of the clearance gauge zone 17 set | ประธาน | 0 | Depot | 2026-05-01 | 2026-01-12 | 100% | Completed | 2026-02-27 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-03-18 | 100% | Completed |  | MDW-39526 | MDW-69552 | MDW-69553
195 | MDW-39528 | Lot02 | MO-BEM11.1 | MO-BEM | Washing Area in Cleaning Staff Room at Stabling Yard - Civil & AR | สหชาติ | 0 | Depot | 2026-08-03 | 2026-06-03 | 100% | Completed | 2026-07-04 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-01 | 100% | Completed |  | MDW-39528 | MDW-69556 | MDW-69557
196 | MDW-39529 | Lot02 | MO-BEM11.2 | MO-BEM | Washing Area in Cleaning Staff Room at Stabling Yard - Building Services | ประธาน | 0 | Depot | 2026-08-04 | 2026-04-14 | 100% | Completed | 2026-05-30 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-03-31 | 100% | Completed |  | MDW-39529 | MDW-69558 | MDW-69559
197 | MDW-39522 | Lot02 | MO-BEM12 | MO-BEM | Rain protection for Water treatment Building | สหชาติ | 0 | Depot | 2026-08-05 | 2026-04-29 | 100% | Completed | 2026-05-30 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-01 | 100% | Completed |  | MDW-39522 | MDW-69544 | MDW-69545
198 | MDW-39522 | Lot02 | MO-BEM13.1 | MO-BEM | Zero Discharge Water treatment in Depot - Civil & AR | สหชาติ | 0 | Depot | 2027-01-01 | 2026-08-15 | 100% | Completed | 2026-09-30 | 75% | Late | 0 | 0% | 0% | 2026-12-31 | 63% | On Schedule | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39522 | MDW-69544 | MDW-69545
199 | MDW-39530 | Lot02 | MO-BEM13.2 | MO-BEM | Zero Discharge Water treatment in Depot - Building Services | ประธาน | 0 | Depot | 2027-01-01 | 2026-08-15 | 100% | Completed | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 50% | On Schedule | 0 | 0% | 0% | 46325 | 1 | Completed |  | MDW-39530 | MDW-69560 | MDW-69561
200 | MDW-39516 | Lot02 | MO-BEM14.1 | MO-BEM | Modification Works : Walkway Bridge between BL Depot and ORL Depot - Civil & AR | สหชาติ | 0 | Depot | 2026-08-02 | 2026-02-28 | 100% | Completed | 2026-06-15 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 95% | Late | 0 | 0% | 0% | 2026-08-31 | 100% | Completed |  | MDW-39516 | MDW-69532 | MDW-69533
201 | MDW-39517 | Lot02 | MO-BEM14.2 | MO-BEM | Modification Works : Walkway Bridge between BL Depot and ORL Depot - Building Services | ประธาน | 0 | Depot | 2026-08-03 | 2026-01-14 | 100% | Completed | 2026-03-01 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 10% | Late | 0 | 0% | 0% | 2026-08-31 | 100% | Completed |  | MDW-39517 | MDW-69534 | MDW-69535
202 | MDW-39514 | Lot02 | MO-BEM15.1 | MO-BEM | Roof for cars parking lots area (184 car)t - Civil & AR | สหชาติ | 0 | Depot | 2026-08-03 | 2026-02-28 | 100% | Completed | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-24 | 100% | Completed |  | MDW-39514 | MDW-69528 | MDW-69529
203 | MDW-39515 | Lot02 | MO-BEM15.2 | MO-BEM | Roof for cars parking lots area (184 car) - Building Services | ประธาน | 0 | Depot | 2026-08-03 | 2026-02-28 | 100% | Completed | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-23 | 0% | Late | รอส่งงานกับ BEM | MDW-39515 | MDW-69530 | MDW-69531
204 | MDW-39519 | Lot02 | MO-BEM16 | MO-BEM | Walkway roof and High roof across the road from Admin ORL to Depot slap | สหชาติ | 0 | Depot | 2026-08-01 | 2026-06-15 | 100% | Completed | 2026-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-10-31 | 57% | On Schedule | 0 | 0% | 0% | 2026-08-31 | 100% | Completed |  | MDW-39519 | MDW-69538 | MDW-69539
205 | MDW-39519 | Lot02 | MO-BEM17 | MO-BEM | Walkway roof to car park in front of admin ORL(3x5m.) | สหชาติ | 0 | Depot | 2026-08-01 | 2026-06-15 | 100% | Completed | 2026-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-10-31 | 70% | On Schedule | 0 | 0% | 0% | 2026-08-31 | 100% | Completed |  | MDW-39519 | MDW-69538 | MDW-69539
206 | MDW-39519 | Lot02 | MO-BEM18 | MO-BEM | Walkway roof over the footpath near depot slab (1.50 m. x 290 m.) and stair up to depot slap. | สหชาติ | 0 | Depot | 2026-08-01 | 2026-06-15 | 100% | Completed | 2026-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-10-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-08-31 | 100% | Completed |  | MDW-39519 | MDW-69538 | MDW-69539
207 | MDW-39557 | Lot02 | MO-BEM19 | MO-BEM | Install Chain Link fence to enclose parking area | สหชาติ | 0 | Depot | 2026-10-01 | 2026-06-29 | 100% | Completed | 2026-07-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 0% | Late | 0 | 0% | 0% | 2026-09-30 | 90% | Late | 0 | MDW-39557 | MDW-69614 | MDW-69615
208 | MDW-39523 | Lot02 | MO-BEM20 | MO-BEM | Hose bib 1/2" 4 sets for Tree around Admin area | ประธาน | 0 | Depot | 2026-06-01 | 2026-04-23 | 100% | Completed | 2026-06-08 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-03-31 | 100% | Completed |  | MDW-39523 | MDW-69546 | MDW-69547
209 | - | Lot02 | MO-BEM21 | MO-BEM | Relocate Security Guard Box at Front Gate and Install Roof 3x5m. | สหชาติ | 0 | Depot | 2027-01-03 | 2026-07-31 | 100% | Completed | 2026-09-30 | 75% | Late | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule |  |  | 0 | 0
210 | MDW-39534 | Lot02 | MO-BEM21.1 | MO-BEM | Modification Works : Security Guard Box at ORL Depot Entrance - Civil & AR | สหชาติ | 0 | Depot | 2027-01-02 | 2026-07-31 | 100% | Completed | 2026-09-30 | 67% | Late | 0 | 0% | 0% | 2026-12-31 | 100% | Completed | 0 | 0% | 0% | 2026-12-01 | 50% | On Schedule |  | MDW-39534 | MDW-69568 | MDW-69569
211 | MDW-39535 | Lot02 | MO-BEM21.2 | MO-BEM | Modification Works : Security Guard Box at ORL Depot Entrance - Building Services | ประธาน | 0 | Depot | 2027-01-03 | 2026-07-31 | 100% | Completed | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 50% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule |  | MDW-39535 | MDW-69570 | MDW-69571
212 | MDW-39532 | Lot02 | MO-BEM22 | MO-BEM | Addition Spike fence for MRTA fence and Chain link at Klong Chourdyai 400m. | สหชาติ | 0 | Depot | 2027-01-01 | 2026-08-30 | 70% | Late | 2026-09-30 | 0% | Late | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule |  | MDW-39532 | MDW-69564 | MDW-69565
213 | MDW-39527 | Lot02 | MO-BEM23 | MO-BEM | Hand sink with eye wash station | ประธาน | พี่ต่อ | Depot | 2027-01-01 | 2026-08-30 | 100% | Completed | 2026-10-15 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 100% | Completed | 0 | 0% | 0% | 2026-12-01 | 100% | Completed |  | MDW-39527 | MDW-69554 | MDW-69555
214 | MDW-39531 | Lot02 | MO-BEM24 | MO-BEM | Guard rail protection for Fire Hose Cabinet 8 set | สหชาติ | 0 | Depot | 2026-06-01 | 2026-03-14 | 100% | Completed | 2026-04-14 | 100% | Completed | 0 | 0% | 0% | 2026-08-15 | 100% | Completed | 0 | 0% | 0% | 2026-07-16 | 100% | Completed |  | MDW-39531 | MDW-69562 | MDW-69563
215 | MDW-39557 | Lot02 | MO-BEM25.1 | MO-BEM | Chain Link Fence to divide controlled areas on Depot slab 3 m.x 485 m. - Civil & AR | สหชาติ | 0 | Depot | 2026-10-01 | 2026-06-14 | 100% | Completed | 2026-07-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 0% | Late | 0 | 0% | 0% | 2026-09-30 | 50% | Late |  | MDW-39557 | MDW-69614 | MDW-69615
216 | MDW-39520 | Lot02 | MO-BEM25.2 | MO-BEM | Chain Link Fence to divide controlled areas on Depot slab 3 m.x 485 m.- Building Services | ประธาน | 0 | Depot | 2026-10-01 | 2026-06-14 | 100% | Completed | 2026-07-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 0% | Late | 0 | 0% | 0% | 2026-09-30 | 0% | Late |  | MDW-39520 | MDW-69540 | MDW-69541
217 | MDW-39518 | Lot02 | MO-BEM26 | MO-BEM | Street Lighting system area between MRTA Fence and Depot slab | ประธาน | 0 | Depot | 2026-08-01 | 2026-04-14 | 50% | Late | 2026-05-15 | 0% | Late | 0 | 0% | 0% | 2026-07-31 | 0% | Late | 0 | 0% | 0% | 2026-09-30 | 0% | Late |  | MDW-39518 | MDW-69536 | MDW-69537
218 | - | Lot02 | MO-BEM27 | MO-BEM | Compacted gravel walkway along the Test Track OR-BL 1.2 m. | สหชาติ | พรพรหม | Depot | 2027-01-01 | 2026-08-30 | 100% | Completed | 2026-09-30 | 0% | Late | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule |  |  | 0 | 0
219 | MDW-39524 | Lot02 | MO-BEM28.1 | MO-BEM | Walkway under Depot Slab for Maintenance Service - Civil & AR | สหชาติ | 0 | Depot | 2027-01-02 | 2026-09-14 | 100% | Completed | 2026-10-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 100% | Completed | 0 | 0% | 0% | 2026-12-01 | 50% | On Schedule |  | MDW-39524 | MDW-69548 | MDW-69549
220 | MDW-39525 | Lot02 | MO-BEM28.2 | MO-BEM | Walkway under Depot Slab for Maintenance Service - Building Services | ประธาน | 0 | Depot | 2027-01-03 | 2026-09-14 | 100% | Completed | 2026-10-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 50% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule |  | MDW-39525 | MDW-69550 | MDW-69551
221 | MDW-39521 | Lot02 | MO-BEM29 | MO-BEM | Walkway Bridge across the canal for Depot area inspection patrols 3 location | สหชาติ | 0 | Depot | 2027-01-01 | 2026-08-15 | 100% | Completed | 2026-09-30 | 67% | Late | 0 | 0% | 0% | 2026-12-31 | 95% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 100% | Completed |  | MDW-39521 | MDW-69542 | MDW-69543
222 | - | Lot02 | MO-BEM30 | MO-BEM | Cut down trees between Depot BL+ORL and MRTA Fence | สหชาติ | 0 | Depot | 2027-01-01 | 2026-10-29 | 0% | Late | 2026-11-29 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule |  |  | 0 | 0
223 | 0 | Lot02 | MO-BEM31 | MO-BEM | Provide facility system and interface to MMC room (Fire Alarm / CCTV / VMS / TEL / CASS / Radio / PA) | บัณฑิต | 0 | Depot | 2026-10-01 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
224 | - | Lot02 | MO-BEM32 | MO-BEM | Stainless Guard rail balustrade for waiting area | สหชาติ | 0 | Depot | 2026-05-01 |  |  | 0% |  |  | 0% | 0 | 0% | 0% |  |  | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
225 | - | Lot02 | MO-BEM33 | MO-BEM | Concrete walkway 2 x 80 m. For fire escape route | สหชาติ | 0 | Depot | 2026-05-01 |  |  | 0% |  |  | 0% | 0 | 0% | 0% |  |  | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
226 | - | Lot02 | MO-BEM34 | MO-BEM | Access Gate (Full Height Turnstile) at 1st floor admin ORL | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule |  |  | 0 | 0
227 | - | Lot02 | MO-BEM35 | MO-BEM | Access Gate (Tripod with Swing Gate) at MWS Entrance | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule |  |  | 0 | 0
228 | - | Lot02 | MO-BEM36 | MO-BEM | Access Gate (Tripod with Swing Gate) at Admin 2nd floor connect to OCC | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule |  |  | 0 | 0
229 | - | Lot02 | MO-BEM37 | MO-BEM | Access Gate (Tripod with Swing Gate) on Klong Chourdyai bridge | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule |  |  | 0 | 0
230 | - | Lot02 | MO-BEM38 | MO-BEM | Access Gate (Tripod with roof covering) at parking lot OCC | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule |  |  | 0 | 0
231 | - | Lot02 | MO-BEM39 | MO-BEM | Access Gate (Tripod with roof covering) at Stair up to Depot slab | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule |  |  | 0 | 0
232 | - | Lot02 | MO-BEM40 | MO-BEM | Access Control (2 Factors, Card + Finger Print) at High Security rooms - CCR/PTR/Store | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule |  |  | 0 | 0
233 | - | Lot02 | MO-BEM41 | MO-BEM | Link CCTV Landscape of all depot ORL area for MMC BL monitoring. | บัณฑิต | 0 | 0 | 2027-01-01 | 2026-11-28 | 0% | On Schedule | 2026-11-29 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule |  |  | 0 | 0
234 | - | Lot02 | MO-BEM42 | MO-BEM | Fire Suppression Control Panel Cover which located in tunnel | สู่โชค | 0 | 0 | 2027-01-01 |  |  | 0% |  |  | 0% | 0 | 0% | 0% |  |  | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
235 | MDW-39537 | Lot02 | MO-BEM43 | MO-BEM | Handrails for ladder at IVS and Vent buildings | สหชาติ | 0 | 0 | 2026-09-01 | 2026-03-31 | 70% | Late | 2026-05-01 | 0% | Late | 0 | 0% | 0% | 2026-08-31 | 0% | Late | 0 | 0% | 0% | 2026-10-31 | 0% | On Schedule |  | MDW-39537 | MDW-69574 | MDW-69575
236 | MDW-39538 | Lot02 | MO-BEM44 | MO-BEM | Escalator Anti-Slide device for all station. | สหชาติ | 0 | 0 | 2026-09-01 | 2026-05-30 | 100% | Completed | 2026-06-30 | 100% | Completed | 2027-01-31 | 100% | Completed | 2027-02-28 | 70% | On Schedule | 0 | 0% | 0% | 2027-01-29 | 0% | On Schedule |  | MDW-39538 | MDW-69576 | MDW-69577
237 | MDW-39539 | Lot02 | MO-BEM45 | MO-BEM | Roof for control panel on vent building | สหชาติ | 0 | 0 | 2027-01-01 | 2026-09-14 | 70% | Late | 2026-10-30 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule |  | MDW-39539 | MDW-69578 | MDW-69579
238 | MDW-39553 | Lot02 | MO-BEM46 | MO-BEM | Provide Standing plate or ladder to access the Fire Valve in at Omega points for all underground stations. | สหชาติ | 0 | Depot | 2027-01-01 | 2026-09-14 | 0% | Late | 2026-10-30 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule |  | MDW-39553 | MDW-69606 | MDW-69607
239 | MDW-39540 | Lot02 | MO-BEM47 | MO-BEM | Water drop protection above UPS cabinet at station and Depot | สหชาติ | 0 | 0 | 2027-01-01 | 2026-09-14 | 0% | Late | 2026-10-30 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule |  | MDW-39540 | MDW-69580 | MDW-69581
240 | MDW-39541 | Lot02 | MO-BEM48 | MO-BEM | Fire alarm manual call point cover in public area at all station | ประธาน | 0 | 0 | 2027-01-01 | 2026-09-14 | 50% | Late | 2026-10-30 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule |  | MDW-39541 | MDW-69582 | MDW-69583
241 | MDW-39542 | Lot02 | MO-BEM49 | MO-BEM | Emergency stop button cover for escalator at all station. | สหชาติ | 0 | 0 | 2027-01-01 | 2026-09-14 | 0% | Late | 2026-10-30 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule |  | MDW-39542 | MDW-69584 | MDW-69585
242 | 0 | Lot02 | MO-BEM50 | MO-BEM | Modify maintenance service door to the roof of OR13 vent building to easier access while maintaining safe operational standards | สู่โชค | 0 | Depot | 2027-01-01 | 2026-10-29 | 0% | Late | 2026-10-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule |  |  | 0 | 0
243 | MDW-39514 | Lot02 | MO-BEM51 | MO-BEM | Modify existing car park to be 220 motorcycle parking lots including floor painting and parking roof | สหชาติ | 0 | Depot | 2026-08-01 | 2026-01-29 | 100% | Completed | 2026-03-16 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-01 | 100% | Completed |  | MDW-39514 | MDW-69528 | MDW-69529
244 | MDW-39534 | Lot02 | MO-BEM52 | MO-BEM | Modify the sidewalk for temporary parking at entrance | สหชาติ | 0 | Depot | 2027-01-01 | 2026-07-31 | 100% | Completed | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 100% | Completed | 0 | 0% | 0% | 2026-12-01 | 50% | On Schedule |  | MDW-39534 | MDW-69568 | MDW-69569
245 | MDW-39554 | Lot02 | MO-BEM53.1 | MO-BEM | Modification Works : Security Guard Box at OCC Parking Area - Civil & AR | สหชาติ | 0 | Depot | 2027-01-02 | 2026-09-14 | 100% | Completed | 2026-10-31 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 50% | On Schedule |  | MDW-39554 | MDW-69608 | MDW-69609
246 | MDW-39555 | Lot02 | MO-BEM53.2 | MO-BEM | Modification Works : Security Guard Box at OCC Parking Area - Building Services | ประธาน | 0 | 0 | 2027-01-02 | 2026-09-14 | 100% | Completed | 2026-10-31 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 50% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule |  | MDW-39555 | MDW-69610 | MDW-69611
247 | NoDrawing | Lot02 | MO-BEM54 | MO-BEM | Strengthen the Maintenance Walkway of the TEF fan | สหชาติ | 0 | 0 | 2027-01-01 | 2026-07-16 | 100% | Completed | 2026-08-16 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule |  |  | 0 | 0
Lot 1
[32 empty] | CK Pesonsible Person | Total | Completed | Late | On Schedule
[32 empty] | สหชาติ | 26 | 17 | 5 | 4
[32 empty] | ประธาน | 37 | 31 | 2 | 4
[32 empty] | สมศักดิ์ | 13 | 6 | 6 | 1
[32 empty] | กำพล | 9 | 1 | 4 | 4
[32 empty] | บัณฑิต | 4 | 0 | 2 | 2
[32 empty] | สู่โชค | 1 | 0 | 1 | 0
[32 empty] | ธัญวิทย์ | 0 | 0 | 0 | 0
[32 empty] | มนตรี | 3 | 0 | 1 | 2
[32 empty] | มนต์ชัย | 1 | 0 | 1 | 0
[32 empty] | - | 2 | 1 | 1 | 0
Lot 2
[32 empty] | CK Pesonsible Person | Total | Completed | Late | On Schedule
[32 empty] | สหชาติ | 60 | 20 | 14 | 26
[32 empty] | ประธาน | 25 | 12 | 6 | 7
[32 empty] | บัณฑิต | 8 | 0 | 0 | 8
[32 empty] | สู่โชค | 1 | 0 | 0 | 1

## Inspection (hidden)
Inspection
No. | Design Submission | Lot No. | Code | System | Activity Name | CK Responsible Person |  | Location | Expected Completion Month | Design (PLAN) | Design (%) | Design (Status) | Procurement (PLAN) | Procurement (%) | Procurement (Status) | Manufacturing / Delivery Process (PLAN) | Manufacturing / Delivery Process (%) | Manufacturing / Delivery (Status) | Construction /Installation (PLAN) | Construction /Installation (%) | Construction /Installation (Status) | T&C (PLAN) | T&C (%) | T&C (Status) | Test Procedure (PLAN) | Test Procedure (%) | Test Procedure (Status) | Inspection (PLAN) | Inspection (%) | Inspection (Status) | Note | Design Submission | Procedure No. | Test Report No.
1 | MDW-39246-60 | Lot01 | GEN1 | GEN | Rooms and Building Service Systems Modification in Stations Area | - | 0 | 0 | 2026-08-01 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39246 | MDW-69259 | MDW-69260
2 | MDW-39246 | Lot01 | GEN1.1 | GEN | Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR13 - OR17 | ประธาน | 0 | 0 | 2026-08-01 | 2026-01-30 | 100% | Completed | 2026-03-01 | 100% | Completed | 0 | 0% | 0% | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 46326 | 1 | Completed |  | MDW-39246 | MDW-69259 | MDW-69260
3 | MDW-39247 | Lot01 | GEN1.2 | GEN | Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR18 - OR22 | ประธาน | 0 | 0 | 2026-08-01 | 2025-12-30 | 100% | Completed | 2026-01-29 | 100% | Completed | 0 | 0% | 0% | 2026-02-28 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 46326 | 1 | Completed |  | MDW-39247 | MDW-69259 | MDW-69261
4 | MDW-39248 | Lot01 | GEN1.3 | GEN | Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR23 - OR29 | ประธาน | 0 | 0 | 2026-08-01 | 2026-01-30 | 100% | Completed | 2026-03-01 | 100% | Completed | 0 | 0% | 0% | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 46326 | 1 | Completed |  | MDW-39248 | MDW-69259 | MDW-69262
5 | MDW-39252 | Lot01 | GEN1.4 | GEN | Modification of Fire Suppression System (N2) in Commerial Room at OR14 | ประธาน | 0 | 0 | 2026-08-01 | 2025-12-30 | 100% | Completed | 2026-01-29 | 100% | Completed | 0 | 0% | 0% | 2026-02-28 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 46326 | 1 | Completed |  | MDW-39252 | MDW-69269 | MDW-69270
6 | MDW-39253 | Lot01 | GEN1.5 | GEN | Modification of Civil Work in Telecommunication Room at OR14 | สหชาติ | 0 | 0 | 2026-08-01 | 2025-12-30 | 100% | Completed | 2026-01-29 | 100% | Completed | 0 | 0% | 0% | 2026-02-28 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39253 | MDW-69271 | MDW-69272
7 | MDW-39254 | Lot01 | GEN1.6 | GEN | Modification in Staff Mess Room at OR13-OR17 | ประธาน | 0 | 0 | 2026-08-01 | 2026-01-30 | 100% | Completed | 2026-03-01 | 100% | Completed | 0 | 0% | 0% | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 46326 | 1 | Completed |  | MDW-39254 | MDW-69273 | MDW-69274
8 | MDW-39255 | Lot01 | GEN1.7 | GEN | Modification in Staff Mess Room at OR18-OR22 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 46326 | 0 | On Schedule | 0 | MDW-39255 | MDW-69273 | MDW-69275
9 | MDW-39256 | Lot01 | GEN1.8 | GEN | Modification in Staff Mess Room at OR23-OR29 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 46356 | 0 | On Schedule | 0 | MDW-39256 | MDW-69273 | MDW-69276
10 | MDW-39257 | Lot01 | GEN1.9 | GEN | Modification of Air Conditioning in CER and SER at OR13-OR19 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 99% | Late | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 46356 | 0 | On Schedule | 0 | MDW-39257 | MDW-69277 | MDW-69278
11 | MDW-39258 | Lot01 | GEN1.10 | GEN | Modification of Air Conditioning in CER and SER at OR20-OR22 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 99% | Late | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 46356 | 0 | On Schedule | 0 | MDW-39258 | MDW-69277 | MDW-69279
12 | MDW-39259 | Lot01 | GEN1.11 | GEN | Modification of Air Conditioning in CER and SER at OR23-OR29 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 99% | Late | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 46356 | 0 | On Schedule | 0 | MDW-39259 | MDW-69277 | MDW-69280
13 | MDW-39272 | Lot01 | GEN1.12 | GEN | Modification of New M&E Room at IVS15 - IVS17 Civil & AR | สหชาติ | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39272 | MDW-69299 | MDW-69300
14 | MDW-39273 | Lot01 | GEN1.13 | GEN | Modification of New M&E UPS Room at IVS15-IVS17 - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 99% | Late | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 46356 | 0 | On Schedule | 0 | MDW-39273 | MDW-69301 | MDW-69302
15 | MDW-39294 | Lot01 | GEN1.14 | GEN | Provision of Architectural Work in new M&E UPS room at OR23 | สหชาติ | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39294 | MDW-69339 | MDW-69340
16 | MDW-39299 | Lot01 | GEN1.15 | GEN | Provision of Air Conditioning System in Commercial Room at OR13-OR19 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 46326 | 0 | On Schedule | 0 | MDW-39299 | MDW-69349 | MDW-69350
17 | MDW-39306 | Lot01 | GEN1.16 | GEN | Modification CER and First Aid Room at OR14 - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 46326 | 1 | Completed |  | MDW-39306 | MDW-69363 | MDW-69364
18 | MDW-39307 | Lot01 | GEN1.17 | GEN | Additional Fence at Back of House OR13 - OR22 and IVS East Section | สหชาติ | 0 | 0 | 2026-08-01 | 2026-09-30 | 100% | Completed | 2026-10-31 | 50% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39307 | MDW-69365 | MDW-69366
19 | MDW-39249 | Lot01 | GEN1.18 | GEN | SOR Counter and Workstation Hanging Support Installation on East Section | สหชาติ | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39249 | MDW-69263 | MDW-69264
20 | MDW-39250 | Lot01 | GEN1.19 | GEN | Ticket Office Modification on East Section | สหชาติ | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39250 | MDW-69265 | MDW-69266
21 | MDW-39261 | Lot01 | GEN2 | GEN | Rooms and Building Service Systems Modification in Depot Area | - | 0 | Depot | 2026-08-01 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39261 | MDW-69283 | MDW-69284
22 | MDW-39260 | Lot01 | GEN2.1 | GEN | Modification of Air Conditioning in M&E Room at OCC Building | ประธาน | 0 | 0 | 2026-08-01 | 2025-12-30 | 100% | Completed | 2026-01-29 | 100% | Completed | 0 | 0% | 0% | 2026-02-28 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 46326 | 1 | Completed |  | MDW-39260 | MDW-69281 | MDW-69282
23 | MDW-39261 | Lot01 | GEN2.2 | GEN | Provision of UPS for MDB Control at Main Workshop, OCC Building, Admin Building, Stabling Yard and Train Washing Plant | ประธาน | 0 | 0 | 2026-08-01 | 2026-09-01 | 100% | Completed | 2026-10-01 | 100% | Completed | 0 | 0% | 0% | 2026-10-31 | 90% | On Schedule | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 46326 | 0 | On Schedule | 0 | MDW-39261 | MDW-69283 | MDW-69284
24 | MDW-39262 | Lot01 | GEN2.3 | GEN | Provision of Redundant MDB at OCC Building, Admin Building and Canteen | ประธาน | 0 | 0 | 2026-08-01 | 2026-09-01 | 100% | Completed | 2026-10-01 | 100% | Completed | 0 | 0% | 0% | 2026-10-31 | 95% | On Schedule | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 46326 | 0 | On Schedule | 0 | MDW-39262 | MDW-69285 | MDW-69286
25 | MDW-39263 | Lot01 | GEN2.4 | GEN | Additonal Lighting System at Depot Area | ประธาน | 0 | 0 | 2026-08-01 | 2026-04-01 | 100% | Completed | 2026-05-01 | 100% | Completed | 0 | 0% | 0% | 2026-05-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 46326 | 1 | Completed |  | MDW-39263 | MDW-69287 | MDW-69288
26 | MDW-39290 | Lot01 | GEN2.5 | GEN | Modification Room for PSY at Depot Buildings - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 46326 | 0 | On Schedule | 0 | MDW-39290 | MDW-69331 | MDW-69332
27 | MDW-39300 | Lot01 | GEN2.6 | GEN | Modification SIG-PSD Office at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 46326 | 0 | On Schedule | 0 | MDW-39300 | MDW-69351 | MDW-69352
28 | MDW-39301 | Lot01 | GEN2.7 | GEN | Modification Backup CCR Room at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 46326 | 0 | On Schedule | 0 | MDW-39301 | MDW-69353 | MDW-69354
29 | MDW-39302 | Lot01 | GEN2.8 | GEN | Modification SER at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 46326 | 0 | On Schedule | 0 | MDW-39302 | MDW-69355 | MDW-69356
30 | MDW-39303 | Lot01 | GEN2.9 | GEN | Modification CER & SCADA Room at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 46326 | 0 | On Schedule | 0 | MDW-39303 | MDW-69357 | MDW-69358
31 | MDW-39309 | Lot01 | GEN2.10 | GEN | Modification Air Conditioning System at CCR | ประธาน | 0 | 0 | 2026-08-01 | 2026-10-01 | 100% | Completed | 2026-10-31 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 80% | On Schedule | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 46326 | 0 | On Schedule | 0 | MDW-39309 | MDW-69369 | MDW-69370
32 | MDW-39312 | Lot01 | GEN2.11 | GEN | Modification Electronic Workshop at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-10-31 | 100% | Completed | 2026-11-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 46326 | 0 | On Schedule | 0 | MDW-39312 | MDW-69375 | MDW-69376
33 | MDW-39313 | Lot01 | GEN2.12 | GEN | Modification Battery Charger Room at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-10-31 | 100% | Completed | 2026-11-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 46326 | 0 | On Schedule | 0 | MDW-39313 | MDW-69377 | MDW-69378
34 | MDW-39314 | Lot01 | GEN2.13 | GEN | Modification Machining Room at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-10-31 | 90% | On Schedule | 2026-11-30 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 46326 | 0 | On Schedule | 0 | MDW-39314 | MDW-69379 | MDW-69380
35 | MDW-39315 | Lot01 | GEN2.14 | GEN | Modification Electronic Workshop, Battery Charger and Machining Room at Main Workshop - Civil & AR | สหชาติ | 0 | 0 | 2026-08-01 | 2026-10-31 | 70% | On Schedule | 2026-11-30 | 90% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 0 | 0 | 0 |  | MDW-39315 | MDW-69383 | MDW-69384
36 | MDW-39297 | Lot01 | GEN2.15 | GEN | Training Room at Ratchada Station (Part 2) | สหชาติ | 0 | 0 | 2026-08-01 | 2026-08-01 | 0% | Late | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 0 | 0 | 0 |  | MDW-39297 | MDW-69345 | MDW-69346
37 | MDW-39291 | Lot01 | GEN2.16 | GEN | Conductor Rail Arrangement Modification at Main Line East Section | กำพล | 0 | 0 | 2026-08-01 | 2026-09-30 | 100% | Completed | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 90% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 0 | 0 | 0 |  | MDW-39291 | MDW-69333 | MDW-69334
38 | MDW-39292 | Lot01 | GEN2.17 | GEN | Conductor Rail Arrangement Modification at Depot | กำพล | 0 | 0 | 2026-08-01 | 2026-09-30 | 100% | Completed | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 90% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 0 | 0 | 0 |  | MDW-39292 | MDW-69335 | MDW-69336
39 | MDW-39295 | Lot01 | GEN2.18 | GEN | Dangerous Goods Building in Depot - Civil & AR | สหชาติ | 0 | 0 | 2026-08-01 | 2026-01-27 | 100% | Completed | 2026-02-27 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0 | 0 |  | MDW-39295 | MDW-69341 | MDW-69342
40 | MDW-39296 | Lot01 | GEN2.19 | GEN | Dangerous Goods Building in Depot - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2025-12-13 | 100% | Completed | 2026-01-28 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 46326 | 0 | On Schedule | 0 | MDW-39296 | MDW-69343 | MDW-69344
41 | MDW-39308 | Lot01 | GEN2.20 | GEN | Additional Locking Devices for Main Line Tandem Turnouts 2007, 2010 & 2013 and Depot Turnout D16 | กำพล | 0 | 0 | 2026-08-01 | 2026-11-30 | 50% | On Schedule | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 0 | 0 | 0 |  | MDW-39308 | MDW-69367 | MDW-69368
42 | MDW-39200-31 | Lot01 | GEN3 | GEN | Cable Containment Modification | - | 0 | 0 | 2025-05-28 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39200
43 | - | Lot01 | GEN4 | GEN | Training Room and Workshop Room | - | 0 | 0 | 2026-04-01 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
44 | MDW-39242 | Lot01 | GEN4.0 | GEN | Modification Works for Training Room at Ratchada Station | ประธาน | 0 | 0 | 2026-04-01 | 2025-12-30 | 100% | Completed | 2026-01-31 | 100% | Completed | 0 | 0% | 0% | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-03-16 | 100% | Completed | 2026-09-30 | 100% | Completed |  | MDW-39242 | MDW-69251 | MDW-69252
45 | MDW-39244 | Lot01 | GEN4.1 | GEN | AFC Training Room Modification - Civil & AR | สหชาติ | 0 | 0 | 2026-08-21 | 2026-09-30 | 10% | Late | 2026-10-15 | 100% | Completed | 0 | 0% | 0% | 2026-11-15 | 0% | On Schedule | 0 | 0% | 0% | 2026-10-31 | 0% | On Schedule | 2026-11-22 | 0% | On Schedule | อยู่ระหว่างจัดทำแบบก่อสร้าง | MDW-39244 | MDW-69255 | MDW-69256
46 | MDW-39245 | Lot01 | GEN4.2 | GEN | AFC Training Room Modification - Building Services | ประธาน | 0 | 0 | 2026-08-21 | 2025-12-30 | 100% | Completed | 2026-01-31 | 100% | Completed | 0 | 0% | 0% | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-03-24 | 100% | Completed | 2026-08-07 | 100% | Completed |  | MDW-39245 | MDW-69257 | MDW-69258
47 | MDW-39235 | Lot01 | GEN5 | GEN | Raised Floor | สหชาติ | 0 | 0 | 2026-06-01 | 2025-05-15 | 100% | Completed | 2024-12-14 | 100% | Completed | 2025-08-04 | 100% | Completed | 2025-12-28 | 100% | Completed | 0 | 0% | 0% | 2025-11-28 | 100% | Completed | 2026-09-30 | 0% | Late | 0 | MDW-39235 | MDW-69237 | MDW-69238
48 | MDW-39271 | Lot01 | GEN6 | GEN | Wayside Cable Containment in Depot | - | 0 | Depot | 2026-02-22 | 2025-05-15 | 100% | Completed | 2024-12-14 | 100% | Completed | 2025-08-04 | 100% | Completed | 2025-12-28 | 100% | Completed | 0 | 0% | 0% | 2026-08-26 | 100% | Completed | 2026-09-30 | 0% | Late | 0 | MDW-39271 | MDW-69297 | MDW-69298
49 | MDW-39269 | Lot01 | GEN6.1 | GEN | PSY Wayside Cable Containment for 24 Kv Cable under the Depot slab | ประธาน | 0 | Depot | 2026-02-22 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39269 | MDW-69293 | MDW-69294
50 | MDW-39270 | Lot01 | GEN6.2 | GEN | COM/SIG Wayside Cable Containment in the Depot | มนตรี/ประธาน | 0 | Depot | 2026-02-22 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39270 | MDW-69295 | MDW-69296
51 | - | Lot01 | GEN7 | GEN | Dangerous Waste Storage Building in Depot | - | 0 | Depot | 2026-09-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
52 | DWE-39024 | Lot01 | GEN7.1 | GEN | Dangerous Waste Storage Building in Depot - Civil & AR | สหชาติ | 0 | Depot | 2026-09-20 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-07-15 | 100% | Completed | 2026-06-08 | 100% | Completed |  | DWE-39024 | DWE-69024 | DWE-69124
53 | DWE-39025 | Lot01 | GEN7.2 | GEN | Dangerous Waste Storage Building in Depot - Building service | ประธาน | 0 | Depot | 2026-09-20 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed | 0 | 0% | 0% | 2026-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-04-20 | 100% | Completed | 2026-06-08 | 100% | Completed |  | DWE-39025 | DWE-69025 | DWE-69125
54 | - | Lot01 | GEN8 | GEN | General Waste Storage Building in Depot | - | 0 | Depot | 2026-09-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
55 | DWE-39026 | Lot01 | GEN8.1 | GEN | General Waste Storage Building in Depot - Civil & AR | สหชาติ | 0 | Depot | 2026-09-20 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-07-15 | 100% | Completed | 2026-06-08 | 100% | Completed |  | DWE-39026 | DWE-69026 | DWE-69126
56 | DWE-39025 | Lot01 | GEN8.2 | GEN | General Waste Storage Building in Depot - Building service | ประธาน | 0 | Depot | 2026-09-20 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed | 0 | 0% | 0% | 2026-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-04-20 | 100% | Completed | 2026-06-08 | 100% | Completed |  | DWE-39025 | DWE-69025 | DWE-69125
57 | DWE-39021 | Lot01 | GEN9 | GEN | Operation Support Equipment | สมศักดิ์ | 0 | Depot | 2026-08-21 | 2025-03-02 | 100% | Completed | 2025-11-02 | 100% | Completed | 2026-11-16 | 90% | On Schedule | 0 | 0% | 0% | 0 | 0% | 0% | 2026-10-17 | 0% | Late | 2026-11-23 | 0% | On Schedule | คงเหลือจัดส่ง Signal Lamp | DWE-39021 | DWE-69021 | DWE-69121
58 | GRS-39001-40 | Lot01 | GEN10.1 | GEN | Graphic and Signage Station | สหชาติ | 0 | 0 | 2026-08-21 | 2026-06-30 | 100% | Completed | 2026-05-31 | 95% | Late | 2027-01-31 | 76% | On Schedule | 2027-02-28 | 34% | On Schedule | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | GRS-39001 | GRS-69001 | GRS-69002
59 | GRS-39001-40 | Lot01 | GEN10.2 | GEN | Graphic and Signage Mainline & IVS,VS | สหชาติ | 0 | 0 | 2026-08-21 | 2026-06-15 | 79% | Late | 2026-05-31 | 95% | Late | 2026-07-31 | 0% | Late | 2026-07-31 | 0% | Late | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | GRS-39001 | GRS-69001 | GRS-69002
60 | GRS-39001-40 | Lot01 | GEN10.3 | GEN | Graphic and Signage Depot | สหชาติ | 0 | 0 | 2026-08-21 | 2026-08-15 | 90% | Late | 2026-07-31 | 93% | Late | 2026-06-30 | 56% | Late | 2026-06-30 | 19% | Late | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | GRS-39001 | GRS-69001 | GRS-69002
61 | MDW-39289 | Lot01 | GEN11 | GEN | Earthing and Bonding Modification | ประธาน | 0 | 0 | 2026-03-01 | 2025-01-31 | 100% | Completed | 2025-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-02-28 | 100% | Completed | 2026-03-30 | 100% | Completed | 2026-09-23 | 0% | Late | 2026-09-30 | 0% | Late | 0 | MDW-39289 | MDW-69329 | MDW-69330
62 | - | Lot01 | GEN12 | GEN | Mainline Cable Trough Modification on East Section | - | 0 | 0 | 2026-06-22 | 2025-10-31 | 100% | Completed | 2025-11-30 | 100% | Completed | 2025-12-30 | 100% | Completed | 2026-03-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 80% | Late | 2026-10-07 | 0% | Late | 0 |  | 0 | 0
63 | MDW-39233 | Lot01 | GEN12.1 | GEN | Main Line Cable Trough Modification (PSY) | มนต์ชัย | 0 | Depot | 2026-06-22 | 2025-10-31 | 100% | Completed | 2025-11-30 | 100% | Completed | 2025-12-30 | 100% | Completed | 2026-03-30 | 100% | Completed | 0% | 0% | 0% | 2026-09-30 | 80% | Late | 2026-10-07 | 0% | Late | 0 | MDW-39233
64 | MDW-39234 | Lot01 | GEN12.2 | GEN | Main Line Cable Trough Modification (SIG/COM) | มนตรี | 0 | 0 | 2026-06-22 | 2025-10-31 | 100% | Completed | 2025-11-30 | 100% | Completed | 2025-12-30 | 100% | Completed | 2026-03-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 80% | Late | 2026-10-07 | 0% | Late | งานจบแล้ว | MDW-39234 | MDW-69234 | MDW-69236
65 | MDW-39236 | Lot01 | GEN13 | GEN | Bird Protection System | สหชาติ | 0 | 0 | 2026-11-19 | 2025-06-30 | 100% | Completed | 2025-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-01-26 | 100% | Completed | 0 | 0% | 0% | 2026-07-15 | 100% | Completed | 2026-09-30 | 100% | Completed |  | MDW-39236 | MDW-69239 | MDW-69240
66 | - | Lot01 | GEN14 | GEN | Train Crew Office at Thailand Cultural Centre Station | สหชาติ | 0 | 0 | 2026-08-21 | 2025-09-30 | 100% | Completed | 2026-02-27 | 100% | Completed | 0 | 0% | 0% | 2026-05-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-23 | 0% | Late | 2026-09-30 | 0% | Late | 0 |  | 0 | 0
67 | MDW-39240 | Lot01 | GEN14.1 | GEN | Driver Train Simulation Room and Train Crew Office at OR18 - Civil & AR | สหชาติ | 0 | Depot | 2026-08-21 | 2025-09-30 | 100% | Completed | 2026-02-28 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-07-15 | 100% | Completed | 2026-08-07 | 100% | Completed |  | MDW-39240 | MDW-69247 | MDW-69248
68 | MDW-39241 | Lot01 | GEN14.2 | GEN | Driver Train Simulation Room and Train Crew Office at OR18 - Building Services | ประธาน | 0 | 0 | 2026-08-21 | 2025-09-30 | 100% | Completed | 2026-02-28 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-03-12 | 100% | Completed | 2026-08-07 | 100% | Completed |  | MDW-39241 | MDW-69249 | MDW-69250
69 | MDW-39239 | Lot01 | GEN15 | GEN | Access Panel Closeout for Traction Substation Room in Main Workshop | สหชาติ | 0 | 0 | 2026-03-24 | 2026-01-30 | 100% | Completed | 2026-03-01 | 100% | Completed | 0 | 0% | 0% | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-15 | 100% | Completed | 2026-09-30 | 100% | Completed |  | MDW-39239 | MDW-69245 | MDW-69246
70 | MDW-39232 | Lot01 | GEN16 | GEN | Level Crossing at Turnout | กำพล | 0 | 0 | 2026-08-21 | 2026-09-30 | 100% | Completed | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-11-15 | 46% | On Schedule | 0 | 0% | 0% |  | 0% | On Schedule |  | 0% | On Schedule | 0 | MDW-39232 | MDW-69232 | MDW-69233
71 | MDW-39232 | Lot01 | GEN17 | GEN | Track Slab Crossing | ชฎิล/กำพล | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39232 | MDW-69232 | MDW-69233
72 | MDW-39243 | Lot01 | GEN18 | GEN | Eye Adaptation Lighting (Lighting at Tunnel to Expose) | ประธาน | 0 | 0 | 2026-11-19 | 2025-09-30 | 100% | Completed | 2025-10-30 | 100% | Completed | 0 | 0% | 0% | 2026-04-13 | 100% | Completed | 0 | 0% | 0% | 2026-02-18 | 100% | Completed | 2026-10-07 | 0% | Late | Progress DPA1 : 100% Progress DPA2 : 100% Progress Cut&Cover OR22 : 95% | MDW-39243 | MDW-69253 | MDW-69254
73 | - | Lot01 | GEN19 | GEN | Train Simulation Room and AFC Training Room | - | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
74 | MDW-39244 | Lot01 | GEN19.1 | GEN | Modification AFC Training Center at OR19 - Civil & AR | สหชาติ | 0 | 0 | 2026-11-30 | 2026-09-30 | 100% | Completed | 2026-10-31 | 58% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 0 | 0% | 0% | 2026-10-31 | 0% | On Schedule | 2026-12-07 | 0% | On Schedule | Progress Cut&Cover OR22 : 95% | MDW-39244 | MDW-69255 | MDW-69256
75 | MDW-39245 | Lot01 | GEN19.2 | GEN | Modification AFC Training Center at OR19 - Building Services | ประธาน | บัณฑิต | 0 | 2026-11-30 | 2026-09-30 | 100% | Completed | 2026-10-31 | 100% | Completed | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 0 | 0% | 0% | 2026-10-31 | 0% | On Schedule | 2026-12-07 | 0% | On Schedule | 0 | MDW-39245 | MDW-69257 | MDW-69258
76 | - | Lot01 | GEN20 | GEN | Dormitory Cable Containments (if any) | - | 0 | 0 | - | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
77 |  | Lot01 | GEN21 | GEN | Project Information Management System (PIMS) | บัณฑิต | 0 | 0 | 2024-09-30 | 2024-08-10 | 100% | Completed | 2024-08-15 | 100% | Completed | 0 | 0% | 0% | 2024-09-04 | 100% | Completed | 2024-09-14 | 100% | Completed | 2026-09-23 | 0% | Late | 2026-09-30 | 0% | Late | งานจบแล้ว
78 | MDW-39237 | Lot01 | GEN22 | GEN | Central BEMS for the MRT Orange Line System | บัณฑิต | 0 | 0 | 2026-08-21 | 2026-04-30 | 0% | Late | 2026-06-30 | 0% | Late | 0 | 0% | 0% | 2026-08-15 | 0% | Late | 2026-08-31 | 0% | Late | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | PPR Oct-26 กำลังเปรียบเทียบ Spec | MDW-39237 | MDW-69241 | MDW-69242
79 |  | Lot01 | GEN23 | GEN | Asset Information | บัณฑิต | 0 | 0 | 2026-11-19 | 0 | 0% | 0% | 2026-08-30 | 100% | Completed | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0
80 | MDW-39282 | Lot01 | PSD1 | PSD | Holes for PSD Cable Wiring | กำพล | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39282 | MDW-69315 | MDW-69316
81 | MDW-39004 | Lot01 | PSD2 | PSD | Rubber Gap Fillers on Platform Edge | กำพล | 0 | 0 | 2026-08-21 | 2025-07-30 | 100% | Completed | 2026-01-31 | 100% | Completed | 0 | 0% | 0% | 2026-08-31 | 40% | Late | 0 | 0% | 0% | 2026-09-30 | 25% | Late | 2026-10-07 | 0% | Late | แผนเข้าติดตั้ง 1/10/26-30/11/26 | MDW-39004 | MDW-69007 | MDW-69008
82 | MDW-39280 | Lot01 | PSD3 | PSD | Platform Finishing | กำพล | 0 | 0 | 2026-08-21 | 2025-07-30 | 100% | Completed | 2025-09-16 | 100% | Completed | 0 | 0% | 0% | 2026-01-07 | 100% | Completed | 0 | 0% | 0% | 2026-08-17 | 100% | Completed | 2026-09-30 | 0% | Late | 0 | MDW-39280 | MDW-69311 | MDW-69312
83 | MDW-39281 | Lot01 | PSD4 | PSD | Cladding Barrier between EWD and Station Structure | กำพล | 0 | 0 | 2026-08-21 | 2026-02-28 | 100% | Completed | 2026-03-15 | 100% | Completed | 0 | 0% | 0% | 2026-08-15 | 100% | Completed | 0 | 0% | 0% | 2026-09-23 | 0% | Late | 2026-09-30 | 0% | Late | 0 | MDW-39281 | MDW-69313 | MDW-69314
84 | - | Lot01 | AFC1 | AFC | Park and Ride System | บัณฑิต/สหชาติ | 0 | 0 | 2026-10-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
85 | MDW-39276 | Lot01 | AFC2 | AFC | Ticket Issuing Machine (TIM) Wall Opening and Closing | สหชาติ | 0 | 0 | 2026-09-20 | 2026-01-30 | 100% | Completed | 2026-03-15 | 50% | Late | 0 | 0% | 0% | 2026-07-13 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 50% | Late | 2026-10-07 | 0% | Late | มีแก้ไขตำแหน่ง OR14,17,18,23 | MDW-39276 | MDW-69303 | MDW-69304
86 | MDW-39279 | Lot01 | AFC3 | AFC | Balustrade Modification Along AFC Gate Line | สหชาติ | 0 | 0 | 2026-09-20 | 2026-06-30 | 10% | Late | 2026-08-15 | 50% | Late | 0 | 0% | 0% | 2026-11-06 | 0% | On Schedule | 0 | 0% | 0% | 2026-10-07 | 0% | Late | 2026-11-13 | 0% | On Schedule | จัดเตรียมแบบ ออกPPR Oct-26 | MDW-39279 | MDW-69309 | MDW-69310
87 | MDW-39278 | Lot01 | AFC4 | AFC | Underfloor Embedded Duct Modification for AFC Gates Line | สหชาติ | 0 | Depot | 2026-09-20 | 2026-01-30 | 100% | Completed | 2026-04-02 | 67% | Late | 0 | 0% | 0% | 2026-10-09 | 81% | Late | 0 | 0% | 0% | 2026-09-30 | 0% | Late | 2026-10-16 | 0% | Late | 0 | MDW-39278 | MDW-69307 | MDW-69308
88 | MDW-39002 | Lot01 | SIG1 | SIG | Test Track Shelters and Test Track Building | สหชาติ | 0 | 0 | 2026-06-22 | 2025-11-22 | 100% | Completed | 2026-01-18 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-04-15 | 100% | Completed | 0 | 0% | 0% | 2026-05-15 | 100% | Completed | 2026-06-08 | 100% | Completed |  | MDW-39002 | MDW-69003 | MDW-69004
89 | MDW-39293 | Lot01 | SIG2 | SIG | Rearrangement of track crossing walkway at stabling yard to consistent with the layout of 4-car train parking | กำพล | 0 | Depot | 2026-06-22 | 2025-11-30 | 100% | Completed | 2025-12-30 | 100% | Completed | 0 | 0% | 0% | 2026-03-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 50% | Late | 2026-10-07 | 0% | Late | 0 | MDW-39293 | MDW-69337 | MDW-69338
90 | MDW-39288 | Lot01 | SIG3 | SIG | Point Machine Foundation Construction | กำพล | 0 | 0 | 2026-08-21 | 2025-11-21 | 100% | Completed | 2025-12-30 | 100% | Completed | 0 | 0% | 0% | 2026-03-19 | 100% | Completed | 0 | 0% | 0% | 2026-09-23 | 25% | Late | 2026-09-30 | 0% | Late | 0 | MDW-39288 | MDW-69327 | MDW-69328
91 | MDW-39001 | Lot01 | SIG4 | SIG | Modification of Depot Track Route Line to Stabling Yard | สู่โชค | 0 | Depot | 2026-06-22 | 2025-10-30 | 100% | Completed | 2025-11-29 | 100% | Completed | 0 | 0% | 0% | 2026-05-28 | 95% | Late | 0 | 0% | 0% | 2026-09-30 | 50% | Late | 2026-10-07 | 0% | Late | คงเหลือเก็บงาน Progress by ช.ธนัท | MDW-39001 | MDW-69001 | MDW-69002
92 | MDW-39287 | Lot01 | SIG5 | SIG | Strobe Light at Buffer Stops | ประธาน | 0 | Depot | 2026-08-21 | 2026-05-30 | 100% | Completed | 2026-06-29 | 100% | Completed | 0 | 0% | 0% | 2026-08-28 | 100% | Completed | 0 | 0% | 0% | 2026-03-14 | 100% | Completed | 2026-06-30 | 0% | Late | 0 | MDW-39287 | MDW-69323 | MDW-69324
93 | DWE-39016 | Lot01 | DWE1 | DWE | Diesel Fuel Storage Tank for Maintenance Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-01-16 | 100% | Completed | 2026-06-30 | 100% | Completed | 2026-07-31 | 100% | Completed | 2026-08-09 | 0% | Late | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39016 | DWE-69016 | DWE-69116
94 | DWE-39011 | Lot01 | DWE2 | DWE | Movable Height Maintenance Platform Vehicle (Boom Lift) | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-08-06 | 100% | Completed | 2025-12-31 | 100% | Completed | 2026-06-30 | 100% | Completed | 2026-07-09 | 0% | Late | 2026-05-22 | 100% | Completed | 2026-09-30 | 0% | Late | Test 9-15/11/26 | DWE-39011 | DWE-69011 | DWE-69111
95 | DWE-39012 | Lot01 | DWE3 | DWE | Fork Lift Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-03-31 | 100% | Completed | 2026-06-01 | 100% | Completed | 2026-06-30 | 100% | Completed | 2026-07-30 | 0% | Late | 2026-09-30 | 0% | Late | 2026-10-07 | 0% | Late | Test 9-15/11/26 | DWE-39012 | DWE-69012 | DWE-69112
96 | DWE-39015 | Lot01 | DWE4 | DWE | Compressed Air System and Portable Air Compressor for Depot | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-01-10 | 100% | Completed | 2026-02-15 | 100% | Completed | 2026-09-19 | 0% | Late | 2026-09-29 | 0% | Late | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39015 | DWE-69015 | DWE-69115
97 | DWE-39017 | Lot01 | DWE5 | DWE | Pallet Storage Shelves in Hazardous Storage | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-12-16 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-05-31 | 100% | Completed | 2026-06-05 | 0% | Late | 2026-07-17 | 100% | Completed | 2026-09-30 | 0% | Late | Test 26-30/10/26 | DWE-39017 | DWE-69017 | DWE-69117
98 | DWE-39017 | Lot01 | DWE6 | DWE | Pallet Storage in Main Storage Room | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-12-16 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-05-31 | 100% | Completed | 2026-06-05 | 0% | Late | 2026-07-17 | 100% | Completed | 2026-09-30 | 0% | Late | Test 26-30/10/26 | DWE-39017 | DWE-69017 | DWE-69117
99 | DWE-39017 | Lot01 | DWE7 | DWE | Two-Tier Shelf | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-12-16 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-05-31 | 100% | Completed | 2026-06-05 | 0% | Late | 2026-07-17 | 100% | Completed | 2026-09-30 | 0% | Late | Test 26-30/10/26 | DWE-39017 | DWE-69017 | DWE-69117
100 | DWE-39017 | Lot01 | DWE8 | DWE | Tool Storage | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-12-16 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-05-31 | 100% | Completed | 2026-06-05 | 0% | Late | 2026-07-17 | 100% | Completed | 2026-09-30 | 0% | Late | Test 26-30/10/26 | DWE-39017 | DWE-69017 | DWE-69117
101 | DWE-39018 | Lot01 | DWE9 | DWE | Repair Equipment | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-07-31 | 50% | Late | 2026-10-30 | 70% | On Schedule | 2027-03-03 | 0% | On Schedule | 2027-04-02 | 0% | On Schedule | 2027-03-03 | 0% | On Schedule | 2027-04-09 | 0% | On Schedule | คงเหลือจัดส่งอุปกรณ์ | DWE-39018 | DWE-69018 | DWE-69118
102 | DWE-39020 | Lot01 | DWE10 | DWE | Oil & Grease Disposal | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-01-16 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-03-31 | 100% | Completed | 2026-07-05 | 0% | Late | 2026-09-30 | 0% | Late | 2026-10-07 | 0% | Late | Test 9-15/11/26 | DWE-39020 | DWE-69020 | DWE-69120
103 | DWE-39020 | Lot01 | DWE11 | DWE | Grease Dispensers | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-01-16 | 100% | Completed | 2026-04-28 | 100% | Completed | 2026-05-25 | 100% | Completed | 2026-07-05 | 0% | Late | 2026-09-30 | 0% | Late | 2026-10-07 | 0% | Late | Test 9-15/11/26 | DWE-39020 | DWE-69020 | DWE-69120
104 | DWE-39020 | Lot01 | DWE12 | DWE | Waste Disposal | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-01-16 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-03-31 | 100% | Completed | 2026-07-05 | 0% | Late | 2026-09-30 | 0% | Late | 2026-10-07 | 0% | Late | Test 9-15/11/26 | DWE-39020 | DWE-69020 | DWE-69120
105 | MDW-39305 | Lot01 | DWE13 | DWE | Safety Provision for Maintenance Pits | สหชาติ | 0 | Depot | 2026-09-20 | 2025-11-30 | 100% | Completed | 2026-04-29 | 100% | Completed | 0 | 0% | 0% | 2026-07-29 | 70% | Late | 0 | 0% | 0% | 2026-09-30 | 50% | Late | 2026-10-07 | 0% | Late | งาน Handrail ที่ Pits Wheel Reprofling Plant ติดตั้งแล้วเหลืองานเก็บสี | MDW-39305 | MDW-69361 | MDW-69362
106 | DWE-39xxx | Lot01 | DWE14 | DWE | Pit Drainage System in Main Workshop | สมศักดิ์ | 0 | Depot | 2026-09-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39xxx | MDW-69361 | MDW-69362
107 | DWE-39023 | Lot01 | DWE15 | DWE | Provision of Civil Works and Building Services to support Train Washing Equipment | สหชาติ | 0 | Depot | 2026-08-01 | 2025-11-30 | 100% | Completed | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-05-31 | 100% | Completed | 0 | 0% | 0% | 2026-08-31 | 100% | Completed | 2026-09-30 | 0% | Late | 0 | DWE-39023 | DWE-69023 | DWE-69123
108 | DWE-39013 | Lot01 | DWE16 | DWE | Overhead Traveling Crane | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-04-30 | 100% | Completed | 2026-03-20 | 100% | Completed | 0 | 0% | 0% | 2026-04-04 | 100% | Completed | 2026-05-26 | 100% | Completed | 2026-09-30 | 0% | Late | 0 | DWE-39013 | DWE-69013 | DWE-69113-513
109 | DWE-39009 | Lot01 | DWE17 | DWE | Vehicle Inspection and Servicing Facilities | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-12-18 | 100% | Completed | 2026-09-07 | 100% | Completed | 0 | 0% | 0% | 2026-10-01 | 0% | Late | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39009 | DWE-69009 | DWE-69109
110 | DWE-39014 | Lot01 | DWE18 | DWE | Permanent Way Maintenance Facility | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-04-30 | 100% | Completed | 2027-02-28 | 100% | Completed | 2027-01-15 | 70% | On Schedule | 0 | 0% | 0% | 2027-03-30 | 0% | On Schedule | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39014 | DWE-69014 | DWE-69114
111 | - | Lot01 | DWE19 | DWE | Permanent Way Vehicles | สมศักดิ์ | 0 | Depot | 2026-09-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
112 | DWE-39001 | Lot01 | DWE19.1 | DWE | Shunting Locomotive | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-12-18 | 100% | Completed | 2026-12-15 | 50% | On Schedule | 0 | 0% | 0% | 2026-12-30 | 0% | On Schedule | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39001 | DWE-69001 | DWE-69101
113 | DWE-39002 | Lot01 | DWE19.2 | DWE | Tunnel Inspection and Cleaning Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 0% | Late | 2025-12-18 | 100% | Completed | 2026-12-30 | 40% | On Schedule | 0 | 0% | 0% | 2026-10-11 | 0% | Late | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39002 | DWE-69002 | DWE-69102
114 | DWE-39003 | Lot01 | DWE19.3 | DWE | Hi/Rail Maintenance Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-12-18 | 100% | Completed | 2026-11-30 | 55% | On Schedule | 0 | 0% | 0% | 2026-12-16 | 0% | On Schedule | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39003 | DWE-69003 | DWE-69103
115 | DWE-39004 | Lot01 | DWE19.4 | DWE | Flat wagon | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-12-18 | 100% | Completed | 2026-10-30 | 68% | On Schedule | 0 | 0% | 0% | 2026-08-11 | 0% | Late | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39004 | DWE-69004 | DWE-69104
116 | DWE-39005 | Lot01 | DWE19.5 | DWE | Re-railing Equipment | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-11-10 | 100% | Completed | 2026-07-15 | 90% | Late | 0 | 0% | 0% | 2026-08-31 | 0% | Late | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39005 | DWE-69005 | DWE-69105
117 | DWE-39006 | Lot01 | DWE19.6 | DWE | Self-Propelled Rail Based Inspection Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-12-18 | 100% | Completed | 2026-11-03 | 55% | On Schedule | 0 | 0% | 0% | 2026-12-16 | 0% | On Schedule | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39006 | DWE-69006 | DWE-69106
118 | DWE-39007 | Lot01 | DWE19.7 | DWE | Rail Head Grinding Machine Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 0% | Late | 2025-12-18 | 100% | Completed | 2027-07-31 | 0% | On Schedule | 0 | 0% | 0% | 2027-08-31 | 0% | On Schedule | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39007 | DWE-69007 | DWE-69107
119 | DWE-39008 | Lot01 | DWE19.8 | DWE | Multi Measuring Rail Vehicle | สมศักดิ์ | 0 | 0 | 2026-09-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39008 | DWE-69008 | DWE-69108
120 | DWE-39010 | Lot01 | DWE19.9 | DWE | High Work Inspection Vehicle | สมศักดิ์ | 0 | 0 | 2026-09-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39010
121 | - | Lot01 | DWE20 | DWE | Building Maintenance Vehicle | - | 0 | 0 | 2026-09-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
122 | EPS-39001 | Lot01 | PSY1 | PSY | Diesel Fuel Storage Tanks for Power Generators | สมศักดิ์ | 0 | 0 | 2026-03-24 | 2026-01-16 | 100% | Completed | 2026-03-31 | 100% | Completed | 2026-03-31 | 100% | Completed | 2026-06-30 | 75% | Late | 2026-07-10 | 0% | Late | 2026-10-23 | 0% | Late | 2026-10-30 | 0% | On Schedule | คงเหลืองานเดินท่อและ Pump น้ำมัน | EPS-39001 | EPS-69001 | EPS-69002
123 | PSY-39001-9 | Lot01 | PSY2 | PSY | GIS and BSS Building and Other Facilities | สหชาติ | 0 | 0 | 2026-03-24 | 2024-08-29 | 100% | Completed | 2024-09-28 | 69% | Late | 0 | 0% | 0% | 2025-12-04 | 100% | Completed | 0 | 0% | 0% | 2026-09-23 | 100% | Completed | 2026-09-30 | 100% | Completed |  | PSY-39001 | PSY-69001 | PSY-69002
124 | PSY-39011 | Lot01 | PSY3 | PSY | Steel Grating Raised Floor for EE Panel | สหชาติ | 0 | 0 | 2026-03-24 | 2024-09-30 | 100% | Completed | 2024-10-30 | 75% | Late | 0 | 0% | 0% | 2025-07-14 | 100% | Completed | 0 | 0% | 0% | 2026-06-14 | 100% | Completed | 2026-09-30 | 0% | Late | 0 | PSY-39011 | PSY-69015 | PSY-69016
125 | - | Lot01 | PSY4 | PSY | Trapping Box between PSY Service Sub Station (SSS) and Low Volt (LV) System | - | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
126 | SCA-39200 | Lot01 | SCA1 | SCA | Modification of BEMS to receive PSD Signal on East Section | ธารทิพย์ | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | SCA-39200 | SCA-69200 | SCA-69201
127 | - | Lot01 | SCA2 | SCA | Modification of Escalator Interface Point with CCTV and SCADA, East Section | - | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
128 | - | Lot01 | SCA3 | SCA | Magnetic of Fire Alarm System Interface Point with CCTV and SCADA | - | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
129 | SCA-39203 | Lot01 | SCA4 | SCA | Add/Modify Civil Scada Hardwire for all Station | ประธาน/ธารทิพย์ | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | SCA-39203 | SCA-69206 | SCA-69207
130 | COM-39200 | Lot01 | COM1 | COM | Magnetic Door Lock | มนตรี | 0 | 0 | 2026-08-21 | 2025-06-30 | 100% | Completed | 2026-05-15 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 27.25% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | กำลังดำเนินการ Progress by CIP | COM-39200 | COM-69200 | COM-69201
131 | MDW-39283 | Lot01 | COM2 | COM | Intercom System in Cash Handling Room (if require) | บัณฑิต | 0 | 0 | 2026-12-19 | 2025-09-30 | 100% | Completed | 2026-06-30 | 50% | Late | 0 | 0% | 0% | 2026-10-31 | 0% | On Schedule | 2026-12-30 | 0% | On Schedule | 2026-09-30 | 0% | Late | 2026-11-07 | 0% | On Schedule | รอพื้นที่เข้าติดตั้ง | MDW-39283 | MDW-69317 | MDW-69318
132 | COM-39001 | Lot01 | COM3 | COM | Walk-Through Metal Detector System (WTMD), 1 per entrance | มนตรี | 0 | 0 | 2026-11-19 | 2025-08-31 | 0% | Late | 2026-06-30 | 0% | Late | 0 | 0% | 0% | 2027-02-28 | 0% | On Schedule | 0 | 0% | 0% | 2027-01-29 | 0% | On Schedule | 2027-03-07 | 0% | On Schedule | รอออก PPR อยู่ระหว่างการตรวจสอบสินค้า | COM-39001 | COM-69001 | COM-69002
133 | MDW-39284 | Lot01 | COM4 | COM | Traveling Cable in all Lifts | มนตรี | 0 | 0 | - | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39284 | MDW-69319 | MDW-69320
134 | MDW-39304 | Lot01 | COM5 | COM | MEA Radio | ประธาน | 0 | 0 | 2026-09-20 | 2026-01-30 | 100% | Completed | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-06-30 | 95% | Late | 2026-09-30 | 0% | Late | 2026-09-23 | 0% | Late | 2026-10-07 | 0% | Late | รอเฟอร์นิเจอร์ Fore cast Dec-26 | MDW-39304 | COM-69202 | COM-69203
135 | COM-39004 | Lot01 | COM6 | COM | Main Cable Containment for M&E Dedicated communication link to MRTA Head Quarter | มนตรี | 0 | 0 | 2026-09-20 | 2026-01-31 | 100% | Completed | 2026-02-28 | 100% | Completed | 0 | 0% | 0% | 2026-08-31 | 75% | Late | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | COM-39004 | COM-69005 | COM-69006
136 | AFC-39001 | Lot01 | COM7 | COM | Mini Paging in Ticket Office | บัณฑิต | 0 | 0 | 2026-12-19 | 2025-09-10 | 100% | Completed | 2026-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 0% | Late | 2026-11-30 | 0% | On Schedule | 2026-10-31 | 0% | On Schedule | 2026-12-07 | 0% | On Schedule | ของมาแล้ว รอพื้นที่เข้าติดตั้ง | AFC-39002 | AFC-69003 | AFC-69004
137 | MDW-39285 | Lot01 | COM8 | COM | Provision of Cable Containment between OCC ORL and OCC BL | มนตรี | 0 | 0 | 2026-07-22 | 0 | 0% | 0% | 0% | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39285
138 | COM-39005 | Lot01 | COM9 | COM | Power Distribution for M&E Systems at MRTA Head Quarter | มนตรี | 0 | 0 | 2026-09-20 | 2026-03-31 | 100% | Completed | 2026-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | COM-39005 | COM-69007 | COM-69008
139 | COM-39205 | Lot01 | COM10 | COM | Underground Cable Containment at Public Areas (if require) | มนตรี | 0 | 0 | 2026-08-21 | 2026-04-30 | 100% | Completed | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 100% | Completed | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39205 | MDW-69200 | MDW-69205
140 | - | Lot01 | COM11 | COM | Intercom at Ticket Issuing Machine | บัณฑิต | 0 | Depot | - | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
141 | RST-39004,8 | Lot01 | RST1 | RST | Driver Training Simulator | ธัญวิทย์ | 0 | Depot | 2026-09-20 | 2025-05-30 | 100% | Completed | 2025-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 81% | On Schedule | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | RST-39004,8
142 | MDW-39500 | Lot02 | MO-CK1.1 | MO-CK | Store Modification Works at Main Workshop - Civil&AR | สหชาติ | 0 | Depot | 2026-06-03 | 2026-02-27 | 100% | Completed | 2026-03-30 | 100% | Completed | 0 | 0% | 0% | 2026-05-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 50% | Late | 2026-10-07 | 100% | Completed |  | MDW-39500 | MDW-69500 | MDW-69501
143 | MDW-39501 | Lot02 | MO-CK1.2 | MO-CK | Store Modification Works at Main Workshop - Building Services | ประธาน | 0 | Depot | 2026-06-04 | 2026-02-12 | 100% | Completed | 2026-03-30 | 100% | Completed | 0 | 0% | 0% | 2026-05-28 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 0% | Late | 2026-10-07 | 100% | Completed |  | MDW-39501 | MDW-69502 | MDW-69503
144 | MDW-39503 | Lot02 | MO-CK2 | MO-CK | New MMC at Admin Building - Civil&AR | สหชาติ | 0 | Depot | 2026-08-03 | 2026-04-14 | 100% | Completed | 2026-05-15 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 50% | Late | 2026-09-30 | 0% | Late | กำลังทำเอกสาร Test Report | MDW-39503 | MDW-69506 | MDW-69507
145 | MDW-39504 | Lot02 | MO-CK3 | MO-CK | Move or link Workstation and control panel to MMC room at admin C 2nd floor | ประธาน | 0 | Depot | 2026-08-02 | 2026-02-28 | 100% | Completed | 2026-04-15 | 100% | Completed | 0 | 0% | 0% | 2026-08-31 | 90% | Late | 0 | 0% | 0% | 2026-09-30 | 0% | Late | 2026-09-30 | 0% | Late | Fore cast Oct-26 | MDW-39504 | MDW-69508 | MDW-69509
146 | MDW-39543 | Lot02 | MO-CK4 | MO-CK | Bird & Rain Protection for Open space Admin C | สหชาติ | 0 | Depot | 2026-08-01 | 2026-04-29 | 100% | Completed | 2026-05-30 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 50% | Late | 2026-09-30 | 0% | Late | 0 | MDW-39543 | MDW-69586 | MDW-69587
147 | MDW-39547 | Lot02 | MO-CK5 | MO-CK | Relocate door in front of toilet and build partition wall to conceal the view in side of toilet | สหชาติ | 0 | Depot | 2026-08-02 | 2026-05-14 | 100% | Completed | 2026-06-14 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-15 | 100% | Completed | 2026-10-07 | 0% | Late | 0 | MDW-39547 | MDW-69594 | MDW-69595
148 | MDW-39547 | Lot02 | MO-CK6 | MO-CK | Modify Lockset the emergency door to be used for passage between the 2nd and 3rd floors inside the building. | สหชาติ | 0 | Depot | 2026-08-03 | 2026-04-29 | 100% | Completed | 2026-06-14 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-01 | 100% | Completed | 2026-09-30 | 0% | Late | 0 | MDW-39547 | MDW-69594 | MDW-69595
149 | MDW-39556 | Lot02 | MO-CK7 | MO-CK | Addition small power for lounge and pantry room at 2nd floor and Hall and observation room at 3nd floor | ประธาน | 0 | Depot | 2026-08-04 | 2026-05-14 | 100% | Completed | 2026-06-14 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-05-05 | 100% | Completed | 2026-09-30 | 100% | Completed |  | MDW-39556 | MDW-69612 | MDW-69613
150 | MDW-39548 | Lot02 | MO-CK8 | MO-CK | Air Condition for using store room to be pantry room. 2nd floor | ประธาน | 0 | Depot | 2026-08-05 | 2026-04-29 | 100% | Completed | 2026-06-14 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-03-24 | 100% | Completed | 2026-09-30 | 100% | Completed |  | MDW-39548 | MDW-69596 | MDW-69597
151 | MDW-39552 | Lot02 | MO-CK9 | MO-CK | Walk Way Hand rail high 90 cm 1 side (144 m. x 7 route) | สหชาติ | 0 | Depot | 2026-10-01 | 2026-05-30 | 100% | Completed | 2026-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 98.77% | Late | 0 | 0% | 0% | 2026-09-30 | 50% | Late | 2026-10-07 | 0% | Late | คงเหลืองานคอนกรีตทางเดินข้ามราง | MDW-39552 | MDW-69604 | MDW-69605
152 | MDW-39544 | Lot02 | MO-CK10 | MO-CK | Barbed wire fence Viaduct CE CW | บัณฑิต/สหชาติ | พี่ต่อ | Depot | 2027-01-01 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39544 | MDW-69588 | MDW-69589
153 | MDW-39545 | Lot02 | MO-CK11 | MO-CK | Chain Link at Cut & Cover 600m. | สหชาติ | พรพรหม | Depot | 2026-06-01 | 2026-02-27 | 100% | Completed | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-08-01 | 100% | Completed | 2026-09-30 | 0% | Late | มีงานเพิ่มอีก 18 แผง | MDW-39545 | MDW-69590 | MDW-69591
154 | MDW-39546 | Lot02 | MO-CK12 | MO-CK | Chain Link under slab high 1.70 m | สหชาติ | 0 | 0 | 2027-01-01 | 2026-06-30 | 100% | Completed | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 67.27% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 50% | On Schedule | 2027-01-07 | 0% | On Schedule | เริ่มติดตั้ง Chainlink แล้ว | MDW-39546 | MDW-69592 | MDW-69593
155 | MDW-39550 | Lot02 | MO-CK13.1 | MO-CK | Satellite Store at OR21 - Civil & AR | สหชาติ | 0 | 0 | 2027-01-02 | 2026-08-30 | 100% | Completed | 2026-10-15 | 0% | Late | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 100% | Completed | 2027-01-07 | 0% | On Schedule | 0 | MDW-39550 | MDW-69600 | MDW-695601
156 | MDW-39549 | Lot02 | MO-CK13.2 | MO-CK | Maintenance Room and Satellite Store at Stations - Building Services | ประธาน | 0 | 0 | 2027-01-03 | 2026-08-30 | 100% | Completed | 2026-10-15 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 80% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 100% | Completed | 2027-01-07 | 0% | On Schedule | 0 | MDW-39549 | MDW-69598 | MDW-69599
157 | MDW-39551 | Lot02 | MO-CK14 | MO-CK | Modify Cleaner room at OR29 to be Train crew Standby office with facility system | ประธาน | 0 | Depot | 2026-07-01 | 2026-03-14 | 100% | Completed | 2026-04-29 | 100% | Completed | 0 | 0% | 0% | 2026-06-30 | 95% | Late | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 2026-10-07 | 0% | Late | 0 | MDW-39551 | MDW-69602 | MDW-69603
158 | MDW-39295 | Lot02 | MO-CK15.1 | MO-CK | Epoxy Floor Installation and Curb Installation at the Entrance - Civil & AR | สหชาติ | 0 | Depot | 2026-05-01 | 2026-01-27 | 100% | Completed | 2026-02-27 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 50% | Late | 2026-10-07 | 100% | Completed |  | MDW-39295 | MDW-69341 | MDW-69342
159 | MDW-39296 | Lot02 | MO-CK15.2 | MO-CK | Change Electrical Equipment to be Explosion-proof type - Building Services | ประธาน | 0 | Depot | 2026-05-01 | 2025-12-13 | 100% | Completed | 2026-01-28 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 90% | Late | 0 | 0% | 0% | 2026-09-30 | 0% | Late | 2026-10-07 | 0% | Late | Fore cast Nov-26 | MDW-39296 | MDW-69343 | MDW-69344
160 | DWE-39024 | Lot02 | MO-CK16 | MO-CK | Dangerous waste Storage 30 x 5 m. =10 room | สหชาติ | 0 | Depot | 2026-05-01 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-07-15 | 100% | Completed | 2026-06-08 | 100% | Completed |  | DWE-39024 | DWE-69024 | DWE-69124
161 | 0 | Lot02 | MO-CK17 | MO-CK | Safety Sign all Depot Area building | สหชาติ | 0 | Depot | 2026-05-01 | 2025-11-28 | 100% | Completed | 2026-06-15 | 100% | Completed | 2026-09-20 | 27% | Late | 2026-10-15 | 0% | Late | 0 | 0% | 0% | 0 | 0% | Late | 0 | 0% | Late | GRS |  | 0 | 0
162 | 0 | Lot02 | MO-CK18 | MO-CK | Emergency escape route map | สหชาติ | 0 | Depot | 2027-01-01 | 2026-09-30 | 0% | Late | 2026-10-30 | 50% | On Schedule | 2026-12-31 | 0% | On Schedule | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | GRS |  | 0 | 0
163 | 0 | Lot02 | MO-CK19 | MO-CK | Traffic Line Marking (Thermoplastic Paint) | สหชาติ | 0 | Depot | 2026-05-01 | 2026-04-30 | 100% | Completed | 2026-06-15 | 100% | Completed | 2026-10-15 | 100% | Completed | 2026-10-15 | 25% | Late | 0 | 0% | 0% | 0 | 0% | Late | 0 | 0% | Late | GRS |  | 0 | 0
164 | 0 | Lot02 | MO-CK20 | MO-CK | Emergency Car Parking location Painting in front of MWS | สหชาติ | 0 | Depot | 2026-05-01 | 2026-04-30 | 100% | Completed | 2026-06-15 | 100% | Completed | 2026-10-15 | 0% | Late | 2026-10-15 | 0% | Late | 0 | 0% | 0% | 0 | 0% | Late | 0 | 0% | Late | GRS |  | 0 | 0
165 | GRS-39022 | Lot02 | MO-CK21 | MO-CK | Safety Line painting in MWS, Stabling Area, P-way, Track | สหชาติ | 0 | Depot | 2027-01-01 | 2026-06-01 | 100% | Completed | 2026-08-01 | 100% | Completed | 2026-10-15 | 100% | Completed | 2026-12-31 | 81% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | GRS | GRS-39022 | GRS-69001 | GRS-69022
166 | 0 | Lot02 | MO-CK22 | MO-CK | Fire escape stairs level signs in the Depot, VS and IVS areas | สหชาติ | 0 | Depot | 2027-01-01 | 2026-09-30 | 50% | Late | 2026-10-31 | 0% | On Schedule | 2026-10-20 | 0% | Late | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | GRS |  | 0 | 0
167 | DWE-39026 | Lot02 | MO-CK23 | MO-CK | General waste Storage 22 x 5 m | สหชาติ | 0 | Depot | 2026-05-01 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-07-15 | 100% | Completed | 2026-06-08 | 100% | Completed |  | DWE-39026 | DWE-69026 | DWE-69126
168 | 0 | Lot02 | MO-CK24 | MO-CK | Modify Traffic paint and traffic sign | สหชาติ | 0 | 0 | 2026-05-01 | 2026-04-30 | 100% | Completed | 2026-06-15 | 100% | Completed | 2026-10-15 | 64% | Late | 2026-10-15 | 13% | Late | 0 | 0% | 0% | 0 | 0% | Late | 0 | 0% | Late | GRS |  | 0 | 0
169 | 0 | Lot02 | MO-CK25 | MO-CK | Station Area sign 28 stations | สหชาติ | 0 | 0 | 2026-05-01 | 2026-06-15 | 80% | Late | 2026-06-30 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-12-20 | 0% | On Schedule | 0 | 0% | 0% | 0 | 0% | Late | 2026-10-07 | 0% | Late | GRS |  | 0 | 0
170 |  | Lot02 | MO-CK26 | MO-CK | Safety and warning signage for lift and escalator at all station | สหชาติ | 0 | Depot | 2027-01-01 | 2026-06-16 | 100% | Completed | 2026-07-17 | 100% | Completed | 2027-01-31 | 76% | On Schedule | 2027-02-28 | 26% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 0 | 0% | Late | GRS
171 | MDW-39532 | Lot02 | MO-CK27 | MO-CK | Spike fence for Depot slab | สหชาติ | 0 | Depot | 2027-01-01 | 2026-07-31 | 70% | Late | 2026-08-31 | 0% | Late | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | อยู่ระหว่างส่งขออนุมัติแบบรอ Approve | MDW-39532 | MDW-69564 | MDW-69565
172 | 0 | Lot02 | MO-CK28 | MO-CK | Bird net and Flashing at MWS and Skywalk to Stabling yard | สหชาติ | 0 | 0 | 2026-05-01 |  |  | 0% |  |  | 0% | 0 | 0% | 0% |  |  | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
173 | MDW-39541 | Lot02 | MO-CK29 | MO-CK | Fire Alarm Manual Call Point signage at all elevated station | สหชาติ | 0 | 0 | 2027-01-01 |  |  | 0% | 2026-07-30 | 100% | Completed | 0 | 0% | 0% |  |  | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39541 | MDW-69582 | MDW-69583
174 | 0 | Lot02 | MO-CK30 | MO-CK | Lighting for sealed space under stairs and behind lift shaft at underground station | ประธาน | 0 | 0 | 2027-01-01 | 2026-10-14 | 0% | Late | 2026-11-14 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | ไฟส่องสว่างสำหรับพื้นที่ปิดใต้บันไดและด้านหลังช่องลิฟต์ที่สถานีรถไฟใต้ดิน |  | 0 | 0
175 | 0 | Lot02 | MO-CK31 | MO-CK | Modify the access door of sealed space (under-stairs room) with a Sump Pump or ESPS cabinet | สหชาติ | 0 | 0 | 2027-01-01 | 2026-07-16 | 0% | Late | 2026-08-16 | 0% | Late | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 0 |  | 0 | 0
176 | 0 | Lot02 | MO-CK32 | MO-CK | Lighting to the sealed space (under-stairs room) with a Sump Pump or ESPS cabinet | ประธาน | 0 | Depot | 2027-01-01 | 2026-11-03 | 0% | On Schedule | 2026-12-04 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | ซื้อสปอร์ตไลท์+แบต จำนวน 4 ชุด แทนการลากสายไฟ |  | 0 | 0
177 | 0 | Lot02 | MO-CK33 | MO-CK | Additional lighting in areas where the lux level does not meet occupational health standards | ประธาน | 0 | Depot | 2027-01-01 | 2026-09-14 | 100% | Completed | 2026-10-15 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 95% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 0 |  | 0 | 0
178 | 0 | Lot02 | MO-CK34 | MO-CK | Provide and install confined space signage for Station and Depot | สหชาติ | 0 | 0 | 2027-01-01 | 2026-08-15 | 100% | Completed | 2026-09-15 | 100% | Completed | 2027-01-31 | 76% | On Schedule | 2027-02-28 | 26% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 0 | 0% | Late | GRS |  | 0 | 0
179 |  | Lot02 | MO-CK35 | MO-CK | Build room for Train crew main office at OR18 with office area, resting area, meeting room, pantry, toilet and locker room | สหชาติ/บัณฑิต/ประธาน | 0 | Depot | - |  |  | 0% |  |  | 0% | 0 | 0% | 0% |  |  | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0
180 |  | Lot02 | MO-CK36 | MO-CK | Dormitory Cable Containments (if any) | มนตรี | 0 | Depot | - |  |  | 0% |  |  | 0% | 0 | 0% | 0% |  |  | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0
181 | 0 | Lot02 | MO-CK37 | MO-CK | Provide Raise floor and building Service in Training &Simulator (OCC Admin) | สหชาติ | 0 | Depot | - | 0% | 0% | 0% |  |  |  | 0 | 0% | 0% |  |  | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
182 |  | Lot02 | MO-CK38 | MO-CK | Add N2 in Playback and Training Room and Backup Control Room | บุญประเสริฐ | 0 | Depot | - |  |  | 0% |  |  | 0% | 0 | 0% | 0% |  |  | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0
183 | MDW-39505 | Lot02 | MO-BEM1.1 | MO-BEM | Walkway from Main Work Shop to Stabling Area - Civil & AR | สหชาติ | 0 | Depot | 2026-08-02 | 2026-04-28 | 100% | Completed | 2026-05-29 | 92% | Late | 0 | 0% | 0% | 2026-09-30 | 93% | Late | 0 | 0% | 0% | 2026-08-31 | 100% | Completed | 2026-09-30 | 0% | Late | คงเหลืองานมุงหลังคา Metal sheet | MDW-39505 | MDW-69510 | MDW-69511
184 | MDW-39506 | Lot02 | MO-BEM1.2 | MO-BEM | Walkway from Main Work Shop to Stabling Area - Building Services | ประธาน | 0 | Depot | 2026-08-02 | 2026-04-28 | 100% | Completed | 2026-05-29 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 0% | Late | 0 | 0% | 0% | 2026-09-23 | 100% | Completed | 2026-09-30 | 0% | Late | รองานหลังคา CIV Oct-26 | MDW-39506 | MDW-69512 | MDW-69513
185 | MDW-39507 | Lot02 | MO-BEM2 | MO-BEM | High Roof at Main Work Shop Entrance and Store | สหชาติ | 0 | Depot | 2026-08-01 | 2026-02-13 | 100% | Completed | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-01 | 100% | Completed | 2026-09-30 | 0% | Late | กำลังทำเอกสาร Test Report | MDW-39507 | MDW-69514 | MDW-69515
186 | MDW-39509 | Lot02 | MO-BEM3 | MO-BEM | High Roof at the entrance and exit of the under floor wheel lathe | สหชาติ | 0 | Depot | 2026-08-04 | 2026-02-13 | 100% | Completed | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-01 | 100% | Completed | 2026-09-30 | 0% | Late | กำลังทำเอกสาร Test Report | MDW-39509 | MDW-69518
187 | MDW-39511 | Lot02 | MO-BEM4.1 | MO-BEM | Maintenance Office Rooms at Main Workshop - Civil & AR | สหชาติ | 0 | Depot | 2026-07-03 | 2026-04-13 | 100% | Completed | 2026-05-14 | 100% | Completed | 0 | 0% | 0% | 2026-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-05-31 | 100% | Completed | 2026-09-30 | 100% | Completed |  | MDW-39511 | MDW-69522 | MDW-69523
188 | MDW-39512 | Lot02 | MO-BEM4.2 | MO-BEM | Maintenance Office Rooms at Main Workshop - Building Services | ประธาน | 0 | Depot | 2026-07-04 | 2026-04-13 | 100% | Completed | 2026-05-14 | 100% | Completed | 0 | 0% | 0% | 2026-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-23 | 100% | Completed | 2026-09-30 | 0% | Late | รอส่งงานกับ BEM | MDW-39512 | MDW-69524 | MDW-69525
189 | MDW-39513 | Lot02 | MO-BEM5 | MO-BEM | Install Concrete car barrier along the walkway in front of MWS building | สหชาติ | 0 | Depot | 2027-01-01 | 2026-10-14 | 100% | Completed | 2026-11-14 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 100% | Completed | 0 | 0% | 0% | 2026-12-01 | 50% | On Schedule | 2027-01-07 | 100% | Completed |  | MDW-39513 | MDW-69526 | MDW-69527
190 | 0 | Lot02 | MO-BEM6 | MO-BEM | Handrail on top of the water tank on the rooftop of the Admin Building | สหชาติ | 0 | Depot | 2027-01-01 | 2026-10-19 | 100% | Completed | 2026-11-19 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 0 |  | 0 | 0
191 | 0 | Lot02 | MO-BEM7 | MO-BEM | Modify maintenance service door to the roof building to easier access while maintaining safe operational standards | สหชาติ | 0 | Depot | 2027-01-01 | 2026-10-19 | 50% | Late | 2026-11-19 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 0 |  | 0 | 0
192 | MDW-39536 | Lot02 | MO-BEM8 | MO-BEM | Company logo and Central Control Room sign in CCR room. | สหชาติ | 0 | Depot | 2026-05-01 | 2026-01-27 | 100% | Completed | 2026-03-14 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 50% | Late | 2026-10-07 | 0% | Late | 0 | MDW-39536 | MDW-69572 | MDW-69573
193 | MDW-39536 | Lot02 | MO-BEM9 | MO-BEM | Soundproof insulation on the wall and structure and equipment in the CCR room. | สหชาติ | 0 | Depot | 2026-05-01 | 2026-01-12 | 100% | Completed | 2026-02-27 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 50% | Late | 2026-10-07 | 0% | Late | 0 | MDW-39536 | MDW-69572 | MDW-69573
194 | MDW-39526 | Lot02 | MO-BEM10 | MO-BEM | Relocate Fire Hose Cabinet to be outside of the clearance gauge zone 17 set | ประธาน | 0 | Depot | 2026-05-01 | 2026-01-12 | 100% | Completed | 2026-02-27 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-03-18 | 100% | Completed | 2026-09-30 | 100% | Completed |  | MDW-39526 | MDW-69552 | MDW-69553
195 | MDW-39528 | Lot02 | MO-BEM11.1 | MO-BEM | Washing Area in Cleaning Staff Room at Stabling Yard - Civil & AR | สหชาติ | 0 | Depot | 2026-08-03 | 2026-06-03 | 100% | Completed | 2026-07-04 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-01 | 100% | Completed | 2026-09-30 | 50% | Late | 0 | MDW-39528 | MDW-69556 | MDW-69557
196 | MDW-39529 | Lot02 | MO-BEM11.2 | MO-BEM | Washing Area in Cleaning Staff Room at Stabling Yard - Building Services | ประธาน | 0 | Depot | 2026-08-04 | 2026-04-14 | 100% | Completed | 2026-05-30 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-03-31 | 100% | Completed | 2026-07-01 | 100% | Completed |  | MDW-39529 | MDW-69558 | MDW-69559
197 | MDW-39522 | Lot02 | MO-BEM12 | MO-BEM | Rain protection for Water treatment Building | สหชาติ | 0 | Depot | 2026-08-05 | 2026-04-29 | 100% | Completed | 2026-05-30 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-01 | 100% | Completed | 2026-09-30 | 0% | Late | 0 | MDW-39522 | MDW-69544 | MDW-69545
198 | MDW-39522 | Lot02 | MO-BEM13.1 | MO-BEM | Zero Discharge Water treatment in Depot - Civil & AR | สหชาติ | 0 | Depot | 2027-01-01 | 2026-08-15 | 100% | Completed | 2026-09-30 | 75% | Late | 0 | 0% | 0% | 2026-12-31 | 63% | On Schedule | 0 | 0% | 0% | 0 | 0% | 0% | 2027-01-07 | 0% | On Schedule | คงเหลืองานประกอบและติดตั้งโครงหลงัคา | MDW-39522 | MDW-69544 | MDW-69545
199 | MDW-39530 | Lot02 | MO-BEM13.2 | MO-BEM | Zero Discharge Water treatment in Depot - Building Services | ประธาน | 0 | Depot | 2027-01-01 | 2026-08-15 | 100% | Completed | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 50% | On Schedule | 0 | 0% | 0% | 2026-10-30 | 100% | Completed | 2027-01-07 | 0% | On Schedule | 0 | MDW-39530 | MDW-69560 | MDW-69561
200 | MDW-39516 | Lot02 | MO-BEM14.1 | MO-BEM | Modification Works : Walkway Bridge between BL Depot and ORL Depot - Civil & AR | สหชาติ | 0 | Depot | 2026-08-02 | 2026-02-28 | 100% | Completed | 2026-06-15 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 95% | Late | 0 | 0% | 0% | 2026-08-31 | 100% | Completed | 2026-10-07 | 0% | Late | คงเหลืองานติดตั้งสะพานและปรับพื้นที่ถนน | MDW-39516 | MDW-69532 | MDW-69533
201 | MDW-39517 | Lot02 | MO-BEM14.2 | MO-BEM | Modification Works : Walkway Bridge between BL Depot and ORL Depot - Building Services | ประธาน | 0 | Depot | 2026-08-03 | 2026-01-14 | 100% | Completed | 2026-03-01 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 10% | Late | 0 | 0% | 0% | 2026-08-31 | 100% | Completed | 2026-10-07 | 0% | Late | รองานหลังคา CIV Oct-26 | MDW-39517 | MDW-69534 | MDW-69535
202 | MDW-39514 | Lot02 | MO-BEM15.1 | MO-BEM | Roof for cars parking lots area (184 car)t - Civil & AR | สหชาติ | 0 | Depot | 2026-08-03 | 2026-02-28 | 100% | Completed | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-24 | 100% | Completed | 2026-09-30 | 0% | Late | กำลังทำเอกสาร Test Report | MDW-39514 | MDW-69528 | MDW-69529
203 | MDW-39515 | Lot02 | MO-BEM15.2 | MO-BEM | Roof for cars parking lots area (184 car) - Building Services | ประธาน | 0 | Depot | 2026-08-03 | 2026-02-28 | 100% | Completed | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-23 | 0% | Late | 2026-09-30 | 0% | Late | รอส่งงานกับ BEM | MDW-39515 | MDW-69530 | MDW-69531
204 | MDW-39519 | Lot02 | MO-BEM16 | MO-BEM | Walkway roof and High roof across the road from Admin ORL to Depot slap | สหชาติ | 0 | Depot | 2026-08-01 | 2026-06-15 | 100% | Completed | 2026-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-10-31 | 57% | On Schedule | 0 | 0% | 0% | 2026-08-31 | 100% | Completed | 2026-11-07 | 0% | On Schedule | คงเหลืองานโครงเหล็ก หลังคา และ Composite | MDW-39519 | MDW-69538 | MDW-69539
205 | MDW-39519 | Lot02 | MO-BEM17 | MO-BEM | Walkway roof to car park in front of admin ORL(3x5m.) | สหชาติ | 0 | Depot | 2026-08-01 | 2026-06-15 | 100% | Completed | 2026-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-10-31 | 70% | On Schedule | 0 | 0% | 0% | 2026-08-31 | 100% | Completed | 2026-11-07 | 0% | On Schedule | คงเหลืองานโครงหลังคาและมุงหลังคา | MDW-39519 | MDW-69538 | MDW-69539
206 | MDW-39519 | Lot02 | MO-BEM18 | MO-BEM | Walkway roof over the footpath near depot slab (1.50 m. x 290 m.) and stair up to depot slap. | สหชาติ | 0 | Depot | 2026-08-01 | 2026-06-15 | 100% | Completed | 2026-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-10-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-08-31 | 100% | Completed | 2026-11-07 | 0% | On Schedule | รอ BEM สรุปว่ายกเลิกหรือทำ | MDW-39519 | MDW-69538 | MDW-69539
207 | MDW-39557 | Lot02 | MO-BEM19 | MO-BEM | Install Chain Link fence to enclose parking area | สหชาติ | 0 | Depot | 2026-10-01 | 2026-06-29 | 100% | Completed | 2026-07-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 0% | Late | 0 | 0% | 0% | 2026-09-30 | 90% | Late | 2026-10-07 | 0% | Late | 0 | MDW-39557 | MDW-69614 | MDW-69615
208 | MDW-39523 | Lot02 | MO-BEM20 | MO-BEM | Hose bib 1/2" 4 sets for Tree around Admin area | ประธาน | 0 | Depot | 2026-06-01 | 2026-04-23 | 100% | Completed | 2026-06-08 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-03-31 | 100% | Completed | 2026-09-30 | 100% | Completed |  | MDW-39523 | MDW-69546 | MDW-69547
209 | - | Lot02 | MO-BEM21 | MO-BEM | Relocate Security Guard Box at Front Gate and Install Roof 3x5m. | สหชาติ | 0 | Depot | 2027-01-03 | 2026-07-31 | 100% | Completed | 2026-09-30 | 75% | Late | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule |  |  | 0 | 0
210 | MDW-39534 | Lot02 | MO-BEM21.1 | MO-BEM | Modification Works : Security Guard Box at ORL Depot Entrance - Civil & AR | สหชาติ | 0 | Depot | 2027-01-02 | 2026-07-31 | 100% | Completed | 2026-09-30 | 67% | Late | 0 | 0% | 0% | 2026-12-31 | 100% | Completed | 0 | 0% | 0% | 2026-12-01 | 50% | On Schedule | 2027-01-07 | 0% | On Schedule |  | MDW-39534 | MDW-69568 | MDW-69569
211 | MDW-39535 | Lot02 | MO-BEM21.2 | MO-BEM | Modification Works : Security Guard Box at ORL Depot Entrance - Building Services | ประธาน | 0 | Depot | 2027-01-03 | 2026-07-31 | 100% | Completed | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 50% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule |  | MDW-39535 | MDW-69570 | MDW-69571
212 | MDW-39532 | Lot02 | MO-BEM22 | MO-BEM | Addition Spike fence for MRTA fence and Chain link at Klong Chourdyai 400m. | สหชาติ | 0 | Depot | 2027-01-01 | 2026-08-30 | 70% | Late | 2026-09-30 | 0% | Late | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule |  | MDW-39532 | MDW-69564 | MDW-69565
213 | MDW-39527 | Lot02 | MO-BEM23 | MO-BEM | Hand sink with eye wash station | ประธาน | พี่ต่อ | Depot | 2027-01-01 | 2026-08-30 | 100% | Completed | 2026-10-15 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 100% | Completed | 0 | 0% | 0% | 2026-12-01 | 100% | Completed | 2027-01-07 | 0% | On Schedule |  | MDW-39527 | MDW-69554 | MDW-69555
214 | MDW-39531 | Lot02 | MO-BEM24 | MO-BEM | Guard rail protection for Fire Hose Cabinet 8 set | สหชาติ | 0 | Depot | 2026-06-01 | 2026-03-14 | 100% | Completed | 2026-04-14 | 100% | Completed | 0 | 0% | 0% | 2026-08-15 | 100% | Completed | 0 | 0% | 0% | 2026-07-16 | 100% | Completed | 2026-09-30 | 100% | Completed |  | MDW-39531 | MDW-69562 | MDW-69563
215 | MDW-39557 | Lot02 | MO-BEM25.1 | MO-BEM | Chain Link Fence to divide controlled areas on Depot slab 3 m.x 485 m. - Civil & AR | สหชาติ | 0 | Depot | 2026-10-01 | 2026-06-14 | 100% | Completed | 2026-07-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 0% | Late | 0 | 0% | 0% | 2026-09-30 | 50% | Late | 2026-10-07 | 0% | Late |  | MDW-39557 | MDW-69614 | MDW-69615
216 | MDW-39520 | Lot02 | MO-BEM25.2 | MO-BEM | Chain Link Fence to divide controlled areas on Depot slab 3 m.x 485 m.- Building Services | ประธาน | 0 | Depot | 2026-10-01 | 2026-06-14 | 100% | Completed | 2026-07-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 0% | Late | 0 | 0% | 0% | 2026-09-30 | 0% | Late | 2026-10-07 | 0% | Late |  | MDW-39520 | MDW-69540 | MDW-69541
217 | MDW-39518 | Lot02 | MO-BEM26 | MO-BEM | Street Lighting system area between MRTA Fence and Depot slab | ประธาน | 0 | Depot | 2026-08-01 | 2026-04-14 | 50% | Late | 2026-05-15 | 0% | Late | 0 | 0% | 0% | 2026-07-31 | 0% | Late | 0 | 0% | 0% | 2026-09-30 | 0% | Late | 2026-10-07 | 0% | Late |  | MDW-39518 | MDW-69536 | MDW-69537
218 | - | Lot02 | MO-BEM27 | MO-BEM | Compacted gravel walkway along the Test Track OR-BL 1.2 m. | สหชาติ | พรพรหม | Depot | 2027-01-01 | 2026-08-30 | 100% | Completed | 2026-09-30 | 0% | Late | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule |  |  | 0 | 0
219 | MDW-39524 | Lot02 | MO-BEM28.1 | MO-BEM | Walkway under Depot Slab for Maintenance Service - Civil & AR | สหชาติ | 0 | Depot | 2027-01-02 | 2026-09-14 | 100% | Completed | 2026-10-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 100% | Completed | 0 | 0% | 0% | 2026-12-01 | 50% | On Schedule | 2027-01-07 | 0% | On Schedule |  | MDW-39524 | MDW-69548 | MDW-69549
220 | MDW-39525 | Lot02 | MO-BEM28.2 | MO-BEM | Walkway under Depot Slab for Maintenance Service - Building Services | ประธาน | 0 | Depot | 2027-01-03 | 2026-09-14 | 100% | Completed | 2026-10-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 50% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule |  | MDW-39525 | MDW-69550 | MDW-69551
221 | MDW-39521 | Lot02 | MO-BEM29 | MO-BEM | Walkway Bridge across the canal for Depot area inspection patrols 3 location | สหชาติ | 0 | Depot | 2027-01-01 | 2026-08-15 | 100% | Completed | 2026-09-30 | 67% | Late | 0 | 0% | 0% | 2026-12-31 | 95% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 100% | Completed | 2027-01-07 | 0% | On Schedule |  | MDW-39521 | MDW-69542 | MDW-69543
222 | - | Lot02 | MO-BEM30 | MO-BEM | Cut down trees between Depot BL+ORL and MRTA Fence | สหชาติ | 0 | Depot | 2027-01-01 | 2026-10-29 | 0% | Late | 2026-11-29 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule |  |  | 0 | 0
223 | 0 | Lot02 | MO-BEM31 | MO-BEM | Provide facility system and interface to MMC room (Fire Alarm / CCTV / VMS / TEL / CASS / Radio / PA) | บัณฑิต | 0 | Depot | 2026-10-01 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
224 | - | Lot02 | MO-BEM32 | MO-BEM | Stainless Guard rail balustrade for waiting area | สหชาติ | 0 | Depot | 2026-05-01 |  |  | 0% |  |  | 0% | 0 | 0% | 0% |  |  | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
225 | - | Lot02 | MO-BEM33 | MO-BEM | Concrete walkway 2 x 80 m. For fire escape route | สหชาติ | 0 | Depot | 2026-05-01 |  |  | 0% |  |  | 0% | 0 | 0% | 0% |  |  | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
226 | - | Lot02 | MO-BEM34 | MO-BEM | Access Gate (Full Height Turnstile) at 1st floor admin ORL | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule |  |  | 0 | 0
227 | - | Lot02 | MO-BEM35 | MO-BEM | Access Gate (Tripod with Swing Gate) at MWS Entrance | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule |  |  | 0 | 0
228 | - | Lot02 | MO-BEM36 | MO-BEM | Access Gate (Tripod with Swing Gate) at Admin 2nd floor connect to OCC | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule |  |  | 0 | 0
229 | - | Lot02 | MO-BEM37 | MO-BEM | Access Gate (Tripod with Swing Gate) on Klong Chourdyai bridge | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule |  |  | 0 | 0
230 | - | Lot02 | MO-BEM38 | MO-BEM | Access Gate (Tripod with roof covering) at parking lot OCC | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule |  |  | 0 | 0
231 | - | Lot02 | MO-BEM39 | MO-BEM | Access Gate (Tripod with roof covering) at Stair up to Depot slab | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule |  |  | 0 | 0
232 | - | Lot02 | MO-BEM40 | MO-BEM | Access Control (2 Factors, Card + Finger Print) at High Security rooms - CCR/PTR/Store | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule |  |  | 0 | 0
233 | - | Lot02 | MO-BEM41 | MO-BEM | Link CCTV Landscape of all depot ORL area for MMC BL monitoring. | บัณฑิต | 0 | 0 | 2027-01-01 | 2026-11-28 | 0% | On Schedule | 2026-11-29 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule |  |  | 0 | 0
234 | - | Lot02 | MO-BEM42 | MO-BEM | Fire Suppression Control Panel Cover which located in tunnel | สู่โชค | 0 | 0 | 2027-01-01 |  |  | 0% |  |  | 0% | 0 | 0% | 0% |  |  | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
235 | MDW-39537 | Lot02 | MO-BEM43 | MO-BEM | Handrails for ladder at IVS and Vent buildings | สหชาติ | 0 | 0 | 2026-09-01 | 2026-03-31 | 70% | Late | 2026-05-01 | 0% | Late | 0 | 0% | 0% | 2026-08-31 | 0% | Late | 0 | 0% | 0% | 2026-10-31 | 0% | On Schedule | 2026-11-15 | 0% | On Schedule |  | MDW-39537 | MDW-69574 | MDW-69575
236 | MDW-39538 | Lot02 | MO-BEM44 | MO-BEM | Escalator Anti-Slide device for all station. | สหชาติ | 0 | 0 | 2026-09-01 | 2026-05-30 | 100% | Completed | 2026-06-30 | 100% | Completed | 2027-01-31 | 100% | Completed | 2027-02-28 | 70% | On Schedule | 0 | 0% | 0% | 2027-01-29 | 0% | On Schedule | 2027-02-28 | 0% | On Schedule |  | MDW-39538 | MDW-69576 | MDW-69577
237 | MDW-39539 | Lot02 | MO-BEM45 | MO-BEM | Roof for control panel on vent building | สหชาติ | 0 | 0 | 2027-01-01 | 2026-09-14 | 70% | Late | 2026-10-30 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule |  | MDW-39539 | MDW-69578 | MDW-69579
238 | MDW-39553 | Lot02 | MO-BEM46 | MO-BEM | Provide Standing plate or ladder to access the Fire Valve in at Omega points for all underground stations. | สหชาติ | 0 | Depot | 2027-01-01 | 2026-09-14 | 0% | Late | 2026-10-30 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule |  | MDW-39553 | MDW-69606 | MDW-69607
239 | MDW-39540 | Lot02 | MO-BEM47 | MO-BEM | Water drop protection above UPS cabinet at station and Depot | สหชาติ | 0 | 0 | 2027-01-01 | 2026-09-14 | 0% | Late | 2026-10-30 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule |  | MDW-39540 | MDW-69580 | MDW-69581
240 | MDW-39541 | Lot02 | MO-BEM48 | MO-BEM | Fire alarm manual call point cover in public area at all station | ประธาน | 0 | 0 | 2027-01-01 | 2026-09-14 | 50% | Late | 2026-10-30 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule |  | MDW-39541 | MDW-69582 | MDW-69583
241 | MDW-39542 | Lot02 | MO-BEM49 | MO-BEM | Emergency stop button cover for escalator at all station. | สหชาติ | 0 | 0 | 2027-01-01 | 2026-09-14 | 0% | Late | 2026-10-30 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule |  | MDW-39542 | MDW-69584 | MDW-69585
242 | 0 | Lot02 | MO-BEM50 | MO-BEM | Modify maintenance service door to the roof of OR13 vent building to easier access while maintaining safe operational standards | สู่โชค | 0 | Depot | 2027-01-01 | 2026-10-29 | 0% | Late | 2026-10-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule |  |  | 0 | 0
243 | MDW-39514 | Lot02 | MO-BEM51 | MO-BEM | Modify existing car park to be 220 motorcycle parking lots including floor painting and parking roof | สหชาติ | 0 | Depot | 2026-08-01 | 2026-01-29 | 100% | Completed | 2026-03-16 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-01 | 100% | Completed | 2026-09-30 | 0% | Late |  | MDW-39514 | MDW-69528 | MDW-69529
244 | MDW-39534 | Lot02 | MO-BEM52 | MO-BEM | Modify the sidewalk for temporary parking at entrance | สหชาติ | 0 | Depot | 2027-01-01 | 2026-07-31 | 100% | Completed | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 100% | Completed | 0 | 0% | 0% | 2026-12-01 | 50% | On Schedule | 2027-01-07 | 0% | On Schedule |  | MDW-39534 | MDW-69568 | MDW-69569
245 | MDW-39554 | Lot02 | MO-BEM53.1 | MO-BEM | Modification Works : Security Guard Box at OCC Parking Area - Civil & AR | สหชาติ | 0 | Depot | 2027-01-02 | 2026-09-14 | 100% | Completed | 2026-10-31 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 50% | On Schedule | 2027-01-07 | 0% | On Schedule |  | MDW-39554 | MDW-69608 | MDW-69609
246 | MDW-39555 | Lot02 | MO-BEM53.2 | MO-BEM | Modification Works : Security Guard Box at OCC Parking Area - Building Services | ประธาน | 0 | 0 | 2027-01-02 | 2026-09-14 | 100% | Completed | 2026-10-31 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 50% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule |  | MDW-39555 | MDW-69610 | MDW-69611
247 | NoDrawing | Lot02 | MO-BEM54 | MO-BEM | Strengthen the Maintenance Walkway of the TEF fan | สหชาติ | 0 | 0 | 2027-01-01 | 2026-07-16 | 100% | Completed | 2026-08-16 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule |  |  | 0 | 0
Lot 1 Inspection
[35 empty] | CK Pesonsible Person | Total | Completed | Late | On Schedule
[35 empty] | สหชาติ | 17 | 7 | 7 | 3
[35 empty] | ประธาน | 37 | 13 | 4 | 20
[35 empty] | สมศักดิ์ | 13 | 0 | 10 | 3
[35 empty] | กำพล | 6 | 0 | 5 | 1
[35 empty] | บัณฑิต | 4 | 0 | 1 | 3
[35 empty] | สู่โชค | 1 | 0 | 1 | 0
[35 empty] | มนตรี | 3 | 0 | 1 | 2
[35 empty] | มนต์ชัย | 1 | 0 | 1 | 0
[35 empty] | - | 2 | 0 | 2 | 0
Lot 2 Inspection
[35 empty] | CK Pesonsible Person | Total | Completed | Late | On Schedule
[35 empty] | สหชาติ | 61 | 7 | 25 | 29
[35 empty] | ประธาน | 25 | 6 | 9 | 10
[35 empty] | บัณฑิต | 8 | 0 | 0 | 8
[35 empty] | สู่โชค | 1 | 0 | 0 | 1

## Test Report (hidden)
Test Report
No. | Design Submission | Lot No. | Code | System | Activity Name | CK Responsible Person |  | Location | Expected Completion Month | Design (PLAN) | Design (%) | Design (Status) | Procurement (PLAN) | Procurement (%) | Procurement (Status) | Manufacturing / Delivery Process (PLAN) | Manufacturing / Delivery Process (%) | Manufacturing / Delivery (Status) | Construction /Installation (PLAN) | Construction /Installation (%) | Construction /Installation (Status) | T&C (PLAN) | T&C (%) | T&C (Status) | Test Procedure (PLAN) | Test Procedure (%) | Test Procedure (Status) | Inspection (PLAN) | Inspection (%) | Inspection (Status) | Test Report (PLAN) | Test Report (%) | Test Report (Status) | Note | Design Submission | Procedure No. | Test Report No.
1 | MDW-39246-60 | Lot01 | GEN1 | GEN | Rooms and Building Service Systems Modification in Stations Area | - | 0 | 0 | 2026-08-01 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39246 | MDW-69259 | MDW-69260
2 | MDW-39246 | Lot01 | GEN1.1 | GEN | Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR13 - OR17 | ประธาน | 0 | 0 | 2026-08-01 | 2026-01-30 | 100% | Completed | 2026-03-01 | 100% | Completed | 0 | 0% | 0% | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 2026-10-31 | 100% | Completed | 2026-10-31 | 0% | On Schedule | 0 | MDW-39246 | MDW-69259 | MDW-69260
3 | MDW-39247 | Lot01 | GEN1.2 | GEN | Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR18 - OR22 | ประธาน | 0 | 0 | 2026-08-01 | 2025-12-30 | 100% | Completed | 2026-01-29 | 100% | Completed | 0 | 0% | 0% | 2026-02-28 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 2026-10-31 | 100% | Completed | 2026-10-31 | 0% | On Schedule | 0 | MDW-39247 | MDW-69259 | MDW-69261
4 | MDW-39248 | Lot01 | GEN1.3 | GEN | Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR23 - OR29 | ประธาน | 0 | 0 | 2026-08-01 | 2026-01-30 | 100% | Completed | 2026-03-01 | 100% | Completed | 0 | 0% | 0% | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 2026-10-31 | 100% | Completed | 2026-10-31 | 0% | On Schedule | 0 | MDW-39248 | MDW-69259 | MDW-69262
5 | MDW-39252 | Lot01 | GEN1.4 | GEN | Modification of Fire Suppression System (N2) in Commerial Room at OR14 | ประธาน | 0 | 0 | 2026-08-01 | 2025-12-30 | 100% | Completed | 2026-01-29 | 100% | Completed | 0 | 0% | 0% | 2026-02-28 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 2026-10-31 | 100% | Completed | 2026-10-31 | 0% | On Schedule | 0 | MDW-39252 | MDW-69269 | MDW-69270
6 | MDW-39253 | Lot01 | GEN1.5 | GEN | Modification of Civil Work in Telecommunication Room at OR14 | สหชาติ | 0 | 0 | 2026-08-01 | 2025-12-30 | 100% | Completed | 2026-01-29 | 100% | Completed | 0 | 0% | 0% | 2026-02-28 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-10-31 | 0% | On Schedule | 0 | MDW-39253 | MDW-69271 | MDW-69272
7 | MDW-39254 | Lot01 | GEN1.6 | GEN | Modification in Staff Mess Room at OR13-OR17 | ประธาน | 0 | 0 | 2026-08-01 | 2026-01-30 | 100% | Completed | 2026-03-01 | 100% | Completed | 0 | 0% | 0% | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 2026-10-31 | 100% | Completed | 2026-10-31 | 0% | On Schedule | 0 | MDW-39254 | MDW-69273 | MDW-69274
8 | MDW-39255 | Lot01 | GEN1.7 | GEN | Modification in Staff Mess Room at OR18-OR22 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 2026-10-31 | 0% | On Schedule | 2026-10-31 | 0% | On Schedule | 0 | MDW-39255 | MDW-69273 | MDW-69275
9 | MDW-39256 | Lot01 | GEN1.8 | GEN | Modification in Staff Mess Room at OR23-OR29 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 2026-11-30 | 0% | On Schedule | 2026-10-31 | 0% | On Schedule | 0 | MDW-39256 | MDW-69273 | MDW-69276
10 | MDW-39257 | Lot01 | GEN1.9 | GEN | Modification of Air Conditioning in CER and SER at OR13-OR19 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 99% | Late | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 2026-11-30 | 0% | On Schedule | 2026-10-31 | 0% | On Schedule | 0 | MDW-39257 | MDW-69277 | MDW-69278
11 | MDW-39258 | Lot01 | GEN1.10 | GEN | Modification of Air Conditioning in CER and SER at OR20-OR22 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 99% | Late | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 2026-11-30 | 0% | On Schedule | 2026-10-31 | 0% | On Schedule | 0 | MDW-39258 | MDW-69277 | MDW-69279
12 | MDW-39259 | Lot01 | GEN1.11 | GEN | Modification of Air Conditioning in CER and SER at OR23-OR29 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 99% | Late | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 2026-11-30 | 0% | On Schedule | 2026-10-31 | 0% | On Schedule | 0 | MDW-39259 | MDW-69277 | MDW-69280
13 | MDW-39272 | Lot01 | GEN1.12 | GEN | Modification of New M&E Room at IVS15 - IVS17 Civil & AR | สหชาติ | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-10-31 | 0% | On Schedule | 0 | MDW-39272 | MDW-69299 | MDW-69300
14 | MDW-39273 | Lot01 | GEN1.13 | GEN | Modification of New M&E UPS Room at IVS15-IVS17 - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 99% | Late | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 2026-11-30 | 0% | On Schedule | 2026-10-31 | 0% | On Schedule | 0 | MDW-39273 | MDW-69301 | MDW-69302
15 | MDW-39294 | Lot01 | GEN1.14 | GEN | Provision of Architectural Work in new M&E UPS room at OR23 | สหชาติ | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-10-31 | 0% | On Schedule | 0 | MDW-39294 | MDW-69339 | MDW-69340
16 | MDW-39299 | Lot01 | GEN1.15 | GEN | Provision of Air Conditioning System in Commercial Room at OR13-OR19 | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 2026-10-31 | 0% | On Schedule | 2026-10-31 | 0% | On Schedule | 0 | MDW-39299 | MDW-69349 | MDW-69350
17 | MDW-39306 | Lot01 | GEN1.16 | GEN | Modification CER and First Aid Room at OR14 - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 2026-10-31 | 100% | Completed | 2026-10-31 | 0% | On Schedule | 0 | MDW-39306 | MDW-69363 | MDW-69364
18 | MDW-39307 | Lot01 | GEN1.17 | GEN | Additional Fence at Back of House OR13 - OR22 and IVS East Section | สหชาติ | 0 | 0 | 2026-08-01 | 2026-09-30 | 100% | Completed | 2026-10-31 | 50% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2027-01-30 | 0% | On Schedule | 0 | MDW-39307 | MDW-69365 | MDW-69366
19 | MDW-39249 | Lot01 | GEN1.18 | GEN | SOR Counter and Workstation Hanging Support Installation on East Section | สหชาติ | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-10-31 | 0% | On Schedule | 0 | MDW-39249 | MDW-69263 | MDW-69264
20 | MDW-39250 | Lot01 | GEN1.19 | GEN | Ticket Office Modification on East Section | สหชาติ | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-10-31 | 0% | On Schedule | 0 | MDW-39250 | MDW-69265 | MDW-69266
21 | MDW-39261 | Lot01 | GEN2 | GEN | Rooms and Building Service Systems Modification in Depot Area | - | 0 | Depot | 2026-08-01 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39261 | MDW-69283 | MDW-69284
22 | MDW-39260 | Lot01 | GEN2.1 | GEN | Modification of Air Conditioning in M&E Room at OCC Building | ประธาน | 0 | 0 | 2026-08-01 | 2025-12-30 | 100% | Completed | 2026-01-29 | 100% | Completed | 0 | 0% | 0% | 2026-02-28 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 2026-10-31 | 100% | Completed | 2026-10-31 | 0% | On Schedule | 0 | MDW-39260 | MDW-69281 | MDW-69282
23 | MDW-39261 | Lot01 | GEN2.2 | GEN | Provision of UPS for MDB Control at Main Workshop, OCC Building, Admin Building, Stabling Yard and Train Washing Plant | ประธาน | 0 | 0 | 2026-08-01 | 2026-09-01 | 100% | Completed | 2026-10-01 | 100% | Completed | 0 | 0% | 0% | 2026-10-31 | 90% | On Schedule | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 2026-10-31 | 0% | On Schedule | 2026-11-30 | 0% | On Schedule | 0 | MDW-39261 | MDW-69283 | MDW-69284
24 | MDW-39262 | Lot01 | GEN2.3 | GEN | Provision of Redundant MDB at OCC Building, Admin Building and Canteen | ประธาน | 0 | 0 | 2026-08-01 | 2026-09-01 | 100% | Completed | 2026-10-01 | 100% | Completed | 0 | 0% | 0% | 2026-10-31 | 95% | On Schedule | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 2026-10-31 | 0% | On Schedule | 2026-11-30 | 0% | On Schedule | 0 | MDW-39262 | MDW-69285 | MDW-69286
25 | MDW-39263 | Lot01 | GEN2.4 | GEN | Additonal Lighting System at Depot Area | ประธาน | 0 | 0 | 2026-08-01 | 2026-04-01 | 100% | Completed | 2026-05-01 | 100% | Completed | 0 | 0% | 0% | 2026-05-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 2026-10-31 | 100% | Completed | 2026-10-31 | 0% | On Schedule | 0 | MDW-39263 | MDW-69287 | MDW-69288
26 | MDW-39290 | Lot01 | GEN2.5 | GEN | Modification Room for PSY at Depot Buildings - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 2026-10-31 | 0% | On Schedule | 2026-10-31 | 0% | On Schedule | 0 | MDW-39290 | MDW-69331 | MDW-69332
27 | MDW-39300 | Lot01 | GEN2.6 | GEN | Modification SIG-PSD Office at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 2026-10-31 | 0% | On Schedule | 2026-10-31 | 0% | On Schedule | 0 | MDW-39300 | MDW-69351 | MDW-69352
28 | MDW-39301 | Lot01 | GEN2.7 | GEN | Modification Backup CCR Room at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 2026-10-31 | 0% | On Schedule | 2026-10-31 | 0% | On Schedule | 0 | MDW-39301 | MDW-69353 | MDW-69354
29 | MDW-39302 | Lot01 | GEN2.8 | GEN | Modification SER at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 2026-10-31 | 0% | On Schedule | 2026-10-31 | 0% | On Schedule | 0 | MDW-39302 | MDW-69355 | MDW-69356
30 | MDW-39303 | Lot01 | GEN2.9 | GEN | Modification CER & SCADA Room at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-08-01 | 100% | Completed | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 2026-10-31 | 0% | On Schedule | 2026-10-31 | 0% | On Schedule | 0 | MDW-39303 | MDW-69357 | MDW-69358
31 | MDW-39309 | Lot01 | GEN2.10 | GEN | Modification Air Conditioning System at CCR | ประธาน | 0 | 0 | 2026-08-01 | 2026-10-01 | 100% | Completed | 2026-10-31 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 80% | On Schedule | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 2026-10-31 | 0% | On Schedule | 2027-01-30 | 0% | On Schedule | 0 | MDW-39309 | MDW-69369 | MDW-69370
32 | MDW-39312 | Lot01 | GEN2.11 | GEN | Modification Electronic Workshop at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-10-31 | 100% | Completed | 2026-11-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 2026-10-31 | 0% | On Schedule | 2027-01-30 | 0% | On Schedule | 0 | MDW-39312 | MDW-69375 | MDW-69376
33 | MDW-39313 | Lot01 | GEN2.12 | GEN | Modification Battery Charger Room at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-10-31 | 100% | Completed | 2026-11-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 2026-10-31 | 0% | On Schedule | 2027-01-30 | 0% | On Schedule | 0 | MDW-39313 | MDW-69377 | MDW-69378
34 | MDW-39314 | Lot01 | GEN2.13 | GEN | Modification Machining Room at Main Workshop - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2026-10-31 | 90% | On Schedule | 2026-11-30 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 2026-10-31 | 0% | On Schedule | 2027-01-30 | 0% | On Schedule | 0 | MDW-39314 | MDW-69379 | MDW-69380
35 | MDW-39315 | Lot01 | GEN2.14 | GEN | Modification Electronic Workshop, Battery Charger and Machining Room at Main Workshop - Civil & AR | สหชาติ | 0 | 0 | 2026-08-01 | 2026-10-31 | 70% | On Schedule | 2026-11-30 | 90% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 0 | 0% | 0% | 2027-01-30 | 0% | On Schedule | 0 | MDW-39315 | MDW-69383 | MDW-69384
36 | MDW-39297 | Lot01 | GEN2.15 | GEN | Training Room at Ratchada Station (Part 2) | สหชาติ | 0 | 0 | 2026-08-01 | 2026-08-01 | 0% | Late | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 0 | 0% | 0% | 2026-10-30 | 0% | On Schedule | 0 | MDW-39297 | MDW-69345 | MDW-69346
37 | MDW-39291 | Lot01 | GEN2.16 | GEN | Conductor Rail Arrangement Modification at Main Line East Section | กำพล | 0 | 0 | 2026-08-01 | 2026-09-30 | 100% | Completed | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 90% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 0 | 0% | 0% | 2027-01-30 | 0% | On Schedule | 0 | MDW-39291 | MDW-69333 | MDW-69334
38 | MDW-39292 | Lot01 | GEN2.17 | GEN | Conductor Rail Arrangement Modification at Depot | กำพล | 0 | 0 | 2026-08-01 | 2026-09-30 | 100% | Completed | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 90% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 0 | 0% | 0% | 2027-01-30 | 0% | On Schedule | 0 | MDW-39292 | MDW-69335 | MDW-69336
39 | MDW-39295 | Lot01 | GEN2.18 | GEN | Dangerous Goods Building in Depot - Civil & AR | สหชาติ | 0 | 0 | 2026-08-01 | 2026-01-27 | 100% | Completed | 2026-02-27 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-10-31 | 0% | On Schedule | 0 | MDW-39295 | MDW-69341 | MDW-69342
40 | MDW-39296 | Lot01 | GEN2.19 | GEN | Dangerous Goods Building in Depot - Building Services | ประธาน | 0 | 0 | 2026-08-01 | 2025-12-13 | 100% | Completed | 2026-01-28 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 2026-10-31 | 0% | On Schedule | 2026-10-31 | 0% | On Schedule | 0 | MDW-39296 | MDW-69343 | MDW-69344
41 | MDW-39308 | Lot01 | GEN2.20 | GEN | Additional Locking Devices for Main Line Tandem Turnouts 2007, 2010 & 2013 and Depot Turnout D16 | กำพล | 0 | 0 | 2026-08-01 | 2026-11-30 | 50% | On Schedule | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 0 | 0% | 0% | 2027-01-30 | 0% | On Schedule | 0 | MDW-39308 | MDW-69367 | MDW-69368
42 | MDW-39200-31 | Lot01 | GEN3 | GEN | Cable Containment Modification | - | 0 | 0 | 2025-05-28 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39200
43 | - | Lot01 | GEN4 | GEN | Training Room and Workshop Room | - | 0 | 0 | 2026-04-01 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
44 | MDW-39242 | Lot01 | GEN4.0 | GEN | Modification Works for Training Room at Ratchada Station | ประธาน | 0 | 0 | 2026-04-01 | 2025-12-30 | 100% | Completed | 2026-01-31 | 100% | Completed | 0 | 0% | 0% | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-03-16 | 100% | Completed | 2026-09-30 | 100% | Completed | 2026-10-21 | 100% | Completed |  | MDW-39242 | MDW-69251 | MDW-69252
45 | MDW-39244 | Lot01 | GEN4.1 | GEN | AFC Training Room Modification - Civil & AR | สหชาติ | 0 | 0 | 2026-08-21 | 2026-09-30 | 10% | Late | 2026-10-15 | 100% | Completed | 0 | 0% | 0% | 2026-11-15 | 0% | On Schedule | 0 | 0% | 0% | 2026-10-31 | 0% | On Schedule | 2026-11-22 | 0% | On Schedule | 2026-12-15 | 0% | On Schedule | อยู่ระหว่างจัดทำแบบก่อสร้าง | MDW-39244 | MDW-69255 | MDW-69256
46 | MDW-39245 | Lot01 | GEN4.2 | GEN | AFC Training Room Modification - Building Services | ประธาน | 0 | 0 | 2026-08-21 | 2025-12-30 | 100% | Completed | 2026-01-31 | 100% | Completed | 0 | 0% | 0% | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-03-24 | 100% | Completed | 2026-08-07 | 100% | Completed | 2026-09-30 | 0% | Late | 0 | MDW-39245 | MDW-69257 | MDW-69258
47 | MDW-39235 | Lot01 | GEN5 | GEN | Raised Floor | สหชาติ | 0 | 0 | 2026-06-01 | 2025-05-15 | 100% | Completed | 2024-12-14 | 100% | Completed | 2025-08-04 | 100% | Completed | 2025-12-28 | 100% | Completed | 0 | 0% | 0% | 2025-11-28 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late | 0 | MDW-39235 | MDW-69237 | MDW-69238
48 | MDW-39271 | Lot01 | GEN6 | GEN | Wayside Cable Containment in Depot | - | 0 | Depot | 2026-02-22 | 2025-05-15 | 100% | Completed | 2024-12-14 | 100% | Completed | 2025-08-04 | 100% | Completed | 2025-12-28 | 100% | Completed | 0 | 0% | 0% | 2026-08-26 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late | 0 | MDW-39271 | MDW-69297 | MDW-69298
49 | MDW-39269 | Lot01 | GEN6.1 | GEN | PSY Wayside Cable Containment for 24 Kv Cable under the Depot slab | ประธาน | 0 | Depot | 2026-02-22 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39269 | MDW-69293 | MDW-69294
50 | MDW-39270 | Lot01 | GEN6.2 | GEN | COM/SIG Wayside Cable Containment in the Depot | มนตรี/ประธาน | 0 | Depot | 2026-02-22 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39270 | MDW-69295 | MDW-69296
51 | - | Lot01 | GEN7 | GEN | Dangerous Waste Storage Building in Depot | - | 0 | Depot | 2026-09-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
52 | DWE-39024 | Lot01 | GEN7.1 | GEN | Dangerous Waste Storage Building in Depot - Civil & AR | สหชาติ | 0 | Depot | 2026-09-20 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-07-15 | 100% | Completed | 2026-06-08 | 100% | Completed | 2026-09-30 | 0% | Late | 0 | DWE-39024 | DWE-69024 | DWE-69124
53 | DWE-39025 | Lot01 | GEN7.2 | GEN | Dangerous Waste Storage Building in Depot - Building service | ประธาน | 0 | Depot | 2026-09-20 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed | 0 | 0% | 0% | 2026-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-04-20 | 100% | Completed | 2026-06-08 | 100% | Completed | 2026-09-30 | 0% | Late | 0 | DWE-39025 | DWE-69025 | DWE-69125
54 | - | Lot01 | GEN8 | GEN | General Waste Storage Building in Depot | - | 0 | Depot | 2026-09-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
55 | DWE-39026 | Lot01 | GEN8.1 | GEN | General Waste Storage Building in Depot - Civil & AR | สหชาติ | 0 | Depot | 2026-09-20 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-07-15 | 100% | Completed | 2026-06-08 | 100% | Completed | 2026-09-30 | 0% | Late | 0 | DWE-39026 | DWE-69026 | DWE-69126
56 | DWE-39025 | Lot01 | GEN8.2 | GEN | General Waste Storage Building in Depot - Building service | ประธาน | 0 | Depot | 2026-09-20 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed | 0 | 0% | 0% | 2026-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-04-20 | 100% | Completed | 2026-06-08 | 100% | Completed | 2026-09-30 | 0% | Late | 0 | DWE-39025 | DWE-69025 | DWE-69125
57 | DWE-39021 | Lot01 | GEN9 | GEN | Operation Support Equipment | สมศักดิ์ | 0 | Depot | 2026-08-21 | 2025-03-02 | 100% | Completed | 2025-11-02 | 100% | Completed | 2026-11-16 | 90% | On Schedule | 0 | 0% | 0% | 0 | 0% | 0% | 2026-10-17 | 0% | Late | 2026-11-23 | 0% | On Schedule | 2026-12-16 | 0% | On Schedule | คงเหลือจัดส่ง Signal Lamp | DWE-39021 | DWE-69021 | DWE-69121
58 | GRS-39001-40 | Lot01 | GEN10.1 | GEN | Graphic and Signage Station | สหชาติ | 0 | 0 | 2026-08-21 | 2026-06-30 | 100% | Completed | 2026-05-31 | 95% | Late | 2027-01-31 | 76% | On Schedule | 2027-02-28 | 34% | On Schedule | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | GRS-39001 | GRS-69001 | GRS-69002
59 | GRS-39001-40 | Lot01 | GEN10.2 | GEN | Graphic and Signage Mainline & IVS,VS | สหชาติ | 0 | 0 | 2026-08-21 | 2026-06-15 | 79% | Late | 2026-05-31 | 95% | Late | 2026-07-31 | 0% | Late | 2026-07-31 | 0% | Late | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | GRS-39001 | GRS-69001 | GRS-69002
60 | GRS-39001-40 | Lot01 | GEN10.3 | GEN | Graphic and Signage Depot | สหชาติ | 0 | 0 | 2026-08-21 | 2026-08-15 | 90% | Late | 2026-07-31 | 93% | Late | 2026-06-30 | 56% | Late | 2026-06-30 | 19% | Late | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | GRS-39001 | GRS-69001 | GRS-69002
61 | MDW-39289 | Lot01 | GEN11 | GEN | Earthing and Bonding Modification | ประธาน | 0 | 0 | 2026-03-01 | 2025-01-31 | 100% | Completed | 2025-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-02-28 | 100% | Completed | 2026-03-30 | 100% | Completed | 2026-09-23 | 0% | Late | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late | 0 | MDW-39289 | MDW-69329 | MDW-69330
62 | - | Lot01 | GEN12 | GEN | Mainline Cable Trough Modification on East Section | - | 0 | 0 | 2026-06-22 | 2025-10-31 | 100% | Completed | 2025-11-30 | 100% | Completed | 2025-12-30 | 100% | Completed | 2026-03-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 80% | Late | 2026-10-07 | 0% | Late | 2026-10-30 | 0% | On Schedule | 0 |  | 0 | 0
63 | MDW-39233 | Lot01 | GEN12.1 | GEN | Main Line Cable Trough Modification (PSY) | มนต์ชัย | 0 | Depot | 2026-06-22 | 2025-10-31 | 100% | Completed | 2025-11-30 | 100% | Completed | 2025-12-30 | 100% | Completed | 2026-03-30 | 100% | Completed | 0% | 0% | 0% | 2026-09-30 | 80% | Late | 2026-10-07 | 0% | Late | 2026-10-30 | 0% | On Schedule | 0 | MDW-39233
64 | MDW-39234 | Lot01 | GEN12.2 | GEN | Main Line Cable Trough Modification (SIG/COM) | มนตรี | 0 | 0 | 2026-06-22 | 2025-10-31 | 100% | Completed | 2025-11-30 | 100% | Completed | 2025-12-30 | 100% | Completed | 2026-03-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 80% | Late | 2026-10-07 | 0% | Late | 2026-10-30 | 0% | On Schedule | งานจบแล้ว | MDW-39234 | MDW-69234 | MDW-69236
65 | MDW-39236 | Lot01 | GEN13 | GEN | Bird Protection System | สหชาติ | 0 | 0 | 2026-11-19 | 2025-06-30 | 100% | Completed | 2025-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-01-26 | 100% | Completed | 0 | 0% | 0% | 2026-07-15 | 100% | Completed | 2026-09-30 | 100% | Completed | 2026-10-21 | 0% | Late | 0 | MDW-39236 | MDW-69239 | MDW-69240
66 | - | Lot01 | GEN14 | GEN | Train Crew Office at Thailand Cultural Centre Station | สหชาติ | 0 | 0 | 2026-08-21 | 2025-09-30 | 100% | Completed | 2026-02-27 | 100% | Completed | 0 | 0% | 0% | 2026-05-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-23 | 0% | Late | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late | 0 |  | 0 | 0
67 | MDW-39240 | Lot01 | GEN14.1 | GEN | Driver Train Simulation Room and Train Crew Office at OR18 - Civil & AR | สหชาติ | 0 | Depot | 2026-08-21 | 2025-09-30 | 100% | Completed | 2026-02-28 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-07-15 | 100% | Completed | 2026-08-07 | 100% | Completed | 2026-09-30 | 0% | Late | 0 | MDW-39240 | MDW-69247 | MDW-69248
68 | MDW-39241 | Lot01 | GEN14.2 | GEN | Driver Train Simulation Room and Train Crew Office at OR18 - Building Services | ประธาน | 0 | 0 | 2026-08-21 | 2025-09-30 | 100% | Completed | 2026-02-28 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-03-12 | 100% | Completed | 2026-08-07 | 100% | Completed | 2026-09-30 | 0% | Late | 0 | MDW-39241 | MDW-69249 | MDW-69250
69 | MDW-39239 | Lot01 | GEN15 | GEN | Access Panel Closeout for Traction Substation Room in Main Workshop | สหชาติ | 0 | 0 | 2026-03-24 | 2026-01-30 | 100% | Completed | 2026-03-01 | 100% | Completed | 0 | 0% | 0% | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-15 | 100% | Completed | 2026-09-30 | 100% | Completed | 2026-10-21 | 0% | Late | 0 | MDW-39239 | MDW-69245 | MDW-69246
70 | MDW-39232 | Lot01 | GEN16 | GEN | Level Crossing at Turnout | กำพล | 0 | 0 | 2026-08-21 | 2026-09-30 | 100% | Completed | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-11-15 | 46% | On Schedule | 0 | 0% | 0% |  | 0% | On Schedule |  | 0% | On Schedule |  | 0% | On Schedule | 0 | MDW-39232 | MDW-69232 | MDW-69233
71 | MDW-39232 | Lot01 | GEN17 | GEN | Track Slab Crossing | ชฎิล/กำพล | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39232 | MDW-69232 | MDW-69233
72 | MDW-39243 | Lot01 | GEN18 | GEN | Eye Adaptation Lighting (Lighting at Tunnel to Expose) | ประธาน | 0 | 0 | 2026-11-19 | 2025-09-30 | 100% | Completed | 2025-10-30 | 100% | Completed | 0 | 0% | 0% | 2026-04-13 | 100% | Completed | 0 | 0% | 0% | 2026-02-18 | 100% | Completed | 2026-10-07 | 0% | Late | 2026-10-30 | 0% | On Schedule | Progress DPA1 : 100% Progress DPA2 : 100% Progress Cut&Cover OR22 : 95% | MDW-39243 | MDW-69253 | MDW-69254
73 | - | Lot01 | GEN19 | GEN | Train Simulation Room and AFC Training Room | - | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
74 | MDW-39244 | Lot01 | GEN19.1 | GEN | Modification AFC Training Center at OR19 - Civil & AR | สหชาติ | 0 | 0 | 2026-11-30 | 2026-09-30 | 100% | Completed | 2026-10-31 | 58% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 0 | 0% | 0% | 2026-10-31 | 0% | On Schedule | 2026-12-07 | 0% | On Schedule | 2026-12-28 | 0% | On Schedule | Progress Cut&Cover OR22 : 95% | MDW-39244 | MDW-69255 | MDW-69256
75 | MDW-39245 | Lot01 | GEN19.2 | GEN | Modification AFC Training Center at OR19 - Building Services | ประธาน | บัณฑิต | 0 | 2026-11-30 | 2026-09-30 | 100% | Completed | 2026-10-31 | 100% | Completed | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 0 | 0% | 0% | 2026-10-31 | 0% | On Schedule | 2026-12-07 | 0% | On Schedule | 2026-12-28 | 0% | On Schedule | 0 | MDW-39245 | MDW-69257 | MDW-69258
76 | - | Lot01 | GEN20 | GEN | Dormitory Cable Containments (if any) | - | 0 | 0 | - | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
77 |  | Lot01 | GEN21 | GEN | Project Information Management System (PIMS) | บัณฑิต | 0 | 0 | 2024-09-30 | 2024-08-10 | 100% | Completed | 2024-08-15 | 100% | Completed | 0 | 0% | 0% | 2024-09-04 | 100% | Completed | 2024-09-14 | 100% | Completed | 2026-09-23 | 0% | Late | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late | งานจบแล้ว
78 | MDW-39237 | Lot01 | GEN22 | GEN | Central BEMS for the MRT Orange Line System | บัณฑิต | 0 | 0 | 2026-08-21 | 2026-04-30 | 0% | Late | 2026-06-30 | 0% | Late | 0 | 0% | 0% | 2026-08-15 | 0% | Late | 2026-08-31 | 0% | Late | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule | PPR Oct-26 กำลังเปรียบเทียบ Spec | MDW-39237 | MDW-69241 | MDW-69242
79 |  | Lot01 | GEN23 | GEN | Asset Information | บัณฑิต | 0 | 0 | 2026-11-19 | 0 | 0% | 0% | 2026-08-30 | 100% | Completed | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0
80 | MDW-39282 | Lot01 | PSD1 | PSD | Holes for PSD Cable Wiring | กำพล | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39282 | MDW-69315 | MDW-69316
81 | MDW-39004 | Lot01 | PSD2 | PSD | Rubber Gap Fillers on Platform Edge | กำพล | 0 | 0 | 2026-08-21 | 2025-07-30 | 100% | Completed | 2026-01-31 | 100% | Completed | 0 | 0% | 0% | 2026-08-31 | 40% | Late | 0 | 0% | 0% | 2026-09-30 | 25% | Late | 2026-10-07 | 0% | Late | 2026-10-30 | 50% | On Schedule | แผนเข้าติดตั้ง 1/10/26-30/11/26 | MDW-39004 | MDW-69007 | MDW-69008
82 | MDW-39280 | Lot01 | PSD3 | PSD | Platform Finishing | กำพล | 0 | 0 | 2026-08-21 | 2025-07-30 | 100% | Completed | 2025-09-16 | 100% | Completed | 0 | 0% | 0% | 2026-01-07 | 100% | Completed | 0 | 0% | 0% | 2026-08-17 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late | 0 | MDW-39280 | MDW-69311 | MDW-69312
83 | MDW-39281 | Lot01 | PSD4 | PSD | Cladding Barrier between EWD and Station Structure | กำพล | 0 | 0 | 2026-08-21 | 2026-02-28 | 100% | Completed | 2026-03-15 | 100% | Completed | 0 | 0% | 0% | 2026-08-15 | 100% | Completed | 0 | 0% | 0% | 2026-09-23 | 0% | Late | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late | 0 | MDW-39281 | MDW-69313 | MDW-69314
84 | - | Lot01 | AFC1 | AFC | Park and Ride System | บัณฑิต/สหชาติ | 0 | 0 | 2026-10-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
85 | MDW-39276 | Lot01 | AFC2 | AFC | Ticket Issuing Machine (TIM) Wall Opening and Closing | สหชาติ | 0 | 0 | 2026-09-20 | 2026-01-30 | 100% | Completed | 2026-03-15 | 50% | Late | 0 | 0% | 0% | 2026-07-13 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 50% | Late | 2026-10-07 | 0% | Late | 2026-10-30 | 0% | On Schedule | มีแก้ไขตำแหน่ง OR14,17,18,23 | MDW-39276 | MDW-69303 | MDW-69304
86 | MDW-39279 | Lot01 | AFC3 | AFC | Balustrade Modification Along AFC Gate Line | สหชาติ | 0 | 0 | 2026-09-20 | 2026-06-30 | 10% | Late | 2026-08-15 | 50% | Late | 0 | 0% | 0% | 2026-11-06 | 0% | On Schedule | 0 | 0% | 0% | 2026-10-07 | 0% | Late | 2026-11-13 | 0% | On Schedule | 2026-11-30 | 0% | On Schedule | จัดเตรียมแบบ ออกPPR Oct-26 | MDW-39279 | MDW-69309 | MDW-69310
87 | MDW-39278 | Lot01 | AFC4 | AFC | Underfloor Embedded Duct Modification for AFC Gates Line | สหชาติ | 0 | Depot | 2026-09-20 | 2026-01-30 | 100% | Completed | 2026-04-02 | 67% | Late | 0 | 0% | 0% | 2026-10-09 | 81% | Late | 0 | 0% | 0% | 2026-09-30 | 0% | Late | 2026-10-16 | 0% | Late | 2026-10-24 | 0% | Late | 0 | MDW-39278 | MDW-69307 | MDW-69308
88 | MDW-39002 | Lot01 | SIG1 | SIG | Test Track Shelters and Test Track Building | สหชาติ | 0 | 0 | 2026-06-22 | 2025-11-22 | 100% | Completed | 2026-01-18 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-04-15 | 100% | Completed | 0 | 0% | 0% | 2026-05-15 | 100% | Completed | 2026-06-08 | 100% | Completed | 2026-09-30 | 0% | Late | 0 | MDW-39002 | MDW-69003 | MDW-69004
89 | MDW-39293 | Lot01 | SIG2 | SIG | Rearrangement of track crossing walkway at stabling yard to consistent with the layout of 4-car train parking | กำพล | 0 | Depot | 2026-06-22 | 2025-11-30 | 100% | Completed | 2025-12-30 | 100% | Completed | 0 | 0% | 0% | 2026-03-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 50% | Late | 2026-10-07 | 0% | Late | 2026-10-30 | 0% | On Schedule | 0 | MDW-39293 | MDW-69337 | MDW-69338
90 | MDW-39288 | Lot01 | SIG3 | SIG | Point Machine Foundation Construction | กำพล | 0 | 0 | 2026-08-21 | 2025-11-21 | 100% | Completed | 2025-12-30 | 100% | Completed | 0 | 0% | 0% | 2026-03-19 | 100% | Completed | 0 | 0% | 0% | 2026-09-23 | 25% | Late | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late | 0 | MDW-39288 | MDW-69327 | MDW-69328
91 | MDW-39001 | Lot01 | SIG4 | SIG | Modification of Depot Track Route Line to Stabling Yard | สู่โชค | 0 | Depot | 2026-06-22 | 2025-10-30 | 100% | Completed | 2025-11-29 | 100% | Completed | 0 | 0% | 0% | 2026-05-28 | 95% | Late | 0 | 0% | 0% | 2026-09-30 | 50% | Late | 2026-10-07 | 0% | Late | 2026-10-30 | 0% | On Schedule | คงเหลือเก็บงาน Progress by ช.ธนัท | MDW-39001 | MDW-69001 | MDW-69002
92 | MDW-39287 | Lot01 | SIG5 | SIG | Strobe Light at Buffer Stops | ประธาน | 0 | Depot | 2026-08-21 | 2026-05-30 | 100% | Completed | 2026-06-29 | 100% | Completed | 0 | 0% | 0% | 2026-08-28 | 100% | Completed | 0 | 0% | 0% | 2026-03-14 | 100% | Completed | 2026-06-30 | 0% | Late | 2026-09-30 | 0% | Late | 0 | MDW-39287 | MDW-69323 | MDW-69324
93 | DWE-39016 | Lot01 | DWE1 | DWE | Diesel Fuel Storage Tank for Maintenance Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-01-16 | 100% | Completed | 2026-06-30 | 100% | Completed | 2026-07-31 | 100% | Completed | 2026-08-09 | 0% | Late | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39016 | DWE-69016 | DWE-69116
94 | DWE-39011 | Lot01 | DWE2 | DWE | Movable Height Maintenance Platform Vehicle (Boom Lift) | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-08-06 | 100% | Completed | 2025-12-31 | 100% | Completed | 2026-06-30 | 100% | Completed | 2026-07-09 | 0% | Late | 2026-05-22 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late | Test 9-15/11/26 | DWE-39011 | DWE-69011 | DWE-69111
95 | DWE-39012 | Lot01 | DWE3 | DWE | Fork Lift Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-03-31 | 100% | Completed | 2026-06-01 | 100% | Completed | 2026-06-30 | 100% | Completed | 2026-07-30 | 0% | Late | 2026-09-30 | 0% | Late | 2026-10-07 | 0% | Late | 2026-10-28 | 0% | Late | Test 9-15/11/26 | DWE-39012 | DWE-69012 | DWE-69112
96 | DWE-39015 | Lot01 | DWE4 | DWE | Compressed Air System and Portable Air Compressor for Depot | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-01-10 | 100% | Completed | 2026-02-15 | 100% | Completed | 2026-09-19 | 0% | Late | 2026-09-29 | 0% | Late | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39015 | DWE-69015 | DWE-69115
97 | DWE-39017 | Lot01 | DWE5 | DWE | Pallet Storage Shelves in Hazardous Storage | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-12-16 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-05-31 | 100% | Completed | 2026-06-05 | 0% | Late | 2026-07-17 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late | Test 26-30/10/26 | DWE-39017 | DWE-69017 | DWE-69117
98 | DWE-39017 | Lot01 | DWE6 | DWE | Pallet Storage in Main Storage Room | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-12-16 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-05-31 | 100% | Completed | 2026-06-05 | 0% | Late | 2026-07-17 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late | Test 26-30/10/26 | DWE-39017 | DWE-69017 | DWE-69117
99 | DWE-39017 | Lot01 | DWE7 | DWE | Two-Tier Shelf | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-12-16 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-05-31 | 100% | Completed | 2026-06-05 | 0% | Late | 2026-07-17 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late | Test 26-30/10/26 | DWE-39017 | DWE-69017 | DWE-69117
100 | DWE-39017 | Lot01 | DWE8 | DWE | Tool Storage | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2025-12-16 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-05-31 | 100% | Completed | 2026-06-05 | 0% | Late | 2026-07-17 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late | Test 26-30/10/26 | DWE-39017 | DWE-69017 | DWE-69117
101 | DWE-39018 | Lot01 | DWE9 | DWE | Repair Equipment | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-07-31 | 50% | Late | 2026-10-30 | 70% | On Schedule | 2027-03-03 | 0% | On Schedule | 2027-04-02 | 0% | On Schedule | 2027-03-03 | 0% | On Schedule | 2027-04-09 | 0% | On Schedule | 2027-05-02 | 0% | On Schedule | คงเหลือจัดส่งอุปกรณ์ | DWE-39018 | DWE-69018 | DWE-69118
102 | DWE-39020 | Lot01 | DWE10 | DWE | Oil & Grease Disposal | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-01-16 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-03-31 | 100% | Completed | 2026-07-05 | 0% | Late | 2026-09-30 | 0% | Late | 2026-10-07 | 0% | Late | 2026-10-28 | 0% | Late | Test 9-15/11/26 | DWE-39020 | DWE-69020 | DWE-69120
103 | DWE-39020 | Lot01 | DWE11 | DWE | Grease Dispensers | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-01-16 | 100% | Completed | 2026-04-28 | 100% | Completed | 2026-05-25 | 100% | Completed | 2026-07-05 | 0% | Late | 2026-09-30 | 0% | Late | 2026-10-07 | 0% | Late | 2026-10-28 | 0% | Late | Test 9-15/11/26 | DWE-39020 | DWE-69020 | DWE-69120
104 | DWE-39020 | Lot01 | DWE12 | DWE | Waste Disposal | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-12-17 | 100% | Completed | 2026-01-16 | 100% | Completed | 2026-02-28 | 100% | Completed | 2026-03-31 | 100% | Completed | 2026-07-05 | 0% | Late | 2026-09-30 | 0% | Late | 2026-10-07 | 0% | Late | 2026-10-28 | 0% | Late | Test 9-15/11/26 | DWE-39020 | DWE-69020 | DWE-69120
105 | MDW-39305 | Lot01 | DWE13 | DWE | Safety Provision for Maintenance Pits | สหชาติ | 0 | Depot | 2026-09-20 | 2025-11-30 | 100% | Completed | 2026-04-29 | 100% | Completed | 0 | 0% | 0% | 2026-07-29 | 70% | Late | 0 | 0% | 0% | 2026-09-30 | 50% | Late | 2026-10-07 | 0% | Late | 2026-10-30 | 0% | On Schedule | งาน Handrail ที่ Pits Wheel Reprofling Plant ติดตั้งแล้วเหลืองานเก็บสี | MDW-39305 | MDW-69361 | MDW-69362
106 | DWE-39xxx | Lot01 | DWE14 | DWE | Pit Drainage System in Main Workshop | สมศักดิ์ | 0 | Depot | 2026-09-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39xxx | MDW-69361 | MDW-69362
107 | DWE-39023 | Lot01 | DWE15 | DWE | Provision of Civil Works and Building Services to support Train Washing Equipment | สหชาติ | 0 | Depot | 2026-08-01 | 2025-11-30 | 100% | Completed | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-05-31 | 100% | Completed | 0 | 0% | 0% | 2026-08-31 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-15 | 0% | Late | 0 | DWE-39023 | DWE-69023 | DWE-69123
108 | DWE-39013 | Lot01 | DWE16 | DWE | Overhead Traveling Crane | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-04-30 | 100% | Completed | 2026-03-20 | 100% | Completed | 0 | 0% | 0% | 2026-04-04 | 100% | Completed | 2026-05-26 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late | 0 | DWE-39013 | DWE-69013 | DWE-69113-513
109 | DWE-39009 | Lot01 | DWE17 | DWE | Vehicle Inspection and Servicing Facilities | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-12-18 | 100% | Completed | 2026-09-07 | 100% | Completed | 0 | 0% | 0% | 2026-10-01 | 0% | Late | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39009 | DWE-69009 | DWE-69109
110 | DWE-39014 | Lot01 | DWE18 | DWE | Permanent Way Maintenance Facility | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-04-30 | 100% | Completed | 2027-02-28 | 100% | Completed | 2027-01-15 | 70% | On Schedule | 0 | 0% | 0% | 2027-03-30 | 0% | On Schedule | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39014 | DWE-69014 | DWE-69114
111 | - | Lot01 | DWE19 | DWE | Permanent Way Vehicles | สมศักดิ์ | 0 | Depot | 2026-09-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
112 | DWE-39001 | Lot01 | DWE19.1 | DWE | Shunting Locomotive | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-12-18 | 100% | Completed | 2026-12-15 | 50% | On Schedule | 0 | 0% | 0% | 2026-12-30 | 0% | On Schedule | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39001 | DWE-69001 | DWE-69101
113 | DWE-39002 | Lot01 | DWE19.2 | DWE | Tunnel Inspection and Cleaning Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 0% | Late | 2025-12-18 | 100% | Completed | 2026-12-30 | 40% | On Schedule | 0 | 0% | 0% | 2026-10-11 | 0% | Late | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39002 | DWE-69002 | DWE-69102
114 | DWE-39003 | Lot01 | DWE19.3 | DWE | Hi/Rail Maintenance Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-12-18 | 100% | Completed | 2026-11-30 | 55% | On Schedule | 0 | 0% | 0% | 2026-12-16 | 0% | On Schedule | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39003 | DWE-69003 | DWE-69103
115 | DWE-39004 | Lot01 | DWE19.4 | DWE | Flat wagon | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-12-18 | 100% | Completed | 2026-10-30 | 68% | On Schedule | 0 | 0% | 0% | 2026-08-11 | 0% | Late | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39004 | DWE-69004 | DWE-69104
116 | DWE-39005 | Lot01 | DWE19.5 | DWE | Re-railing Equipment | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-11-10 | 100% | Completed | 2026-07-15 | 90% | Late | 0 | 0% | 0% | 2026-08-31 | 0% | Late | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39005 | DWE-69005 | DWE-69105
117 | DWE-39006 | Lot01 | DWE19.6 | DWE | Self-Propelled Rail Based Inspection Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 100% | Completed | 2025-12-18 | 100% | Completed | 2026-11-03 | 55% | On Schedule | 0 | 0% | 0% | 2026-12-16 | 0% | On Schedule | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39006 | DWE-69006 | DWE-69106
118 | DWE-39007 | Lot01 | DWE19.7 | DWE | Rail Head Grinding Machine Vehicle | สมศักดิ์ | 0 | Depot | 2026-09-20 | 2025-08-31 | 0% | Late | 2025-12-18 | 100% | Completed | 2027-07-31 | 0% | On Schedule | 0 | 0% | 0% | 2027-08-31 | 0% | On Schedule | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39007 | DWE-69007 | DWE-69107
119 | DWE-39008 | Lot01 | DWE19.8 | DWE | Multi Measuring Rail Vehicle | สมศักดิ์ | 0 | 0 | 2026-09-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39008 | DWE-69008 | DWE-69108
120 | DWE-39010 | Lot01 | DWE19.9 | DWE | High Work Inspection Vehicle | สมศักดิ์ | 0 | 0 | 2026-09-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | DWE-39010
121 | - | Lot01 | DWE20 | DWE | Building Maintenance Vehicle | - | 0 | 0 | 2026-09-20 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
122 | EPS-39001 | Lot01 | PSY1 | PSY | Diesel Fuel Storage Tanks for Power Generators | สมศักดิ์ | 0 | 0 | 2026-03-24 | 2026-01-16 | 100% | Completed | 2026-03-31 | 100% | Completed | 2026-03-31 | 100% | Completed | 2026-06-30 | 75% | Late | 2026-07-10 | 0% | Late | 2026-10-23 | 0% | Late | 2026-10-30 | 0% | On Schedule | 2026-11-20 | 0% | On Schedule | คงเหลืองานเดินท่อและ Pump น้ำมัน | EPS-39001 | EPS-69001 | EPS-69002
123 | PSY-39001-9 | Lot01 | PSY2 | PSY | GIS and BSS Building and Other Facilities | สหชาติ | 0 | 0 | 2026-03-24 | 2024-08-29 | 100% | Completed | 2024-09-28 | 69% | Late | 0 | 0% | 0% | 2025-12-04 | 100% | Completed | 0 | 0% | 0% | 2026-09-23 | 100% | Completed | 2026-09-30 | 100% | Completed | 2026-10-21 | 50% | Late | 0 | PSY-39001 | PSY-69001 | PSY-69002
124 | PSY-39011 | Lot01 | PSY3 | PSY | Steel Grating Raised Floor for EE Panel | สหชาติ | 0 | 0 | 2026-03-24 | 2024-09-30 | 100% | Completed | 2024-10-30 | 75% | Late | 0 | 0% | 0% | 2025-07-14 | 100% | Completed | 0 | 0% | 0% | 2026-06-14 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late | 0 | PSY-39011 | PSY-69015 | PSY-69016
125 | - | Lot01 | PSY4 | PSY | Trapping Box between PSY Service Sub Station (SSS) and Low Volt (LV) System | - | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
126 | SCA-39200 | Lot01 | SCA1 | SCA | Modification of BEMS to receive PSD Signal on East Section | ธารทิพย์ | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | SCA-39200 | SCA-69200 | SCA-69201
127 | - | Lot01 | SCA2 | SCA | Modification of Escalator Interface Point with CCTV and SCADA, East Section | - | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
128 | - | Lot01 | SCA3 | SCA | Magnetic of Fire Alarm System Interface Point with CCTV and SCADA | - | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
129 | SCA-39203 | Lot01 | SCA4 | SCA | Add/Modify Civil Scada Hardwire for all Station | ประธาน/ธารทิพย์ | 0 | 0 | 2026-08-21 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | SCA-39203 | SCA-69206 | SCA-69207
130 | COM-39200 | Lot01 | COM1 | COM | Magnetic Door Lock | มนตรี | 0 | 0 | 2026-08-21 | 2025-06-30 | 100% | Completed | 2026-05-15 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 27.25% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule | กำลังดำเนินการ Progress by CIP | COM-39200 | COM-69200 | COM-69201
131 | MDW-39283 | Lot01 | COM2 | COM | Intercom System in Cash Handling Room (if require) | บัณฑิต | 0 | 0 | 2026-12-19 | 2025-09-30 | 100% | Completed | 2026-06-30 | 50% | Late | 0 | 0% | 0% | 2026-10-31 | 0% | On Schedule | 2026-12-30 | 0% | On Schedule | 2026-09-30 | 0% | Late | 2026-11-07 | 0% | On Schedule | 2026-11-28 | 0% | On Schedule | รอพื้นที่เข้าติดตั้ง | MDW-39283 | MDW-69317 | MDW-69318
132 | COM-39001 | Lot01 | COM3 | COM | Walk-Through Metal Detector System (WTMD), 1 per entrance | มนตรี | 0 | 0 | 2026-11-19 | 2025-08-31 | 0% | Late | 2026-06-30 | 0% | Late | 0 | 0% | 0% | 2027-02-28 | 0% | On Schedule | 0 | 0% | 0% | 2027-01-29 | 0% | On Schedule | 2027-03-07 | 0% | On Schedule | 2027-03-28 | 0% | On Schedule | รอออก PPR อยู่ระหว่างการตรวจสอบสินค้า | COM-39001 | COM-69001 | COM-69002
133 | MDW-39284 | Lot01 | COM4 | COM | Traveling Cable in all Lifts | มนตรี | 0 | 0 | - | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39284 | MDW-69319 | MDW-69320
134 | MDW-39304 | Lot01 | COM5 | COM | MEA Radio | ประธาน | 0 | 0 | 2026-09-20 | 2026-01-30 | 100% | Completed | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-06-30 | 95% | Late | 2026-09-30 | 0% | Late | 2026-09-23 | 0% | Late | 2026-10-07 | 0% | Late | 2026-10-30 | 0% | On Schedule | รอเฟอร์นิเจอร์ Fore cast Dec-26 | MDW-39304 | COM-69202 | COM-69203
135 | COM-39004 | Lot01 | COM6 | COM | Main Cable Containment for M&E Dedicated communication link to MRTA Head Quarter | มนตรี | 0 | 0 | 2026-09-20 | 2026-01-31 | 100% | Completed | 2026-02-28 | 100% | Completed | 0 | 0% | 0% | 2026-08-31 | 75% | Late | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | COM-39004 | COM-69005 | COM-69006
136 | AFC-39001 | Lot01 | COM7 | COM | Mini Paging in Ticket Office | บัณฑิต | 0 | 0 | 2026-12-19 | 2025-09-10 | 100% | Completed | 2026-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 0% | Late | 2026-11-30 | 0% | On Schedule | 2026-10-31 | 0% | On Schedule | 2026-12-07 | 0% | On Schedule | 2026-12-28 | 0% | On Schedule | ของมาแล้ว รอพื้นที่เข้าติดตั้ง | AFC-39002 | AFC-69003 | AFC-69004
137 | MDW-39285 | Lot01 | COM8 | COM | Provision of Cable Containment between OCC ORL and OCC BL | มนตรี | 0 | 0 | 2026-07-22 | 0 | 0% | 0% | 0% | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39285
138 | COM-39005 | Lot01 | COM9 | COM | Power Distribution for M&E Systems at MRTA Head Quarter | มนตรี | 0 | 0 | 2026-09-20 | 2026-03-31 | 100% | Completed | 2026-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | COM-39005 | COM-69007 | COM-69008
139 | COM-39205 | Lot01 | COM10 | COM | Underground Cable Containment at Public Areas (if require) | มนตรี | 0 | 0 | 2026-08-21 | 2026-04-30 | 100% | Completed | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 100% | Completed | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39205 | MDW-69200 | MDW-69205
140 | - | Lot01 | COM11 | COM | Intercom at Ticket Issuing Machine | บัณฑิต | 0 | Depot | - | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
141 | RST-39004,8 | Lot01 | RST1 | RST | Driver Training Simulator | ธัญวิทย์ | 0 | Depot | 2026-09-20 | 2025-05-30 | 100% | Completed | 2025-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 81% | On Schedule | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | RST-39004,8
142 | MDW-39500 | Lot02 | MO-CK1.1 | MO-CK | Store Modification Works at Main Workshop - Civil&AR | สหชาติ | 0 | Depot | 2026-06-03 | 2026-02-27 | 100% | Completed | 2026-03-30 | 100% | Completed | 0 | 0% | 0% | 2026-05-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 50% | Late | 2026-10-07 | 100% | Completed | 2026-10-30 | 0% | On Schedule | 0 | MDW-39500 | MDW-69500 | MDW-69501
143 | MDW-39501 | Lot02 | MO-CK1.2 | MO-CK | Store Modification Works at Main Workshop - Building Services | ประธาน | 0 | Depot | 2026-06-04 | 2026-02-12 | 100% | Completed | 2026-03-30 | 100% | Completed | 0 | 0% | 0% | 2026-05-28 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 0% | Late | 2026-10-07 | 100% | Completed | 2026-10-30 | 0% | On Schedule | รอสรุปตำแหน่ง Power Plug ชาร์จโฟลคลิฟท์ Oct-26 | MDW-39501 | MDW-69502 | MDW-69503
144 | MDW-39503 | Lot02 | MO-CK2 | MO-CK | New MMC at Admin Building - Civil&AR | สหชาติ | 0 | Depot | 2026-08-03 | 2026-04-14 | 100% | Completed | 2026-05-15 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 50% | Late | 2026-09-30 | 0% | Late | 2026-10-30 | 0% | On Schedule | กำลังทำเอกสาร Test Report | MDW-39503 | MDW-69506 | MDW-69507
145 | MDW-39504 | Lot02 | MO-CK3 | MO-CK | Move or link Workstation and control panel to MMC room at admin C 2nd floor | ประธาน | 0 | Depot | 2026-08-02 | 2026-02-28 | 100% | Completed | 2026-04-15 | 100% | Completed | 0 | 0% | 0% | 2026-08-31 | 90% | Late | 0 | 0% | 0% | 2026-09-30 | 0% | Late | 2026-09-30 | 0% | Late | 2026-10-30 | 0% | On Schedule | Fore cast Oct-26 | MDW-39504 | MDW-69508 | MDW-69509
146 | MDW-39543 | Lot02 | MO-CK4 | MO-CK | Bird & Rain Protection for Open space Admin C | สหชาติ | 0 | Depot | 2026-08-01 | 2026-04-29 | 100% | Completed | 2026-05-30 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 50% | Late | 2026-09-30 | 0% | Late | 2026-10-30 | 0% | On Schedule | 0 | MDW-39543 | MDW-69586 | MDW-69587
147 | MDW-39547 | Lot02 | MO-CK5 | MO-CK | Relocate door in front of toilet and build partition wall to conceal the view in side of toilet | สหชาติ | 0 | Depot | 2026-08-02 | 2026-05-14 | 100% | Completed | 2026-06-14 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-15 | 100% | Completed | 2026-10-07 | 0% | Late | 2026-10-30 | 0% | On Schedule | 0 | MDW-39547 | MDW-69594 | MDW-69595
148 | MDW-39547 | Lot02 | MO-CK6 | MO-CK | Modify Lockset the emergency door to be used for passage between the 2nd and 3rd floors inside the building. | สหชาติ | 0 | Depot | 2026-08-03 | 2026-04-29 | 100% | Completed | 2026-06-14 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-01 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late | 0 | MDW-39547 | MDW-69594 | MDW-69595
149 | MDW-39556 | Lot02 | MO-CK7 | MO-CK | Addition small power for lounge and pantry room at 2nd floor and Hall and observation room at 3nd floor | ประธาน | 0 | Depot | 2026-08-04 | 2026-05-14 | 100% | Completed | 2026-06-14 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-05-05 | 100% | Completed | 2026-09-30 | 100% | Completed | 2026-10-21 | 100% | Completed |  | MDW-39556 | MDW-69612 | MDW-69613
150 | MDW-39548 | Lot02 | MO-CK8 | MO-CK | Air Condition for using store room to be pantry room. 2nd floor | ประธาน | 0 | Depot | 2026-08-05 | 2026-04-29 | 100% | Completed | 2026-06-14 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-03-24 | 100% | Completed | 2026-09-30 | 100% | Completed | 2026-07-10 | 100% | Completed |  | MDW-39548 | MDW-69596 | MDW-69597
151 | MDW-39552 | Lot02 | MO-CK9 | MO-CK | Walk Way Hand rail high 90 cm 1 side (144 m. x 7 route) | สหชาติ | 0 | Depot | 2026-10-01 | 2026-05-30 | 100% | Completed | 2026-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 98.77% | Late | 0 | 0% | 0% | 2026-09-30 | 50% | Late | 2026-10-07 | 0% | Late | 2026-10-30 | 0% | On Schedule | คงเหลืองานคอนกรีตทางเดินข้ามราง | MDW-39552 | MDW-69604 | MDW-69605
152 | MDW-39544 | Lot02 | MO-CK10 | MO-CK | Barbed wire fence Viaduct CE CW | บัณฑิต/สหชาติ | พี่ต่อ | Depot | 2027-01-01 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39544 | MDW-69588 | MDW-69589
153 | MDW-39545 | Lot02 | MO-CK11 | MO-CK | Chain Link at Cut & Cover 600m. | สหชาติ | พรพรหม | Depot | 2026-06-01 | 2026-02-27 | 100% | Completed | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-08-31 | 100% | Completed | 0 | 0% | 0% | 2026-08-01 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late | มีงานเพิ่มอีก 18 แผง | MDW-39545 | MDW-69590 | MDW-69591
154 | MDW-39546 | Lot02 | MO-CK12 | MO-CK | Chain Link under slab high 1.70 m | สหชาติ | 0 | 0 | 2027-01-01 | 2026-06-30 | 100% | Completed | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 67.27% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 50% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule | เริ่มติดตั้ง Chainlink แล้ว | MDW-39546 | MDW-69592 | MDW-69593
155 | MDW-39550 | Lot02 | MO-CK13.1 | MO-CK | Satellite Store at OR21 - Civil & AR | สหชาติ | 0 | 0 | 2027-01-02 | 2026-08-30 | 100% | Completed | 2026-10-15 | 0% | Late | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 100% | Completed | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule | 0 | MDW-39550 | MDW-69600 | MDW-695601
156 | MDW-39549 | Lot02 | MO-CK13.2 | MO-CK | Maintenance Room and Satellite Store at Stations - Building Services | ประธาน | 0 | 0 | 2027-01-03 | 2026-08-30 | 100% | Completed | 2026-10-15 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 80% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 100% | Completed | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule | 0 | MDW-39549 | MDW-69598 | MDW-69599
157 | MDW-39551 | Lot02 | MO-CK14 | MO-CK | Modify Cleaner room at OR29 to be Train crew Standby office with facility system | ประธาน | 0 | Depot | 2026-07-01 | 2026-03-14 | 100% | Completed | 2026-04-29 | 100% | Completed | 0 | 0% | 0% | 2026-06-30 | 95% | Late | 0 | 0% | 0% | 2026-09-30 | 100% | Completed | 2026-10-07 | 0% | Late | 2026-10-30 | 0% | On Schedule | 0 | MDW-39551 | MDW-69602 | MDW-69603
158 | MDW-39295 | Lot02 | MO-CK15.1 | MO-CK | Epoxy Floor Installation and Curb Installation at the Entrance - Civil & AR | สหชาติ | 0 | Depot | 2026-05-01 | 2026-01-27 | 100% | Completed | 2026-02-27 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 50% | Late | 2026-10-07 | 100% | Completed | 2026-10-30 | 0% | On Schedule | 0 | MDW-39295 | MDW-69341 | MDW-69342
159 | MDW-39296 | Lot02 | MO-CK15.2 | MO-CK | Change Electrical Equipment to be Explosion-proof type - Building Services | ประธาน | 0 | Depot | 2026-05-01 | 2025-12-13 | 100% | Completed | 2026-01-28 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 90% | Late | 0 | 0% | 0% | 2026-09-30 | 0% | Late | 2026-10-07 | 0% | Late | 2026-10-30 | 0% | On Schedule | Fore cast Nov-26 | MDW-39296 | MDW-69343 | MDW-69344
160 | DWE-39024 | Lot02 | MO-CK16 | MO-CK | Dangerous waste Storage 30 x 5 m. =10 room | สหชาติ | 0 | Depot | 2026-05-01 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-07-15 | 100% | Completed | 2026-06-08 | 100% | Completed | 2026-09-30 | 0% | Late | 0 | DWE-39024 | DWE-69024 | DWE-69124
161 | 0 | Lot02 | MO-CK17 | MO-CK | Safety Sign all Depot Area building | สหชาติ | 0 | Depot | 2026-05-01 | 2025-11-28 | 100% | Completed | 2026-06-15 | 100% | Completed | 2026-09-20 | 27% | Late | 2026-10-15 | 0% | Late | 0 | 0% | 0% | 0 | 0% | Late | 0 | 0% | Late | 0 | 0% | Late | GRS |  | 0 | 0
162 | 0 | Lot02 | MO-CK18 | MO-CK | Emergency escape route map | สหชาติ | 0 | Depot | 2027-01-01 | 2026-09-30 | 0% | Late | 2026-10-30 | 50% | On Schedule | 2026-12-31 | 0% | On Schedule | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule | GRS |  | 0 | 0
163 | 0 | Lot02 | MO-CK19 | MO-CK | Traffic Line Marking (Thermoplastic Paint) | สหชาติ | 0 | Depot | 2026-05-01 | 2026-04-30 | 100% | Completed | 2026-06-15 | 100% | Completed | 2026-10-15 | 100% | Completed | 2026-10-15 | 25% | Late | 0 | 0% | 0% | 0 | 0% | Late | 0 | 0% | Late | 0 | 0% | Late | GRS |  | 0 | 0
164 | 0 | Lot02 | MO-CK20 | MO-CK | Emergency Car Parking location Painting in front of MWS | สหชาติ | 0 | Depot | 2026-05-01 | 2026-04-30 | 100% | Completed | 2026-06-15 | 100% | Completed | 2026-10-15 | 0% | Late | 2026-10-15 | 0% | Late | 0 | 0% | 0% | 0 | 0% | Late | 0 | 0% | Late | 0 | 0% | Late | GRS |  | 0 | 0
165 | GRS-39022 | Lot02 | MO-CK21 | MO-CK | Safety Line painting in MWS, Stabling Area, P-way, Track | สหชาติ | 0 | Depot | 2027-01-01 | 2026-06-01 | 100% | Completed | 2026-08-01 | 100% | Completed | 2026-10-15 | 100% | Completed | 2026-12-31 | 81% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule | GRS | GRS-39022 | GRS-69001 | GRS-69022
166 | 0 | Lot02 | MO-CK22 | MO-CK | Fire escape stairs level signs in the Depot, VS and IVS areas | สหชาติ | 0 | Depot | 2027-01-01 | 2026-09-30 | 50% | Late | 2026-10-31 | 0% | On Schedule | 2026-10-20 | 0% | Late | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule | GRS |  | 0 | 0
167 | DWE-39026 | Lot02 | MO-CK23 | MO-CK | General waste Storage 22 x 5 m | สหชาติ | 0 | Depot | 2026-05-01 | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-07-15 | 100% | Completed | 2026-06-08 | 100% | Completed | 2026-09-30 | 0% | Late | 0 | DWE-39026 | DWE-69026 | DWE-69126
168 | 0 | Lot02 | MO-CK24 | MO-CK | Modify Traffic paint and traffic sign | สหชาติ | 0 | 0 | 2026-05-01 | 2026-04-30 | 100% | Completed | 2026-06-15 | 100% | Completed | 2026-10-15 | 64% | Late | 2026-10-15 | 13% | Late | 0 | 0% | 0% | 0 | 0% | Late | 0 | 0% | Late | 0 | 0% | Late | GRS |  | 0 | 0
169 | 0 | Lot02 | MO-CK25 | MO-CK | Station Area sign 28 stations | สหชาติ | 0 | 0 | 2026-05-01 | 2026-06-15 | 80% | Late | 2026-06-30 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-12-20 | 0% | On Schedule | 0 | 0% | 0% | 0 | 0% | Late | 2026-10-07 | 0% | Late | 0 | 0% | Late | GRS |  | 0 | 0
170 |  | Lot02 | MO-CK26 | MO-CK | Safety and warning signage for lift and escalator at all station | สหชาติ | 0 | Depot | 2027-01-01 | 2026-06-16 | 100% | Completed | 2026-07-17 | 100% | Completed | 2027-01-31 | 76% | On Schedule | 2027-02-28 | 26% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 0 | 0% | Late | 0 | 0% | Late | GRS
171 | MDW-39532 | Lot02 | MO-CK27 | MO-CK | Spike fence for Depot slab | สหชาติ | 0 | Depot | 2027-01-01 | 2026-07-31 | 70% | Late | 2026-08-31 | 0% | Late | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule | อยู่ระหว่างส่งขออนุมัติแบบรอ Approve | MDW-39532 | MDW-69564 | MDW-69565
172 | 0 | Lot02 | MO-CK28 | MO-CK | Bird net and Flashing at MWS and Skywalk to Stabling yard | สหชาติ | 0 | 0 | 2026-05-01 |  |  | 0% |  |  | 0% | 0 | 0% | 0% |  |  | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
173 | MDW-39541 | Lot02 | MO-CK29 | MO-CK | Fire Alarm Manual Call Point signage at all elevated station | สหชาติ | 0 | 0 | 2027-01-01 |  |  | 0% | 2026-07-30 | 100% | Completed | 0 | 0% | 0% |  |  | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  | MDW-39541 | MDW-69582 | MDW-69583
174 | 0 | Lot02 | MO-CK30 | MO-CK | Lighting for sealed space under stairs and behind lift shaft at underground station | ประธาน | 0 | 0 | 2027-01-01 | 2026-10-14 | 0% | Late | 2026-11-14 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule | ไฟส่องสว่างสำหรับพื้นที่ปิดใต้บันไดและด้านหลังช่องลิฟต์ที่สถานีรถไฟใต้ดิน |  | 0 | 0
175 | 0 | Lot02 | MO-CK31 | MO-CK | Modify the access door of sealed space (under-stairs room) with a Sump Pump or ESPS cabinet | สหชาติ | 0 | 0 | 2027-01-01 | 2026-07-16 | 0% | Late | 2026-08-16 | 0% | Late | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule | 0 |  | 0 | 0
176 | 0 | Lot02 | MO-CK32 | MO-CK | Lighting to the sealed space (under-stairs room) with a Sump Pump or ESPS cabinet | ประธาน | 0 | Depot | 2027-01-01 | 2026-11-03 | 0% | On Schedule | 2026-12-04 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule | ซื้อสปอร์ตไลท์+แบต จำนวน 4 ชุด แทนการลากสายไฟ |  | 0 | 0
177 | 0 | Lot02 | MO-CK33 | MO-CK | Additional lighting in areas where the lux level does not meet occupational health standards | ประธาน | 0 | Depot | 2027-01-01 | 2026-09-14 | 100% | Completed | 2026-10-15 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 95% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule | 0 |  | 0 | 0
178 | 0 | Lot02 | MO-CK34 | MO-CK | Provide and install confined space signage for Station and Depot | สหชาติ | 0 | 0 | 2027-01-01 | 2026-08-15 | 100% | Completed | 2026-09-15 | 100% | Completed | 2027-01-31 | 76% | On Schedule | 2027-02-28 | 26% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 0 | 0% | Late | 0 | 0% | Late | GRS |  | 0 | 0
179 |  | Lot02 | MO-CK35 | MO-CK | Build room for Train crew main office at OR18 with office area, resting area, meeting room, pantry, toilet and locker room | สหชาติ/บัณฑิต/ประธาน | 0 | Depot | - |  |  | 0% |  |  | 0% | 0 | 0% | 0% |  |  | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0
180 |  | Lot02 | MO-CK36 | MO-CK | Dormitory Cable Containments (if any) | มนตรี | 0 | Depot | - |  |  | 0% |  |  | 0% | 0 | 0% | 0% |  |  | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0
181 | 0 | Lot02 | MO-CK37 | MO-CK | Provide Raise floor and building Service in Training &Simulator (OCC Admin) | สหชาติ | 0 | Depot | - | 0% | 0% | 0% |  |  |  | 0 | 0% | 0% |  |  | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
182 |  | Lot02 | MO-CK38 | MO-CK | Add N2 in Playback and Training Room and Backup Control Room | บุญประเสริฐ | 0 | Depot | - |  |  | 0% |  |  | 0% | 0 | 0% | 0% |  |  | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0
183 | MDW-39505 | Lot02 | MO-BEM1.1 | MO-BEM | Walkway from Main Work Shop to Stabling Area - Civil & AR | สหชาติ | 0 | Depot | 2026-08-02 | 2026-04-28 | 100% | Completed | 2026-05-29 | 92% | Late | 0 | 0% | 0% | 2026-09-30 | 93% | Late | 0 | 0% | 0% | 2026-08-31 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late | คงเหลืองานมุงหลังคา Metal sheet | MDW-39505 | MDW-69510 | MDW-69511
184 | MDW-39506 | Lot02 | MO-BEM1.2 | MO-BEM | Walkway from Main Work Shop to Stabling Area - Building Services | ประธาน | 0 | Depot | 2026-08-02 | 2026-04-28 | 100% | Completed | 2026-05-29 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 0% | Late | 0 | 0% | 0% | 2026-09-23 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late | รองานหลังคา CIV Oct-26 | MDW-39506 | MDW-69512 | MDW-69513
185 | MDW-39507 | Lot02 | MO-BEM2 | MO-BEM | High Roof at Main Work Shop Entrance and Store | สหชาติ | 0 | Depot | 2026-08-01 | 2026-02-13 | 100% | Completed | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-01 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late | กำลังทำเอกสาร Test Report | MDW-39507 | MDW-69514 | MDW-69515
186 | MDW-39509 | Lot02 | MO-BEM3 | MO-BEM | High Roof at the entrance and exit of the under floor wheel lathe | สหชาติ | 0 | Depot | 2026-08-04 | 2026-02-13 | 100% | Completed | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-01 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late | กำลังทำเอกสาร Test Report | MDW-39509 | MDW-69518
187 | MDW-39511 | Lot02 | MO-BEM4.1 | MO-BEM | Maintenance Office Rooms at Main Workshop - Civil & AR | สหชาติ | 0 | Depot | 2026-07-03 | 2026-04-13 | 100% | Completed | 2026-05-14 | 100% | Completed | 0 | 0% | 0% | 2026-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-05-31 | 100% | Completed | 2026-09-30 | 100% | Completed | 2026-10-21 | 0% | Late | 0 | MDW-39511 | MDW-69522 | MDW-69523
188 | MDW-39512 | Lot02 | MO-BEM4.2 | MO-BEM | Maintenance Office Rooms at Main Workshop - Building Services | ประธาน | 0 | Depot | 2026-07-04 | 2026-04-13 | 100% | Completed | 2026-05-14 | 100% | Completed | 0 | 0% | 0% | 2026-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-23 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late | รอส่งงานกับ BEM | MDW-39512 | MDW-69524 | MDW-69525
189 | MDW-39513 | Lot02 | MO-BEM5 | MO-BEM | Install Concrete car barrier along the walkway in front of MWS building | สหชาติ | 0 | Depot | 2027-01-01 | 2026-10-14 | 100% | Completed | 2026-11-14 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 100% | Completed | 0 | 0% | 0% | 2026-12-01 | 50% | On Schedule | 2027-01-07 | 100% | Completed | 2027-01-28 | 0% | On Schedule | 0 | MDW-39513 | MDW-69526 | MDW-69527
190 | 0 | Lot02 | MO-BEM6 | MO-BEM | Handrail on top of the water tank on the rooftop of the Admin Building | สหชาติ | 0 | Depot | 2027-01-01 | 2026-10-19 | 100% | Completed | 2026-11-19 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule | 0 |  | 0 | 0
191 | 0 | Lot02 | MO-BEM7 | MO-BEM | Modify maintenance service door to the roof building to easier access while maintaining safe operational standards | สหชาติ | 0 | Depot | 2027-01-01 | 2026-10-19 | 50% | Late | 2026-11-19 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule | 0 |  | 0 | 0
192 | MDW-39536 | Lot02 | MO-BEM8 | MO-BEM | Company logo and Central Control Room sign in CCR room. | สหชาติ | 0 | Depot | 2026-05-01 | 2026-01-27 | 100% | Completed | 2026-03-14 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 50% | Late | 2026-10-07 | 0% | Late | 2026-10-30 | 0% | On Schedule | 0 | MDW-39536 | MDW-69572 | MDW-69573
193 | MDW-39536 | Lot02 | MO-BEM9 | MO-BEM | Soundproof insulation on the wall and structure and equipment in the CCR room. | สหชาติ | 0 | Depot | 2026-05-01 | 2026-01-12 | 100% | Completed | 2026-02-27 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 50% | Late | 2026-10-07 | 0% | Late | 2026-10-30 | 0% | On Schedule | 0 | MDW-39536 | MDW-69572 | MDW-69573
194 | MDW-39526 | Lot02 | MO-BEM10 | MO-BEM | Relocate Fire Hose Cabinet to be outside of the clearance gauge zone 17 set | ประธาน | 0 | Depot | 2026-05-01 | 2026-01-12 | 100% | Completed | 2026-02-27 | 100% | Completed | 0 | 0% | 0% | 2026-04-30 | 100% | Completed | 0 | 0% | 0% | 2026-03-18 | 100% | Completed | 2026-09-30 | 100% | Completed | 2026-05-15 | 100% | Completed |  | MDW-39526 | MDW-69552 | MDW-69553
195 | MDW-39528 | Lot02 | MO-BEM11.1 | MO-BEM | Washing Area in Cleaning Staff Room at Stabling Yard - Civil & AR | สหชาติ | 0 | Depot | 2026-08-03 | 2026-06-03 | 100% | Completed | 2026-07-04 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-01 | 100% | Completed | 2026-09-30 | 50% | Late | 2026-10-15 | 0% | Late | 0 | MDW-39528 | MDW-69556 | MDW-69557
196 | MDW-39529 | Lot02 | MO-BEM11.2 | MO-BEM | Washing Area in Cleaning Staff Room at Stabling Yard - Building Services | ประธาน | 0 | Depot | 2026-08-04 | 2026-04-14 | 100% | Completed | 2026-05-30 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-03-31 | 100% | Completed | 2026-07-01 | 100% | Completed | 2026-07-10 | 100% | Completed |  | MDW-39529 | MDW-69558 | MDW-69559
197 | MDW-39522 | Lot02 | MO-BEM12 | MO-BEM | Rain protection for Water treatment Building | สหชาติ | 0 | Depot | 2026-08-05 | 2026-04-29 | 100% | Completed | 2026-05-30 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-01 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late | 0 | MDW-39522 | MDW-69544 | MDW-69545
198 | MDW-39522 | Lot02 | MO-BEM13.1 | MO-BEM | Zero Discharge Water treatment in Depot - Civil & AR | สหชาติ | 0 | Depot | 2027-01-01 | 2026-08-15 | 100% | Completed | 2026-09-30 | 75% | Late | 0 | 0% | 0% | 2026-12-31 | 63% | On Schedule | 0 | 0% | 0% | 0 | 0% | 0% | 2027-01-07 | 0% | On Schedule | 0 | 0 | 0 |  | MDW-39522 | MDW-69544 | MDW-69545
199 | MDW-39530 | Lot02 | MO-BEM13.2 | MO-BEM | Zero Discharge Water treatment in Depot - Building Services | ประธาน | 0 | Depot | 2027-01-01 | 2026-08-15 | 100% | Completed | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 50% | On Schedule | 0 | 0% | 0% | 2026-10-30 | 100% | Completed | 2027-01-07 | 0% | On Schedule | 46415 | 0 | On Schedule | 0 | MDW-39530 | MDW-69560 | MDW-69561
200 | MDW-39516 | Lot02 | MO-BEM14.1 | MO-BEM | Modification Works : Walkway Bridge between BL Depot and ORL Depot - Civil & AR | สหชาติ | 0 | Depot | 2026-08-02 | 2026-02-28 | 100% | Completed | 2026-06-15 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 95% | Late | 0 | 0% | 0% | 2026-08-31 | 100% | Completed | 2026-10-07 | 0% | Late | 2026-10-21 | 0% | Late | คงเหลืองานติดตั้งสะพานและปรับพื้นที่ถนน | MDW-39516 | MDW-69532 | MDW-69533
201 | MDW-39517 | Lot02 | MO-BEM14.2 | MO-BEM | Modification Works : Walkway Bridge between BL Depot and ORL Depot - Building Services | ประธาน | 0 | Depot | 2026-08-03 | 2026-01-14 | 100% | Completed | 2026-03-01 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 10% | Late | 0 | 0% | 0% | 2026-08-31 | 100% | Completed | 2026-10-07 | 0% | Late | 2026-10-21 | 0% | Late | รองานหลังคา CIV Oct-26 | MDW-39517 | MDW-69534 | MDW-69535
202 | MDW-39514 | Lot02 | MO-BEM15.1 | MO-BEM | Roof for cars parking lots area (184 car)t - Civil & AR | สหชาติ | 0 | Depot | 2026-08-03 | 2026-02-28 | 100% | Completed | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-24 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late | กำลังทำเอกสาร Test Report | MDW-39514 | MDW-69528 | MDW-69529
203 | MDW-39515 | Lot02 | MO-BEM15.2 | MO-BEM | Roof for cars parking lots area (184 car) - Building Services | ประธาน | 0 | Depot | 2026-08-03 | 2026-02-28 | 100% | Completed | 2026-03-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-09-23 | 0% | Late | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late | รอส่งงานกับ BEM | MDW-39515 | MDW-69530 | MDW-69531
204 | MDW-39519 | Lot02 | MO-BEM16 | MO-BEM | Walkway roof and High roof across the road from Admin ORL to Depot slap | สหชาติ | 0 | Depot | 2026-08-01 | 2026-06-15 | 100% | Completed | 2026-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-10-31 | 57% | On Schedule | 0 | 0% | 0% | 2026-08-31 | 100% | Completed | 2026-11-07 | 0% | On Schedule | 2026-11-28 | 0% | On Schedule | คงเหลืองานโครงเหล็ก หลังคา และ Composite | MDW-39519 | MDW-69538 | MDW-69539
205 | MDW-39519 | Lot02 | MO-BEM17 | MO-BEM | Walkway roof to car park in front of admin ORL(3x5m.) | สหชาติ | 0 | Depot | 2026-08-01 | 2026-06-15 | 100% | Completed | 2026-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-10-31 | 70% | On Schedule | 0 | 0% | 0% | 2026-08-31 | 100% | Completed | 2026-11-07 | 0% | On Schedule | 2026-11-28 | 0% | On Schedule | คงเหลืองานโครงหลังคาและมุงหลังคา | MDW-39519 | MDW-69538 | MDW-69539
206 | MDW-39519 | Lot02 | MO-BEM18 | MO-BEM | Walkway roof over the footpath near depot slab (1.50 m. x 290 m.) and stair up to depot slap. | สหชาติ | 0 | Depot | 2026-08-01 | 2026-06-15 | 100% | Completed | 2026-06-30 | 100% | Completed | 0 | 0% | 0% | 2026-10-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-08-31 | 100% | Completed | 2026-11-07 | 0% | On Schedule | 2026-11-28 | 0% | On Schedule | รอ BEM สรุปว่ายกเลิกหรือทำ | MDW-39519 | MDW-69538 | MDW-69539
207 | MDW-39557 | Lot02 | MO-BEM19 | MO-BEM | Install Chain Link fence to enclose parking area | สหชาติ | 0 | Depot | 2026-10-01 | 2026-06-29 | 100% | Completed | 2026-07-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 0% | Late | 0 | 0% | 0% | 2026-09-30 | 90% | Late | 2026-10-07 | 0% | Late | 2026-10-28 | 0% | Late | 0 | MDW-39557 | MDW-69614 | MDW-69615
208 | MDW-39523 | Lot02 | MO-BEM20 | MO-BEM | Hose bib 1/2" 4 sets for Tree around Admin area | ประธาน | 0 | Depot | 2026-06-01 | 2026-04-23 | 100% | Completed | 2026-06-08 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-03-31 | 100% | Completed | 2026-09-30 | 100% | Completed | 2026-07-10 | 100% | Completed |  | MDW-39523 | MDW-69546 | MDW-69547
209 | - | Lot02 | MO-BEM21 | MO-BEM | Relocate Security Guard Box at Front Gate and Install Roof 3x5m. | สหชาติ | 0 | Depot | 2027-01-03 | 2026-07-31 | 100% | Completed | 2026-09-30 | 75% | Late | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  |  | 0 | 0
210 | MDW-39534 | Lot02 | MO-BEM21.1 | MO-BEM | Modification Works : Security Guard Box at ORL Depot Entrance - Civil & AR | สหชาติ | 0 | Depot | 2027-01-02 | 2026-07-31 | 100% | Completed | 2026-09-30 | 67% | Late | 0 | 0% | 0% | 2026-12-31 | 100% | Completed | 0 | 0% | 0% | 2026-12-01 | 50% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | MDW-39534 | MDW-69568 | MDW-69569
211 | MDW-39535 | Lot02 | MO-BEM21.2 | MO-BEM | Modification Works : Security Guard Box at ORL Depot Entrance - Building Services | ประธาน | 0 | Depot | 2027-01-03 | 2026-07-31 | 100% | Completed | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 50% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | MDW-39535 | MDW-69570 | MDW-69571
212 | MDW-39532 | Lot02 | MO-BEM22 | MO-BEM | Addition Spike fence for MRTA fence and Chain link at Klong Chourdyai 400m. | สหชาติ | 0 | Depot | 2027-01-01 | 2026-08-30 | 70% | Late | 2026-09-30 | 0% | Late | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | MDW-39532 | MDW-69564 | MDW-69565
213 | MDW-39527 | Lot02 | MO-BEM23 | MO-BEM | Hand sink with eye wash station | ประธาน | พี่ต่อ | Depot | 2027-01-01 | 2026-08-30 | 100% | Completed | 2026-10-15 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 100% | Completed | 0 | 0% | 0% | 2026-12-01 | 100% | Completed | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | MDW-39527 | MDW-69554 | MDW-69555
214 | MDW-39531 | Lot02 | MO-BEM24 | MO-BEM | Guard rail protection for Fire Hose Cabinet 8 set | สหชาติ | 0 | Depot | 2026-06-01 | 2026-03-14 | 100% | Completed | 2026-04-14 | 100% | Completed | 0 | 0% | 0% | 2026-08-15 | 100% | Completed | 0 | 0% | 0% | 2026-07-16 | 100% | Completed | 2026-09-30 | 100% | Completed | 2026-10-21 | 0% | Late |  | MDW-39531 | MDW-69562 | MDW-69563
215 | MDW-39557 | Lot02 | MO-BEM25.1 | MO-BEM | Chain Link Fence to divide controlled areas on Depot slab 3 m.x 485 m. - Civil & AR | สหชาติ | 0 | Depot | 2026-10-01 | 2026-06-14 | 100% | Completed | 2026-07-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 0% | Late | 0 | 0% | 0% | 2026-09-30 | 50% | Late | 2026-10-07 | 0% | Late | 2026-10-28 | 0% | Late |  | MDW-39557 | MDW-69614 | MDW-69615
216 | MDW-39520 | Lot02 | MO-BEM25.2 | MO-BEM | Chain Link Fence to divide controlled areas on Depot slab 3 m.x 485 m.- Building Services | ประธาน | 0 | Depot | 2026-10-01 | 2026-06-14 | 100% | Completed | 2026-07-30 | 100% | Completed | 0 | 0% | 0% | 2026-09-30 | 0% | Late | 0 | 0% | 0% | 2026-09-30 | 0% | Late | 2026-10-07 | 0% | Late | 2026-10-28 | 0% | Late |  | MDW-39520 | MDW-69540 | MDW-69541
217 | MDW-39518 | Lot02 | MO-BEM26 | MO-BEM | Street Lighting system area between MRTA Fence and Depot slab | ประธาน | 0 | Depot | 2026-08-01 | 2026-04-14 | 50% | Late | 2026-05-15 | 0% | Late | 0 | 0% | 0% | 2026-07-31 | 0% | Late | 0 | 0% | 0% | 2026-09-30 | 0% | Late | 2026-10-07 | 0% | Late | 2026-10-28 | 0% | Late |  | MDW-39518 | MDW-69536 | MDW-69537
218 | - | Lot02 | MO-BEM27 | MO-BEM | Compacted gravel walkway along the Test Track OR-BL 1.2 m. | สหชาติ | พรพรหม | Depot | 2027-01-01 | 2026-08-30 | 100% | Completed | 2026-09-30 | 0% | Late | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  |  | 0 | 0
219 | MDW-39524 | Lot02 | MO-BEM28.1 | MO-BEM | Walkway under Depot Slab for Maintenance Service - Civil & AR | สหชาติ | 0 | Depot | 2027-01-02 | 2026-09-14 | 100% | Completed | 2026-10-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 100% | Completed | 0 | 0% | 0% | 2026-12-01 | 50% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | MDW-39524 | MDW-69548 | MDW-69549
220 | MDW-39525 | Lot02 | MO-BEM28.2 | MO-BEM | Walkway under Depot Slab for Maintenance Service - Building Services | ประธาน | 0 | Depot | 2027-01-03 | 2026-09-14 | 100% | Completed | 2026-10-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 50% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | MDW-39525 | MDW-69550 | MDW-69551
221 | MDW-39521 | Lot02 | MO-BEM29 | MO-BEM | Walkway Bridge across the canal for Depot area inspection patrols 3 location | สหชาติ | 0 | Depot | 2027-01-01 | 2026-08-15 | 100% | Completed | 2026-09-30 | 67% | Late | 0 | 0% | 0% | 2026-12-31 | 95% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 100% | Completed | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | MDW-39521 | MDW-69542 | MDW-69543
222 | - | Lot02 | MO-BEM30 | MO-BEM | Cut down trees between Depot BL+ORL and MRTA Fence | สหชาติ | 0 | Depot | 2027-01-01 | 2026-10-29 | 0% | Late | 2026-11-29 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  |  | 0 | 0
223 | 0 | Lot02 | MO-BEM31 | MO-BEM | Provide facility system and interface to MMC room (Fire Alarm / CCTV / VMS / TEL / CASS / Radio / PA) | บัณฑิต | 0 | Depot | 2026-10-01 | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
224 | - | Lot02 | MO-BEM32 | MO-BEM | Stainless Guard rail balustrade for waiting area | สหชาติ | 0 | Depot | 2026-05-01 |  |  | 0% |  |  | 0% | 0 | 0% | 0% |  |  | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
225 | - | Lot02 | MO-BEM33 | MO-BEM | Concrete walkway 2 x 80 m. For fire escape route | สหชาติ | 0 | Depot | 2026-05-01 |  |  | 0% |  |  | 0% | 0 | 0% | 0% |  |  | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
226 | - | Lot02 | MO-BEM34 | MO-BEM | Access Gate (Full Height Turnstile) at 1st floor admin ORL | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  |  | 0 | 0
227 | - | Lot02 | MO-BEM35 | MO-BEM | Access Gate (Tripod with Swing Gate) at MWS Entrance | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  |  | 0 | 0
228 | - | Lot02 | MO-BEM36 | MO-BEM | Access Gate (Tripod with Swing Gate) at Admin 2nd floor connect to OCC | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  |  | 0 | 0
229 | - | Lot02 | MO-BEM37 | MO-BEM | Access Gate (Tripod with Swing Gate) on Klong Chourdyai bridge | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  |  | 0 | 0
230 | - | Lot02 | MO-BEM38 | MO-BEM | Access Gate (Tripod with roof covering) at parking lot OCC | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  |  | 0 | 0
231 | - | Lot02 | MO-BEM39 | MO-BEM | Access Gate (Tripod with roof covering) at Stair up to Depot slab | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  |  | 0 | 0
232 | - | Lot02 | MO-BEM40 | MO-BEM | Access Control (2 Factors, Card + Finger Print) at High Security rooms - CCR/PTR/Store | บัณฑิต | 0 | Depot | 2027-01-01 | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  |  | 0 | 0
233 | - | Lot02 | MO-BEM41 | MO-BEM | Link CCTV Landscape of all depot ORL area for MMC BL monitoring. | บัณฑิต | 0 | 0 | 2027-01-01 | 2026-11-28 | 0% | On Schedule | 2026-11-29 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-11-30 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  |  | 0 | 0
234 | - | Lot02 | MO-BEM42 | MO-BEM | Fire Suppression Control Panel Cover which located in tunnel | สู่โชค | 0 | 0 | 2027-01-01 |  |  | 0% |  |  | 0% | 0 | 0% | 0% |  |  | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0 | 0 |  |  | 0 | 0
235 | MDW-39537 | Lot02 | MO-BEM43 | MO-BEM | Handrails for ladder at IVS and Vent buildings | สหชาติ | 0 | 0 | 2026-09-01 | 2026-03-31 | 70% | Late | 2026-05-01 | 0% | Late | 0 | 0% | 0% | 2026-08-31 | 0% | Late | 0 | 0% | 0% | 2026-10-31 | 0% | On Schedule | 2026-11-15 | 0% | On Schedule | 2026-11-30 | 0% | On Schedule |  | MDW-39537 | MDW-69574 | MDW-69575
236 | MDW-39538 | Lot02 | MO-BEM44 | MO-BEM | Escalator Anti-Slide device for all station. | สหชาติ | 0 | 0 | 2026-09-01 | 2026-05-30 | 100% | Completed | 2026-06-30 | 100% | Completed | 2027-01-31 | 100% | Completed | 2027-02-28 | 70% | On Schedule | 0 | 0% | 0% | 2027-01-29 | 0% | On Schedule | 2027-02-28 | 0% | On Schedule | 2027-03-15 | 0% | On Schedule |  | MDW-39538 | MDW-69576 | MDW-69577
237 | MDW-39539 | Lot02 | MO-BEM45 | MO-BEM | Roof for control panel on vent building | สหชาติ | 0 | 0 | 2027-01-01 | 2026-09-14 | 70% | Late | 2026-10-30 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | MDW-39539 | MDW-69578 | MDW-69579
238 | MDW-39553 | Lot02 | MO-BEM46 | MO-BEM | Provide Standing plate or ladder to access the Fire Valve in at Omega points for all underground stations. | สหชาติ | 0 | Depot | 2027-01-01 | 2026-09-14 | 0% | Late | 2026-10-30 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | MDW-39553 | MDW-69606 | MDW-69607
239 | MDW-39540 | Lot02 | MO-BEM47 | MO-BEM | Water drop protection above UPS cabinet at station and Depot | สหชาติ | 0 | 0 | 2027-01-01 | 2026-09-14 | 0% | Late | 2026-10-30 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | MDW-39540 | MDW-69580 | MDW-69581
240 | MDW-39541 | Lot02 | MO-BEM48 | MO-BEM | Fire alarm manual call point cover in public area at all station | ประธาน | 0 | 0 | 2027-01-01 | 2026-09-14 | 50% | Late | 2026-10-30 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | MDW-39541 | MDW-69582 | MDW-69583
241 | MDW-39542 | Lot02 | MO-BEM49 | MO-BEM | Emergency stop button cover for escalator at all station. | สหชาติ | 0 | 0 | 2027-01-01 | 2026-09-14 | 0% | Late | 2026-10-30 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | MDW-39542 | MDW-69584 | MDW-69585
242 | 0 | Lot02 | MO-BEM50 | MO-BEM | Modify maintenance service door to the roof of OR13 vent building to easier access while maintaining safe operational standards | สู่โชค | 0 | Depot | 2027-01-01 | 2026-10-29 | 0% | Late | 2026-10-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  |  | 0 | 0
243 | MDW-39514 | Lot02 | MO-BEM51 | MO-BEM | Modify existing car park to be 220 motorcycle parking lots including floor painting and parking roof | สหชาติ | 0 | Depot | 2026-08-01 | 2026-01-29 | 100% | Completed | 2026-03-16 | 100% | Completed | 0 | 0% | 0% | 2026-07-31 | 100% | Completed | 0 | 0% | 0% | 2026-07-01 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-21 | 0% | Late |  | MDW-39514 | MDW-69528 | MDW-69529
244 | MDW-39534 | Lot02 | MO-BEM52 | MO-BEM | Modify the sidewalk for temporary parking at entrance | สหชาติ | 0 | Depot | 2027-01-01 | 2026-07-31 | 100% | Completed | 2026-09-30 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 100% | Completed | 0 | 0% | 0% | 2026-12-01 | 50% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | MDW-39534 | MDW-69568 | MDW-69569
245 | MDW-39554 | Lot02 | MO-BEM53.1 | MO-BEM | Modification Works : Security Guard Box at OCC Parking Area - Civil & AR | สหชาติ | 0 | Depot | 2027-01-02 | 2026-09-14 | 100% | Completed | 2026-10-31 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 50% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | MDW-39554 | MDW-69608 | MDW-69609
246 | MDW-39555 | Lot02 | MO-BEM53.2 | MO-BEM | Modification Works : Security Guard Box at OCC Parking Area - Building Services | ประธาน | 0 | 0 | 2027-01-02 | 2026-09-14 | 100% | Completed | 2026-10-31 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 50% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  | MDW-39555 | MDW-69610 | MDW-69611
247 | NoDrawing | Lot02 | MO-BEM54 | MO-BEM | Strengthen the Maintenance Walkway of the TEF fan | สหชาติ | 0 | 0 | 2027-01-01 | 2026-07-16 | 100% | Completed | 2026-08-16 | 100% | Completed | 0 | 0% | 0% | 2026-12-31 | 0% | On Schedule | 0 | 0% | 0% | 2026-12-01 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule | 2027-01-28 | 0% | On Schedule |  |  | 0 | 0
Lot 1 Test Report
[38 empty] | CK Pesonsible Person | Total | Completed | Late | On Schedule
[38 empty] | สหชาติ | 26 | 0 | 12 | 14
[38 empty] | ประธาน | 37 | 1 | 6 | 30
[38 empty] | สมศักดิ์ | 13 | 0 | 10 | 3
[38 empty] | กำพล | 9 | 0 | 3 | 6
[38 empty] | บัณฑิต | 4 | 0 | 1 | 3
[38 empty] | สู่โชค | 1 | 0 | 0 | 1
[38 empty] | มนตรี | 3 | 0 | 0 | 3
[38 empty] | มนต์ชัย | 1 | 0 | 0 | 1
[38 empty] | - | 2 | 0 | 1 | 1
Lot 2 Test Report
[38 empty] | CK Pesonsible Person | Total | Completed | Late | On Schedule
[38 empty] | สหชาติ | 60 | 0 | 23 | 37
[38 empty] | ประธาน | 25 | 5 | 6 | 14
[38 empty] | บัณฑิต | 8 | 0 | 0 | 8
[38 empty] | สู่โชค | 1 | 0 | 0 | 1

## ตารางสรุป Summary
Status Summary
Lot 1
Action stage | Total | Completed | Remain
Design | 114 | 102 | 12
Procurement | 115 | 99 | 16
Manufacturing/Delivery Process | 33 | 20 | 13
Construction/Installation | 103 | 65 | 38
T&C | 29 | 3 | 26
Test Procedure | 96 | 56 | 40
Inspection | 84 | 20 | 64
Test Report | 96 | 1 | 95
Lot 2
Action stage | Total | Completed | Remain
Design | 95 | 76 | 19
Procurement | 97 | 72 | 25
Manufacturing/Delivery Process | 11 | 3 | 8
Construction/Installation | 95 | 32 | 63
T&C | 0 | 0 | 0
Test Procedure | 94 | 32 | 62
Inspection | 95 | 13 | 82
Test Report | 94 | 5 | 89

## 02 Design
No |  |  | System | 9=Requirement Traceability Report 2=Additional Works-internal document | Submission No. | Document No. (QA) | Issued Date | Rev. | Letter No. | Description/Title | Item | System | CK Doc Ctrl | CK Prep by | CK DWG | CK Leader CC | M&E Leader Review | CK Prepare | M&E reviewed | Released | Orignator | Submit Plan by CK | Status | [5 empty] | Description/Title | Test Procedure | Test Report
1 |  | COM7 | AFC | 3 | AFC-39001 |  |  |  |  | Detailed Design - Park and Ride System | 5.1 | AFC | Wijittra | Peerapat | Peerapat | Sahachart S. | [6 empty] | CANCLE |  | บัณฑิต | Sorawit P. | BEM-K.Van |  | Park and Ride System
2 |  | COM7 | AFC | 3 | AFC-39001 | OLW-ME-24/0090 | 2025-09-08 | A | BEM/M/ORM/S0770/68 | Detailed Design - Mini Paging in Ticket Office East Section | 10.7 | COM | Kusuma K. | Sorawit P. | Sub | Pratan L. | Anat U. / Supajak S. | Sorawit P. | Anat U. | Suraphong S. |  | 2025-09-10 | submitted | 2026-12-19 | บัณฑิต | Sorawit P. | BEM-K.Van |  | Mini Paging in Ticket Office East Section | AFC-69001 | AFC-69002
3 |  | COM7 | AFC | 3 | AFC-39002 |  |  |  |  | Detailed Design - Mini Paging in Ticket Office West Section |  |  | Nichapa P. | Sorawit P. | Sub | Pratan L. | Anat U. / Supajak S. | Sorawit P. | Anat U. | Suraphong S. |  |  |  | 2026-12-19 | บัณฑิต | Sorawit P. | BEM-K.Van |  | Mini Paging in Ticket Office West Section | AFC-69003 | AFC-69004
4 |  |  | AFC | 3 | AFC-39003 | OLW-ME-24/0253 | 2026-01-09 | A | BEM/M/ORM/S0045/69 | Detailed Design - Cash Handling Equipment |  |  |  |  | Sub |  | Anat U. / Supajak S. |  | Anat U. | Suraphong S. |  |  | submitted |  | 0 |  |  |  | Cash Handling Equipment
5 |  |  | AFC | 3 | AFC-39003 | OLW-ME-24/0253 | 2026-02-17 | B | BEM/M/ORM/S0315/69 | Detailed Design - Cash Handling Equipment |  |  |  |  | Sub |  | Anat U. / Supajak S. |  | Anat U. | Suraphong S. |  |  | submitted |  | 0 |  |  |  | Cash Handling Equipment
6 |  | COM3 | COM | 3 | COM-39001 |  |  |  |  | Detailed Design - Walk-Through Metal Detector - Installation Drawing East Section | 10.3 | COM | Kusuma K. | Montri S. | Sub | Pratan L. | Sukij U. | Montri S. | Sukij U. | Suraphong S. |  |  |  | 2026-11-19 | มนตรี | Montri S. | BEM-K.Van |  | Walk-Through Metal Detector - Installation Drawing East Section | COM-69001 | COM-69002
7 |  | COM3 | COM | 3 | COM-39002 |  |  |  |  | Detailed Design - Walk-Through Metal Detector - Installation Drawing West Section |  |  | Kusuma K. | Montri S. | Sub | Pratan L. | Sukij U. | Montri S. | Sukij U. | Suraphong S. |  |  |  | 2026-11-19 | มนตรี | Montri S. | BEM-K.Van |  | Walk-Through Metal Detector - Installation Drawing West Section | COM-69003 | COM-69004
8 |  | COM3 | COM | 3 | COM-39003 |  |  |  |  | Detailed Design - Walk-Through Metal Detector - Material Approval |  |  | Kusuma K. | Montri S. | Sub | Pratan L. | Sukij U. | Montri S. | Sukij U. | Suraphong S. |  |  |  | 2026-11-19 | มนตรี | Montri S. | BEM-K.Van |  | Walk-Through Metal Detector - Material Approval
9 |  | COM6 | COM | 3 | COM-39004 |  |  |  |  | Detailed Design - Main Cable Containment for M&E Dedicated communication link to MRTA Headquarter |  |  | Kusuma K. | Montri S. | Sub | Pratan L. | Sukij U. / Supajak S. | Montri S. | Sukij U. | Suraphong S. |  |  | CANCLE | 2026-09-20 | มนตรี | Montri S. | BEM-K.Van |  | Main Cable Containment for M&E Dedicated communication link to MRTA Headquarter | COM-69005 | COM-69006
10 |  | COM9 | COM | 3 | COM-39005 |  |  |  |  | Detailed Design - Power Distribution for M&E Systems at MRTA Headquarter | 10.9 | COM | Kusuma K. | Montri S. | Sub | Pratan L. | Sukij U. / Supajak S. | Montri S. | Sukij U. | Suraphong S. |  |  | CANCLE | 2026-09-20 | มนตรี | Montri S. | BEM-K.Van |  | Power Distribution for M&E Systems at MRTA Headquarter | COM-69007 | COM-69008
11 |  | COM1 | COM | 3 | COM-39200 |  |  |  |  | Detailed Design - Magnetic Door Lock for East Section | 10.1 | COM | Kusuma K. | Montri S. | Sub | Pratan L. | Sukij U. / Supajak S. | Montri S. | Sukij U. | Suraphong S. |  |  |  | 2026-08-21 | มนตรี | Montri S. | BEM-K.Van |  | Magnetic Door Lock for East Section | COM-69200 | COM-69201
12 |  | COM1 | COM | 3 | COM-39201 | OLW-ME-24/0141 | 2025-08-27 | A |  | Detailed Design - Magnetic Door Lock - Material Approval | 10.1 | COM | Kusuma K. | Montri S. | Sub | Pratan L. | Sukij U. / Supajak S. | Montri S. | Sukij U. | Suraphong S. |  |  | submitted | 2026-08-21 | มนตรี | Montri S. | BEM-K.Van |  | Magnetic Door Lock - Material Approval
13 |  | COM1 | COM | 3 | COM-39201 | OLW-ME-24/0141 | 2026-01-19 | B |  | Detailed Design - Magnetic Door Lock - Material Approval | 10.1 | COM | Kusuma K. | Montri S. | Sub | Pratan L. | Sukij U. / Supajak S. | Montri S. | Sukij U. | Suraphong S. |  |  | submitted | 2026-08-21 | มนตรี | Montri S. | BEM-K.Van |  | Magnetic Door Lock - Material Approval
14 |  | COM1 | COM | 3 | COM-39203 |  |  |  |  | Detailed Design - Magnetic Door Lock for West Section | 10.1 | COM | Kusuma K. | Montri S. | Sub | Pratan L. | Sukij U. / Supajak S. | Montri S. | Sukij U. | Suraphong S. |  |  |  | 2026-08-21 | มนตรี | Montri S. | BEM-K.Van |  | Magnetic Door Lock for West Section | COM-69204 | COM-69205
15 |  | DWE19.1 | DWE | 3 | DWE-39001 |  |  |  |  | Detailed Design - Shunting Locomotive |  | DWE | Nichapa P. | Somsak S. | Sub | Suchock P. | Komsun N. / Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  |  | 2026-09-20 | สมศักดิ์ |  |  |  | Shunting Locomotive | DWE-69001 | DWE-69101
16 |  | DWE19.2 | DWE | 3 | DWE-39002 |  |  |  |  | Detailed Design - Tunnel Inspection and Cleaning Vehicle |  | DWE | Nichapa P. | Somsak S. | Sub | Suchock P. | Komsun N. / Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  |  | 2026-09-20 | สมศักดิ์ |  |  |  | Tunnel Inspection and Cleaning Vehicle | DWE-69002 | DWE-69102
17 |  | DWE19.3 | DWE | 3 | DWE-39003 |  |  |  |  | Detailed Design - Rail Maintenance Vehicle |  | DWE | Nichapa P. | Somsak S. | Sub | Suchock P. | Komsun N. / Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  |  | 2026-09-20 | สมศักดิ์ |  |  |  | Rail Maintenance Vehicle | DWE-69003 | DWE-69103
18 |  | DWE19.4 | DWE | 3 | DWE-39004 |  |  |  |  | Detailed Design - Flat Wagon |  | DWE | Nichapa P. | Somsak S. | Sub | Suchock P. | Komsun N. / Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  |  | 2026-09-20 | สมศักดิ์ |  |  |  | Flat Wagon | DWE-69004 | DWE-69104
19 |  | DWE19.5 | DWE | 3 | DWE-39005 |  |  |  |  | Detailed Design - Re-railing Equipment |  | DWE | Nichapa P. | Somsak S. | Sub | Suchock P. | Komsun N. / Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  |  | 2026-09-20 | สมศักดิ์ |  |  |  | Re-railing Equipment | DWE-69005 | DWE-69105
20 |  | DWE19.6 | DWE | 3 | DWE-39006 |  |  |  |  | Detailed Design - Self-propelled Rail Based Inspection Vehicle |  | DWE | Nichapa P. | Somsak S. | Sub | Suchock P. | Komsun N. / Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  |  | 2026-09-20 | สมศักดิ์ |  |  |  | Self-propelled Rail Based Inspection Vehicle | DWE-69006 | DWE-69106
21 |  | DWE19.7 | DWE | 3 | DWE-39007 |  |  |  |  | Detailed Design - Rail-head Grinding Machine Vehicle |  | DWE | Nichapa P. | Somsak S. | Sub | Suchock P. | Komsun N. / Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  |  | 2026-09-20 | สมศักดิ์ |  |  |  | Rail-head Grinding Machine Vehicle | DWE-69007 | DWE-69107
22 |  | DWE19.8 | DWE | 3 | DWE-39008 |  |  |  |  | Detailed Design - Multi Measuring Rail Vehicle |  | DWE | Nichapa P. | Somsak S. | Sub | 0 | Komsun N. / Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  | CANCLE | 2026-09-20 | สมศักดิ์ |  |  |  | Multi Measuring Rail Vehicle | DWE-69008 | DWE-69108
23 |  | DWE17 | DWE | 3 | DWE-39009 | OLW-ME-24/0291 | 2026-03-26 | A | BEM/M/ORM/S0834/69 | Detailed Design - Rail / Road Shunting Vehicle |  | DWE | Nichapa P. | Somsak S. | Sub | 0 | Komsun N. / Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  | submitted | 2026-09-20 | สมศักดิ์ |  |  |  | Rail / Road Shunting Vehicle | DWE-69009 | DWE-69109
24 |  | DWE19.9 | DWE | 3 | DWE-39010 |  |  |  |  | Detailed Design - High Work Inspection Vehicle |  | DWE | Nichapa P. | Somsak S. | Sub | 0 | Komsun N. / Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  | CANCLE | 2026-09-20 | สมศักดิ์ |  |  |  | High Work Inspection Vehicle
25 |  | DWE2 | DWE | 3 | DWE-39011 | OLW-ME-24/0263 | 2026-05-15 | A | BEM/M/ORM/S1393/69 | Detailed Design - Movable Height Maintenance Platform Vehicle |  | DWE | Nichapa P. | Somsak S. | Sub | 0 | Komsun N. / Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  | submitted | 2026-09-20 | สมศักดิ์ |  |  |  | Movable Height Maintenance Platform Vehicle | DWE-69011 | DWE-69111
26 |  | DWE3 | DWE | 3 | DWE-39012 | OLW-ME-24/0395 | 2026-05-20 | A | BEM/M/ORM/S1391/69 | Detailed Design - Forklifts |  | DWE | Nichapa P. | Somsak S. | Sub | 0 | Komsun N. / Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  | submitted | 2026-09-20 | สมศักดิ์ |  |  |  | Forklifts | DWE-69012 | DWE-69112
27 |  | DWE16 | DWE | 3 | DWE-39013 | OLW-ME-24/0102 | 2025-07-01 | A | BEM/M/ORM/S0441/68 | Detailed Design - Overhead Traveling Crane | 7.16 | DWE | Nichapa P. | Somsak S. | Sub | 0 | Komsun N. / Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  | submitted | 2026-09-20 | สมศักดิ์ |  |  |  | Overhead Traveling Crane | DWE-69013 | DWE-69113-513
28 |  | DWE16 | DWE | 3 | DWE-39013 | OLW-ME-24/0102 | 2025-11-10 | B | BEM/M/ORM/S1272/68 | Detailed Design - Overhead Traveling Crane | 7.16 | DWE | Nichapa P. | Somsak S. | Sub | 0 | Komsun N. / Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  | submitted | 2026-09-20 | สมศักดิ์ |  |  |  | Overhead Traveling Crane | DWE-69013 | DWE-69113-513
29 |  | DWE16 | DWE | 3 | DWE-39013 | OLW-ME-24/0102 | 2026-03-23 | C | BEM/M/ORM/S0833/69 | Detailed Design - Overhead Traveling Crane | 7.16 | DWE | Nichapa P. | Somsak S. | Sub | 0 | Komsun N. / Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  | submitted | 2026-09-20 | สมศักดิ์ |  |  |  | Overhead Traveling Crane | DWE-69013 | DWE-69113-513
30 |  | DWE18 | DWE | 3 | DWE-39014 | เตรียมออก 25/7/26 OLW-ME-24/0292 |  |  |  | Detailed Design - Trackwork Equipment |  | DWE | Nichapa P. | Somsak S. | Sub |  | Komsun N. / Supajak S. | Somsak S. |  | Suraphong S. |  |  |  | 2026-09-20 | สมศักดิ์ |  |  |  | Trackwork Equipment | DWE-69014 | DWE-69114
31 | Depot | DWE4 | DWE | 3 | DWE-39015 |  |  |  |  | Detailed Design - Compressed Air System and Portable Air Compressor for Depot |  | DWE | Nichapa P. | Somsak S. | Sub | 0 | Komsun N. / Supajak S. | Somsak S. |  | Suraphong S. |  |  |  | 2026-09-20 | สมศักดิ์ |  |  |  | Compressed Air System and Portable Air Compressor for Depot | DWE-69015 | DWE-69115
32 | Depot | DWE1 | DWE | 3 | DWE-39016 | OLW-ME-24/0376 | 2026-05-14 | A | BEM/M/ORM/S1259/69 | Detailed Design - Diesel Fuel Storage Tank for Maintenance Vehicle at Depot |  | DWE | Nichapa P. | Somsak S. | Sub | 0 | Komsun N. / Supajak S. | Somsak S. |  | Suraphong S. |  |  | submitted | 2026-09-20 | สมศักดิ์ | Somsak S. | BEM-K.Van |  | Diesel Fuel Storage Tank for Maintenance Vehicle at Depot | DWE-69016 | DWE-69116
33 |  | DWE6 | DWE | 3 | DWE-39017 | OLW-ME-24/0352 | 2026-03-26 | A | BEM/M/ORM/S0835/69 | Detailed Design - Pallet Shelves, Two - Tier Shelves and Tool Storage | 7.5 | DWE | Nichapa P. | Somsak S. | Sub | 0 | Komsun N. / Supajak S. | Somsak S. |  | Suraphong S. |  |  | submitted | 2026-09-20 | สมศักดิ์ | Somsak S. | BEM-K.Van |  | Pallet Shelves, Two - Tier Shelves and Tool Storage | DWE-69017 | DWE-69117
34 |  | DWE6 | DWE | 3 | DWE-39017 | OLW-ME-24/0352 | 2026-05-12 | B | BEM/M/ORM/S1258/69 | Detailed Design - Pallet Shelves, Two - Tier Shelves and Tool Storage | 7.5 | DWE | Nichapa P. | Somsak S. | Sub | 0 | Komsun N. / Supajak S. | Somsak S. |  | Suraphong S. |  |  | submitted | 2026-09-20 | สมศักดิ์ | Somsak S. | BEM-K.Van |  | Pallet Shelves, Two - Tier Shelves and Tool Storage | DWE-69017 | DWE-69117
35 |  | DWE6 | DWE | 3 | DWE-39017 | OLW-ME-24/0352 | 2026-07-17 | C | BEM/M/ORM/S2293/69 | Detailed Design - Pallet Shelves, Two - Tier Shelves and Tool Storage | 7.5 | DWE | Nichapa P. | Somsak S. | Sub | 0 | Komsun N. / Supajak S. | Somsak S. |  | Suraphong S. |  |  | submitted | 2026-09-20 | สมศักดิ์ | Somsak S. | BEM-K.Van |  | Pallet Shelves, Two - Tier Shelves and Tool Storage | DWE-69017 | DWE-69117
36 |  | DWE6 | DWE | 3 | DWE-39117 | Include in submission DWE-39017 |  |  |  | Detailed Design - Pallet Storage Shelves in Dangerous Goods Building | 7.6 | DWE | Nichapa P. | Somsak S. | Sub | Suchock P. | Komsun N. / Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  | CANCLE | 2026-09-20 | สมศักดิ์ | Somsak S. | BEM-K.Van |  | Pallet Storage Shelves in Dangerous Goods Building | DWE-69217 | DWE-69317
37 |  | DWE6 | DWE | 3 | DWE-39217 | Include in submission DWE-39018 |  |  |  | Detailed Design - Two-Tier Shelf | 7.7 | DWE | Nichapa P. | Somsak S. | Sub |  | Komsun N. / Supajak S. | Somsak S. |  | Suraphong S. |  |  | CANCLE | 2026-09-20 | สมศักดิ์ | Somsak S. | BEM-K.Van |  | Two-Tier Shelf | DWE-69417 | DWE-69517
38 |  | DWE6 | DWE | 3 | DWE-39317 | Include in submission DWE-39019 |  |  |  | Detailed Design - Tool Storage | 7.8 | DWE | Nichapa P. | Somsak S. | Sub |  | Komsun N. / Supajak S. | Somsak S. |  | Suraphong S. |  |  | CANCLE | 2026-09-20 | สมศักดิ์ | Somsak S. | BEM-K.Van |  | Tool Storage | DWE-69617 | DWE-69717
39 |  | DWE9 | DWE | 3 | DWE-39018 |  |  |  |  | Detailed Design - Repair Equipment | 7.9 | DWE | Nichapa P. | Somsak S. | Sub |  | Komsun N. / Supajak S. | Somsak S. |  | Suraphong S. |  |  |  | 2026-09-20 | สมศักดิ์ |  |  |  | Repair Equipment | DWE-69018 | DWE-69118
40 |  | GEN2 | DWE | 3 | DWE-39019 | เตรียมออก 27/7/26 OLW-ME-24/0510 |  |  |  | Detailed Design - Paint Shop Equipment |  | DWE | Nichapa P. | Somsak S. | Sub |  | Komsun N. / Supajak S. | Somsak S. |  | Suraphong S. |  |  |  | 2026-08-01 | - |  |  |  | Paint Shop Equipment | DWE-69019 | DWE-69119
41 |  | DWE10 | DWE | 3 | DWE-39020 |  |  |  |  | Detailed Design - Oil & Grease Disposal and Waste Disposal | 7.10,7.11,7.12 | DWE | Nichapa P. | Somsak S. | Sub |  | Komsun N. / Supajak S. | Somsak S. |  | Suraphong S. |  |  |  | 2026-09-20 | สมศักดิ์ |  |  |  | Oil & Grease Disposal and Waste Disposal | DWE-69020 | DWE-69120
42 |  | GEN9 | DWE | 3 | DWE-39021 | OLW-ME-24/0293 | 2026-03-26 | A | BEM/M/ORM/S0836/69 | Detailed Design - Operation Support Equipment | 3.6 | EE/ME | Nichapa P. | Somsak S. | Sub | Suchock P. | Komsun N. / Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  | submitted | 2026-08-21 | สมศักดิ์ |  |  |  | Operation Support Equipment | DWE-69021 | DWE-69121
43 |  |  | DWE | 3 | DWE-39022 |  |  |  |  | Detailed Design - DWE - List of Spare Parts, Consumables, Special Tools and Test Equipment, List of Critical Spare Parts |  | DWE | Nichapa P. | Somsak S. | Sub |  | Komsun N. / Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  |  |  | 0 |  |  |  | DWE - List of Spare Parts, Consumables, Special Tools and Test Equipment, List of Critical Spare Parts
44 |  |  | DWE | 3 | DWE-39028 | [19 empty] | 0 |  |  |  | #VALUE!
45 |  |  | DWE | 3 | DWE-39029 | [19 empty] | 0 |  |  |  | #VALUE!
46 |  |  | DWE | 3 | DWE-39030 | OLW-ME-24/0161 | 2025-09-01 | A | BEM/M/ORM/S0784/68 | Workshop Manual - DWE Part 2 Phase: Outline,Definitive and Detailed Design | [6 empty] | Komsun N. / Supajak S. | [5 empty] | submitted |  | 0 |  |  |  | DWE Part 2 Phase: Outline,Definitive and Detailed Design
47 |  | DWE13 | DWE | 3 | DWE-39xxx |  |  |  |  | Detailed Design - Safety Provision for Maintenance Pits | 7.13 | DWE | Wijittra M. | Sahachart S. | Tanyawit | Tanyawit K. | Komsun N. / Supajak S. | Sahachart S. | Komsun N. | Suraphong S. |  |  |  | 2026-09-20 | สหชาติ |  |  |  | Safety Provision for Maintenance Pits | MDW-69361 | MDW-69362
48 |  | DWE14 | DWE | 3 | DWE-39xxx |  |  |  |  | Detailed Design - Pit Drainage System in Main Workshop | 7.14 | DWE | Nichapa P. | Somsak S. | Sub |  | Komsun N. / Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  |  | 2026-09-20 | สมศักดิ์ |  |  |  | Pit Drainage System in Main Workshop
49 |  | DWE15 | DWE | 3 | DWE-39023 | OLW-ME-24/0242 | 2025-01-29 | A | Internal Only | Detailed Design - Provision of Civil Works to support Train Washing Equipment | 7.15 | DWE | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Komsun N. / Supajak S. | Sahachart S. | Komsun N. | Suraphong S. |  |  | submitted | 2026-08-01 | สหชาติ | Sahachart S. | BEM-K.Van |  | Provision of Civil Works to support Train Washing Equipment | DWE-69023 | DWE-69123
50 | Depot | GEN7.1 | DWE | 3 | DWE-39024 | OLW-ME-24/0049 | 2025-10-08 | A | Internal Only | Detailed Design - Dangerous Waste Storage Building in Depot - Civil & AR | 3.5 | ST/AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Komsun N. / Supajak S. | Sahachart S. | Komsun N. | Suraphong S. |  |  | submitted | 2026-09-20 | สหชาติ | Sahachart S. | BEM-K.Van |  | Dangerous Waste Storage Building in Depot - Civil & AR | DWE-69024 | DWE-69124
51 | Depot | GEN7.2 | DWE | 3 | DWE-39025 | OLW-ME-24/0264 | 2026-01-15 | A | Internal Only | Detailed Design - Dangerous Waste Storage Building and General Waste Storage Building in Depot - Building Service | 3.5 | EE/ME | Nichapa P. | Atiraj K. | Sub | Pratan L. | Komsun N. / Supajak S. | Atiraj K. | Komsun N. | Suraphong S. |  |  | submitted | 2026-09-20 | ประธาน | Atiraj K. | BEM-K.Van |  | Dangerous Waste Storage Building and General Waste Storage Building in Depot - Building Service | DWE-69025 | DWE-69125
52 | Depot | GEN8.1 | DWE | 3 | DWE-39026 | OLW-ME-24/0050 | 2025-10-08 | A | Internal Only | Detailed Design - General Waste Storage Building in Depot - Civil & AR | 3.6 | ST/AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Komsun N. / Supajak S. | Sahachart S. | Komsun N. | Suraphong S. |  |  | submitted | 2026-09-20 | สหชาติ | Sahachart S. | BEM-K.Van |  | General Waste Storage Building in Depot - Civil & AR | DWE-69026 | DWE-69126
53 | Depot | GEN8.2 | DWE | 3 | DWE-39027 |  |  |  | Internal Only | Detailed Design - General Waste Storage Building in Depot - Building Service | 3.5 | EE/ME | Nichapa P. | Atiraj K. | Sub | Pratan L. | Komsun N. / Supajak S. | Atiraj K. | Komsun N. | Suraphong S. |  |  | CANCLE | 2026-09-20 | ประธาน |  |  |  | General Waste Storage Building in Depot - Building Service | DWE-69027 | DWE-69127
54 |  | PSY1 | EPS | 3 | EPS-39001 | OLW-ME-24/0382 | 2026-05-18 | A | BEM/M/ORM/S1474/69 | Detailed Design - Diesel Fuel Storage Tanks for Power Generators |  | CIV/AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Praphat M./ Supajak S. | Sahachart S. | Praphat M. | Suraphong S. |  |  | submitted | 2026-03-24 | สมศักดิ์ | Sahachart S. | BEM-K.Van |  | Diesel Fuel Storage Tanks for Power Generators | EPS-69001 | EPS-69002
55 |  | PSY1 | EPS | 3 | EPS-39002 | Include in submission EPS-39001 |  |  |  | Detailed Design - Diesel Fuel Storage Tanks for Power Generators - Building Services |  | EE/ME | Nichapa P. | Jaturong W. | Sub | Pratan L. | Praphat M./ Supajak S. | Jaturong W. | Praphat M. | Suraphong S. |  |  | CANCLE | 2026-03-24 | สมศักดิ์ |  |  |  | Diesel Fuel Storage Tanks for Power Generators - Building Services | EPS-69003 | EPS-69004
56 |  | PSY1 | EPS | 3 | EPS-39003 | Include in submission EPS-39001 |  |  |  | Detailed Design - Diesel Fuel Storage Tanks for Power Generators : Material Approval - Civil & AR |  |  | Nichapa P. | Somsak S. | Sub | Pratan L. | Praphat M./ Supajak S. | Somsak S. | Praphat M. | Suraphong S. |  |  | CANCLE | 2026-03-24 | สมศักดิ์ |  |  |  | Diesel Fuel Storage Tanks for Power Generators : Material Approval - Civil & AR
57 |  | PSY1 | EPS | 3 | EPS-39004 | Include in submission EPS-39001 |  |  |  | Detailed Design - Diesel Fuel Storage Tanks for Power Generators : Material Approval - Building Service |  |  | Nichapa P. | Somsak S. | Sub | Pratan L. | Praphat M./ Supajak S. | Somsak S. | Praphat M. | Suraphong S. |  |  | CANCLE | 2026-03-24 | สมศักดิ์ |  |  |  | Diesel Fuel Storage Tanks for Power Generators : Material Approval - Building Service
58 |  | GEN10 | GRS | 3 | GRS-39001 | OLW-ME-24/0222 | 2025-11-24 | A | BEM/M/ORM/S1433/68 | Detailed Design - Graphic and Signage on East Section, OR13 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. |  |  | submitted | [5 empty] | Graphic and Signage on East Section, OR13 | GRS-69001 | GRS-69002
59 |  | GEN10 | GRS | 3 | GRS-39001 | OLW-ME-24/0222 | 2026-03-05 | B | BEM/M/ORM/S1328/69 | Detailed Design - Graphic and Signage on East Section, OR13 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. |  |  | submitted | [5 empty] | Graphic and Signage on East Section, OR13 | GRS-69001 | GRS-69002
60 |  | GEN10 | GRS | 3 | GRS-39002 | OLW-ME-24/0325 | 2026-04-23 | A | BEM/M/ORM/S1329/69 | Detailed Design - Graphic and Signage on East Section, OR14 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. |  |  | submitted | [5 empty] | Graphic and Signage on East Section, OR14 | GRS-69001 | GRS-69003
61 |  | GEN10 | GRS | 3 | GRS-39003 | OLW-ME-24/0379 | 2026-05-06 | A | BEM/M/ORM/S1771/69 | Detailed Design - Graphic and Signage on East Section, OR15 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. |  |  | submitted | [5 empty] | Graphic and Signage on East Section, OR15 | GRS-69001 | GRS-69004
62 |  | GEN10 | GRS | 3 | GRS-39004 | OLW-ME-24/0385 | 2026-05-12 | A | BEM/M/ORM/S1770/69 | Detailed Design - Graphic and Signage on East Section, OR16 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. |  |  | submitted | [5 empty] | Graphic and Signage on East Section, OR16 | GRS-69001 | GRS-69005
63 |  | GEN10 | GRS | 3 | GRS-39005 | OLW-ME-24/0394 | 2026-05-21 | A | BEM/M/ORM/S1772/69 | Detailed Design - Graphic and Signage on East Section, OR17 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. |  |  | submitted | [5 empty] | Graphic and Signage on East Section, OR17 | GRS-69001 | GRS-69006
64 |  | GEN10 | GRS | 3 | GRS-39006 | OLW-ME-24/0403 | 2026-06-12 | A | BEM/M/ORM/S2000/69 | Detailed Design - Graphic and Signage on East Section, OR18 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. |  |  | submitted | [5 empty] | Graphic and Signage on East Section, OR18 | GRS-69001 | GRS-69007
65 |  | GEN10 | GRS | 3 | GRS-39007 | OLW-ME-24/0410 | 2026-06-15 | A | BEM/M/ORM/S1999/69 | Detailed Design - Graphic and Signage on East Section, OR19 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. |  |  | submitted | [5 empty] | Graphic and Signage on East Section, OR19 | GRS-69001 | GRS-69008
66 |  | GEN10 | GRS | 3 | GRS-39008 | Total 48 pages, A3 - 39 sheets |  |  |  | Detailed Design - Graphic and Signage on East Section, OR20 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. |  |  | submitted | [5 empty] | Graphic and Signage on East Section, OR20 | GRS-69001 | GRS-69009
67 |  | GEN10 | GRS | 3 | GRS-39009 | Total 41 pages, A3 - 33 sheets |  |  |  | Detailed Design - Graphic and Signage on East Section, OR21 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. |  |  | submitted | [5 empty] | Graphic and Signage on East Section, OR21 | GRS-69001 | GRS-69010
68 |  | GEN10 | GRS | 3 | GRS-39010 | Total 40 pages, A3 - 32 sheets |  |  |  | Detailed Design - Graphic and Signage on East Section, OR22 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. |  |  | submitted | [5 empty] | Graphic and Signage on East Section, OR22 | GRS-69001 | GRS-69011
69 |  | GEN10 | GRS | 3 | GRS-39011 | Total 37 pages, A3 - 29 sheets |  |  |  | Detailed Design - Graphic and Signage on East Section, OR23 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. |  |  | submitted | [5 empty] | Graphic and Signage on East Section, OR23 | GRS-69001 | GRS-69012
70 |  | GEN10 | GRS | 3 | GRS-39012 | OLW-ME-24/0416 | 2026-06-18 | A | BEM/M/ORM/S1998/69 | Detailed Design - Graphic and Signage on East Section, OR24 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. |  |  | submitted | [5 empty] | Graphic and Signage on East Section, OR24 | GRS-69001 | GRS-69013
71 |  | GEN10 | GRS | 3 | GRS-39013 | Total 50 pages, A3 - 41 sheets |  |  |  | Detailed Design - Graphic and Signage on East Section, OR25 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. |  |  | submitted | [5 empty] | Graphic and Signage on East Section, OR25 | GRS-69001 | GRS-69014
72 |  | GEN10 | GRS | 3 | GRS-39014 | Total 48 pages, dwg. 39 sheets |  |  |  | Detailed Design - Graphic and Signage on East Section, OR26 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. |  |  | submitted | [5 empty] | Graphic and Signage on East Section, OR26 | GRS-69001 | GRS-69015
73 |  | GEN10 | GRS | 3 | GRS-39015 | Total 73 pages, dwg. 40 sheets |  |  |  | Detailed Design - Graphic and Signage on East Section, OR27 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. |  |  | submitted | [5 empty] | Graphic and Signage on East Section, OR27 | GRS-69001 | GRS-69016
74 |  | GEN10 | GRS | 3 | GRS-39016 | OLW-ME-24/0237 | 2025-12-11 | A | BEM/M/ORM/S1577/68 | Detailed Design - Graphic and Signage on East Section, OR28 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. |  |  | submitted | [5 empty] | Graphic and Signage on East Section, OR28 | GRS-69001 | GRS-69017
75 |  | GEN10 | GRS | 3 | GRS-39016 |  | Total 42 pages 34 pages - A3 | B |  | Detailed Design - Graphic and Signage on East Section, OR28 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. |  |  | submitted | [5 empty] | Graphic and Signage on East Section, OR28 | GRS-69001 | GRS-69017
76 |  | GEN10 | GRS | 3 | GRS-39017 |  | Total 41 pages 33 pages - A3 |  |  | Detailed Design - Graphic and Signage on East Section, OR29 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. |  |  | submitted | [5 empty] | Graphic and Signage on East Section, OR29 | GRS-69001 | GRS-69018
77 |  | GEN10 | GRS | 3 | GRS-39018 |  |  |  |  | Detailed Design - Graphic and Signage on East Section, IVS, VS, EEEN and Transition Area | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. | [8 empty] | Graphic and Signage on East Section, IVS, VS, EEEN and Transition Area | GRS-69001 | GRS-69019
78 | Depot | GEN10 | GRS | 3 | GRS-39019 |  |  |  |  | Detailed Design - Graphic and Signage at Depot, Main Workshop and Other Buildings | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. | [8 empty] | Graphic and Signage at Depot, Main Workshop and Other Buildings | GRS-69001 | GRS-69020
79 | Depot | GEN10 | GRS | 3 | GRS-39020 |  |  |  |  | Detailed Design - Graphic and Signage at Depot, OCC and Admin Building | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. | [8 empty] | Graphic and Signage at Depot, OCC and Admin Building | GRS-69001 | GRS-69021
80 |  | GEN10 | GRS | 3 | GRS-39021 |  |  |  |  | Detailed Design - Graphic and Signage on East Section, at BSS1, BSS2 and Generator Building | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. | [8 empty] | Graphic and Signage on East Section, at BSS1, BSS2 and Generator Building | GRS-69001 | GRS-69023
81 | Depot | GEN10 | GRS | 3 | GRS-39022 |  |  |  |  | Detailed Design - Graphic and Signage on East Section, Safety Line for Depot Buildings | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. | [8 empty] | Graphic and Signage on East Section, Safety Line for Depot Buildings | GRS-69001 | GRS-69022
82 | Depot | GEN10 | GRS | 3 | GRS-39023 |  |  |  |  | Detailed Design - Graphic and Signage on East Section, Track Area at Depot | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. | [8 empty] | Graphic and Signage on East Section, Track Area at Depot | GRS-69001 | GRS-69024
83 |  | GEN10 | GRS | 3 | GRS-39024 |  |  |  |  | Detailed Design - Graphic and Signage on East Section, Track Area at Main Line | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. | [8 empty] | Graphic and Signage on East Section, Track Area at Main Line | GRS-69001 | GRS-69025
84 |  | GEN10 | GRS | 3 | GRS-39025 |  |  |  |  | Detailed Design - Graphic and Signage on East Section, Power Supply for Signage | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. | [8 empty] | Graphic and Signage on East Section, Power Supply for Signage | GRS-69001 | GRS-69026
85 |  | GEN10 | GRS | 3 | GRS-39026 |  |  |  |  | Detailed Design - Graphic and Signage on West Section, OR02 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. | [8 empty] | Graphic and Signage on West Section, OR02 | GRS-69001 | GRS-69027
86 |  | GEN10 | GRS | 3 | GRS-39027 |  |  |  |  | Detailed Design - Graphic and Signage on West Section, OR03 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. | [8 empty] | Graphic and Signage on West Section, OR03 | GRS-69001 | GRS-69028
87 |  | GEN10 | GRS | 3 | GRS-39028 |  |  |  |  | Detailed Design - Graphic and Signage on West Section, OR04 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. | [8 empty] | Graphic and Signage on West Section, OR04 | GRS-69001 | GRS-69029
88 |  | GEN10 | GRS | 3 | GRS-39029 |  |  |  |  | Detailed Design - Graphic and Signage on West Section, OR05 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. | [8 empty] | Graphic and Signage on West Section, OR05 | GRS-69001 | GRS-69030
89 |  | GEN10 | GRS | 3 | GRS-39030 |  |  |  |  | Detailed Design - Graphic and Signage on West Section, OR06 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. | [8 empty] | Graphic and Signage on West Section, OR06 | GRS-69001 | GRS-69031
90 |  | GEN10 | GRS | 3 | GRS-39031 |  |  |  |  | Detailed Design - Graphic and Signage on West Section, OR07 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. | [8 empty] | Graphic and Signage on West Section, OR07 | GRS-69001 | GRS-69032
91 |  | GEN10 | GRS | 3 | GRS-39032 |  |  |  |  | Detailed Design - Graphic and Signage on West Section, OR08 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. | [8 empty] | Graphic and Signage on West Section, OR08 | GRS-69001 | GRS-69033
92 |  | GEN10 | GRS | 3 | GRS-39033 |  |  |  |  | Detailed Design - Graphic and Signage on West Section, OR09 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. | [8 empty] | Graphic and Signage on West Section, OR09 | GRS-69001 | GRS-69034
93 |  | GEN10 | GRS | 3 | GRS-39034 |  |  |  |  | Detailed Design - Graphic and Signage on West Section, OR10 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. | [8 empty] | Graphic and Signage on West Section, OR10 | GRS-69001 | GRS-69035
94 |  | GEN10 | GRS | 3 | GRS-39035 |  |  |  |  | Detailed Design - Graphic and Signage on West Section, OR11 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. | [8 empty] | Graphic and Signage on West Section, OR11 | GRS-69001 | GRS-69036
95 |  | GEN10 | GRS | 3 | GRS-39036 |  |  |  |  | Detailed Design - Graphic and Signage on West Section, OR12 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. | [8 empty] | Graphic and Signage on West Section, OR12 | GRS-69001 | GRS-69037
96 |  | GEN10 | GRS | 3 | GRS-39037 |  |  |  |  | Detailed Design - Graphic and Signage on West Section, IVS and EEEN | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. | [8 empty] | Graphic and Signage on West Section, IVS and EEEN | GRS-69001 | GRS-69038
97 |  | GEN10 | GRS | 3 | GRS-39038 |  |  |  |  | Detailed Design - Graphic and Signage on West Section, at BSS3 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. | [8 empty] | Graphic and Signage on West Section, at BSS3 | GRS-69001 | GRS-69039
98 |  | GEN10 | GRS | 3 | GRS-39039 |  |  |  |  | Detailed Design - Graphic and Signage on West Section, Track Area at Main Line | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. | [8 empty] | Graphic and Signage on West Section, Track Area at Main Line | GRS-69001 | GRS-69040
99 |  | GEN10 | GRS | 3 | GRS-39040 |  |  |  |  | Detailed Design - Graphic and Signage on West Section, Power Supply for Signage | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. | [8 empty] | Graphic and Signage on West Section, Power Supply for Signage | GRS-69001 | GRS-69041
100 |  | PSY2 | PSY | 3 | PSY-39001 | OLW-ME-24/0038 | 2025-03-26 | A | BEM/M/ORM/S0065/68 | Detailed Design - BSS1 : Architectural Installation Drawing | 8.2 | ST/AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Praphat M. / Supajak S, | Sahachart S. | Praphat M. | Suraphong S. |  |  | submitted | 2026-03-24 | สหชาติ | Sahachart S. | BEM-K.Van |  | BSS1 : Architectural Installation Drawing | PSY-69001 | PSY-69002
101 |  | PSY2 | PSY | 3 | PSY-39001 | OLW-ME-24/0038 | 2025-08-01 | B | BEM/M/ORM/S0688/68 | Detailed Design - BSS1 : Architectural Installation Drawing | 8.2 | ST/AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Praphat M. / Supajak S, | Sahachart S. | Praphat M. | Suraphong S. |  |  | submitted | 2026-03-24 | สหชาติ | Sahachart S. | BEM-K.Van |  | BSS1 : Architectural Installation Drawing | PSY-69001 | PSY-69002
102 |  | PSY2 | PSY | 3 | PSY-39002 | OLW-ME-24/0039 | 2025-03-26 | A | BEM/M/ORM/S0066/68 | Detailed Design - BSS1 : Structural Installation Drawing | 8.2 | ST/AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Praphat M. / Supajak S, | Sahachart S. | Praphat M. | Suraphong S. |  |  | submitted | 2026-03-24 | สหชาติ | Sahachart S. | BEM-K.Van |  | BSS1 : Structural Installation Drawing | PSY-69003 | PSY-69004
103 |  | PSY2 | PSY | 3 | PSY-39002 | OLW-ME-24/0039 | 2025-06-04 | B | BEM/M/ORM/S0357/68 | Detailed Design - BSS1 : Structural Installation Drawing | 8.2 | ST/AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Praphat M. / Supajak S, | Sahachart S. | Praphat M. | Suraphong S. |  |  | submitted | 2026-03-24 | สหชาติ | Sahachart S. | BEM-K.Van |  | BSS1 : Structural Installation Drawing | PSY-69003 | PSY-69004
104 |  | PSY2 | PSY | 3 | PSY-39003 | OLW-ME-24/0181 | 2025-09-17 | A | BEM/M/ORM/S1033/68 | Detailed Design - BSS1 : Building Services Installation Drawing | 8.2 | EE/ME | Nichapa P. | Jaturong W. | Sub | Pratan L. | Praphat M. / Supajak S, | Jaturong W. | Praphat M. | Suraphong S. |  |  | submitted | 2026-03-24 | สหชาติ | Jaturong W. | BEM-K.Van |  | BSS1 : Building Services Installation Drawing | PSY-69005 | PSY-69006
105 |  | PSY2 | PSY | 3 | PSY-39004 | OLW-ME-24/0040 | 2025-03-17 | A | BEM/M/ORM/S0054/68 | Detailed Design - BSS2 : Architectural Installation Drawing | 8.2 | ST/AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Praphat M. / Supajak S, | Sahachart S. | Praphat M. | Suraphong S. |  |  | submitted | 2026-03-24 | สหชาติ | Sahachart S. | BEM-K.Van |  | BSS2 : Architectural Installation Drawing | PSY-69007 | PSY-69008
106 |  | PSY2 | PSY | 3 | PSY-39004 | OLW-ME-24/0040 | 2025-08-15 | B | BEM/M/ORM/S0651/68 | Detailed Design - BSS2 : Architectural Installation Drawing | 8.2 | ST/AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Praphat M. / Supajak S, | Sahachart S. | Praphat M. | Suraphong S. |  |  | submitted | 2026-03-24 | สหชาติ | Sahachart S. | BEM-K.Van |  | BSS2 : Architectural Installation Drawing | PSY-69007 | PSY-69008
107 |  | PSY2 | PSY | 3 | PSY-39005 | OLW-ME-24/0041 | 2025-03-17 | A | BEM/M/ORM/S0053/68 | Detailed Design - BSS2 : Structural Installation Drawing | 8.2 | ST/AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Praphat M. / Supajak S, | Sahachart S. | Praphat M. | Suraphong S. |  |  | submitted | 2026-03-24 | สหชาติ | Sahachart S. | BEM-K.Van |  | BSS2 : Structural Installation Drawing | PSY-69009 | PSY-69010
108 |  | PSY2 | PSY | 3 | PSY-39005 | OLW-ME-24/0041 | 2025-07-18 | B | BEM/M/ORM/S0562/68 | Detailed Design - BSS2 : Structural Installation Drawing | 8.2 | ST/AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Praphat M. / Supajak S, | Sahachart S. | Praphat M. | Suraphong S. |  |  | submitted | 2026-03-24 | สหชาติ | Sahachart S. | BEM-K.Van |  | BSS2 : Structural Installation Drawing | PSY-69009 | PSY-69010
109 |  | PSY2 | PSY | 3 | PSY-39006 | OLW-ME-24/0086 | 2025-05-19 | A | BEM/M/ORM/S0261/68 | Detailed Design - BSS2 : Building Services Installation Drawing | 8.2 | EE/ME | Nichapa P. | Jaturong W. | Sub | Pratan L. | Praphat M. / Supajak S, | Jaturong W. | Praphat M. | Suraphong S. |  |  | submitted | 2026-03-24 | สหชาติ | Jaturong W. | BEM-K.Van |  | BSS2 : Building Services Installation Drawing | PSY-69011 | PSY-69012
110 |  | PSY2 | PSY | 3 | PSY-39007 |  |  |  |  | Detailed Design - BSS1,2 : Material Approval - Civil & AR |  | ST/AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Praphat M. / Supajak S, | Sahachart S. | Praphat M. | Suraphong S. |  |  |  | 2026-03-24 | สหชาติ | Sahachart S. | BEM-K.Van |  | BSS1,2 : Material Approval - Civil & AR
111 |  | PSY2 | PSY | 3 | PSY-39008 | OLW-ME-24/0282 | 2026-02-09 | A | BEM/M/ORM/S0289/69 | Detailed Design - BSS1,2 : Material Approval - Building Services |  | EE/ME | Nichapa P. | Jaturong W. | Sub | Pratan L. | Praphat M. / Supajak S, | Jaturong W. | Praphat M. | Suraphong S. |  |  | submitted | 2026-03-24 | สหชาติ | Jaturong W. | BEM-K.Van |  | BSS1,2 : Material Approval - Building Services
112 |  | PSY2 | PSY | 3 | PSY-39009 | OLW-ME-24/0054 | 2025-04-05 | A | BEM/M/ORM/S0084/68 | Detailed Design - HV Cable Ducts from MEA Interface Point to BSS1 | 8.2 | ST/AR | Nichapa P. | Jaturong W. | Sub | Pratan L. | Praphat M. / Supajak S, | Jaturong W. | Praphat M. | Suraphong S. |  |  | submitted | 2026-03-24 | สหชาติ | Sahachart S. | BEM-K.Van |  | HV Cable Ducts from MEA Interface Point to BSS1 | PSY-69013 | PSY-69014
113 |  | PSY2 | PSY | [6 empty] | Detailed Design - HV Cable Ducts from MEA Interface Point to BSS2 | 8.2 | ST/AR | Nichapa P. | Jaturong W. | Sub | Pratan L. | Praphat M. / Supajak S, | Jaturong W. | Praphat M. | Suraphong S. |  |  | CANCLE | 2026-03-24 | สหชาติ |  |  |  | HV Cable Ducts from MEA Interface Point to BSS2
114 |  | GEN11 | PSY | 3 | PSY-39010 | MOVE TO MDW MDW-39289 |  |  |  | Detailed Design - Earthing and Bonding Modification on East Section |  | EE/ME | Nichapa P. | Jaturong W. | Sub | Pratan L. | Praphat M. / Supajak S, | Jaturong W. | Praphat M. | Suraphong S. |  |  | CANCLE | 2026-03-01 | ประธาน |  |  |  | Earthing and Bonding Modification on East Section | PSY-690XX | PSY-690XX
115 |  | PSY3 | PSY | 3 | PSY-39011 | OLW-ME-24/0052 | 2025-03-26 | A | BEM/M/ORM/S0064/68 | Detailed Design - Steel Grating Raised Floor for EE Panel on East Section | 8.3 | ST/AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Praphat M. / Supajak S, | Sahachart S. | Praphat M. | Suraphong S. |  |  | submitted | 2026-03-24 | สหชาติ | Sahachart S. | BEM-K.Van |  | Steel Grating Raised Floor for EE Panel on East Section | PSY-69015 | PSY-69016
116 |  |  | PSY | [6 empty] | Detailed Design - Steel Grating Raised Floor for EE Panel | [14 empty] | 0 | 0 | 0 |  | Steel Grating Raised Floor for EE Panel
117 |  |  | PSY | [6 empty] | Detailed Design - Steel grating raised floor support for all PSY switchgear panels and PSY cabinets in TSS and SSS rooms | [14 empty] | 0 | 0 | 0 |  | Steel grating raised floor support for all PSY switchgear panels and PSY cabinets in TSS and SSS rooms
118 |  |  | PSY | [6 empty] | Detailed Design - Steel Grating | [14 empty] | 0 | 0 | 0 |  | Steel Grating
119 |  |  | PSY | [6 empty] | Detailed Design - Podium | [14 empty] | 0 | 0 | 0 |  | Podium
120 |  |  | PSY | [6 empty] | Detailed Design - Chainlink | [14 empty] | 0 | 0 | 0 |  | Chainlink
121 |  |  | PSY | [6 empty] | Detailed Design - Support Transformer | [14 empty] | 0 | 0 | 0 |  | Support Transformer
122 |  | PSY2 | PSY | 3 | PSY-39012 | OLW-ME-24/0197 | 2025-10-17 | A | BEM/M/ORM/S1206/68 | Detailed Design - Overhead Traveling Crane for BSS1 | [6 empty] | Praphat M. / Supajak S, | 0 | Praphat M. | Suraphong S. |  |  | submitted | 2026-03-24 | สหชาติ | Somsak S. | BEM-K.Van |  | Overhead Traveling Crane for BSS1 | PSY-69017 | PSY-69018
123 |  | PSY2 | PSY | 3 | PSY-39013 | OLW-ME-24/0162 | 2025-09-01 | A | BEM/M/ORM/S0912/68 | Detailed Design - Overhead Traveling Crane for BSS2 | [6 empty] | Praphat M. / Supajak S, | 0 | Praphat M. | Suraphong S. |  |  | submitted | 2026-03-24 | สหชาติ | Somsak S. | BEM-K.Van |  | Overhead Traveling Crane for BSS2 | PSY-69017 | PSY-69018
124 |  | PSY2 | PSY | 3 | PSY-39014 |  |  |  |  | Detailed Design - Overhead Traveling Crane for BSS3 | [6 empty] | Praphat M. / Supajak S, | 0 | Praphat M. | Suraphong S. |  |  |  | 2026-03-24 | สหชาติ | Somsak S. | BEM-K.Van |  | Overhead Traveling Crane for BSS3 | PSY-69019 | PSY-69020
125 |  | PSY2 | PSY | 3 | PSY-39015 | เตรียมออก 24/7/26 OLW-ME-24/0453 | Total page 75 page, A3 - 65 sheets |  |  | Detailed Design - BSS3 : Architectural Installation Drawing | [13 empty] | 2026-03-24 | สหชาติ | Sahachart S. | BEM-K.Van |  | BSS3 : Architectural Installation Drawing
126 |  | PSY2 | PSY | 3 | PSY-39016 |  |  |  |  | Detailed Design - BSS3 : Structural Installation Drawing | [13 empty] | 2026-03-24 | สหชาติ | Sahachart S. | BEM-K.Van |  | BSS3 : Structural Installation Drawing
127 |  | PSY2 | PSY | 3 | PSY-39017 |  |  |  |  | Detailed Design - BSS3 : Building Services Installation Drawing | [13 empty] | 2026-03-24 | สหชาติ | Jaturong W. | BEM-K.Van |  | BSS3 : Building Services Installation Drawing
128 |  | PSY2 | PSY | 3 | PSY-39018 |  |  |  |  | Detailed Design - BSS3 : Material Approval - Civil & AR | [13 empty] | 2026-03-24 | สหชาติ | Sahachart S. | BEM-K.Van |  | BSS3 : Material Approval - Civil & AR
129 |  | PSY2 | PSY | 3 | PSY-39019 |  |  |  |  | Detailed Design - BSS3 : Material Approval - Building Services | [13 empty] | 2026-03-24 | สหชาติ | Jaturong W. | BEM-K.Van |  | BSS3 : Material Approval - Building Services
130 |  | GEN11 | PSY | 3 | PSY-390xx |  |  |  |  | Detailed Design - Earthing and Bonding Modification on West Section | [13 empty] | 2026-03-01 | ประธาน | 0 | 0 |  | Earthing and Bonding Modification on West Section | PSY-690XX | PSY-690XX
131 |  | PSY3 | PSY | 3 | PSY-390xx |  |  |  |  | Detailed Design - Steel Grating Raised Floor for EE Panel on West Section | [13 empty] | 2026-03-24 | สหชาติ | 0 | 0 |  | Steel Grating Raised Floor for EE Panel on West Section | PSY-690XX | PSY-690XX
132 |  |  | SCA | 3 | SCA-39200 |  |  |  |  | Detailed Design - Modification of BEMS to receive PSD Signal on East Section | 9.1 | SCA | Kusuma K. | Thanthip S. | Sub | Pratan L. | Wanlop W./ K.Supajak S. | Thanthip S. | Wanlop W. | Suraphong S. |  |  | CANCLE |  | 0 |  |  |  | Modification of BEMS to receive PSD Signal on East Section | SCA-69200 | SCA-69201
133 |  |  | SCA | 3 | SCA-39201 |  |  |  |  | Detailed Design - Modification of Escalator Interface Point with CCTV and SCADA on East Section | 9.3 | SCA | Kusuma K. | Thanthip S. | Sub | Pratan L. | Wanlop W./ K.Supajak S. | Thanthip S. | Wanlop W. | Suraphong S. |  |  | CANCLE |  | 0 |  |  |  | Modification of Escalator Interface Point with CCTV and SCADA on East Section | SCA-69202 | SCA-69203
134 |  |  | SCA | 3 | SCA-39202 |  |  |  |  | Detailed Design - Modification of Fire Alarm System Interface Point with CCTV and SCADA on East Section |  |  | Kusuma K. | Thanthip S. | Sub | Pratan L. | Wanlop W./ K.Supajak S. | Thanthip S. | Wanlop W. | Suraphong S. |  |  | CANCLE |  | 0 |  |  |  | Modification of Fire Alarm System Interface Point with CCTV and SCADA on East Section | SCA-69204 | SCA-69205
135 |  |  | SCA | 3 | SCA-39203 |  |  |  |  | Detailed Design - Modification of SCADA Hardwire on East Section | *NEW* | SCA | Kusuma K. | Thanthip S. | Sub | Pratan L. | Wanlop W./ K.Supajak S. | Thanthip S. | Wanlop W. | Suraphong S. |  |  | CANCLE |  | 0 |  |  |  | Modification of SCADA Hardwire on East Section | SCA-69206 | SCA-69207
136 | Depot | SIG4 | MDW | 3 | MDW-39001 | OLW-ME-24/0150 | 2025-10-01 | A | BEM/M/ORM/S1135/68 | Detailed Design - Modification of Depot Track Alignment at Stabling Yard | 6.4 | ST | Nichapa P. | Kamphol H. | Sub | Suchock P. | Supajak S. | Kamphol H. | Supajak S. | Suraphong S. |  |  | submitted | 2026-06-22 | สู่โชค | Kamphol H. | BEM-K.Van |  | Modification of Depot Track Alignment at Stabling Yard | MDW-69001 | MDW-69002
137 | Depot | SIG1 | MDW | 3 | MDW-39002 | OLW-ME-24/0208 | 2025-11-07 | A | BEM/M/ORM/S1309/68 | Detailed Design - Modification Motorized Gate and Shelters at Test Track Depot - Civil & AR | 6.1 | ST | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Eddy / Supajak S. | Sahachart S. | Supajak S. | Suraphong S. |  |  | submitted | 2026-06-22 | สหชาติ | Sahachart S. | BEM-K.Van |  | Modification Motorized Gate and Shelters at Test Track Depot - Civil & AR | MDW-69003 | MDW-69004
138 | Depot | SIG1 | MDW | 3 | MDW-39002 | OLW-ME-24/0208 | 2026-02-16 | B | BEM/M/ORM/S0668/69 | Detailed Design - Modification Motorized Gate and Shelters at Test Track Depot - Civil & AR | 6.1 | ST | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Eddy / Supajak S. | Sahachart S. | Supajak S. | Suraphong S. |  |  | submitted | 2026-06-22 | สหชาติ | Sahachart S. | BEM-K.Van |  | Modification Motorized Gate and Shelters at Test Track Depot - Civil & AR | MDW-69003 | MDW-69004
139 | Depot | SIG1 | MDW | 3 | MDW-39003 | OLW-ME-24/0180 | 2025-10-07 | A | BEM/M/ORM/S1136/68 | Detailed Design - Modification Motorized Gate and Shelters at Test Track Depot - Building Service | 6.1 | ST | Nichapa P. | Atiraj K. | Sub | Pratan L. | Eddy / Supajak S. | Atiraj K. | Supajak S. | Suraphong S. |  |  | submitted | 2026-06-22 | สหชาติ | Atiraj K. | BEM-K.Van |  | Modification Motorized Gate and Shelters at Test Track Depot - Building Service | MDW-69005 | MDW-69006
140 |  | PSD2 | MDW | 3 | MDW-39004 | OLW-ME-24/0419 | 2026-07-09 | A | BEM/M/ORM/S2140/69 | Detailed Design - Rubber Gap Fillers on Platform Edge on East Section | 4.2 | ST/AR | Nichapa P. | Kamphol H. | Sub | Suchock P. | Supajak S. | Kamphol H. | Supajak S. | Suraphong S. |  |  | submitted | 2026-08-21 | กำพล | Kamphol H. | BEM-K.Van |  | Rubber Gap Fillers on Platform Edge on East Section | MDW-69007 | MDW-69008
141 | Depot |  | MDW | 3 | MDW-39001 |  |  |  |  | Detailed Design - Eye Adaptation Lighting at Transition Area and Depot Approach | 3.16 | EE | Nichapa | Jaturong | Sub | Pratan | Supajak S. | [5 empty] | CANCLE |  | 0 | Kamphol H. | BEM-K.Van |  | Eye Adaptation Lighting at Transition Area and Depot Approach | MDW-69253 | MDW-69254
142 | Depot |  | MDW | 3 | MDW-39002 |  |  |  |  | Detailed Design - Dangerous Waste Storage Building in Depot | 3.5 | ST/AR | Wijittra | Peerapat | Peerapat | Sahachart | Supajak S. | [5 empty] | CANCLE |  | 0 | Sahachart S. | BEM-K.Van |  | Dangerous Waste Storage Building in Depot
143 | Depot |  | MDW | 3 | MDW-39003 |  |  |  |  | Detailed Design - General Waste Storage Building in Depot | 3.6 | ST/AR | Wijittra | Peerapat | Peerapat | Sahachart | Supajak S. | [5 empty] | CANCLE |  | 0 | Atiraj K. | BEM-K.Van |  | General Waste Storage Building in Depot
144 | Depot |  | MDW | 3 | MDW-39004 |  |  |  |  | Detailed Design - Wayside Cable Containment in Depot | [12 empty] | CANCLE |  | 0 | Kamphol H. | BEM-K.Van |  | Wayside Cable Containment in Depot
145 |  |  | MDW | [6 empty] | Detailed Design - PSY Wayside Cable Containment for 24 Kv Cable under the Depot slab | 3.4 | EE | Kusuma | Monchai | Peerapat | Pratan | [8 empty] | 0 | 0 | 0 |  | PSY Wayside Cable Containment for 24 Kv Cable under the Depot slab
146 |  |  | MDW | [6 empty] | Detailed Design - COM/SIG Wayside Cable Containment in the Depot | 3.4 | EE | Kusuma | Montri | Peerapat | Pratan | [8 empty] | 0 | 0 | 0 |  | COM/SIG Wayside Cable Containment in the Depot
147 |  |  | MDW | 3 | MDW-39005 |  |  |  |  | Detailed Design - Driver Train Simulation Room and AFC Training Room Modification - Civil & AR |  | ST/AR | Wijittra | Somsak | Peerapat | Suchock | Supajak S. | [5 empty] | CANCLE |  | 0 |  |  |  | Driver Train Simulation Room and AFC Training Room Modification - Civil & AR
148 |  |  | MDW | 3 | MDW-39006 |  |  |  |  | Detailed Design - Driver Train Simulation Room and AFC Training Room Modification - Building Services |  | EE/ME | Nichapa | Jaturong | Sub | Pratan | Supajak S. | [5 empty] | CANCLE |  | 0 |  |  |  | Driver Train Simulation Room and AFC Training Room Modification - Building Services
149 |  | GEN3 | MDW | 3 | MDW-39200 | OLW-ME-24/0024 | 2025-03-03 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment Material for Approval | 3.4 | EE | Kusuma K. | Montri S. | Sub | Pratan L. | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted | 2025-05-28 | - | Montri S. | BEM-K.Van |  | Modification Work of M&E Cable Containment Material for Approval
150 |  | GEN3 | MDW | 3 | MDW-39201 | OLW-ME-24/0077 | 2025-03-24 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of OR13 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted | 2025-05-28 | - | Montri S. | BEM-K.Van |  | Modification Work of M&E Cable Containment of OR13 | MDW-69200 | MDW-69201
151 |  | GEN3 | MDW | 3 | MDW-39202 | OLW-ME-24/0078 | 2025-03-24 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of OR14 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted | 2025-05-28 | - | Montri S. | BEM-K.Van |  | Modification Work of M&E Cable Containment of OR14 | MDW-69200 | MDW-69202
152 |  | GEN3 | MDW | 3 | MDW-39203 | OLW-ME-24/0109 | 2025-06-20 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of OR15 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted | 2025-05-28 | - | Montri S. | BEM-K.Van |  | Modification Work of M&E Cable Containment of OR15 | MDW-69200 | MDW-69203
153 |  | GEN3 | MDW | 3 | MDW-39204 | OLW-ME-24/0106 | 2025-06-20 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of OR16 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted | 2025-05-28 | - | Montri S. | BEM-K.Van |  | Modification Work of M&E Cable Containment of OR16 | MDW-69200 | MDW-69204
154 |  | GEN3 | MDW | 3 | MDW-39205 | OLW-ME-24/0107 | 2025-06-20 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of OR17 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted | 2025-05-28 | - | Montri S. | BEM-K.Van |  | Modification Work of M&E Cable Containment of OR17 | MDW-69200 | MDW-69205
155 |  | GEN3 | MDW | 3 | MDW-39206 | OLW-ME-24/0027 | 2025-03-03 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of OR18 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted | 2025-05-28 | - | Montri S. | BEM-K.Van |  | Modification Work of M&E Cable Containment of OR18 | MDW-69200 | MDW-69206
156 |  | GEN3 | MDW | 3 | MDW-39207 | OLW-ME-24/0028 | 2025-03-03 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of OR19 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted | 2025-05-28 | - | Montri S. | BEM-K.Van |  | Modification Work of M&E Cable Containment of OR19 | MDW-69200 | MDW-69207
157 |  | GEN3 | MDW | 3 | MDW-39208 | OLW-ME-24/0029 | 2025-03-03 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of OR20 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted | 2025-05-28 | - | Montri S. | BEM-K.Van |  | Modification Work of M&E Cable Containment of OR20 | MDW-69200 | MDW-69208
158 |  | GEN3 | MDW | 3 | MDW-39209 | OLW-ME-24/0030 | 2025-03-03 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of OR21 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted | 2025-05-28 | - | Montri S. | BEM-K.Van |  | Modification Work of M&E Cable Containment of OR21 | MDW-69200 | MDW-69209
159 |  | GEN3 | MDW | 3 | MDW-39210 | OLW-ME-24/0031 | 2025-03-03 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of OR22 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted | 2025-05-28 | - | Montri S. | BEM-K.Van |  | Modification Work of M&E Cable Containment of OR22 | MDW-69200 | MDW-69210
160 |  | GEN3 | MDW | 3 | MDW-39211 | OLW-ME-24/0036 | 2025-03-06 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of OR23 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted | 2025-05-28 | - | Montri S. | BEM-K.Van |  | Modification Work of M&E Cable Containment of OR23 | MDW-69200 | MDW-69211
161 |  | GEN3 | MDW | 3 | MDW-39212 | OLW-ME-24/0037 | 2025-03-06 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of OR24 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted | 2025-05-28 | - | Montri S. | BEM-K.Van |  | Modification Work of M&E Cable Containment of OR24 | MDW-69200 | MDW-69212
162 |  | GEN3 | MDW | 3 | MDW-39213 | OLW-ME-24/0046 | 2025-03-06 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of OR25 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted | 2025-05-28 | - | Montri S. | BEM-K.Van |  | Modification Work of M&E Cable Containment of OR25 | MDW-69200 | MDW-69213
163 |  | GEN3 | MDW | 3 | MDW-39214 | OLW-ME-24/0047 | 2025-03-06 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of OR26 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted | 2025-05-28 | - | Montri S. | BEM-K.Van |  | Modification Work of M&E Cable Containment of OR26 | MDW-69200 | MDW-69214
164 |  | GEN3 | MDW | 3 | MDW-39215 | OLW-ME-24/0048 | 2025-03-06 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of OR27 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted | 2025-05-28 | - | Montri S. | BEM-K.Van |  | Modification Work of M&E Cable Containment of OR27 | MDW-69200 | MDW-69215
165 |  | GEN3 | MDW | 3 | MDW-39216 | OLW-ME-24/0032 | 2025-03-03 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of OR28 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted | 2025-05-28 | - | Montri S. | BEM-K.Van |  | Modification Work of M&E Cable Containment of OR28 | MDW-69200 | MDW-69216
166 |  | GEN3 | MDW | 3 | MDW-39217 | OLW-ME-24/0033 | 2025-03-03 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of OR29 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted | 2025-05-28 | - | Montri S. | BEM-K.Van |  | Modification Work of M&E Cable Containment of OR29 | MDW-69200 | MDW-69217
167 |  | GEN3 | MDW | 3 | MDW-39218 | OLW-ME-24/0168 | 2025-09-03 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of VS02 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted | 2025-05-28 | - | Montri S. | BEM-K.Van |  | Modification Work of M&E Cable Containment of VS02 | MDW-69200 | MDW-69218
168 |  | GEN3 | MDW | 3 | MDW-39219 | OLW-ME-24/0169 | 2025-09-03 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of VS03 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted | 2025-05-28 | - | Montri S. | BEM-K.Van |  | Modification Work of M&E Cable Containment of VS03 | MDW-69200 | MDW-69219
169 |  | GEN3 | MDW | 3 | MDW-39220 | OLW-ME-24/0170 | 2025-09-03 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of IVS08 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted | 2025-05-28 | - | Montri S. | BEM-K.Van |  | Modification Work of M&E Cable Containment of IVS08 | MDW-69200 | MDW-69220
170 |  | GEN3 | MDW | 3 | MDW-39221 | OLW-ME-24/0171 | 2025-09-03 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of IVS09 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted | 2025-05-28 | - | Montri S. | BEM-K.Van |  | Modification Work of M&E Cable Containment of IVS09 | MDW-69200 | MDW-69221
171 |  | GEN3 | MDW | 3 | MDW-39222 | OLW-ME-24/0172 | 2025-09-03 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of IVS10 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted | 2025-05-28 | - | Montri S. | BEM-K.Van |  | Modification Work of M&E Cable Containment of IVS10 | MDW-69200 | MDW-69222
172 |  | GEN3 | MDW | 3 | MDW-39223 | OLW-ME-24/0173 | 2025-09-03 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of IVS11 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted | 2025-05-28 | - | Montri S. | BEM-K.Van |  | Modification Work of M&E Cable Containment of IVS11 | MDW-69200 | MDW-69223
173 |  | GEN3 | MDW | 3 | MDW-39224 | OLW-ME-24/0174 | 2025-11-07 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of IVS12 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted | 2025-05-28 | - | Montri S. | BEM-K.Van |  | Modification Work of M&E Cable Containment of IVS12 | MDW-69200 | MDW-69224
174 |  | GEN3 | MDW | 3 | MDW-39225 | OLW-ME-24/0034 | 2025-03-03 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of IVS13 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted | 2025-05-28 | - | Montri S. | BEM-K.Van |  | Modification Work of M&E Cable Containment of IVS13 | MDW-69200 | MDW-69225
175 |  | GEN3 | MDW | 3 | MDW-39226 | OLW-ME-24/0083 | 2025-05-14 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of IVS14 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted | 2025-05-28 | - | Montri S. | BEM-K.Van |  | Modification Work of M&E Cable Containment of IVS14 | MDW-69200 | MDW-69226
176 |  | GEN3 | MDW | 3 | MDW-39227 | OLW-ME-24/0084 | 2025-05-14 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of IVS15 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted | 2025-05-28 | - | Montri S. | BEM-K.Van |  | Modification Work of M&E Cable Containment of IVS15 | MDW-69200 | MDW-69227
177 |  | GEN3 | MDW | 3 | MDW-39228 | OLW-ME-24/0088 | 2025-05-20 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of IVS16 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted | 2025-05-28 | - | Montri S. | BEM-K.Van |  | Modification Work of M&E Cable Containment of IVS16 | MDW-69200 | MDW-69228
178 |  | GEN3 | MDW | 3 | MDW-39229 | OLW-ME-24/0089 | 2025-05-20 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of IVS17 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted | 2025-05-28 | - | Montri S. | BEM-K.Van |  | Modification Work of M&E Cable Containment of IVS17 | MDW-69200 | MDW-69229
179 |  | GEN3 | MDW | 3 | MDW-39230 | OLW-ME-24/0175 | 2025-09-03 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of EEEN | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted | 2025-05-28 | - | Montri S. | BEM-K.Van |  | Modification Work of M&E Cable Containment of EEEN | MDW-69200 | MDW-69230
180 | Depot | GEN3 | MDW | 3 | MDW-39231 | OLW-ME-24/0081 | 2025-05-14 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of Orange Line - Depot | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted | 2025-05-28 | - | Montri S. | BEM-K.Van |  | Modification Work of M&E Cable Containment of Orange Line - Depot | MDW-69200 | MDW-69231
181 |  | GEN16 | MDW | 3 | MDW-39232 |  |  |  |  | Detailed Design - Level Crossing at Turnout and Track Slab Crossing on Main Line East Section | 3.14 | ST | Nichapa P. | Kamphol H. | Peerapat B. | Suchock P. | Supajak S. | Kamphol H. | Supajak S. | Suraphong S. |  |  |  | 2026-08-21 | กำพล | Kamphol H. | BEM-K.Van |  | Level Crossing at Turnout and Track Slab Crossing on Main Line East Section | MDW-69232 | MDW-69233
182 |  | GEN12 | MDW | 3 | MDW-39233 |  |  |  |  | Detailed Design - Main Line Cable Trough Modification on East Section | [12 empty] | CANCLE | 2026-06-22 | - | Sahachart S. | BEM-K.Van |  | Main Line Cable Trough Modification on East Section
183 |  | GEN12.1 | MDW | 3 | MDW-39233 |  |  |  |  | Detailed Design - Main Line Cable Trough Modification on East Section (PSY) | 3.10 | AR | Kusuma K. | Sahachart S. | Peerapat B. | Tanyawit K. | Supajak S. | Monchai R. | Supajak S. | Suraphong S. |  |  |  | 2026-06-22 | มนต์ชัย | Sahachart S. | BEM-K.Van |  | Main Line Cable Trough Modification on East Section (PSY) | MDW-69234 | MDW-69235
184 |  | GEN12.2 | MDW | 3 | MDW-39234 |  |  |  |  | Detailed Design - Main Line Cable Trough Modification on East Section (SIG/COM) | 3.10 | AR | Kusuma K. | Montri S. | Peerapat B. | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  |  | 2026-06-22 | มนตรี | Montri S. | BEM-K.Van |  | Main Line Cable Trough Modification on East Section (SIG/COM) | MDW-69234 | MDW-69236
185 |  | GEN5 | MDW | 3 | MDW-39235 | OLW-ME-24/0055 | 2025-05-09 | A | Internal Only | Detailed Design - Raised Floor Installation on East Section | 3.3 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Supajak S. | Sahachart S. | Supajak S. | Suraphong S. |  |  | submitted | 2026-06-01 | สหชาติ | Sahachart S. | BEM-K.Van |  | Raised Floor Installation on East Section | MDW-69237 | MDW-69238
186 |  |  | MDW | [6 empty] | Detailed Design - Add Raised Floor and Finish Epoxy Floor in Commercial rm (Sig) at ELEV Station | [14 empty] | 0 | 0 | 0 |  | Add Raised Floor and Finish Epoxy Floor in Commercial rm (Sig) at ELEV Station
187 |  |  | MDW | [6 empty] | Detailed Design - Add Raised Floor in SCADA / CCTV Maintenance Room | [14 empty] | 0 | 0 | 0 |  | Add Raised Floor in SCADA / CCTV Maintenance Room
188 |  |  | MDW | [6 empty] | Detailed Design - Add Raised Floor in Maintenance Management Room | [14 empty] | 0 | 0 | 0 |  | Add Raised Floor in Maintenance Management Room
189 |  |  | MDW | [6 empty] | Detailed Design - Add Raised Floor in Playback and Training Room | [14 empty] | 0 | 0 | 0 |  | Add Raised Floor in Playback and Training Room
190 |  |  | MDW | [6 empty] | Detailed Design - Add Raised Floor in Backup Control Room | [14 empty] | 0 | 0 | 0 |  | Add Raised Floor in Backup Control Room
191 |  |  | MDW | [6 empty] | Detailed Design - Finish Epoxy Floor in Commercial rm (UPS Room) at ELEV Station | [14 empty] | 0 | 0 | 0 |  | Finish Epoxy Floor in Commercial rm (UPS Room) at ELEV Station
192 |  |  | MDW | [6 empty] | Detailed Design - Add Raised Floor in Trainning Room (New SIG Maintenance Room) | [14 empty] | 0 | 0 | 0 |  | Add Raised Floor in Trainning Room (New SIG Maintenance Room)
193 | Depot | GEN13 | MDW | 3 | MDW-39236 | OLE-ME-24/0043 | 2025-08-19 | A | Internal Only | Detailed Design - Bird Protection System at Depot Buildings | 3.11 | AR | Wijittra M. | Sahachart S. | Peerapat | Tanyawit K. | Supajak S. | Sahachart S. | Supajak S. | Suraphong S. |  |  | submitted | 2026-11-19 | สหชาติ | Sahachart S. | BEM-K.Van |  | Bird Protection System at Depot Buildings | MDW-69239 | MDW-69240
194 |  | GEN22 | MDW | 3 | MDW-39237 |  |  |  |  | Detailed Design - Central BEMS for the MRT Orange Line System East Section | 3.21 | COM | Kusuma K. | Thanthip S. | Sub | Pratan L. | Supajak S. | Thanthip S. | Supajak S. | Suraphong S. |  |  |  | 2026-08-21 | บัณฑิต | Thanthip S. | BEM-K.Van |  | Central BEMS for the MRT Orange Line System East Section | MDW-69241 | MDW-69242
195 |  | GEN22 | MDW | 3 | MDW-39238 |  |  |  |  | Detailed Design - Central BEMS for the MRT Orange Line System West Section | 3.21 | COM | Kusuma K. | Thanthip S. | Sub | Pratan L. | Supajak S. | Thanthip S. | Supajak S. | Suraphong S. |  |  |  | 2026-08-21 | บัณฑิต | Thanthip S. | BEM-K.Van |  | Central BEMS for the MRT Orange Line System West Section | MDW-69243 | MDW-69244
196 | Depot | GEN15 | MDW | 3 | MDW-39239 | OLW-ME-24/0187 | 2025-10-01 | A | Internal Only | Detailed Design - Access Panel for TSS, SSS1,SSS2 Room in Depot | 3.13 | ST | Wijittra M. | Sahachart S. | Peerapat | Tanyawit K. | Supajak S. | Sahachart S. | Supajak S. | Suraphong S. |  |  | submitted | 2026-03-24 | สหชาติ | Sahachart S. | BEM-K.Van |  | Access Panel for TSS, SSS1,SSS2 Room in Depot | MDW-69245 | MDW-69246
197 |  | GEN14.1 | MDW | 3 | MDW-39240 | OLW-ME-24/0216 | 2025-11-11 | A | Internal Only | Detailed Design - Driver Train Simulation Room and Train Crew Office at OR18 - Civil & AR | 3.12 | ST/AR | Nichapa P. | Sahachart S. | Peerapat | Tanyawit K. | Supajak S. | Sahachart S. | Supajak S. | Suraphong S. |  |  | submitted | 2026-08-21 | สหชาติ | Sahachart S. | BEM-K.Van |  | Driver Train Simulation Room and Train Crew Office at OR18 - Civil & AR | MDW-69247 | MDW-69248
198 |  | GEN14.2 | MDW | 3 | MDW-39241 | OLW-ME-24/0203 |  |  | Internal Only | Detailed Design - Driver Train Simulation Room and Train Crew Office at OR18 - Building Services | 3.12 | EE/ME | Nichapa P. | Jaturong W. | Sub | Pratan L. | Supajak S. | Jaturong W. | Supajak S. | Suraphong S. |  |  |  | 2026-08-21 | ประธาน | Jaturong W. | BEM-K.Van |  | Driver Train Simulation Room and Train Crew Office at OR18 - Building Services | MDW-69249 | MDW-69250
199 |  | GEN4.0 | MDW | 3 | MDW-39242 | OLW-ME-24/0192 | 2025-10-07 | A | Internal Only | Detailed Design - Modification Works for Training Room at Ratchada Station | 3.1 | EE/ME | Nichapa P. | Boonprasert F. | Sub | Pratan L. | Supajak S. | Boonprasert F. | Supajak S. | Suraphong S. |  |  | submitted | 2026-04-01 | ประธาน | Boonprasert F. | BEM-K.Van |  | Modification Works for Training Room at Ratchada Station | MDW-69251 | MDW-69252
200 | Depot | GEN18 | MDW | 3 | MDW-39243 | OLW-ME-24/0119 | 2025-07-21 | A | Internal Only | Detailed Design - Eye Adaptation Lighting at Transition Area and Depot Approach | 3.16 | EE | Nichapa P. | Jaturong W. | Sub | Pratan L. | Supajak S. | Jaturong W. | Supajak S. | Suraphong S. |  |  | submitted | 2026-11-19 | ประธาน | Jaturong W. | BEM-K.Van |  | Eye Adaptation Lighting at Transition Area and Depot Approach | MDW-69253 | MDW-69254
201 |  | GEN4.1 | MDW | 3 | MDW-39244 |  |  |  |  | Detailed Design - AFC Training Room Modification - Civil & AR | 3.17 | ST/AR | Wijittra M. | Somsak S. | Peerapat | Suchock | Supajak S. | Somsak S. | Supajak S. | Suraphong S. |  |  |  | 2026-08-21 | สหชาติ | Sahachart S. | BEM-K.Van |  | AFC Training Room Modification - Civil & AR | MDW-69255 | MDW-69256
202 |  | GEN4.2 | MDW | 3 | MDW-39245 | OLW-ME-24/0312 | 2026-02-27 | A | Internal Only | Detailed Design - AFC Training Room Modification - Building Services | 3.17 | EE/ME | Nichapa P. | Jaturong W. | Sub | Pratan L. | Supajak S. | Jaturong W. | Supajak S. | Suraphong S. |  |  | submitted | 2026-08-21 | ประธาน | Boonprasert F. | BEM-K.Van |  | AFC Training Room Modification - Building Services | MDW-69257 | MDW-69258
203 |  | GEN1 | MDW | [6 empty] | Detailed Design - Rooms and Building Service Systems Modification in Stations Area | 3.1.1 | [12 empty] | 2026-08-01 | - | 0 | 0 |  | Rooms and Building Service Systems Modification in Stations Area
204 | Station | GEN1.1 | MDW | 3 | MDW-39246 | OLW-ME-24/0235 | 2025-12-11 | A | Internal Only | Detailed Design - Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR13 - OR17 | 3.1.1.10 | EE | Nichapa P. | Atiraj K. | Sub | Pratan L. | Supajak S. | Atiraj K. | Supajak S. | Suraphong S. |  |  | submitted | 2026-08-01 | - | Atiraj K. | BEM-K.Van |  | Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR13 - OR17 | MDW-69259 | MDW-69260
205 | Station | GEN1.2 | MDW | 3 | MDW-39247 | OLW-ME-24/0185 | 2025-09-15 | A | Internal Only | Detailed Design - Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR18 - OR22 | 3.1.1.10 | EE | Nichapa P. | Atiraj K. | Sub | Pratan L. | Supajak S. | Atiraj K. | Supajak S. | Suraphong S. |  |  | submitted | 2026-08-01 | - | Atiraj K. | BEM-K.Van |  | Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR18 - OR22 | MDW-69259 | MDW-69261
206 | Station | GEN1.3 | MDW | 3 | MDW-39247 | OLW-ME-24/0185 |  | B | Internal Only | Detailed Design - Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR18 - OR22 | 3.1.1.10 | EE | Nichapa P. | Atiraj K. | Sub | Pratan L. | Supajak S. | Atiraj K. | Supajak S. | Suraphong S. |  |  |  | 2026-08-01 | - | Atiraj K. | BEM-K.Van |  | Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR18 - OR22 | MDW-69259 | MDW-69261
207 | Station | GEN1.4 | MDW | 3 | MDW-39248 | OLW-ME-24/0202 | 2025-10-22 | A | Internal Only | Detailed Design - Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR23 - OR29 | 3.1.1.10 | EE | Nichapa P. | Atiraj K. | Sub | Pratan L. | Supajak S. | Atiraj K. | Supajak S. | Suraphong S. |  |  | submitted | 2026-08-01 | - | Atiraj K. | BEM-K.Van |  | Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR23 - OR29 | MDW-69259 | MDW-69262
208 | Station | GEN1.5 | MDW | 3 | MDW-39248 | OLW-ME-24/0202 | 2026-01-28 | B | Internal Only | Detailed Design - Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR23 - OR29 | 3.1.1.10 | EE | Nichapa P. | Atiraj K. | Sub | Pratan L. | Supajak S. | Atiraj K. | Supajak S. | Suraphong S. |  |  | submitted | 2026-08-01 | - | Atiraj K. | BEM-K.Van |  | Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR23 - OR29 | MDW-69259 | MDW-69262
209 | Station | GEN1.6 | MDW | 3 | MDW-39249 | OLW-ME-24/0044 | 2025-05-19 | A | Internal Only | Detailed Design - SOR Counter and Workstation Hanging Support Installation on East Section | 3.1.1.12 | AR | Wijittra M. | Sahachart S. | Peerapat | Tanyawit K. | Supajak S. | Sahachart S. | Supajak S. | Suraphong S. |  |  | submitted | 2026-08-01 | - | Sahachart S. | BEM-K.Van |  | SOR Counter and Workstation Hanging Support Installation on East Section | MDW-69263 | MDW-69264
210 | Station | GEN1.7 | MDW | 3 | MDW-39250 | OLW-ME-24/0051 | 2025-06-30 | A | Internal Only | Detailed Design - Ticket Office Modification on East Section | 3.1.1.12 | AR | Wijittra M. | Sahachart S. | Peerapat | Tanyawit K. | Supajak S. | Sahachart S. | Supajak S. | Suraphong S. |  |  | submitted | 2026-08-01 | - | Sahachart S. | BEM-K.Van |  | Ticket Office Modification on East Section | MDW-69265 | MDW-69266
211 |  | GEN1.8 | MDW | [6 empty] | Detailed Design - Modify Raise Floor for Ticket Office Counter at OR23-29 | [13 empty] | 2026-08-01 |  | 0 | 0 |  | Modify Raise Floor for Ticket Office Counter at OR23-29
212 |  | GEN1.9 | MDW | [6 empty] | Detailed Design - Modify Ticket Office Counter at OR20-22 | [13 empty] | 2026-08-01 |  | 0 | 0 |  | Modify Ticket Office Counter at OR20-22
213 | Station | GEN1.10 | MDW | 3 | MDW-39251 |  |  |  |  | Detailed Design - Modification of Eletrical System in Telecommunication Room at OR14 | 3.1.1.1,3.1.1.2 | EE | Nichapa P. | Jaturong W. | Sub | Pratan L. | Supajak S. | Jaturong W. | Supajak S. | Suraphong S. |  |  | CANCLE | 2026-08-01 | - |  |  |  | Modification of Eletrical System in Telecommunication Room at OR14 | MDW-69267 | MDW-69268
214 | Station | GEN1.11 | MDW | 3 | MDW-39252 | OLW-ME-24/0230 | 2025-11-19 | A | Internal Only | Detailed Design - Modification of Fire Suppression System (N2) in Commerial Room at OR14 | 3.1.1.1,3.1.1.2 | ME | Nichapa P. | Boonprasert F. | Sub | Pratan L. | Supajak S. | Boonprasert F. | Supajak S. | Suraphong S. |  |  | submitted | 2026-08-01 | - | Boonprasert F. | BEM-K.Van |  | Modification of Fire Suppression System (N2) in Commerial Room at OR14 | MDW-69269 | MDW-69270
215 | Station | GEN1.12 | MDW | 3 | MDW-39253 | OLW-ME-24/0100 | 2025-07-08 | A | Internal Only | Detailed Design - Modification of Civil Work in Telecommunication Room at OR14 | 3.1.1.1,3.1.1.2 | ST | Wijittra M. | Sahachart S. | Peerapat | Tanyawit K. | Supajak S. | Sahachart S. | Supajak S. | Suraphong S. |  |  | submitted | 2026-08-01 | - | Sahachart S. | BEM-K.Van |  | Modification of Civil Work in Telecommunication Room at OR14 | MDW-69271 | MDW-69272
216 | Station | GEN1.13 | MDW | 3 | MDW-39254 | OLW-ME-24/0266 | 2026-01-15 | A | Internal Only | Detailed Design - Modification in Staff Mess Room at OR13-OR17 | 3.1.1.1,3.1.1.2 | ME | Nichapa P. | Atiraj K. | Sub | Pratan L. | Supajak S. | Atiraj K. | Supajak S. | Suraphong S. |  |  | submitted | 2026-08-01 | - | Atiraj K. | BEM-K.Van |  | Modification in Staff Mess Room at OR13-OR17 | MDW-69273 | MDW-69274
217 | Station | GEN1.14 | MDW | 3 | MDW-39255 | OLW-ME-24/0210 | 2025-11-10 | A | Internal Only | Detailed Design - Modification in Staff Mess Room at OR18-OR22 | 3.1.1.1,3.1.1.2 | ME | Nichapa P. | Atiraj K. | Sub | Pratan L. | Supajak S. | Atiraj K. | Supajak S. | Suraphong S. |  |  | submitted | 2026-08-01 | - | Atiraj K. | BEM-K.Van |  | Modification in Staff Mess Room at OR18-OR22 | MDW-69273 | MDW-69275
218 | Station | GEN1.15 | MDW | 3 | MDW-39256 | OLW-ME-24/0274 | 2026-01-28 | A | Internal Only | Detailed Design - Modification in Staff Mess Room at OR23-OR29 | 3.1.1.1,3.1.1.2 | ME | Nichapa P. | Atiraj K. | Sub | Pratan L. | Supajak S. | Atiraj K. | Supajak S. | Suraphong S. |  |  | submitted | 2026-08-01 | - | Atiraj K. | BEM-K.Van |  | Modification in Staff Mess Room at OR23-OR29 | MDW-69273 | MDW-69276
219 | Station | GEN1.16 | MDW | 3 | MDW-39257 | OLW-ME-24/0126 | 2025-08-18 | A |  | Detailed Design - Modification of Air Conditioning in CER and SER at OR13-OR19 | 3.1.1.1,3.1.1.2 | ME | Nichapa P. | Boonprasert F. | Sub | Pratan L. | Supajak S. | Boonprasert F. | Supajak S. | Suraphong S. |  |  | submitted | 2026-08-01 | - | Boonprasert F. | BEM-K.Van |  | Modification of Air Conditioning in CER and SER at OR13-OR19 | MDW-69277 | MDW-69278
220 | Station | GEN1.17 | MDW | 3 | MDW-39258 | OLW-ME-24/0117 | 2025-07-07 | A |  | Detailed Design - Modification of Air Conditioning in CER and SER at OR20-OR22 | 3.1.1.1,3.1.1.2 | ME | Nichapa P. | Boonprasert F. | Sub | Pratan L. | Supajak S. | Boonprasert F. | Supajak S. | Suraphong S. |  |  | submitted | 2026-08-01 | - | Boonprasert F. | BEM-K.Van |  | Modification of Air Conditioning in CER and SER at OR20-OR22 | MDW-69277 | MDW-69279
221 | Station | GEN1.18 | MDW | 3 | MDW-39258 | OLW-ME-24/0117 | 2025-08-18 | B |  | Detailed Design - Modification of Air Conditioning in CER and SER at OR20-OR22 | 3.1.1.1,3.1.1.2 | ME | Nichapa P. | Boonprasert F. | Sub | Pratan L. | Supajak S. | Boonprasert F. | Supajak S. | Suraphong S. |  |  | submitted | 2026-08-01 |  | Boonprasert F. | BEM-K.Van |  | Modification of Air Conditioning in CER and SER at OR20-OR22 | MDW-69277 | MDW-69279
222 | Station | GEN1.19 | MDW | 3 | MDW-39259 | OLW-ME-24/0120 | 2025-08-18 | A |  | Detailed Design - Modification of Air Conditioning in CER and SER at OR23-OR29 | 3.1.1.1,3.1.1.2 | ME | Nichapa P. | Boonprasert F. | Sub | Pratan L. | Supajak S. | Boonprasert F. | Supajak S. | Suraphong S. |  |  | submitted | 2026-08-01 | - | Boonprasert F. | BEM-K.Van |  | Modification of Air Conditioning in CER and SER at OR23-OR29 | MDW-69277 | MDW-69280
223 | Depot | GEN1.20 | MDW | 3 | MDW-39260 | OLW-ME-24/0177 | 2025-10-27 | A |  | Detailed Design - Modification of Air Conditioning in M&E Room at OCC Building | 3.1.1.1,3.1.1.2 | ME | Nichapa P. | Boonprasert F. | Sub | Pratan L. | Supajak S. | Boonprasert F. | Supajak S. | Suraphong S. |  |  | submitted |  | - | Boonprasert F. | BEM-K.Van |  | Modification of Air Conditioning in M&E Room at OCC Building | MDW-69281 | MDW-69282
224 |  | GEN2 | MDW | [6 empty] | Detailed Design - Rooms and Building Service Systems Modification in Depot Area | 3.2 | [12 empty] | 2026-08-01 | - | 0 | 0 |  | Rooms and Building Service Systems Modification in Depot Area
225 | Depot | GEN2 | MDW | 3 | MDW-39261 | OLW-ME-24/0188 | 2025-10-01 | A | Internal Only | Detailed Design - Provision of UPS for MDB Control at Main Workshop, OCC Building, Admin Building, Stabling Yard and Train Washing Plant | 3.1.2 | EE | Nichapa P. | Jaturong W. | Sub | Pratan L. | Supajak S. | Jaturong W. | Supajak S. | Suraphong S. |  |  | submitted | 2026-08-01 | - | Jaturong W. | BEM-K.Van |  | Provision of UPS for MDB Control at Main Workshop, OCC Building, Admin Building, Stabling Yard and Train Washing Plant | MDW-69283 | MDW-69284
226 | Depot | GEN2 | MDW | 3 | MDW-39262 | OLW-ME-24/0130 | 2025-08-18 | A | Internal Only | Detailed Design - Provision of Redundant MDB at OCC Building, Admin Building and Canteen | 3.1.2 | EE | Nichapa P. | Jaturong W. | Sub | Pratan L. | Supajak S. | Jaturong W. | Supajak S. | Suraphong S. |  |  | submitted | 2026-08-01 | - | Jaturong W. | BEM-K.Van |  | Provision of Redundant MDB at OCC Building, Admin Building and Canteen | MDW-69285 | MDW-69286
227 | Depot | GEN2 | MDW | 3 | MDW-39262 | OLW-ME-24/0130 | 2025-08-27 | B | Internal Only | Detailed Design - Provision of Redundant MDB at OCC Building, Admin Building and Canteen | 3.1.2 | EE | Nichapa P. | Jaturong W. | Sub | Pratan L. | Supajak S. | Jaturong W. | Supajak S. | Suraphong S. |  |  | submitted | 2026-08-01 | - | Jaturong W. | BEM-K.Van |  | Provision of Redundant MDB at OCC Building, Admin Building and Canteen | MDW-69285 | MDW-69286
228 | Depot | GEN2 | MDW | 3 | MDW-39262 | OLW-ME-24/0130 | 2025-11-18 | C | Internal Only | Detailed Design - Provision of Redundant MDB at OCC Building, Admin Building and Canteen | 3.1.2 | EE | Nichapa P. | Jaturong W. | Sub | Pratan L. | Supajak S. | Jaturong W. | Supajak S. | Suraphong S. |  |  | submitted | 2026-08-01 | - | Jaturong W. | BEM-K.Van |  | Provision of Redundant MDB at OCC Building, Admin Building and Canteen | MDW-69285 | MDW-69286
229 | Depot | GEN2 | MDW | 3 | MDW-39263 | OLW-ME-24/0221 | 2025-11-10 | A | Internal Only | Detailed Design - Additonal Lighting System at Depot Area | 3.1.2,.4,.5 | EE | Nichapa P. | Jaturong W. | Sub | Pratan L. | Supajak S. | Jaturong W. | Supajak S. | Suraphong S. |  |  | submitted | 2026-08-01 | - | Jaturong W. | BEM-K.Van |  | Additonal Lighting System at Depot Area | MDW-69287 | MDW-69288
230 | Depot |  | MDW | 3 | MDW-39264 |  |  |  |  | Detailed Design - Block-out and Holes Modification at Depot Platform | 3.1.2,.4,.5 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Supajak S. | Sahachart S. | Supajak S. | Suraphong S. |  |  | CANCLE |  | 0 | Sahachart S. | BEM-K.Van |  | Block-out and Holes Modification at Depot Platform | MDW-69289 | MDW-69290
231 | Depot |  | MDW | 3 | MDW-39268 |  |  |  |  | Detailed Design - Main Cable Containment Modification at Depot | 3.2 | EE | Kusuma K. | Montri S. | Peerapat B. | Pratan L. | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | CANCLE |  | 0 | Montri S. | BEM-K.Van |  | Main Cable Containment Modification at Depot | MDW-69291 | MDW-69292
232 | Depot | GEN6.1 | MDW | 3 | MDW-39269 |  |  |  |  | Detailed Design - PSY Wayside Cable Containment for 24 KV Cable under Depot slab | 3.4 | EE | Kusuma K. | Monchai R. | Peerapat B. | Pratan L. | Supajak S. | Monchai R. | Supajak S. | Suraphong S. |  |  | CANCLE | 2026-02-22 | ประธาน | Monchai R. | BEM-K.Van |  | PSY Wayside Cable Containment for 24 KV Cable under Depot slab | MDW-69293 | MDW-69294
233 | Depot | GEN6.2 | MDW | 3 | MDW-39270 |  |  |  |  | Detailed Design - SIG/COM Wayside Cable Containment in Depot | 3.4 | EE | Kusuma K. | Montri S. | Peerapat B. | Pratan L. | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | CANCLE | 2026-02-22 | มนตรี/ประธาน | Montri S. | BEM-K.Van |  | SIG/COM Wayside Cable Containment in Depot | MDW-69295 | MDW-69296
234 | Depot | GEN6 | MDW | 3 | MDW-39271 | OLW-ME-24/0082 | 2025-05-09 | A | Internal Only | Detailed Design - Wayside Cable Trough in Depot | 3.4 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Supajak S. | Sahachart S. | Supajak S. | Suraphong S. |  |  | submitted | 2026-02-22 | - | Sahachart S. | BEM-K.Van |  | Wayside Cable Trough in Depot | MDW-69297 | MDW-69298
235 | Depot | GEN6 | MDW | 3 | MDW-39271 | OLW-ME-24/0082 | 2025-07-24 | B | Internal Only | Detailed Design - Wayside Cable Trough in Depot | 3.4 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Supajak S. | Sahachart S. | Supajak S. | Suraphong S. |  |  | submitted | 2026-02-22 | - | Sahachart S. | BEM-K.Van |  | Wayside Cable Trough in Depot | MDW-69297 | MDW-69298
236 | Station | GEN1 | MDW | 3 | MDW-39272 | OLW-ME-24/0101 | 2025-07-16 | A | Internal Only | Detailed Design - Modification of New M&E Room at IVS15 Civil & AR | 3.1.1.1 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Supajak S. | Sahachart S. | Supajak S. | Suraphong S. |  |  | submitted | 2026-08-01 | - | Sahachart S. | BEM-K.Van |  | Modification of New M&E Room at IVS15 Civil & AR | MDW-69299 | MDW-69300
237 | Station | GEN1 | MDW | 3 | MDW-39272 | OLW-ME-24/0101 | 2025-10-01 | B | Internal Only | Detailed Design - Modification of New M&E Room at IVS15 Civil & AR | 3.1.1.1 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Supajak S. | Sahachart S. | Supajak S. | Suraphong S. |  |  | submitted | 2026-08-01 | - | Sahachart S. | BEM-K.Van |  | Modification of New M&E Room at IVS15 Civil & AR | MDW-69299 | MDW-69300
238 | Station | GEN1 | MDW | 3 | MDW-39273 |  |  |  |  | Detailed Design - Modification of New M&E UPS Room at IVS15-IVS17 - Building Services | 3.1.1.1 | ME | Nichapa P. | Boonprasert F. | Sub | Pratan L. | Supajak S. | Boonprasert F. | Supajak S. | Suraphong S. |  |  |  | 2026-08-01 | - | Boonprasert F. | BEM-K.Van |  | Modification of New M&E UPS Room at IVS15-IVS17 - Building Services | MDW-69301 | MDW-69302
239 | Station | GEN1 | MDW | 3 | MDW-39274 | OLW-ME-24/0214 | 2025-11-10 | A | Internal Only | Detailed Design - Modification of Air Conditioning at OR13-OR29 and OCC Building - Material Approval (Electrical System) | 3.1.1.1,3.1.1.2 | ME | Nichapa P. | Boonprasert F. | Sub | Pratan L. | Supajak S. | Boonprasert F. | Supajak S. | Suraphong S. |  |  | submitted | 2026-08-01 | - | Boonprasert F. | BEM-K.Van |  | Modification of Air Conditioning at OR13-OR29 and OCC Building - Material Approval (Electrical System)
240 |  | GEN1 | MDW | 3 | MDW-39275 | OLW-ME-24/0190 | 2025-10-01 | A | Internal Only | Detailed Design - Modification of Air Conditioning at OR13-OR29 and OCC Building - Material Approval (Mechanical System) |  | ME | Nichapa P. | Boonprasert F. | Sub | Pratan L. | Supajak S. | Boonprasert F. | Supajak S. | Suraphong S. |  |  | submitted | 2026-08-01 | - | Boonprasert F. | BEM-K.Van |  | Modification of Air Conditioning at OR13-OR29 and OCC Building - Material Approval (Mechanical System)
241 |  | AFC2 | MDW | 3 | MDW-39276 | OLW-ME-24/0338 | 2026-04-24 | A | Internal Only | Detailed Design - Ticket Issuing Machine (TIM) Wall Opening and Closing on East Section | 5.2 | AFC/AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Anat U. / Supajak S. | Sahachart S. | Supajak S. | Suraphong S. |  |  | submitted | 2026-09-20 | สหชาติ | Sahachart S. | BEM-K.Van |  | Ticket Issuing Machine (TIM) Wall Opening and Closing on East Section | MDW-69303 | MDW-69304
242 |  | AFC3 | MDW | 3 | MDW-39277 |  |  |  |  | Detailed Design - Modification Works for AFC - Balustrade Modification Along AFC Gate Line East Section |  | AFC/AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Anat U. / Supajak S. | Sahachart S. | Supajak S. | Suraphong S. |  |  |  | 2026-09-20 | สหชาติ | Sahachart S. | BEM-K.Van |  | Modification Works for AFC - Balustrade Modification Along AFC Gate Line East Section | MDW-69305 | MDW-69306
243 |  | AFC4 | MDW | 3 | MDW-39278 |  |  |  |  | Detailed Design - Underfloor Embedded Duct Modification for AFC Gates Line East Section | 5.4 | AFC | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Anat U. / Supajak S. | Sahachart S. | Supajak S. | Suraphong S. |  |  |  | 2026-09-20 | สหชาติ | Sahachart S. | BEM-K.Van |  | Underfloor Embedded Duct Modification for AFC Gates Line East Section | MDW-69307 | MDW-69308
244 |  | AFC3 | MDW | 3 | MDW-39279 |  |  |  |  | Detailed Design - Balustrade Modification Along AFC Gate Line East Section | 5.3 | AFC | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Anat U. / Supajak S. | Sahachart S. | Supajak S. | Suraphong S. |  |  |  | 2026-09-20 | สหชาติ | Sahachart S. | BEM-K.Van |  | Balustrade Modification Along AFC Gate Line East Section | MDW-69309 | MDW-69310
245 |  | PSD3 | MDW | 3 | MDW-39280 | OLW-ME-24/0195 | 2025-10-27 | A | Internal Only | Detailed Design - Platform Finishing on East Section | 4.3 | ST/AR | Nichapa P. | Kamphol H. | Sub | Suchock P. | Anat U. / Supajak S. | Kamphol H. | Supajak S. | Suraphong S. |  |  | submitted | 2026-08-21 | กำพล | Kamphol H. | BEM-K.Van |  | Platform Finishing on East Section | MDW-69311 | MDW-69312
246 |  | PSD4 | MDW | 3 | MDW-39281 | OLW-ME-24/0309 | 2026-06-11 | A | Internal Only | Detailed Design - Cladding Barrier between EWD and Station Structure on East Section | 4.4 | ST/AR | Nichapa P. | Kamphol H. | Sub | Suchock P. | Anat U. / Supajak S. | Kamphol H. | Supajak S. | Suraphong S. |  |  | submitted | 2026-08-21 | กำพล | Kamphol H. | BEM-K.Van |  | Cladding Barrier between EWD and Station Structure on East Section | MDW-69313 | MDW-69314
247 |  | PSD1 | MDW | 3 | MDW-39282 |  |  |  |  | Detailed Design - Holes for PSD Cable Wiring on East Section | 4.1 | ST/AR | Nichapa P. | Kamphol H. | Sub | Suchock P. | Anat U. / Supajak S. | Kamphol H. | Supajak S. | Suraphong S. |  |  |  | 2026-08-21 | กำพล | Kamphol H. | BEM-K.Van |  | Holes for PSD Cable Wiring on East Section | MDW-69315 | MDW-69316
248 |  | COM2 | MDW | 3 | MDW-39283 |  |  |  |  | Detailed Design - Intercom System in Cash Handling Room East Section | 10.2 | COM | Nichapa P. | Sorawit P. | Sub | Pratan L. | Sukij U. / Supajak S. | Sorawit P. | Supajak S. | Suraphong S. |  |  |  | 2026-12-19 | บัณฑิต | Sorawit P. | BEM-K.Van |  | Intercom System in Cash Handling Room East Section | MDW-69317 | MDW-69318
249 |  |  | MDW | 3 | MDW-39284 |  |  |  |  | Detailed Design - Power Cable and Conduits Modification for Walk-Through Metal Detector East Section | 10.3 | COM | Kusuma K. | Montri S. | Sub | Pratan L. | Sukij U. / Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | CANCLE |  | 0 | Montri S. | BEM-K.Van |  | Power Cable and Conduits Modification for Walk-Through Metal Detector East Section | MDW-69319 | MDW-69320
250 |  |  | MDW | 3 | MDW-39285 |  |  |  |  | Detailed Design - Provision of Cable Containment between OCC ORL and OCC BL | 10.8 | COM | Kusuma K. | Montri S. | Sub | Pratan L. | Sukij U. / Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | CANCLE |  | 0 | Montri S. | BEM-K.Van |  | Provision of Cable Containment between OCC ORL and OCC BL
251 |  |  | MDW | 3 | MDW-39286 |  |  |  |  | Detailed Design - Underground Cable Containment at Station Public Areas East Section | 10.10 | COM | Kusuma K. | Montri S. | Sub | Pratan L. | Sukij U. / Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | CANCLE |  | 0 | Montri S. | BEM-K.Van |  | Underground Cable Containment at Station Public Areas East Section | MDW-69321 | MDW-69322
252 |  | SIG5 | MDW | 3 | MDW-39287 | OLW-ME-24/0151 | 2025-09-25 | A | Internal Only | Detailed Design - Strobe Light at Buffer Stops East Section | 6.5 | EE | Nichapa P. | Jaturong W. | Sub | Suchock P. | Eddy / Supajak S. | Jaturong W. | Supajak S. | Suraphong S. |  |  | submitted | 2026-08-21 | ประธาน | Jaturong W. | BEM-K.Van |  | Strobe Light at Buffer Stops East Section | MDW-69323 | MDW-69324
253 |  | SIG3 | MDW | 3 | MDW-39288 | OLW-ME-24/0199 | 2025-10-27 | A | Internal Only | Detailed Design - Point Machine Foundation Construction on East Section | 6.3 | ST | Nichapa P. | Kamphol H. | Sub | Suchock P. | Eddy / Supajak S. | Kamphol H. | Supajak S. | Suraphong S. |  |  | submitted | 2026-08-21 | กำพล | Kamphol H. | BEM-K.Van |  | Point Machine Foundation Construction on East Section | MDW-69327 | MDW-69328
254 |  | GEN11 | MDW | 3 | MDW-39289 |  |  |  |  | Detailed Design - Earthing and Bonding for Raised Floor on East Section |  | EE/ME | Nichapa P. | Jaturong W. | Sub | Pratan L. | Supajak S. | Jaturong W. | Supajak S. | Suraphong S. |  |  |  | 2026-03-01 | ประธาน | Jaturong W. | BEM-K.Van |  | Earthing and Bonding for Raised Floor on East Section | MDW-69329 | MDW-69330
255 | Depot |  | MDW | 3 | MDW-39290 | OLW-ME-24/0211 | 2025-10-23 | A | Internal Only | Detailed Design - Modification Room for PSY at Depot Buildings - Building Services |  | ME | Nichapa P. | Boonprasert F. | Sub | Pratan L. | Supajak S. | Boonprasert F. | Supajak S. | Suraphong S. |  |  | submitted |  |  | Boonprasert F. | BEM-K.Van |  | Modification Room for PSY at Depot Buildings - Building Services | MDW-69331 | MDW-69332
256 |  |  | MDW | 3 | MDW-39291 | OLW-ME-24/0375 (** แบงค์ & พี่กำพล) | 2026-04-28 | A | Internal Only | Detailed Design - Conductor Rail Arrangement Modification at Main Line East Section |  |  | Nichapa P. | Kamphol H. | Sub | Suchock P. | Supajak S. | Kamphol H. | Supajak S. | Suraphong S. |  |  | submitted |  | 0 | Kamphol H. | BEM-K.Van |  | Conductor Rail Arrangement Modification at Main Line East Section | MDW-69333 | MDW-69334
257 |  |  | MDW | 3 | MDW-39291 | OLW-ME-24/0375 (** แบงค์ & พี่กำพล) | 2026-06-08 | B | Internal Only | Detailed Design - Conductor Rail Arrangement Modification at Main Line East Section |  |  | Nichapa P. | Kamphol H. | Sub | Suchock P. | Supajak S. | Kamphol H. | Supajak S. | Suraphong S. |  |  | submitted |  | 0 | Kamphol H. | BEM-K.Van |  | Conductor Rail Arrangement Modification at Main Line East Section | MDW-69333 | MDW-69334
258 | Depot |  | MDW | 3 | MDW-39292 | OLW-ME--24/0384 (** แบงค์ & พี่กำพล) | 2026-05-18 | A | Internal Only | Detailed Design - Conductor Rail Arrangement Modification at Depot |  |  | Nichapa P. | Kamphol H. | Sub | Suchock P. | Supajak S. | Kamphol H. | Supajak S. | Suraphong S. |  |  | submitted |  | 0 | Kamphol H. | BEM-K.Van |  | Conductor Rail Arrangement Modification at Depot | MDW-69335 | MDW-69336
259 |  | SIG2 | MDW | 3 | MDW-39293 | OLW-ME-24/0104 | 2025-10-27 | A | Internal Only | Detailed Design - Stabling Walkway Modification at Stabling Yard - Civil & AR |  |  | Nichapa P. | Kamphol H. | Sub | Suchock P. | Supajak S. | Kamphol H. | Supajak S. | Suraphong S. |  |  | submitted | 2026-06-22 | กำพล | Kamphol H. | BEM-K.Van |  | Stabling Walkway Modification at Stabling Yard - Civil & AR | MDW-69337 | MDW-69338
260 |  | GEN1 | MDW | 3 | MDW-39294 |  |  |  | Internal Only | Detailed Design - Provision of Architectural Work in new M&E UPS room at OR23 |  |  | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Supajak S. | Sahachart S. | Supajak S. | Suraphong S. |  |  |  | 2026-08-01 | - | Sahachart S. | BEM-K.Van |  | Provision of Architectural Work in new M&E UPS room at OR23 | MDW-69339 | MDW-69340
261 | Depot | MO-CK15.1 | MDW | 3 | MDW-39295 | OLW-ME-24/0303 | 2026-02-18 | A | Internal Only | Detailed Design - Dangerous Goods Building in Depot - Civil & AR | ADW | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Supajak S. | Suraphong S. |  | 2026-01-27 | submitted | 2026-05-01 | สหชาติ | Sahachart S. | BEM-K.Van |  | Dangerous Goods Building in Depot - Civil & AR | MDW-69341 | MDW-69342
262 | Depot | MO-CK15.2 | MDW | 3 | MDW-39296 | OLW-ME-24/0311 | 2026-02-27 | A | Internal Only | Detailed Design - Dangerous Goods Building in Depot - Building Services | ADW | EE/ME | Nichapa P. | Boonprasert |  | Pratan L. | Supajak S. | Boonprasert | Supajak S. | Suraphong S. |  | 2025-12-13 | submitted | 2026-05-01 | ประธาน | Boonprasert | BEM-K.Van |  | Dangerous Goods Building in Depot - Building Services | MDW-69343 | MDW-69344
263 |  | GEN4 | MDW | 3 | MDW-39297 | OLW-ME-24/0238 |  |  | Internal Only | Detailed Design - Training Room at Ratchada Station (Part 2) | ADW | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Supajak S. | Suraphong S. |  |  |  | 2026-04-01 | - | Sahachart S. | BEM-K.Van |  | Training Room at Ratchada Station (Part 2) | MDW-69345 | MDW-69346
264 |  | GEN4 | MDW | 3 | MDW-39298 |  |  |  | Internal Only | Detailed Design - Training Room at Ratchada Station (Part 2) - Building Services | ADW | EE/ME | Nichapa P. | Boonprasert |  | Pratan L. | Supajak S. | Boonprasert | Supajak S. | Suraphong S. |  |  | CANCLE | 2026-04-01 | - | Boonprasert | BEM-K.Van |  | Training Room at Ratchada Station (Part 2) - Building Services | MDW-69347 | MDW-69348
265 |  | GEN1 | MDW | 3 | MDW-39299 | OLW-ME-24/0254 | 2026-01-06 | A | Internal Only | Detailed Design - Provision of Air Conditioning System in Commercial Room at OR13-OR19 | ADW | ME | Nichapa P. | Boonprasert |  | Pratan L. | Supajak S. | Boonprasert | Supajak S. | Suraphong S. |  |  | submitted | 2026-08-01 | - | Boonprasert | BEM-K.Van |  | Provision of Air Conditioning System in Commercial Room at OR13-OR19 | MDW-69349 | MDW-69350
266 |  | GEN2 | MDW | 3 | MDW-39300 | OLW-ME-24/0271 | 2026-01-23 | A | Internal Only | Detailed Design - Modification SIG-PSD Office at Main Workshop - Building Services | ADW |  | Nichapa P. | Boonprasert |  | Pratan L. | Supajak S. | Boonprasert | Supajak S. | Suraphong S. |  |  | submitted | 2026-08-01 | - | Boonprasert | BEM-K.Van |  | Modification SIG-PSD Office at Main Workshop - Building Services | MDW-69351 | MDW-69352
267 |  | GEN2 | MDW | 3 | MDW-39301 | OLW-ME-24/0302 | 2026-02-18 | A | Internal Only | Detailed Design - Modification Backup CCR Room at Main Workshop - Building Services | ADW |  | Nichapa P. | Boonprasert |  | Pratan L. | Supajak S. | Boonprasert | Supajak S. | Suraphong S. |  |  | submitted | 2026-08-01 | - | Boonprasert | BEM-K.Van |  | Modification Backup CCR Room at Main Workshop - Building Services | MDW-69353 | MDW-69354
268 |  | GEN2 | MDW | 3 | MDW-39302 | OLW-ME-24/0283 | 2026-02-09 | A | Internal Only | Detailed Design - Modification SER at Main Workshop - Building Services | ADW |  | Nichapa P. | Boonprasert |  | Pratan L. | Supajak S. | Boonprasert | Supajak S. | Suraphong S. |  |  | submitted | 2026-08-01 | - | Boonprasert | BEM-K.Van |  | Modification SER at Main Workshop - Building Services | MDW-69355 | MDW-69356
269 |  | GEN2 | MDW | 3 | MDW-39303 | OLW-ME-24/0277 | 2026-02-03 | A | Internal Only | Detailed Design - Modification CER & SCADA Room at Main Workshop - Building Services | ADW |  | Nichapa P. | Boonprasert |  | Pratan L. | Supajak S. | Boonprasert | Supajak S. | Suraphong S. |  |  | submitted | 2026-08-01 | - | Boonprasert | BEM-K.Van |  | Modification CER & SCADA Room at Main Workshop - Building Services | MDW-69357 | MDW-69358
270 |  | COM5 | MDW | 3 | MDW-39304 | OLW-ME-24/0284 | 2026-02-26 | A | Internal Only | Detailed Design - MEA Radio | 10.5 | EE | Nichapa P. | Jaturong W. | Sub | Pratan L. | Sukij U. / Supajak S. | Jaturong W. | Sukij U. | Suraphong S. |  |  | submitted | 2026-09-20 | ประธาน | Jaturong W. | BEM-K.Van |  | MEA Radio | COM-69202 | COM-69203
271 |  | DWE13 | MDW | 3 | MDW-39305 | OLW-ME-24/0339 | 2026-03-26 | A | Internal Only | Detailed Design - Safety Provision for Maintenance Pits | [12 empty] | submitted | 2026-09-20 | สหชาติ | Sahachart S. | BEM-K.Van |  | Safety Provision for Maintenance Pits | MDW-69361 | MDW-69362
272 |  | GEN1 | MDW | 3 | MDW-39306 | OLW-ME-24/0402 | 2026-05-25 | A | Internal Only | Detilaed Design - Modification CER and First Aid Room at OR14 - Building Services | ADW |  | Nichapa P. | Boonprasert |  | Pratan L. | Supajak S. | Boonprasert | Supajak S. | Suraphong S. |  |  | submitted | 2026-08-01 | - | Boonprasert | BEM-K.Van | Lot2 MO-CK39 | Modification CER and First Aid Room at OR14 - Building Services | MDW-69363 | MDW-69364
273 |  | GEN1 | MDW | 3 | MDW-39307 | OLW-ME-24/0425 8 pages - A4 50 pages - A3 | 2026-07-01 | A | Internal Only | Detailed Design - Additional Fence at Back of House OR13 - OR22 and IVS East Section | ADW | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Supajak S. | Suraphong S. |  |  | submitted | 2026-08-01 | - | Sahachart S. | BEM-K.Van |  | Additional Fence at Back of House OR13 - OR22 and IVS East Section | MDW-69365 | MDW-69366
274 | Depot |  | MDW | 3 | MDW-39308 |  |  |  | Internal Only | Detailed Design - Additional Locking Devices for Main Line Tandem Turnouts 2007, 2010 & 2013 and Depot Turnout D16 | ADW | TRW | Nichapa P. | Kamphol H. | Sub | Suchock P. | Supajak S. | Kamphol H. | Supajak S. | Suraphong S. |  |  |  |  | 0 | Kamphol H. | BEM-K.Van |  | Additional Locking Devices for Main Line Tandem Turnouts 2007, 2010 & 2013 and Depot Turnout D16 | MDW-69367 | MDW-69368
275 |  | GEN2 | MDW | 3 | MDW-39309 |  |  |  | Internal Only | Detailed Design - Modification Air Conditioning System at CCR | ADW | ME | Nichapa P. | Boonprasert |  | Pratan L. | Supajak S. | Boonprasert | Supajak S. | Suraphong S. |  |  |  | 2026-08-01 | - | Boonprasert | BEM-K.Van |  | Modification Air Conditioning System at CCR | MDW-69369 | MDW-69370
276 |  | GEN19.1 | MDW | 3 | MDW-39310 |  |  |  | Internal Only | Detailed Design - Modification AFC Training Center at OR19 - Civil & AR | ADW | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Supajak S. | Suraphong S. |  |  |  | 2026-11-30 | สหชาติ | Sahachart S. | BEM-K.Van |  | Modification AFC Training Center at OR19 - Civil & AR | MDW-69371 | MDW-69372
277 |  | GEN19.2 | MDW | 3 | MDW-39311 |  |  |  | Internal Only | Detailed Design - Modification AFC Training Center at OR19 - Building Services | ADW | EE/ME | Nichapa P. | Jaturong W. |  | Pratan L. | Supajak S. | Jaturong W. | Supajak S. | Suraphong S. |  |  |  | 2026-11-30 | ประธาน | Jaturong W. | BEM-K.Van |  | Modification AFC Training Center at OR19 - Building Services | MDW-69373 | MDW-69374
278 |  | GEN2 | MDW | 3 | MDW-39312 |  |  |  | Internal Only | Detailed Design - Modification Electronic Workshop at Main Workshop - Building Services | ADW | ME | Nichapa P. | Boonprasert |  | Pratan L. | Supajak S. | Boonprasert | Supajak S. | Suraphong S. |  |  |  | 2026-08-01 | - | Boonprasert | BEM-K.Van |  | Modification Electronic Workshop at Main Workshop - Building Services | MDW-69375 | MDW-69376
279 |  | GEN2 | MDW | 3 | MDW-39313 |  |  |  | Internal Only | Detailed Design - Modification Battery Charger Room at Main Workshop - Building Services | ADW | ME | Nichapa P. | Boonprasert |  | Pratan L. | Supajak S. | Boonprasert | Supajak S. | Suraphong S. |  |  |  | 2026-08-01 | - | Boonprasert | BEM-K.Van |  | Modification Battery Charger Room at Main Workshop - Building Services | MDW-69377 | MDW-69378
280 |  | GEN2 | MDW | 3 | MDW-39314 |  |  |  | Internal Only | Detailed Design - Modification Machining Room at Main Workshop - Building Services | ADW | EE/ME | Nichapa P. | Atiraj K. |  | Pratan L. | Supajak S. | Atiraj K. | Ekasit L. | Suraphong S. |  |  |  | 2026-08-01 | - | Atiraj K. | BEM-K.Van |  | Modification Machining Room at Main Workshop - Building Services | MDW-69379 | MDW-69380
281 |  | GEN2 | MDW | 3 | MDW-39315 |  |  |  | Internal Only | Detailed Design - Modification Paint Shop Room at Main Workshop - Building Services | ADW | ME | Nichapa P. | Boonprasert |  | Pratan L. | Supajak S. | Boonprasert | Supajak S. | Suraphong S. |  |  |  | 2026-08-01 | - | Boonprasert | BEM-K.Van |  | Modification Paint Shop Room at Main Workshop - Building Services | MDW-69381 | MDW-69382
282 |  | GEN2 | MDW | 3 | MDW-39316 |  |  |  | Internal Only | Detailed Design - Modification Electronic Workshop, Battery Charger, Machining and Paint Shop at Main Workshop - Civil & AR | ADW | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Supajak S. | Suraphong S. |  |  |  | 2026-08-01 | - | Sahachart S. | BEM-K.Van |  | Modification Electronic Workshop, Battery Charger, Machining and Paint Shop at Main Workshop - Civil & AR | MDW-69383 | MDW-69384
283 |  |  | MDW |  | Modification Works LOT 2 | [19 empty] | 0 |  |  |  | #VALUE!
284 |  | MO-CK1.1 | MDW | 3 | MDW-39500 | OLW-ME-24/0198 | 2025-10-21 | A | Internal Only | Detailed Design - Modification Works : Storage Office in Main Workshop - Civil & AR | 55 | ST/AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  | 2026-02-27 | submitted | 2026-06-03 | สหชาติ | Sahachart S. | BEM-K.Van |  | Modification Works : Storage Office in Main Workshop - Civil & AR | MDW-69500 | MDW-69501
285 |  | MO-CK1.2 | MDW | 3 | MDW-39501 | OLW-ME-24/0327 | 2026-03-18 | A | Internal Only | Detailed Design - Modification Works : Storage Office in Main Workshop - Building Services | 55 | EE/ME | Nichapa P. | Atiraj K. |  | Pratan L. | Supajak S. | Atiraj K. | Ekasit L. | Suraphong S. |  | 2026-02-12 | submitted | 2026-06-04 | ประธาน | Atiraj K. | BEM-K.Van |  | Modification Works : Storage Office in Main Workshop - Building Services | MDW-69502 | MDW-69503
286 | Depot |  | MDW | 3 | MDW-39502 |  |  |  | Internal Only | Detailed Design - Modification Works : all Fire Alarm System Controller in Depot | 54 | EE/ME | Nichapa P. | Atiraj K. | Sub | Pratan L. | Supajak S. | Atiraj K. | Ekasit L. | Suraphong S. |  |  | CANCLE |  | 0 | Atiraj K. | BEM-K.Van |  | Modification Works : all Fire Alarm System Controller in Depot | MDW-69504 | MDW-69505
287 |  | MO-CK2.1 | MDW | 3 | MDW-39503 | OLW-ME-24/0194 | 2026-01-13 | A | Internal Only | Detailed Design - Modification Works : New MMC at Admin Building - Civil & AR | 53 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  | 2026-04-14 | submitted |  |  | Sahachart S. | BEM-K.Van |  | Modification Works : New MMC at Admin Building - Civil & AR | MDW-69506 | MDW-69507
288 |  | MO-CK2.1 | MDW | 3 | MDW-39503 | OLW-ME-DAS-MDW-39503-001 | 2026-02-12 | A1 | Internal Only | Detailed Design - Modification Works : New MMC at Admin Building - Civil & AR | 53 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  | 2026-04-14 | submitted |  |  | Sahachart S. | BEM-K.Van |  | Modification Works : New MMC at Admin Building - Civil & AR | MDW-69506 | MDW-69507
289 |  | MO-CK2.1 | MDW | 3 | MDW-39503 | OLW-ME-DAS-MDW-39503-002 |  | A2 | Internal Only | Detailed Design - Modification Works : New MMC at Admin Building - Civil & AR | 53 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  | 2026-04-14 |  |  |  | Sahachart S. | BEM-K.Van |  | Modification Works : New MMC at Admin Building - Civil & AR | MDW-69506 | MDW-69507
290 |  | MO-CK2.2 | MDW | 3 | MDW-39504 | OLW-ME-24/0388 | 2026-05-18 | A | Internal Only | Detailed Design - Modification Works : New MMC at Admin Building - Building Services | 53 | EE/ME | Nichapa P. | Atiraj K. | Sub | Pratan L. | Supajak S. | Atiraj K. | Ekasit L. | Suraphong S. |  | 2026-02-28 | submitted |  |  | Atiraj K. | BEM-K.Van |  | Modification Works : New MMC at Admin Building - Building Services | MDW-69508 | MDW-69509
291 |  | MO-BEM1.1 | MDW | 3 | MDW-39505 | OLW-ME-24/0241 | 2025-12-12 | A | Internal Only | Detailed Design - Modification Works : Walkway with Roof from Main Workshop to Stabling Yard - Civil & AR | 1 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  | 2026-04-28 | submitted | 2026-08-02 | สหชาติ | Sahachart S. | BEM-K.Van |  | Modification Works : Walkway with Roof from Main Workshop to Stabling Yard - Civil & AR | MDW-69510 | MDW-69511
292 |  | MO-BEM1.1 | MDW | 3 | MDW-39505 | OLW-ME-DAS-MDW-39505-001 | 2026-02-25 | A1 | Internal Only | Detailed Design - Modification Works : Walkway with Roof from Main Workshop to Stabling Yard - Civil & AR | 1 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  | 2026-04-28 | submitted | 2026-08-02 | สหชาติ | Sahachart S. | BEM-K.Van |  | Modification Works : Walkway with Roof from Main Workshop to Stabling Yard - Civil & AR | MDW-69510 | MDW-69511
293 |  | MO-BEM1.1 | MDW | 3 | MDW-39505 | OLW-ME-DAS-MDW-39505-002 | เตรียมออก 9/5/26, 2/6/26 | A2 | Internal Only | Detailed Design - Modification Works : Walkway with Roof from Main Workshop to Stabling Yard - Civil & AR | 1 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  | 2026-04-28 |  | 2026-08-02 | สหชาติ | Sahachart S. | BEM-K.Van |  | Modification Works : Walkway with Roof from Main Workshop to Stabling Yard - Civil & AR | MDW-69510 | MDW-69511
294 |  | MO-BEM1.2 | MDW | 3 | MDW-39506 | OLW-ME-24/0298 | 2026-02-17 | A | Internal Only | Detailed Design - Modification Works : Walkway with Roof from Main Workshop to Stabling Yard - Building Services | 1 | EE | Nichapa P. | Atiraj K. |  | Pratan L. | Supajak S. | Atiraj K. | Ekasit L. | Suraphong S. |  | 2026-04-28 | submitted | 2026-08-02 | ประธาน | Atiraj K. | BEM-K.Van |  | Modification Works : Walkway with Roof from Main Workshop to Stabling Yard - Building Services | MDW-69512 | MDW-69513
295 |  | MO-BEM2 | MDW | 3 | MDW-39507 | OLW-ME-24/0239 | 2025-12-11 | A | Internal Only | Detailed Design - Modification Works : High Roof in front of MWS Entrance and Store Entrance - Civil & AR | 2 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  | 2026-02-13 | submitted | 2026-08-01 | สหชาติ | Sahachart S. | BEM-K.Van |  | Modification Works : High Roof in front of MWS Entrance and Store Entrance - Civil & AR | MDW-69514 | MDW-69515
296 |  | MO-BEM2 | MDW | 3 | MDW-39507 | OLW-ME-24/0239 | 2026-01-20 | DAS (A1) | Internal Only | Detailed Design - Modification Works : High Roof in front of MWS Entrance and Store Entrance - Civil & AR | 2 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  | 2026-02-13 | submitted | 2026-08-01 | สหชาติ | Sahachart S. | BEM-K.Van |  | Modification Works : High Roof in front of MWS Entrance and Store Entrance - Civil & AR | MDW-69514 | MDW-69515
297 |  |  | MDW | 3 | MDW-39508 |  |  |  | Internal Only | Detailed Design - Modification Works : High Roof in front of MWS Entrance and Store Entrance - Building Services | 2 | EE | Nichapa P. | Atiraj K. |  | Pratan L. | Supajak S. | Atiraj K. | Ekasit L. | Suraphong S. |  |  | CANCLE |  | 0 | Atiraj K. | BEM-K.Van |  | Modification Works : High Roof in front of MWS Entrance and Store Entrance - Building Services | MDW-69516
298 |  | MO-BEM3 | MDW | 3 | MDW-39509 | OLW-ME-24/0246 | 2025-12-18 | A | Internal Only | Detailed Design - Modification Works : High Roof at Under Floor Wheel Lathe - Civil & AR | 3 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  | 2026-02-13 | submitted | 2026-08-04 | สหชาติ | Sahachart S. | BEM-K.Van |  | Modification Works : High Roof at Under Floor Wheel Lathe - Civil & AR | MDW-69518
299 |  |  | MDW | 3 | MDW-39510 |  |  |  | Internal Only | Detailed Design - Modification Works : High Roof at Under Floor Wheel Lathe - Building Services | 3 | EE | Nichapa P. | Atiraj K. |  | Pratan L. | Supajak S. | Atiraj K. | Ekasit L. | Suraphong S. |  |  | CANCLE |  | 0 | Atiraj K. | BEM-K.Van |  | Modification Works : High Roof at Under Floor Wheel Lathe - Building Services | MDW-69520
300 |  | MO-BEM4.1 | MDW | 3 | MDW-39511 | OLW-ME-24/0248 | 2025-12-18 | A | Internal Only | Detailed Design - Modification Works : Maintenance Office Rooms at Main Workshop - Civil & AR | 4 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  | 2026-04-13 | submitted | 2026-07-03 | สหชาติ | Sahachart S. | BEM-K.Van |  | Modification Works : Maintenance Office Rooms at Main Workshop - Civil & AR | MDW-69522 | MDW-69523
301 |  | MO-BEM4.1 | MDW | 3 | MDW-39511 | OLW-ME-24/0248 | 2026-05-06 | B | Internal Only | Detailed Design - Modification Works : Maintenance Office Rooms at Main Workshop - Civil & AR | 4 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  | 2026-04-13 | submitted | 2026-07-03 | สหชาติ | Sahachart S. | BEM-K.Van |  | Modification Works : Maintenance Office Rooms at Main Workshop - Civil & AR | MDW-69522 | MDW-69523
302 |  | MO-BEM4.2 | MDW | 3 | MDW-39512 | OLW-ME-24/0411 | 2026-06-04 | A | Internal Only | Detailed Design - Modification Works : Maintenance Office Rooms at Main Workshop - Building Services | 4 | EE/ME | Nichapa P. | Atiraj K. |  | Pratan L. | Supajak S. | Atiraj K. | Ekasit L. | Suraphong S. |  | 2026-04-13 | submitted | 2026-07-04 | ประธาน | Atiraj K. | BEM-K.Van |  | Modification Works : Maintenance Office Rooms at Main Workshop - Building Services | MDW-69524 | MDW-69525
303 |  | MO-BEM5 | MDW | 3 | MDW-39513 | OLW-ME-24/0200 | 2026-02-20 | A | Internal Only | Detailed Design - Modification Works : Concrete Car Barrier in front of Main Workshop | 5 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  | 2026-10-14 | submitted | 2027-01-01 | สหชาติ | Sahachart S. | BEM-K.Van |  | Modification Works : Concrete Car Barrier in front of Main Workshop | MDW-69526 | MDW-69527
304 | Depot | MO-BEM15.1 | MDW | 3 | MDW-39514 |  | 2025-12-11 | A | Internal Only | Detailed Design - Modification Works : Car Park Roof and Motorcycle in Depot - Civil & AR | 6 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  | 2026-02-28 | submitted | 2026-08-03 | สหชาติ | Sahachart S. | BEM-K.Van |  | Modification Works : Car Park Roof and Motorcycle in Depot - Civil & AR | MDW-69528 | MDW-69529
305 | Depot | MO-BEM15.2 | MDW | 3 | MDW-39515 | OLW-ME-24/0378 | 2026-05-05 | A | Internal Only | Detailed Design - Modification Works : Car Park Roof and Motorcycle in Depot - Building Services | 6 | EE | Nichapa P. | Atiraj K. |  | Pratan L. | Supajak S. | Atiraj K. | Ekasit L. | Suraphong S. |  | 2026-02-28 | submitted | 2026-08-03 | ประธาน | Atiraj K. | BEM-K.Van |  | Modification Works : Car Park Roof and Motorcycle in Depot - Building Services | MDW-69530 | MDW-69531
306 | Depot | MO-BEM14.1 | MDW | 3 | MDW-39516 | OLW-ME-24/0247 | 2025-12-18 | A | Internal Only | Detailed Design - Modification Works : Walkway Bridge between BL Depot and ORL Depot - Civil & AR | 7 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  | 2026-02-28 | submitted | 2026-08-02 | สหชาติ | Sahachart S. | BEM-K.Van |  | Modification Works : Walkway Bridge between BL Depot and ORL Depot - Civil & AR | MDW-69532 | MDW-69533
307 | Depot | MO-BEM14.2 | MDW | 3 | MDW-39517 | OLW-ME-24/0393 | 2026-05-20 | A | Internal Only | Detailed Design - Modification Works : Walkway Bridge between BL Depot and ORL Depot - Building Services | 7 | EE | Nichapa P. | Atiraj K. |  | Pratan L. | Supajak S. | Atiraj K. | Ekasit L. | Suraphong S. |  | 2026-01-14 | submitted | 2026-08-03 | ประธาน | Atiraj K. | BEM-K.Van |  | Modification Works : Walkway Bridge between BL Depot and ORL Depot - Building Services | MDW-69534 | MDW-69535
308 | Depot | MO-BEM26 | MDW | 3 | MDW-39518 | OLW-ME-24/0265 เตรียมออก 22/1/2026 |  |  | Internal Only | Detailed Design - Modification Works : Street Lighting between MRTA Fence and Depot Slab | 8 | EE | Nichapa P. | Jaturong W. |  | Pratan L. | Supajak S. | Jaturong W. | Ekasit L. | Suraphong S. |  | 2026-04-14 |  | 2026-08-01 | ประธาน | Jaturong W. | BEM-K.Van |  | Modification Works : Street Lighting between MRTA Fence and Depot Slab | MDW-69536 | MDW-69537
309 | Depot | MO-BEM16 | MDW | 3 | MDW-39519 | OLW-ME-24/0279 | 2026-06-16 | A | Internal Only | Detailed Design - Modification Works : Walkway with Roof in Depot Area - Civil & AR | 9,10,14,15,20 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  | 2026-06-15 | submitted | 2026-08-01 | สหชาติ | Sahachart S. | BEM-K.Van |  | Modification Works : Walkway with Roof in Depot Area - Civil & AR | MDW-69538 | MDW-69539
310 | Depot | MO-BEM25.2 | MDW | 3 | MDW-39520 | เตรียมออก 9/7/26 OLW-ME-24/0452 |  |  | Internal Only | Detailed Design - Modification Works : Sliding Gate, Chain Link Fence and Walkway with Roof in Depot Area - Building Services | 9,10,14,15,20 | EE | Nichapa P. | Atiraj K. |  | Pratan L. | Supajak S. | Atiraj K. | Ekasit L. | Suraphong S. |  | 2026-06-14 |  | 2026-10-01 | ประธาน | Atiraj K. | BEM-K.Van |  | Modification Works : Sliding Gate, Chain Link Fence and Walkway with Roof in Depot Area - Building Services | MDW-69540 | MDW-69541
311 | Depot | MO-BEM29 | MDW | 3 | MDW-39521 | OLW-ME-24/0249 | 2026-01-05 | A | Internal Only | Detailed Design - Modification Works : Walkway Bridge and Walkway over Canal in Depot | 11,12 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  | 2026-08-15 | submitted | 2027-01-01 | สหชาติ | Sahachart S. | BEM-K.Van |  | Modification Works : Walkway Bridge and Walkway over Canal in Depot | MDW-69542 | MDW-69543
312 | Depot | MO-BEM12 | MDW | 3 | MDW-39522 | OLW-ME-24/0289 | 2026-02-17 | A | Internal Only | Detailed Design - Modification Works : Rain Protection and Zero Discharge Water treatment in Depot - Civil & AR | 13 23 | AR/ME | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  | 2026-04-29 | submitted | 2026-08-05 | สหชาติ | Sahachart S. | BEM-K.Van |  | Modification Works : Rain Protection and Zero Discharge Water treatment in Depot - Civil & AR | MDW-69544 | MDW-69545
313 |  | MO-BEM20 | MDW | 3 | MDW-39523 | OLW-ME-24/0244 | 2025-12-15 | A | Internal Only | Detailed Design - Modification Works : Cold Water System at Admin Building Landscape | 16 | ME | Nichapa P. | Boonprasert |  | Pratan L. | Supajak S. | Boonprasert | Ekasit L. | Suraphong S. |  | 2026-04-23 | submitted | 2026-06-01 | ประธาน | Boonprasert | BEM-K.Van |  | Modification Works : Cold Water System at Admin Building Landscape | MDW-69546 | MDW-69547
314 | Depot | MO-BEM28.1 | MDW | 3 | MDW-39524 | OLW-ME-24/0281 | 2026-02-24 | A | Internal Only | Detailed Design - Modification Works : Walkway under Depot Slab for Maintenance Service - Civil & AR | 17 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  | 2026-09-14 | submitted | 2027-01-02 | สหชาติ | Sahachart S. | BEM-K.Van |  | Modification Works : Walkway under Depot Slab for Maintenance Service - Civil & AR | MDW-69548 | MDW-69549
315 | Depot | MO-BEM28.2 | MDW | 3 | MDW-39525 | OLW-ME-24/0398 | 2026-05-20 | A | Internal Only | Detailed Design - Modification Works : Walkway under Depot Slab for Maintenance Service - Building Services |  | EE | Nichapa P. | Atiraj K. |  | Pratan L. | Supajak S. | Atiraj K. | Ekasit L. | Suraphong S. |  | 2026-09-14 | submitted | 2027-01-03 | ประธาน | Atiraj K. | BEM-K.Van |  | Modification Works : Walkway under Depot Slab for Maintenance Service - Building Services | MDW-69550 | MDW-69551
316 |  | MO-BEM10 | MDW | 3 | MDW-39526 | OLW-ME-24/0240 | 2025-12-11 | A | Internal Only | Detailed Design - Modification Works : FHC Modification at Stabling Yard | 19 | ME | Nichapa P. | Boonprasert |  | Pratan L. | Supajak S. | Boonprasert | Ekasit L. | Suraphong S. |  | 2026-01-12 | submitted | 2026-05-01 | ประธาน | Boonprasert | BEM-K.Van |  | Modification Works : FHC Modification at Stabling Yard | MDW-69552 | MDW-69553
317 | Depot | MO-BEM23 | MDW | 3 | MDW-39527 | OLW-ME-24/0331 | 2026-03-23 | A | Internal Only | Detailed Design - Modification Works : Hand Sink with Emergency Eye Wash Installation in Depot | 21 | ME | Nichapa P. | Boonprasert |  | Pratan L. | Supajak S. | Boonprasert | Ekasit L. | Suraphong S. |  | 2026-08-30 | submitted | 2027-01-01 | ประธาน | Boonprasert | BEM-K.Van |  | Modification Works : Hand Sink with Emergency Eye Wash Installation in Depot | MDW-69554 | MDW-69555
318 |  | MO-BEM11.1 | MDW | 3 | MDW-39528 | OLW-ME-24/0256 | 2026-01-13 | A | Internal Only | Detailed Design - Modification Works : Washing Area in Cleaning Staff Room at Stabling Yard - Civil & AR | 22 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  | 2026-06-03 | submitted | 2026-08-03 | สหชาติ | Sahachart S. | BEM-K.Van |  | Modification Works : Washing Area in Cleaning Staff Room at Stabling Yard - Civil & AR | MDW-69556 | MDW-69557
319 |  | MO-BEM11.2 | MDW | 3 | MDW-39529 | OLW-ME-24/0267 | 2026-01-19 | A | Internal Only | Detailed Design - Modification Works : Washing Area in Cleaning Staff Room at Stabling Yard - Building Services |  | ME | Nichapa P. | Boonprasert |  | Pratan L. | Supajak S. | Boonprasert | Ekasit L. | Suraphong S. |  | 2026-04-14 | submitted | 2026-08-04 | ประธาน | Boonprasert | BEM-K.Van |  | Modification Works : Washing Area in Cleaning Staff Room at Stabling Yard - Building Services | MDW-69558 | MDW-69559
320 | Depot | MO-BEM13.2 | MDW | 3 | MDW-39530 | OLW-ME-24/0308 | 2026-02-21 | A | Internal Only | Detailed Design - Modification Works : Zero Discharge Water treatment in Depot - Building Services | 19 | ME | Nichapa P. | Boonprasert |  | Pratan L. | Supajak S. | Boonprasert | Ekasit L. | Suraphong S. |  |  | submitted | 2027-01-01 | ประธาน | Boonprasert | BEM-K.Van |  | Modification Works : Zero Discharge Water treatment in Depot - Building Services | MDW-69560 | MDW-69561
321 | Depot | MO-BEM24 | MDW | 3 | MDW-39531 | OLW-ME-24/0335 | 2026-03-24 | A | Internal Only | Detailed Design - Modification Works : Guard rail protection for FHC in Depot Area | 24 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  | 2026-03-14 | submitted | 2026-06-01 | สหชาติ | Sahachart S. | BEM-K.Van |  | Modification Works : Guard rail protection for FHC in Depot Area | MDW-69562 | MDW-69563
322 |  | MO-BEM22 | MDW | 3 | MDW-39532 |  |  |  | Internal Only | Detailed Design - Modification Works : Barbed Wire Fences for MRTA Chain Link at Klong Chourdyai | 25 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  | 2026-08-30 |  | 2027-01-01 | สหชาติ | Sahachart S. | BEM-K.Van |  | Modification Works : Barbed Wire Fences for MRTA Chain Link at Klong Chourdyai | MDW-69564 | MDW-69565
323 | Depot | Add งานใน Master เพิ่ม | MDW | 3 | MDW-39533 |  |  |  | Internal Only | Detailed Design - Modification Works : Car Barrier Gate at Depot Area | 26 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. | [5 empty] | Sahachart S. | BEM-K.Van |  | Modification Works : Car Barrier Gate at Depot Area | MDW-69566 | MDW-69567
324 | Depot | MO-BEM21.1 | MDW | 3 | MDW-39534 | OLW-ME-24/0243 | 2026-03-23 | A | Internal Only | Detailed Design - Modification Works : Security Guard Box at ORL Depot Entrance - Civil & AR | 31 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  |  | submitted | 2027-01-02 | สหชาติ | Sahachart S. | BEM-K.Van |  | Modification Works : Security Guard Box at ORL Depot Entrance - Civil & AR | MDW-69568 | MDW-69569
325 | Depot | MO-BEM21.1 | MDW | 3 | MDW-39534 | OLW-ME-24/0243 | เตรียมออก 27/7/26 | B | Internal Only | Detailed Design - Modification Works : Security Guard Box at ORL Depot Entrance - Civil & AR | 31 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  |  |  | 2027-01-02 | สหชาติ | Sahachart S. | BEM-K.Van |  | Modification Works : Security Guard Box at ORL Depot Entrance - Civil & AR | MDW-69568 | MDW-69569
326 | Depot | MO-BEM21.2 | MDW | 3 | MDW-39535 | เตรียมออก 18/7/26 OLW-ME-24/0475 |  |  | Internal Only | Detailed Design - Modification Works : Security Guard Box at ORL Depot Entrance - Building Services |  | EE/ME | Nichapa P. | Atiraj K. |  | Pratan L. | Supajak S. | Atiraj K. | Ekasit L. | Suraphong S. |  |  |  | 2027-01-03 | ประธาน |  | BEM-K.Van |  | Modification Works : Security Guard Box at ORL Depot Entrance - Building Services | MDW-69570 | MDW-69571
327 |  | MO-BEM8 | MDW | 3 | MDW-39536 | OLW-ME-24/0389 Total 24 pages A3 - 9 pages | 2026-06-06 | A | Internal Only | Detailed Design - Modification Works : Soundproof Installation and Company Logo at CCR Room | 33 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  | 2026-01-27 | submitted | 2026-05-01 | สหชาติ | Sahachart S. | BEM-K.Van |  | Modification Works : Soundproof Installation and Company Logo at CCR Room | MDW-69572 | MDW-69573
328 |  |  | MDW | [7 empty] | 34 | [13 empty] | 0 | 0 | 0 |  | #VALUE!
329 |  | MO-BEM43 | MDW | 3 | MDW-39537 |  |  |  | Internal Only | Detailed Design - Modification Works : Fence Installation at Ladder in VS, IVS Buildings | 40 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  | 2026-03-31 |  | 2026-09-01 | สหชาติ | Sahachart S. | BEM-K.Van |  | Modification Works : Fence Installation at Ladder in VS, IVS Buildings | MDW-69574 | MDW-69575
330 |  | MO-BEM44 | MDW | 3 | MDW-39538 |  |  |  | Internal Only | Detailed Design - Modification Works : Anti-Slide Signage at Escalator for all Stations | 41 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  | 2026-05-30 |  | 2026-09-01 | สหชาติ | Sahachart S. | BEM-K.Van |  | Modification Works : Anti-Slide Signage at Escalator for all Stations | MDW-69576 | MDW-69577
331 |  | MO-BEM50 | MDW | 3 | MDW-39539 |  |  |  | Internal Only | Detailed Design - Modification Works : Roofing over Control Panel Installation at VS, IVS Buildings | 42 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  | 2026-10-29 |  | 2027-01-01 | สู่โชค | Sahachart S. | BEM-K.Van |  | Modification Works : Roofing over Control Panel Installation at VS, IVS Buildings | MDW-69578 | MDW-69579
332 | Depot | MO-BEM47 | MDW | 3 | MDW-39540 |  |  |  | Internal Only | Detailed Design - Modification Works : Water Drop Protection for UPS Cabinet for all Stations and Depot | 44 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  | 2026-09-14 |  | 2027-01-01 | สหชาติ | Sahachart S. | BEM-K.Van |  | Modification Works : Water Drop Protection for UPS Cabinet for all Stations and Depot | MDW-69580 | MDW-69581
333 |  | MO-BEM48 | MDW | 3 | MDW-39541 |  |  |  | Internal Only | Detailed Design - Modification Works : Manual Call Point Cover in Public Area at all Stations | 45 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  | 2026-09-14 |  | 2027-01-01 | ประธาน | Sahachart S. | BEM-K.Van |  | Modification Works : Manual Call Point Cover in Public Area at all Stations | MDW-69582 | MDW-69583
334 |  | MO-BEM49 | MDW | 3 | MDW-39542 |  |  |  | Internal Only | Detailed Design - Modification Works : Emergency Stop Button Cover for Escalator at all Stations | 46 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  | 2026-09-14 |  | 2027-01-01 | สหชาติ | Sahachart S. | BEM-K.Van |  | Modification Works : Emergency Stop Button Cover for Escalator at all Stations | MDW-69584 | MDW-69585
335 |  | MO-CK4 | MDW | 3 | MDW-39543 | เตรียมออก 2/6/26 OLW-ME-24/0380 |  |  | Internal Only | Detailed Design - Modification Works : Bird & Rain Protection, Safety Hand Rail Installation at Admin Building | 47,48,49 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  | 2026-04-29 |  | 2026-08-01 | สหชาติ | Sahachart S. | BEM-K.Van |  | Modification Works : Bird & Rain Protection, Safety Hand Rail Installation at Admin Building | MDW-69586 | MDW-69587
336 | Depot | MO-CK10 | MDW | 3 | MDW-39544 |  |  |  | Internal Only | Detailed Design - Modification Works : Barbed Wire Fences for Depot slab | 50 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  | 2026-08-30 |  | 2027-01-01 | บัณฑิต/สหชาติ | Sahachart S. | BEM-K.Van |  | Modification Works : Barbed Wire Fences for Depot slab | MDW-69588 | MDW-69589
337 | Depot | MO-CK11 | MDW | 3 | MDW-39545 | OLW-ME-24/0280 | 2026-02-10 | A | Internal Only | Detailed Design - Modification Works : Chain Link Installation at Cut & Cover Depot Access | 51 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  | 2026-02-27 | submitted | 2026-06-01 | สหชาติ | Sahachart S. | BEM-K.Van |  | Modification Works : Chain Link Installation at Cut & Cover Depot Access | MDW-69590 | MDW-69591
338 | Depot | MO-CK12 | MDW | 3 | MDW-39546 | OLW-ME-24/0381 | 2026-06-20 | A | Internal Only | Detailed Design - Modification Works : Chain Link Installation under Depot Slab | 52 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  | 2026-06-30 | submitted | 2027-01-01 | สหชาติ | Sahachart S. | BEM-K.Van |  | Modification Works : Chain Link Installation under Depot Slab | MDW-69592 | MDW-69593
339 |  | MO-CK5 | MDW | 3 | MDW-39547 | เตรียมออก 16/12/2025 |  |  | Internal Only | Detailed Design - Modification Works : Door and Lockset Modification at OCC Building | 56,57 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  | 2026-05-14 |  | 2026-08-02 | สหชาติ | Sahachart S. | BEM-K.Van |  | Modification Works : Door and Lockset Modification at OCC Building | MDW-69594 | MDW-69595
340 |  | MO-CK8 | MDW | 3 | MDW-39548 | OLW-ME-24/0270 | 2026-01-26 | A | Internal Only | Detailed Design - Modification Works : Air Conditioning System Installation at Pantry room OCC Building | 59 | ME | Nichapa P. | Boonprasert |  | Pratan L. | Supajak S. | Boonprasert | Ekasit L. | Suraphong S. |  | 2026-04-29 | submitted | 2026-08-05 | ประธาน | Boonprasert | BEM-K.Van |  | Modification Works : Air Conditioning System Installation at Pantry room OCC Building | MDW-69596 | MDW-69597
341 |  | MO-CK13.2 | MDW | 3 | MDW-39549 | OLW-ME-24/0269 | 2026-01-23 | A | Internal Only | Detailed Design - Modification Works : Maintenance Room and Satellite Store at Stations - Building Services | 61 | EE/ME | Nichapa P. | Boonprasert |  | Pratan L. | Supajak S. | Boonprasert | Ekasit L. | Suraphong S. |  | 2026-08-30 | submitted | 2027-01-03 | ประธาน | Boonprasert | BEM-K.Van |  | Modification Works : Maintenance Room and Satellite Store at Stations - Building Services | MDW-69598 | MDW-69599
342 |  | MO-CK13.1 | MDW | 3 | MDW-39550 |  |  |  | Internal Only | Detailed Design - Modification Works : Satellite Store at OR21 - Civil & AR | 61 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  | 2026-08-30 |  | 2027-01-02 | สหชาติ | Sahachart S. | BEM-K.Van | เริ่มทำแบบแล้ว | Modification Works : Satellite Store at OR21 - Civil & AR | MDW-69600 | MDW-695601
343 |  | MO-CK14 | MDW | 3 | MDW-39551 | OLW-ME-24/0261 | 2026-01-13 | A | Internal Only | Detailed Design - Modification Works : Train Crew Office at OR29 (รวมงาน AR และ Builind Service) | 62 | AR/ME | Nichapa P. | Boonprasert |  | Pratan L. | Supajak S. | Boonprasert | Ekasit L. | Suraphong S. |  | 2026-03-14 | submitted | 2026-07-01 | ประธาน | Boonprasert | BEM-K.Van |  | Modification Works : Train Crew Office at OR29 (รวมงาน AR และ Builind Service) | MDW-69602 | MDW-69603
344 |  | MO-CK9 | MDW | 3 | MDW-39552 | OLW-ME-24/0313 | 2026-05-08 | A | Internal Only | Detailed Design - Modification Works : Hand Rail Installation at Walk Way in Stabling Yard | 60 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  | 2026-05-30 | submitted | 2026-10-01 | สหชาติ | Sahachart S. | BEM-K.Van |  | Modification Works : Hand Rail Installation at Walk Way in Stabling Yard | MDW-69604 | MDW-69605
345 |  | MO-BEM46 | MDW | 3 | MDW-39553 |  |  |  | Internal Only | Detailed Design - Modification Works : Ladder to Access the Fire Valve at Omega Joints for all Underground Stations | 43 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  | 2026-09-14 |  | 2027-01-01 | สหชาติ | Sahachart S. | BEM-K.Van |  | Modification Works : Ladder to Access the Fire Valve at Omega Joints for all Underground Stations | MDW-69606 | MDW-69607
346 |  |  | MDW | [5 empty] | Internal Only | Detailed Design - Modification Works : Fire Suspension Control Panel Cover Installation at Tunnel Main Line | 39 | ME |  |  |  |  | Supajak S. |  | Ekasit L. | Suraphong S. |  |  | CANCLE |  | 0 | 0 | 0 |  | Modification Works : Fire Suspension Control Panel Cover Installation at Tunnel Main Line
347 |  | MO-BEM53.1 | MDW | 3 | MDW-39554 | เตรียมออก 29/6/2026 Olw-ME-24/0437 | 10 pages, dwg 4 sheets |  | Internal Only | Detailed Design - Modification Works : Security Guard Box at OCC Parking Area - Civil & AR | 32 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  | 2026-09-14 |  | 2027-01-02 | สหชาติ | Sahachart S. | BEM-K.Van |  | Modification Works : Security Guard Box at OCC Parking Area - Civil & AR | MDW-69608 | MDW-69609
348 |  | MO-BEM53.2 | MDW | 3 | MDW-39555 |  |  |  | Internal Only | Detailed Design - Modification Works : Security Guard Box at OCC Parking Area - Building Services |  | EE | Nichapa P. | Atiraj K. |  | Pratan L. | Supajak S. | Atiraj K. | Ekasit L. | Suraphong S. |  | 2026-09-14 |  | 2027-01-02 | ประธาน | Atiraj K. | BEM-K.Van |  | Modification Works : Security Guard Box at OCC Parking Area - Building Services | MDW-69610 | MDW-69611
349 |  | MO-CK7 | MDW | 3 | MDW-39556 | OLW-ME-24/0259 | 2026-01-15 | A | Internal Only | Detailed Design - Modification Works : Additional Small Power System at OCC Building | 58 | EE | Nichapa P. | Atiraj K. |  | Pratan L. | Supajak S. | Atiraj K. | Ekasit L. | Suraphong S. |  | 2026-05-14 | submitted | 2026-08-04 | ประธาน | Atiraj K. | BEM-K.Van |  | Modification Works : Additional Small Power System at OCC Building | MDW-69612 | MDW-69613
350 | Depot | MO-BEM25.1 | MDW | 3 | MDW-39557 |  |  |  | Internal Only | Detailed Design - Modification Works : Sliding Gate and Chain Link Fence in Depot Area - Civil & AR |  | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  |  |  | 2026-10-01 | สหชาติ | Sahachart S. | BEM-K.Van |  | Modification Works : Sliding Gate and Chain Link Fence in Depot Area - Civil & AR | MDW-69614 | MDW-69615
351 |  |  | RST | 3 | RST-39001 |  |  |  |  | Detailed Design - Driver Training Simulator |  |  | Nichapa P. | Somsak S. | Sub | Suchock P. | Komsun N./ Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  | CANCLE |  | 0 |  |  |  | Driver Training Simulator | RST-69003 | RST-69004
352 |  |  | RST | 3 | RST-39002 |  |  |  |  | Detailed Design - List of Spare Part - Driver Training Simulator |  |  | Nichapa P. | Somsak S. | Sub | Suchock P. | Komsun N./ Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  | CANCLE |  | 0 |  |  |  | List of Spare Part - Driver Training Simulator
353 |  |  | RST | 3 | RST-39003 |  |  |  |  | Detailed Design - Sample List - Driver Training Simulator |  |  | Nichapa P. | Somsak S. | Sub | Suchock P. | Komsun N./ Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  | CANCLE |  | 0 |  |  |  | Sample List - Driver Training Simulator
354 |  | RST1 | RST | 3 | RST-39004 |  |  |  |  | Detailed Design - RAM Report - Driver Training Simulator |  |  | Nichapa P. | Somsak S. | Sub | Suchock P. | Komsun N./ Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  |  | 2026-09-20 | ธัญวิทย์ |  |  |  | RAM Report - Driver Training Simulator
355 |  | RST1 | RST | 3 | RST-39005 |  |  |  |  | Detailed Design - Mechanism Design - Driver Training Simulator |  |  | Nichapa P. | Somsak S. | Sub | Suchock P. | Komsun N./ Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  | CANCLE | 2026-09-20 | ธัญวิทย์ |  |  |  | Mechanism Design - Driver Training Simulator
356 |  | RST1 | RST | 3 | RST-39006 |  |  |  |  | Detailed Design - Electrical Circuit Design - Driver Training Simulator |  |  | Nichapa P. | Somsak S. | Sub | Suchock P. | Komsun N./ Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  | CANCLE | 2026-09-20 | ธัญวิทย์ |  |  |  | Electrical Circuit Design - Driver Training Simulator
357 |  | RST1 | RST | 3 | RST-39007 |  |  |  |  | Detailed Design - Room Layout Design - Driver Training Simulator |  |  | Nichapa P. | Somsak S. | Sub | Suchock P. | Komsun N./ Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  | CANCLE | 2026-09-20 | ธัญวิทย์ |  |  |  | Room Layout Design - Driver Training Simulator
358 |  | RST1 | RST | 3 | RST-39008 |  |  |  |  | Detailed Design - Failure Mode and Criticality Analysis - Driver Training Simulator |  |  | Nichapa P. | Somsak S. | Sub | Suchock P. | Komsun N./ Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  |  | 2026-09-20 | ธัญวิทย์ |  |  |  | Failure Mode and Criticality Analysis - Driver Training Simulator
359 |  |  | RST | 3 | RST-39009 |  |  |  |  | Detailed Design - Functional Location Data - Driver Trianing Simulator |  |  | Nichapa P. | Somsak S. | Sub | Suchock P. | Komsun N./ Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  | CANCLE |  | 0 |  |  |  | Functional Location Data - Driver Trianing Simulator
360 |  |  | RST | 3 | RST-39010 |  |  |  |  | Detailed Design - Maintenance Planning Data - Driver Training Simulator |  |  | Nichapa P. | Somsak S. | Sub | Suchock P. | Komsun N./ Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  | CANCLE |  | 0 |  |  |  | Maintenance Planning Data - Driver Training Simulator
361 |  |  | RST | 3 | RST-39011 |  |  |  |  | Detailed Design - Materials Management Data - Driver Training Simulator |  |  | Nichapa P. | Somsak S. | Sub | Suchock P. | Komsun N./ Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  | CANCLE |  | 0 |  |  |  | Materials Management Data - Driver Training Simulator
362 |  |  | RST | 3 | RST-39012 |  |  |  |  | Detailed Design - Scenario Document - Driver Training Simulator |  |  | Nichapa P. | Somsak S. | Sub | Suchock P. | Komsun N./ Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  | CANCLE |  | 0 |  |  |  | Scenario Document - Driver Training Simulator

## สรุปรายการส่งพี่โป้ง (hidden)
Modification & Additional Works in Depot
Location | Code | No | Activity Name | CK Responsible Person | Design (PLAN) | Design (%) | Design (Status) | Procurement (PLAN) | Procurement (%) | Procurement (Status) | Construction /Installation (PLAN) | Construction /Installation (%) | Construction /Installation (Status) | Inspection (PLAN) | Inspection (%) | Inspection (Status)
Lot01
Lot01 | GEN7.1 | 1 | Dangerous Waste Storage Building in Depot - Civil & AR | สหชาติ | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed | 2026-04-30 | 100% | Completed | 2026-06-08 | 100% | Completed
Lot01 | GEN7.2 | 2 | Dangerous Waste Storage Building in Depot - Building service | ประธาน | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed | 2026-06-30 | 100% | Completed | 2026-06-08 | 100% | Completed
Lot01 | GEN8.1 | 3 | General Waste Storage Building in Depot - Civil & AR | สหชาติ | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed | 2026-04-30 | 100% | Completed | 2026-06-08 | 100% | Completed
Lot01 | GEN8.2 | 4 | General Waste Storage Building in Depot - Building service | ประธาน | 2025-09-30 | 100% | Completed | 2026-03-15 | 100% | Completed | 2026-06-30 | 100% | Completed | 2026-06-08 | 100% | Completed
Lot01 | GEN13 | 5 | Bird Protection System | สหชาติ | 2025-06-30 | 100% | Completed | 2025-09-30 | 100% | Completed | 2026-01-26 | 100% | Completed | 2026-09-30 | 100% | Completed
Lot01 | GEN15 | 6 | Access Panel Closeout for Traction Substation Room in Main Workshop | สหชาติ | 2026-01-30 | 100% | Completed | 2026-03-01 | 100% | Completed | 2026-03-31 | 100% | Completed | 2026-09-30 | 100% | Completed
|  | 7 | 0 | 0 | D | 10% | 0 | P | 10% | 0 | C&I | 60% | 0 | I | 1% | 0
|  | 8 | 0 | 0 | D | 10% | 0 | P | 10% | 0 | C&I | 60% | 0 | I | 1% | 0
Landscape on Depot (Lot02)
Landscape on Depot | MO-BEM1.1 | 1 | Walkway from Main Work Shop to Stabling Area - Civil & AR | สหชาติ | 2026-04-28 | 100% | Completed | 2026-05-29 | 92% | Late | 2026-09-30 | 93% | Late | 2026-09-30 | 0% | Late
Landscape on Depot | MO-BEM1.2 | 2 | Walkway from Main Work Shop to Stabling Area - Building Services | ประธาน | 2026-04-28 | 100% | Completed | 2026-05-29 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-09-30 | 0% | Late
Landscape on Depot | MO-BEM2 | 3 | High Roof at Main Work Shop Entrance and Store | สหชาติ | 2026-02-13 | 100% | Completed | 2026-03-31 | 100% | Completed | 2026-07-31 | 100% | Completed | 2026-09-30 | 0% | Late
Landscape on Depot | MO-BEM3 | 4 | High Roof at the entrance and exit of the under floor wheel lathe | สหชาติ | 2026-02-13 | 100% | Completed | 2026-03-31 | 100% | Completed | 2026-07-31 | 100% | Completed | 2026-09-30 | 0% | Late
Landscape on Depot | MO-BEM5 | 5 | Install Concrete car barrier along the walkway in front of MWS building | สหชาติ | 2026-10-14 | 100% | Completed | 2026-11-14 | 100% | Completed | 2026-12-31 | 100% | Completed | 2027-01-07 | 100% | Completed
Landscape on Depot | MO-BEM18 | 6 | Walkway roof over the footpath near depot slab (1.50 m. x 290 m.) and stair up to depot slap. | สหชาติ | 2026-06-15 | 100% | Completed | 2026-06-30 | 100% | Completed | 2026-10-31 | 0% | On Schedule | 2026-11-07 | 0% | On Schedule
Landscape on Depot | MO-BEM24 | 7 | Guard rail protection for Fire Hose Cabinet 8 set | สหชาติ | 2026-03-14 | 100% | Completed | 2026-04-14 | 100% | Completed | 2026-08-15 | 100% | Completed | 2026-09-30 | 100% | Completed
Landscape on Depot | MO-BEM25.1 | 8 | Chain Link Fence to divide controlled areas on Depot slab 3 m.x 485 m. - Civil & AR | สหชาติ | 2026-06-14 | 100% | Completed | 2026-07-30 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-07 | 0% | Late
Landscape on Depot | MO-BEM25.2 | 9 | Chain Link Fence to divide controlled areas on Depot slab 3 m.x 485 m.- Building Services | ประธาน | 2026-06-14 | 100% | Completed | 2026-07-30 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-07 | 0% | Late
Landscape on Depot | MO-CK10 | 10 | Barbed wire fence Viaduct CE CW | สหชาติ | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 0
Landscape on Depot | MO-CK11 | 11 | Chain Link at Cut & Cover 600m. | สหชาติ | 2026-02-27 | 100% | Completed | 2026-04-30 | 100% | Completed | 2026-08-31 | 100% | Completed | 2026-09-30 | 0% | Late
Landscape on Depot | MO-CK12 | 12 | Chain Link under slab high 1.70 m | สหชาติ | 2026-06-30 | 100% | Completed | 2026-07-31 | 100% | Completed | 2026-12-31 | 67.27% | On Schedule | 2027-01-07 | 0% | On Schedule
Landscape on Depot | MO-CK27 | 13 | Spike fence for Depot slab | สหชาติ | 2026-07-31 | 70% | Late | 2026-08-31 | 0% | Late | 2026-12-31 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule
Landscape on Depot | MO-BEM13.1 | 14 | Zero Discharge Water treatment in Depot - Civil & AR | สหชาติ | 2026-08-15 | 100% | Completed | 2026-09-30 | 75% | Late | 2026-12-31 | 63% | On Schedule | 2027-01-07 | 0% | On Schedule
Landscape on Depot | MO-BEM13.2 | 15 | Zero Discharge Water treatment in Depot - Building Services | ประธาน | 2026-08-15 | 100% | Completed | 2026-09-30 | 100% | Completed | 2026-12-31 | 50% | On Schedule | 2027-01-07 | 0% | On Schedule
Landscape on Depot | MO-BEM14.1 | 16 | Modification Works : Walkway Bridge between BL Depot and ORL Depot - Civil & AR | สหชาติ | 2026-02-28 | 100% | Completed | 2026-06-15 | 100% | Completed | 2026-09-30 | 95% | Late | 2026-10-07 | 0% | Late
Landscape on Depot | MO-BEM14.2 | 17 | Modification Works : Walkway Bridge between BL Depot and ORL Depot - Building Services | ประธาน | 2026-01-14 | 100% | Completed | 2026-03-01 | 100% | Completed | 2026-09-30 | 10% | Late | 2026-10-07 | 0% | Late
Landscape on Depot | MO-BEM15.1 | 18 | Roof for cars parking lots area (184 car)t - Civil & AR | สหชาติ | 2026-02-28 | 100% | Completed | 2026-03-31 | 100% | Completed | 2026-07-31 | 100% | Completed | 2026-09-30 | 0% | Late
Landscape on Depot | MO-BEM15.2 | 19 | Roof for cars parking lots area (184 car) - Building Services | ประธาน | 2026-02-28 | 100% | Completed | 2026-03-31 | 100% | Completed | 2026-07-31 | 100% | Completed | 2026-09-30 | 0% | Late
Landscape on Depot | MO-BEM16 | 20 | Walkway roof and High roof across the road from Admin ORL to Depot slap | สหชาติ | 2026-06-15 | 100% | Completed | 2026-06-30 | 100% | Completed | 2026-10-31 | 57% | On Schedule | 2026-11-07 | 0% | On Schedule
Landscape on Depot | MO-BEM17 | 21 | Walkway roof to car park in front of admin ORL(3x5m.) | สหชาติ | 2026-06-15 | 100% | Completed | 2026-06-30 | 100% | Completed | 2026-10-31 | 70% | On Schedule | 2026-11-07 | 0% | On Schedule
Landscape on Depot | MO-BEM20 | 22 | Hose bib 1/2" 4 sets for Tree around Admin area | ประธาน | 2026-04-23 | 100% | Completed | 2026-06-08 | 100% | Completed | 2026-07-31 | 100% | Completed | 2026-09-30 | 100% | Completed
Landscape on Depot | MO-BEM21 | 23 | Relocate Security Guard Box at Front Gate and Install Roof 3x5m. | สหชาติ | 2026-07-31 | 100% | Completed | 2026-09-30 | 75% | Late | 2026-12-31 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule
Landscape on Depot | MO-BEM22 | 24 | Addition Spike fence for MRTA fence and Chain link at Klong Chourdyai 400m. | สหชาติ | 2026-08-30 | 70% | Late | 2026-09-30 | 0% | Late | 2026-12-31 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule
Landscape on Depot | MO-BEM26 | 25 | Street Lighting system area between MRTA Fence and Depot slab | ประธาน | 2026-04-14 | 50% | Late | 2026-05-15 | 0% | Late | 2026-07-31 | 0% | Late | 2026-10-07 | 0% | Late
Landscape on Depot | MO-BEM27 | 26 | Compacted gravel walkway along the Test Track OR-BL 1.2 m. | สหชาติ | 2026-08-30 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-12-31 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule
Landscape on Depot | MO-BEM28.1 | 27 | Walkway under Depot Slab for Maintenance Service - Civil & AR | สหชาติ | 2026-09-14 | 100% | Completed | 2026-10-30 | 100% | Completed | 2026-12-31 | 100% | Completed | 2027-01-07 | 0% | On Schedule
Landscape on Depot | MO-BEM28.2 | 28 | Walkway under Depot Slab for Maintenance Service - Building Services | ประธาน | 2026-09-14 | 100% | Completed | 2026-10-30 | 100% | Completed | 2026-12-31 | 50% | On Schedule | 2027-01-07 | 0% | On Schedule
Landscape on Depot | MO-BEM29 | 29 | Walkway Bridge across the canal for Depot area inspection patrols 3 location | สหชาติ | 2026-08-15 | 100% | Completed | 2026-09-30 | 67% | Late | 2026-12-31 | 95% | On Schedule | 2027-01-07 | 0% | On Schedule
Landscape on Depot | MO-BEM30 | 30 | Cut down trees between Depot BL+ORL and MRTA Fence | สหชาติ | 2026-10-29 | 0% | Late | 2026-11-29 | 0% | On Schedule | 2026-12-31 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule
Landscape on Depot | MO-BEM34 | 31 | Access Gate (Full Height Turnstile) at 1st floor admin ORL | บัณฑิต | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 2026-12-31 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule
Landscape on Depot | MO-BEM35 | 32 | Access Gate (Tripod with Swing Gate) at MWS Entrance | บัณฑิต | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 2026-12-31 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule
Landscape on Depot | MO-BEM36 | 33 | Access Gate (Tripod with Swing Gate) at Admin 2nd floor connect to OCC | บัณฑิต | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 2026-12-31 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule
Landscape on Depot | MO-BEM37 | 34 | Access Gate (Tripod with Swing Gate) on Klong Chourdyai bridge | บัณฑิต | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 2026-12-31 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule
Landscape on Depot | MO-BEM38 | 35 | Access Gate (Tripod with roof covering) at parking lot OCC | บัณฑิต | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 2026-12-31 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule
Landscape on Depot | MO-BEM39 | 36 | Access Gate (Tripod with roof covering) at Stair up to Depot slab | บัณฑิต | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 2026-12-31 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule
Landscape on Depot | MO-BEM51 | 37 | Modify existing car park to be 220 motorcycle parking lots including floor painting and parking roof | สหชาติ | 2026-01-29 | 100% | Completed | 2026-03-16 | 100% | Completed | 2026-07-31 | 100% | Completed | 2026-09-30 | 0% | Late
Landscape on Depot | MO-BEM53.1 | 38 | Modification Works : Security Guard Box at OCC Parking Area - Civil & AR | สหชาติ | 2026-09-14 | 100% | Completed | 2026-10-31 | 100% | Completed | 2026-12-31 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule
Landscape on Depot | MO-BEM53.2 | 39 | Modification Works : Security Guard Box at OCC Parking Area - Building Services | ประธาน | 2026-09-14 | 100% | Completed | 2026-10-31 | 100% | Completed | 2026-12-31 | 50% | On Schedule | 2027-01-07 | 0% | On Schedule
Works in Depot Building (Lot02)
Works in Depot Building | MO-CK1.1 | 1 | Store Modification Works at Main Workshop - Civil&AR | สหชาติ | 2026-02-27 | 100% | Completed | 2026-03-30 | 100% | Completed | 2026-05-31 | 100% | Completed | 2026-10-07 | 100% | Completed
Works in Depot Building | MO-CK1.2 | 2 | Store Modification Works at Main Workshop - Building Services | ประธาน | 2026-02-12 | 100% | Completed | 2026-03-30 | 100% | Completed | 2026-05-28 | 100% | Completed | 2026-10-07 | 100% | Completed
Works in Depot Building | MO-CK2.1 | 3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Works in Depot Building | MO-CK2.2 | 4 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Works in Depot Building | MO-CK4 | 5 | Bird & Rain Protection for Open space Admin C | สหชาติ | 2026-04-29 | 100% | Completed | 2026-05-30 | 100% | Completed | 2026-07-31 | 100% | Completed | 2026-09-30 | 0% | Late
Works in Depot Building | MO-CK5 | 6 | Relocate door in front of toilet and build partition wall to conceal the view in side of toilet | สหชาติ | 2026-05-14 | 100% | Completed | 2026-06-14 | 100% | Completed | 2026-07-31 | 100% | Completed | 2026-10-07 | 0% | Late
Works in Depot Building | MO-CK6 | 7 | Modify Lockset the emergency door to be used for passage between the 2nd and 3rd floors inside the building. | สหชาติ | 2026-04-29 | 100% | Completed | 2026-06-14 | 100% | Completed | 2026-07-31 | 100% | Completed | 2026-09-30 | 0% | Late
Works in Depot Building | MO-CK7 | 8 | Addition small power for lounge and pantry room at 2nd floor and Hall and observation room at 3nd floor | ประธาน | 2026-05-14 | 100% | Completed | 2026-06-14 | 100% | Completed | 2026-07-31 | 100% | Completed | 2026-09-30 | 100% | Completed
Works in Depot Building | MO-CK8 | 9 | Air Condition for using store room to be pantry room. 2nd floor | ประธาน | 2026-04-29 | 100% | Completed | 2026-06-14 | 100% | Completed | 2026-07-31 | 100% | Completed | 2026-09-30 | 100% | Completed
Works in Depot Building | MO-CK9 | 10 | Walk Way Hand rail high 90 cm 1 side (144 m. x 7 route) | สหชาติ | 2026-05-30 | 100% | Completed | 2026-06-30 | 100% | Completed | 2026-09-30 | 98.77% | Late | 2026-10-07 | 0% | Late
Works in Depot Building | MO-CK15.1 | 11 | Epoxy Floor Installation and Curb Installation at the Entrance - Civil & AR | สหชาติ | 2026-01-27 | 100% | Completed | 2026-02-27 | 100% | Completed | 2026-04-30 | 100% | Completed | 2026-10-07 | 100% | Completed
Works in Depot Building | MO-CK15.2 | 12 | Change Electrical Equipment to be Explosion-proof type - Building Services | ประธาน | 2025-12-13 | 100% | Completed | 2026-01-28 | 100% | Completed | 2026-04-30 | 90% | Late | 2026-10-07 | 0% | Late
Works in Depot Building | MO-CK33 | 13 | Additional lighting in areas where the lux level does not meet occupational health standards | ประธาน | 2026-09-14 | 100% | Completed | 2026-10-15 | 100% | Completed | 2026-12-31 | 95% | On Schedule | 2027-01-07 | 0% | On Schedule
Works in Depot Building | MO-BEM4.1 | 14 | Maintenance Office Rooms at Main Workshop - Civil & AR | สหชาติ | 2026-04-13 | 100% | Completed | 2026-05-14 | 100% | Completed | 2026-06-30 | 100% | Completed | 2026-09-30 | 100% | Completed
Works in Depot Building | MO-BEM4.2 | 15 | Maintenance Office Rooms at Main Workshop - Building Services | ประธาน | 2026-04-13 | 100% | Completed | 2026-05-14 | 100% | Completed | 2026-06-30 | 100% | Completed | 2026-09-30 | 0% | Late
Works in Depot Building | MO-BEM6 | 16 | Handrail on top of the water tank on the rooftop of the Admin Building | สหชาติ | 2026-10-19 | 100% | Completed | 2026-11-19 | 100% | Completed | 2026-12-31 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule
Works in Depot Building | MO-BEM7 | 17 | Modify maintenance service door to the roof building to easier access while maintaining safe operational standards | สหชาติ | 2026-10-19 | 50% | Late | 2026-11-19 | 0% | On Schedule | 2026-12-31 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule
Works in Depot Building | MO-BEM8 | 18 | Company logo and Central Control Room sign in CCR room. | สหชาติ | 2026-01-27 | 100% | Completed | 2026-03-14 | 100% | Completed | 2026-04-30 | 100% | Completed | 2026-10-07 | 0% | Late
Works in Depot Building | MO-BEM9 | 19 | Soundproof insulation on the wall and structure and equipment in the CCR room. | สหชาติ | 2026-01-12 | 100% | Completed | 2026-02-27 | 100% | Completed | 2026-04-30 | 100% | Completed | 2026-10-07 | 0% | Late
Works in Depot Building | MO-BEM10 | 20 | Relocate Fire Hose Cabinet to be outside of the clearance gauge zone 17 set | ประธาน | 2026-01-12 | 100% | Completed | 2026-02-27 | 100% | Completed | 2026-04-30 | 100% | Completed | 2026-09-30 | 100% | Completed
Works in Depot Building | MO-BEM11.1 | 21 | Washing Area in Cleaning Staff Room at Stabling Yard - Civil & AR | สหชาติ | 2026-06-03 | 100% | Completed | 2026-07-04 | 100% | Completed | 2026-07-31 | 100% | Completed | 2026-09-30 | 50% | Late
Works in Depot Building | MO-BEM11.2 | 22 | Washing Area in Cleaning Staff Room at Stabling Yard - Building Services | ประธาน | 2026-04-14 | 100% | Completed | 2026-05-30 | 100% | Completed | 2026-07-31 | 100% | Completed | 2026-07-01 | 100% | Completed
Works in Depot Building | MO-BEM12 | 23 | Rain protection for Water treatment Building | สหชาติ | 2026-04-29 | 100% | Completed | 2026-05-30 | 100% | Completed | 2026-07-31 | 100% | Completed | 2026-09-30 | 0% | Late
Works in Depot Building | MO-BEM19 | 24 | Install Chain Link fence to enclose parking area | สหชาติ | 2026-06-29 | 100% | Completed | 2026-07-30 | 100% | Completed | 2026-09-30 | 0% | Late | 2026-10-07 | 0% | Late
Works in Depot Building | MO-BEM23 | 25 | Hand sink with eye wash station | ประธาน | 2026-08-30 | 100% | Completed | 2026-10-15 | 100% | Completed | 2026-12-31 | 100% | Completed | 2027-01-07 | 0% | On Schedule
Works in Depot Building | MO-BEM31 | 26 | Provide facility system and interface to MMC room (Fire Alarm / CCTV / VMS / TEL / CASS / Radio / PA) | บัณฑิต | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 0
Works in Depot Building | MO-BEM40 | 27 | Access Control (2 Factors, Card + Finger Print) at High Security rooms - CCR/PTR/Store | บัณฑิต | 2026-11-28 | 100% | Completed | 2026-11-29 | 100% | Completed | 2026-12-31 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule
Works in Depot Building | MO-BEM41 | 28 | Link CCTV Landscape of all depot ORL area for MMC BL monitoring. | บัณฑิต | 2026-11-28 | 0% | On Schedule | 2026-11-29 | 0% | On Schedule | 2026-12-31 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule
Graphic Signage (Lot02)
Graphic Signage | MO-CK17 | 1 | Safety Sign all Depot Area building | สหชาติ | 2025-11-28 | 100% | Completed | 2026-06-15 | 100% | Completed | 2026-10-15 | 0% | Late | 0 | 0% | Late
Graphic Signage | MO-CK18 | 2 | Emergency escape route map | สหชาติ | 2026-09-30 | 0% | Late | 2026-10-30 | 50% | On Schedule | 2026-12-31 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule
Graphic Signage | MO-CK19 | 3 | Traffic Line Marking (Thermoplastic Paint) | สหชาติ | 2026-04-30 | 100% | Completed | 2026-06-15 | 100% | Completed | 2026-10-15 | 25% | Late | 0 | 0% | Late
Graphic Signage | MO-CK20 | 4 | Emergency Car Parking location Painting in front of MWS | สหชาติ | 2026-04-30 | 100% | Completed | 2026-06-15 | 100% | Completed | 2026-10-15 | 0% | Late | 0 | 0% | Late
Graphic Signage | MO-CK21 | 5 | Safety Line painting in MWS, Stabling Area, P-way, Track | สหชาติ | 2026-06-01 | 100% | Completed | 2026-08-01 | 100% | Completed | 2026-12-31 | 81% | On Schedule | 2027-01-07 | 0% | On Schedule
Graphic Signage | MO-CK22 | 6 | Fire escape stairs level signs in the Depot, VS and IVS areas | สหชาติ | 2026-09-30 | 50% | Late | 2026-10-31 | 0% | On Schedule | 2026-12-31 | 0% | On Schedule | 2027-01-07 | 0% | On Schedule
Graphic Signage | MO-CK24 | 7 | Modify Traffic paint and traffic sign | สหชาติ | 2026-04-30 | 100% | Completed | 2026-06-15 | 100% | Completed | 2026-10-15 | 13% | Late | 0 | 0% | Late
Graphic Signage | MO-CK25 | 8 | Station Area sign 28 stations | สหชาติ | 2026-06-15 | 80% | Late | 2026-06-30 | 100% | Completed | 2026-12-20 | 0% | On Schedule | 2026-10-07 | 0% | Late
Graphic Signage | MO-CK26 | 9 | Safety and warning signage for lift and escalator at all station | สหชาติ | 2026-06-16 | 100% | Completed | 2026-07-17 | 100% | Completed | 2027-02-28 | 26% | On Schedule | 0 | 0% | Late
Graphic Signage | MO-CK34 | 10 | Provide and install confined space signage for Station and Depot | สหชาติ | 2026-08-15 | 100% | Completed | 2026-09-15 | 100% | Completed | 2027-02-28 | 26% | On Schedule | 0 | 0% | Late
Formulas:
Design (PLAN) = XLOOKUP([Code],'01 Summary'!$E:$E,'01 Summary'!L:L)
Procurement (PLAN) = XLOOKUP([Code],'01 Summary'!$E:$E,'01 Summary'!O:O)
Construction /Installation (PLAN) = XLOOKUP([Code],'01 Summary'!$E:$E,'01 Summary'!U:U)
Inspection (PLAN) = XLOOKUP([Code],'01 Summary'!$E:$E,'01 Summary'!AD:AD)

## ตารางสรุปStatus D&P
Modification & Additional Works in Depot
Status Design & Procurement
Action Stage | CK Responsible Person | Total | Completed | Remain
Design Stage | สหชาติ | 52 | 44 | 8
Procurement Stage | สหชาติ | 52 | 40 | 12
Construction Stage | สหชาติ | 52 | 22 | 30
Design Stage | ประธาน | 20 | 19 | 1
Procurement Stage | ประธาน | 20 | 19 | 1
Construction Stage | ประธาน | 20 | 11 | 9

## 03 Procurement
Type of Work | Work Code | Description | Responsible | Total (List) | PPR Issued | PO/WO Issued | ISO Plan |  | Minor Work Plan |  | PPR Status | PO/WO Status | PO/WO %Prog.
[7 empty] | PPR | PO/WO | PPR | PO/WO
Modification/Additional Works (Minor Works Lot1)
GEN |  | General Work |  | #VALUE! | #VALUE! | #VALUE!
GEN1 | DN01B1700001 | Rooms and Building Service Systems Modification in Stations Area |  | #VALUE! | #VALUE! | #VALUE! | -30 | 0 | 2025-10-01 | 2025-10-31 | #VALUE! | #VALUE!
GEN1.1 |  | CIV/AR Works | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2025-10-01 | 2025-10-31 | #VALUE! | #VALUE!
GEN1.2 |  | E&M Works | ประธาน | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2025-10-01 | 2025-10-31 | #VALUE! | #VALUE!
GEN2 | DN01B1700002 | Rooms and Building Service Systems Modification in Depot Area |  | #VALUE! | #VALUE! | #VALUE! | -30 | 0 | 2025-10-01 | 2025-10-31 | #VALUE! | #VALUE!
GEN2.1 |  | CIV/AR Works | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2025-10-01 | 2025-10-31 | #VALUE! | #VALUE!
GEN2.2 |  | E&M Works | ประธาน | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2025-10-01 | 2025-10-31 | #VALUE! | #VALUE!
GEN2.3 |  | E&M Works | สมศักดิ์ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2025-10-01 | 2025-10-31 | #VALUE! | #VALUE!
GEN3 | DN01B1700003 | Cable Containment Modification |  | #VALUE! | #VALUE! | #VALUE! | -30 | 0 | 2026-07-02 | 2026-08-01 | #VALUE! | #VALUE!
GEN3.1 |  | CIV/AR Works | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-07-02 | 2026-08-01 | #VALUE! | #VALUE!
GEN3.2 |  | E&M Works | ประธาน | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2025-04-17 | 2025-05-17 | #VALUE! | #VALUE!
GEN3.3 |  | E&M Works | มนตรี | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-07-02 | 2026-08-01 | #VALUE! | #VALUE!
GEN3.4 |  | E&M Works | ฐิติพงศ์ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-07-02 | 2026-08-01 | #VALUE! | #VALUE!
GEN4 | DN01B1700004 | Training Room and Workshop Room |  | #VALUE! | #VALUE! | #VALUE! | -30 | 0 | 2026-01-01 | 2026-01-31 | #VALUE! | #VALUE!
GEN4.1 |  | CIV/AR Works | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-01-01 | 2026-01-31 | #VALUE! | #VALUE!
GEN4.2 |  | E&M Works | ประธาน | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-01-01 | 2026-01-31 | #VALUE! | #VALUE!
GEN5 | DN01B1700005 | Raised Floor |  | #VALUE! | #VALUE! | #VALUE! | -30 | 0 | 2024-11-14 | 2024-12-14 | #VALUE! | #VALUE!
GEN5.1 |  | CIV/AR Works | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2024-11-14 | 2024-12-14 | #VALUE! | #VALUE!
GEN5.2 |  | E&M Works | ประธาน | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2024-11-14 | 2024-12-14 | #VALUE! | #VALUE!
GEN6 | DN01B1700006 | Wayside Cable Containment in Depot |  | #VALUE! | #VALUE! | #VALUE! | -30 | 0 | 2025-03-03 | 2025-04-02 | #VALUE! | #VALUE!
GEN6.1 |  | CIV/AR Works | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2025-03-03 | 2025-04-02 | #VALUE! | #VALUE!
GEN6.2 |  | E&M Works | มนตรี | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2025-03-03 | 2025-04-02 | #VALUE! | #VALUE!
GEN7 | DN01B1700007 | Dangerous Waste Storage Building in Depot |  | #VALUE! | #VALUE! | #VALUE! | -30 | 0 | 2026-02-13 | 2026-03-15 | #VALUE! | #VALUE!
GEN7.1 |  | CIV/AR Works | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-02-13 | 2026-03-15 | #VALUE! | #VALUE!
GEN7.2 |  | E&M Works | ประธาน | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-02-13 | 2026-03-15 | #VALUE! | #VALUE!
GEN8 | DN01B1700008 | General Waste Storage Building in Depot |  | #VALUE! | #VALUE! | #VALUE! | -30 | 0 | 2026-02-13 | 2026-03-15 | #VALUE! | #VALUE!
GEN8.1 |  | CIV/AR Works | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-02-13 | 2026-03-15 | #VALUE! | #VALUE!
GEN8.2 |  | E&M Works | ประธาน | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-02-13 | 2026-03-15 | #VALUE! | #VALUE!
GEN9 | DN01B1700009 | Operation Support Equipment | สมศักดิ์ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2025-10-03 | 2025-11-02 | #VALUE! | #VALUE!
GEN10 | DN01B1700010 | Graphic and Signage |  | #VALUE! | #VALUE! | #VALUE! | -30 | 0 | 2026-07-01 | 2026-07-31 | #VALUE! | #VALUE!
GEN10.1 |  | CIV/AR Works | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-07-01 | 2026-07-31 | #VALUE! | #VALUE!
GEN10.2 |  | E&M Works | ประธาน | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-07-01 | 2026-07-31 | #VALUE! | #VALUE!
GEN11 | DN01B1700011 | Earthing and Bonding Modification | ประธาน | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2025-08-31 | 2025-09-30 | #VALUE! | #VALUE!
GEN12 | DN01B1700012 | Mainline Cable Trough Modification on East Section |  | #VALUE! | #VALUE! | #VALUE! | -30 | 0 | 2025-10-31 | 2025-11-30 | #VALUE! | #VALUE!
GEN12.1 |  | CIV/AR Works | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2025-10-31 | 2025-11-30 | #VALUE! | #VALUE!
GEN12.2 |  | E&M Works | มนตรี | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2025-10-31 | 2025-11-30 | #VALUE! | #VALUE!
GEN13 | DN01B1700013 | Bird Protection System | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2025-08-31 | 2025-09-30 | #VALUE! | #VALUE!
GEN14 | DN01B1700014 | Train Crew Office at Thailand Cultural Centre Station |  | #VALUE! | #VALUE! | #VALUE! | -30 | 0 | 2026-01-28 | 2026-02-27 | #VALUE! | #VALUE!
GEN14.1 |  | CIV/AR Works | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-01-28 | 2026-02-27 | #VALUE! | #VALUE!
GEN14.2 |  | E&M Works | ประธาน | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-01-28 | 2026-02-27 | #VALUE! | #VALUE!
GEN15 | DN01B1700015 | Access Panel Closeout for Traction Substation Room in Main Workshop | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-01-30 | 2026-03-01 | #VALUE! | #VALUE!
GEN16 | DN01B1700016 | Level Crossing at Turnout | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2025-05-02 | 2025-06-01 | #VALUE! | #VALUE!
GEN17 | DN01B1700017 | Track Slab Crossing | สหชาติ | #VALUE! | #VALUE! | #VALUE!
GEN18 | DN01B1700018 | Eye Adaptation Lighting (Lighting at Tunnel to Expose) | ประธาน | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2025-09-30 | 2025-10-30 | #VALUE! | #VALUE!
GEN19 | DN01B1700019 | Train Simulation Room and AFC Training Room |  | #VALUE! | #VALUE! | #VALUE! | -30 | 0 | 2026-01-29 | 2026-02-28 | #VALUE! | #VALUE!
GEN19.1 |  | CIV/AR Works | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-01-29 | 2026-02-28 | #VALUE! | #VALUE!
GEN19.2 |  | E&M Works | ประธาน | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-01-29 | 2026-02-28 | #VALUE! | #VALUE!
GEN20 | DN01B1700020 | Dormitory Cable Containments (if any) | สหชาติ | #VALUE! | #VALUE! | #VALUE!
GEN21 | DN01B1700021 | Project Information Management System (PIMS) | บัณฑิต | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2024-07-16 | 2024-08-15 | #VALUE! | #VALUE!
GEN22 | DN01B1700022 | Central BEMS for the MRT Orange Line System | บัณฑิต | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-05-31 | 2026-06-30 | #VALUE! | #VALUE!
GEN24 |  | Office Facilities | ทิพย์วัลย์ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2024-07-20 | 2024-08-19 | #VALUE! | #VALUE!
PSD |  | Platform Screen Door |  | #VALUE! | #VALUE! | #VALUE!
PSD1 | DN01B1700031 | Holes for PSD Cable Wiring | กำพล | #VALUE! | #VALUE! | #VALUE!
PSD2 | DN01B1700032 | Rubber Gap Fillers on Platform Edge | กำพล | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-01-01 | 2026-01-31 | #VALUE! | #VALUE!
PSD3 | DN01B1700033 | Platform Finishing |  | #VALUE! | #VALUE! | #VALUE! | -30 | 0 | 2025-08-17 | 2025-09-16 | #VALUE! | #VALUE!
PSD3.1 |  | CIV/AR Works | กำพล | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2025-08-17 | 2025-09-16 | #VALUE! | #VALUE!
PSD3.2 |  | CIV/AR Works | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2025-08-17 | 2025-09-16 | #VALUE! | #VALUE!
PSD4 | DN01B1700034 | Cladding Barrier between EWD and Station Structure | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-02-13 | 2026-03-15 | #VALUE! | #VALUE!
AFC |  | Automatic Fare Collection |  | #VALUE! | #VALUE! | #VALUE!
AFC1 | DN01B1700041 | Park and Ride System | สหชาติ | #VALUE! | #VALUE! | #VALUE!
AFC2 | DN01B1700042 | Ticket Issuing Machine (TIM) Wall Opening and Closing | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-02-13 | 2026-03-15 | #VALUE! | #VALUE!
AFC3 | DN01B1700043 | Balustrade Modification Along AFC Gate Line | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-07-16 | 2026-08-15 | #VALUE! | #VALUE!
AFC4 | DN01B1700044 | Underfloor Embedded Duct Modification for AFC Gates Line | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-03-03 | 2026-04-02 | #VALUE! | #VALUE!
SIG |  | Signalling |  | #VALUE! | #VALUE! | #VALUE!
SIG1 | DN01B1700051 | Test Track Shelters and Test Track Building |  | #VALUE! | #VALUE! | #VALUE! | -30 | 0 | 2025-12-19 | 2026-01-18 | #VALUE! | #VALUE!
SIG1.1 |  | CIV/AR Works | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2025-12-19 | 2026-01-18 | #VALUE! | #VALUE!
SIG1.2 |  | E&M Works | ประธาน | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2025-12-19 | 2026-01-18 | #VALUE! | #VALUE!
SIG2 | DN01B1700052 | Rearrangement of track crossing walkway at stabling yard to consistent with the layout of 4-car train parking | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2025-11-30 | 2025-12-30 | #VALUE! | #VALUE!
SIG3 | DN01B1700053 | Point Machine Foundation Depot |  | #VALUE! | #VALUE! | #VALUE! | -30 | 0 | 2025-11-30 | 2025-12-30 | #VALUE! | #VALUE!
SIG3.1 |  | CIV/AR Works | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2025-11-30 | 2025-12-30 | #VALUE! | #VALUE!
SIG3.2 |  | E&M Works | สู่โชค | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2025-11-30 | 2025-12-30 | #VALUE! | #VALUE!
SIG4 | DN01B1700054 | Modification of Depot Track Route Line to Stabling Yard | สหชาติ | #VALUE! | #VALUE! | #VALUE!
SIG5 | DN01B1700055 | Strobe Light at Buffer Stops | ประธาน | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-05-30 | 2026-06-29 | #VALUE! | #VALUE!
DWE |  | Depot and Workshop Equipment |  | #VALUE! | #VALUE! | #VALUE!
DWE1 | DN01B1800001 | Diesel Fuel Storage Tank for Maintenance Vehicle | สมศักดิ์ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2025-12-17 | 2026-01-16 | #VALUE! | #VALUE!
DWE2 | DN01B1800002 | Movable Height Maintenance Platform Vehicle (Boom Lift) | สมศักดิ์ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2025-07-07 | 2025-08-06 | #VALUE! | #VALUE!
DWE3 | DN01B1800003 | Fork Lift Vehicle | สมศักดิ์ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2025-03-01 | 2025-03-31 | #VALUE! | #VALUE!
DWE4 | DN01B1800004 | Compressed Air System and Portable Air Compressor for Depot | สมศักดิ์ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2025-12-11 | 2026-01-10 | #VALUE! | #VALUE!
DWE5 | DN01B1800005 | Pallet Storage Shelves in Hazardous Storage | สมศักดิ์ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2025-11-16 | 2025-12-16 | #VALUE! | #VALUE!
DWE6 | DN01B1800006 | Pallet Storage in Main Storage Room | สมศักดิ์ | #VALUE! | #VALUE! | #VALUE! | -30 | 0 | 2025-11-16 | 2025-12-16 | #VALUE! | #VALUE!
DWE6.1 |  | CIV/AR Works | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2025-11-16 | 2025-12-16 | #VALUE! | #VALUE!
DWE6.2 |  | E&M Works | สมศักดิ์ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2025-11-16 | 2025-12-16 | #VALUE! | #VALUE!
DWE7 | DN01B1800007 | Two-Tier Shelf | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2025-11-16 | 2025-12-16 | #VALUE! | #VALUE!
DWE8 | DN01B1800008 | Tool Storage | สมศักดิ์ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2025-11-16 | 2025-12-16 | #VALUE! | #VALUE!
DWE9 | DN01B1800009 | Repair Equipment | สมศักดิ์ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-07-01 | 2026-07-31 | #VALUE! | #VALUE!
DWE10 | DN01B1800010 | Oil & Grease Disposal | สมศักดิ์ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2025-12-17 | 2026-01-16 | #VALUE! | #VALUE!
DWE11 | DN01B1800011 | Grease Dispensers | สมศักดิ์ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2025-12-17 | 2026-01-16 | #VALUE! | #VALUE!
DWE12 | DN01B1800012 | Waste Disposal | สมศักดิ์ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2025-12-17 | 2026-01-16 | #VALUE! | #VALUE!
DWE13 | DN01B1800013 | Safety Provision for Maintenance Pits | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-03-30 | 2026-04-29 | #VALUE! | #VALUE!
DWE14 | DN01B1800014 | Pit Drainage System in Main Workshop |  | #VALUE! | #VALUE! | #VALUE! | -30 | 0 | 2026-07-01 | 2026-07-31 | #VALUE! | #VALUE!
DWE14.1 |  | CIV/AR Works | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-07-01 | 2026-07-31 | #VALUE! | #VALUE!
DWE14.2 |  | E&M Works | สมศักดิ์ | #VALUE! | #VALUE! | #VALUE!
DWE15 | DN01B1800015 | Provision of Civil Works and Building Services to support Train Washing Equipment | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-03-01 | 2026-03-31 | #VALUE! | #VALUE!
DWE16 | DN01B1800016 | Overhead Traveling Crane | สมศักดิ์ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2025-03-31 | 2025-04-30 | #VALUE! | #VALUE!
DWE17 | DN01B1800017 | Vehicle Inspection and Servicing Facilities | สมศักดิ์ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2025-09-02 | 2025-10-02 | #VALUE! | #VALUE!
DWE18 | DN01B1800018 | Permanent Way Maintenance Facility | สมศักดิ์ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2027-01-29 | 2027-02-28 | #VALUE! | #VALUE!
DWE19 | DN01B1800019 | Permanent Way Vehicles | สมศักดิ์ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2027-01-29 | 2027-02-28 | #VALUE! | #VALUE!
DWE20 | DN01B1800020 | Building Maintenance Vehicle | สมศักดิ์ | #VALUE! | #VALUE! | #VALUE!
PSY |  | Power Supply |  | #VALUE! | #VALUE! | #VALUE! | [6 empty] | #VALUE!
PSY1 | DN01B1700061 | Diesel Fuel Storage Tanks for Power Generators | สมศักดิ์ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2025-12-17 | 2026-01-16 | #VALUE! | #VALUE!
PSY2 | DN01B1700062 | GIS and BSS Building and Other Facilities (BSS1, BSS2, BSS3) |  | #VALUE! | #VALUE! | #VALUE! | -30 | 0 | 2027-01-31 | 2027-03-02 | #VALUE! | #VALUE! | #VALUE!
PSY2.1 |  | CIV/AR Works | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2027-01-31 | 2027-03-02 | #VALUE! | #VALUE!
PSY2.2 |  | E&M Works | ประธาน | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-11-01 | 2026-12-01 | #VALUE! | #VALUE!
PSY3 | DN01B1700063 | Steel Grating Raised Floor for EE Panel | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2024-09-30 | 2024-10-30 | #VALUE! | #VALUE!
SCA |  | SCADA |  | #VALUE! | #VALUE! | #VALUE!
SCA1 | DN01B1700071 | Modification of BMS to receive PSD Signal, East Section | บัณฑิต | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-03-01 | 2026-03-31 | #VALUE! | #VALUE!
SCA2 | DN01B1700072 | Modification of Escalator Interface Point with CCTV and SCADA, East Section | บัณฑิต | #VALUE! | #VALUE! | #VALUE!
SCA3 | DN01B1700073 | Magnetic of Fire Alarm System Interface Point with CCTV and SCADA | บัณฑิต | #VALUE! | #VALUE! | #VALUE!
SCA4 | DN01B1700074 | Add/Modify Civil Scada Hardwire for all Station | บัณฑิต | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-03-31 | 2026-04-30 | #VALUE! | #VALUE!
COM |  | Communication |  | #VALUE! | #VALUE! | #VALUE! | [6 empty] | #VALUE!
COM1 | DN01B1700081 | Magnetic Door Lock | มนตรี | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-04-15 | 2026-05-15 | #VALUE! | #VALUE!
COM2 | DN01B1700082 | Intercom System in Cash Handling Room (if require) | บัณฑิต | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-05-31 | 2026-06-30 | #VALUE! | #VALUE!
COM3 | DN01B1700083 | Walk-Through Metal Detector System (WTMD), 1 per entrance | บัณฑิต | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-05-31 | 2026-06-30 | #VALUE! | #VALUE!
COM4 | DN01B1700084 | Traveling Cable in all Lifts | ประธาน | #VALUE! | #VALUE! | #VALUE!
COM5 | DN01B1700085 | MEA Radio | ประธาน | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-03-31 | 2026-04-30 | #VALUE! | #VALUE!
COM6 | DN01B1700086 | Main Cable Containment for M&E Dedicated communication link to MRTA Head Quarter | มนตรี | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-01-29 | 2026-02-28 | #VALUE! | #VALUE!
COM7 | DN01B1700087 | Mini Paging in Ticket Office | บัณฑิต | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-05-31 | 2026-06-30 | #VALUE! | #VALUE!
COM8 | DN01B1700088 | Provision of Cable Containment between OCC ORL and OCC BL | มนตรี | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-01-29 | 2026-02-28 | #VALUE! | #VALUE!
COM9 | DN01B1700089 | Power Distribution for M&E Systems at MRTA Head Quarter | มนตรี | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-05-31 | 2026-06-30 | #VALUE! | #VALUE!
COM10 | DN01B1700090 | Underground Cable Containment at Public Areas (if require) | มนตรี | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-07-01 | 2026-07-31 | #VALUE! | #VALUE!
COM11 | DN01B1700091 | Intercom at Ticket Issuing Machine | บัณฑิต | #VALUE! | #VALUE! | #VALUE!
Modification/Additional Works (Minor Works Lot2) |  |  |  | #VALUE! | #VALUE! | #VALUE!
MO-CK1 | DN02B1710001 | Modify Office Store & Tool |  | #VALUE! | #VALUE! | #VALUE! | -30 | 0 | 2026-02-28 | 2026-03-30 | #VALUE! | #VALUE! | #VALUE!
MO-CK1.1 |  | CIV/AR Works | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-02-28 | 2026-03-30 | #VALUE! | #VALUE!
MO-CK1.2 |  | E&M Works | ประธาน | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-02-28 | 2026-03-30 | #VALUE! | #VALUE!
MO-CK2 | DN02B1710002 | Modify room for MMC at Admin C 2 floor.(Corridor out of Lobby) | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-04-15 | 2026-05-15 | #VALUE! | #VALUE!
MO-CK3 | DN02B1710003 | Move or link Workstation and control panel to MMC room at admin C 2nd floor | ประธาน | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-05-02 | 2026-06-01 | #VALUE! | #VALUE!
MO-CK4 | DN02B1710004 | Bird & Rain Protetion for Open space Admin C | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-04-30 | 2026-05-30 | #VALUE! | #VALUE!
MO-CK5 | DN02B1710005 | Relocate door in front of toilet and build partition wall to conceal the view in side of toilet | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-05-15 | 2026-06-14 | #VALUE! | #VALUE!
MO-CK6 | DN02B1710006 | Modify Lockset the emergency door to be used for passage between the 2nd and 3rd floors inside the building | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-05-15 | 2026-06-14 | #VALUE! | #VALUE!
MO-CK7 | DN02B1710007 | Addition small power for lounge and pantry room at 2nd floor and Hall andobservation room at 3nd floor | ประธาน | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-05-15 | 2026-06-14 | #VALUE! | #VALUE!
MO-CK8 | DN02B1710008 | Air Condition for using store room to be pantry room. 2nd floor | ประธาน | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-05-15 | 2026-06-14 | #VALUE! | #VALUE!
MO-CK9 | DN02B1710009 | Walk Way Hand rail high 90 cm 1 side (144 m.x 7 route) | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-05-31 | 2026-06-30 | #VALUE! | #VALUE!
MO-CK10 | DN02B1710010 | Barbed wire fence Viaduct CE CW | บัณฑิต | #VALUE! | #VALUE! | #VALUE!
MO-CK11 | DN02B1710011 | Chain Link at Cut & Cover 600m. | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-03-31 | 2026-04-30 | #VALUE! | #VALUE!
MO-CK12 | DN02B1710012 | Chain Link under slab high 1.70 m | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-07-01 | 2026-07-31 | #VALUE! | #VALUE!
MO-CK13 | DN02B1710013 | Modify Maintenance and Cleaner Room at Interlocking station and OR21 | ประธาน | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-10-20 | 2026-11-19 | #VALUE! | #VALUE!
MO-CK14 | DN02B1710014 | Modify Cleaner room at OR29 to be Train crew Standby office with facility system | ประธาน | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-03-30 | 2026-04-29 | #VALUE! | #VALUE!
MO-CK15 | DN02B1710015 | Change Electrical Equipment to be Explosion-proof type - Electrical, Foam Fire suppression, Epoxy Floor, Closed Floor Drain, Flood barrier curb | ประธาน | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-09-01 | 2026-10-01 | #VALUE! | #VALUE!
MO-CK16 | DN02B1710016 | Dangerous waste Storage 30 x 5 m. =10 room | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-02-13 | 2026-03-15 | #VALUE! | #VALUE!
MO-CK17 | DN02B1710017 | Safety Sign all Depot Area building | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-07-16 | 2026-08-15 | #VALUE! | #VALUE!
MO-CK18 | DN02B1710018 | Emergency escape route map | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-09-30 | 2026-10-30 | #VALUE! | #VALUE!
MO-CK19 | DN02B1710019 | Traffice Line Marking (Thermoplastic Paint) | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-07-16 | 2026-08-15 | #VALUE! | #VALUE!
MO-CK20 | DN02B1710020 | Emergency Car Parking location Painting in front of MWS | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-07-16 | 2026-08-15 | #VALUE! | #VALUE!
MO-CK21 | DN02B1710021 | Safety Line painting in MWS, Stabling Area, P-way, Track | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-05-31 | 2026-06-30 | #VALUE! | #VALUE!
MO-CK22 | DN02B1710022 | Fire escape stairs level signs in the VS and IVS areas | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-09-05 | 2026-10-05 | #VALUE! | #VALUE!
Mo-CK23 | DN02B1710023 | General waste Storage ขนาด 22 x 5 m | สหชาติ | #VALUE! | #VALUE! | #VALUE!
MO-CK24 | DN02B1710024 | Modify Traffic paint and traffic sign | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-07-16 | 2026-08-15 | #VALUE! | #VALUE!
MO-CK25 | DN02B1710025 | Station Area sign 28 stations | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-09-05 | 2026-10-05 | #VALUE! | #VALUE!
MO-CK26 | DN02B1710026 | Safety and warning signage for lift and escalator at all station | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-06-17 | 2026-07-17 | #VALUE! | #VALUE!
MO-CK27 | DN02B1710027 | Spike fence for Depot slab | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-08-01 | 2026-08-31 | #VALUE! | #VALUE!
MO-CK29 | DN02B1710028 | Fire Alarm Manual Call Point signage at all elevated station | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-07-01 | 2026-07-31 | #VALUE! | #VALUE!
MO-CK30 | DN02B1710029 | Lighting for sealed space under stairs and behind lift shaft at underground station | สู่โชค | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-10-15 | 2026-11-14 | #VALUE! | #VALUE!
MO-CK31 | DN02B1710030 | Modify the access door of sealed space (under-stairs room) with a Sump Pump or ESPS cabinet by extend to the full door add lighting to the under stairs room | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-07-17 | 2026-08-16 | #VALUE! | #VALUE!
MO-CK32 | DN02B1710031 | Lighting to the sealed space (under-stairs room) with a Sump Pump or ESPS cabinet | สู่โชค | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-11-04 | 2026-12-04 | #VALUE! | #VALUE!
MO-CK33 | DN02B1710032 | Additional lighting in areas where the lux level does not meet occupational health standards | ประธาน | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-09-15 | 2026-10-15 | #VALUE! | #VALUE!
MO-CK34 | DN02B1710033 | Provide and install confined space signage for Station and Depot | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-08-16 | 2026-09-15 | #VALUE! | #VALUE!
MO-CK35 | DN02B1710034 | Build room for Train crew main office at OR18 with office area, resting area, meeting room, pantry, toilet and locker room | สหชาติ | #VALUE! | #VALUE! | #VALUE!
MO-CK36 | DN02B1710035 | Dormitory Cable Containments (if any) | สหชาติ | #VALUE! | #VALUE! | #VALUE!
MO-CK37 | DN02B1710036 | Provide Raise floor and building Service in Trainning &Simulator (OCC Admin) | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-01-30 | 2026-03-01 | #VALUE! | #VALUE!
MO-CK38 | DN02B1710037 | Add N2 in Playback and Training Room and Backup Control Room | ประธาน | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-04-01 | 2026-05-01 | #VALUE! | #VALUE!
MO-BEM1 | DN02B1720001 | Walkway from Main Work Shop to Stabling Area |  | #VALUE! | #VALUE! | #VALUE! | -30 | 0 | 2026-04-29 | 2026-05-29 | #VALUE! | #VALUE! | #VALUE!
MO-BEM1.1 |  | CIV/AR Works | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-04-29 | 2026-05-29 | #VALUE! | #VALUE!
MO-BEM1.2 |  | E&M Works | ประธาน | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-04-29 | 2026-05-29 | #VALUE! | #VALUE!
MO-BEM2 | DN02B1720002 | High Roof at Main Work Shop Entrance and Store | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-03-01 | 2026-03-31 | #VALUE! | #VALUE!
MO-BEM3 | DN02B1720003 | High Roof at the entance and exit of the under floor wheel lathe | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-03-01 | 2026-03-31 | #VALUE! | #VALUE!
MO-BEM4 | DN02B1720004 | Modify the Maintenance Office rooms and meeting room |  | #VALUE! | #VALUE! | #VALUE! | -30 | 0 | 2026-04-14 | 2026-05-14 | #VALUE! | #VALUE! | #VALUE!
MO-BEM4.1 |  | CIV/AR Works | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-04-14 | 2026-05-14 | #VALUE! | #VALUE!
MO-BEM4.2 |  | E&M Works | ประธาน | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-04-14 | 2026-05-14 | #VALUE! | #VALUE!
MO-BEM5 | DN02B1720005 | Install Concrete car barrier along the walkway in front of MWS building | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-10-15 | 2026-11-14 | #VALUE! | #VALUE!
MO-BEM6 | DN02B1720006 | Handrail on top of the water tank on the rooftop of the Admin Building | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-10-20 | 2026-11-19 | #VALUE! | #VALUE!
MO-BEM7 | DN02B1720007 | Modify maintenance service door to the roof building to easier access while maintaining safe operational standards | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-10-20 | 2026-11-19 | #VALUE! | #VALUE!
MO-BEM8 | DN02B1720008 | Company logo and Central Control Room sign in CCR room. | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-02-12 | 2026-03-14 | #VALUE! | #VALUE!
MO-BEM9 | DN02B1720009 | Soundproof insulation on the wall and structure and equipment in the CCR room. | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-01-28 | 2026-02-27 | #VALUE! | #VALUE!
MO-BEM10 | DN02B1720010 | Ralocate Fire Hose Cabinet to be outside of the clearance guage zone 17 set | ประธาน | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-01-28 | 2026-02-27 | #VALUE! | #VALUE!
MO-BEM11 | DN02B1720011 | Washing Area for Train Cleaning Staff with water tap and floor drainage connects to water treatment system | ประธาน | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-06-04 | 2026-07-04 | #VALUE! | #VALUE!
MO-BEM12 | DN02B1720012 | Rain protection for Water treatment Building | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-04-30 | 2026-05-30 | #VALUE! | #VALUE!
MO-BEM13 | DN02B1720013 | Water gate for Waste water treatment holding pond | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-08-31 | 2026-09-30 | #VALUE! | #VALUE!
MO-BEM14 | DN02B1720014 | Walkway bridge 2 m.Over the canal (Klong chourdyai) Between Depot BL - Depot ORL |  | #VALUE! | #VALUE! | #VALUE! | -30 | 0 | 2026-05-16 | 2026-06-15 | #VALUE! | #VALUE! | #VALUE!
MO-BEM14.1 |  | CIV/AR Works | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-05-16 | 2026-06-15 | #VALUE! | #VALUE!
MO-BEM14.2 |  | E&M Works | ประธาน | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-05-16 | 2026-06-15 | #VALUE! | #VALUE!
MO-BEM15 | DN02B1720015 | Roof for cars parking lots area (184 car) |  | #VALUE! | #VALUE! | #VALUE! | -30 | 0 | 2026-03-01 | 2026-03-31 | #VALUE! | #VALUE! | #VALUE!
MO-BEM15.1 |  | CIV/AR Works | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-03-01 | 2026-03-31 | #VALUE! | #VALUE!
MO-BEM15.2 |  | E&M Works | ประธาน | #VALUE! | #VALUE! | #VALUE!
MO-BEM16 | DN02B1720016 | Walkway roof and High roof across the road from Admin ORL to Depot slap | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-05-31 | 2026-06-30 | #VALUE! | #VALUE!
MO-BEM17 | DN02B1720017 | Walkway roof to car park in front of admin ORL(3x5m.) | สหชาติ | #VALUE! | #VALUE! | #VALUE!
MO-BEM18 | DN02B1720018 | Walkway roof over the footpath near depot slab (1.50 m.x 290 m.) and stair up to depot slap. | สหชาติ | #VALUE! | #VALUE! | #VALUE!
MO-BEM19 | DN02B1720019 | Install Chain Link fence to enclose parking area | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-06-30 | 2026-07-30 | #VALUE! | #VALUE!
MO-BEM20 | DN02B1720020 | Hose bib 1/2" 4 sets for Tree around Admin area | ประธาน | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-05-09 | 2026-06-08 | #VALUE! | #VALUE!
MO-BEM21 | DN02B1720021 | Relocate Security Guard Box at Front Gate and Install Roof 3x5m. |  | #VALUE! | #VALUE! | #VALUE! | -30 | 0 | 2026-08-31 | 2026-09-30 | #VALUE! | #VALUE! | #VALUE!
MO-BEM21.1 |  | CIV/AR Works | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-08-31 | 2026-09-30 | #VALUE! | #VALUE!
MO-BEM21.2 |  | E&M Works | ประธาน | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-08-31 | 2026-09-30 | #VALUE! | #VALUE!
MO-BEM22 | DN02B1720022 | Addition Spike fence for MRTA fence and Chainlink at Klong Chourdyai 400m. | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-08-31 | 2026-09-30 | #VALUE! | #VALUE!
MO-BEM23 | DN02B1720023 | Hand sink with eye wash station (6set) |  | #VALUE! | #VALUE! | #VALUE! | -30 | 0 | 2026-09-15 | 2026-10-15 | #VALUE! | #VALUE! | #VALUE!
MO-BEM23.1 |  | CIV/AR Works | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-09-15 | 2026-10-15 | #VALUE! | #VALUE!
MO-BEM23.2 |  | E&M Works | ประธาน | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-09-15 | 2026-10-15 | #VALUE! | #VALUE!
MO-BEM24 | DN02B1720024 | Guard rail protection for Fire Hose Cabinet 8 set | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-03-15 | 2026-04-14 | #VALUE! | #VALUE!
MO-BEM25 | DN02B1720025 | Chain Link Fence to divide controlled areas on Depot slab 3 m.x 485 m. |  | #VALUE! | #VALUE! | #VALUE! | -30 | 0 | 2026-06-30 | 2026-07-30 | #VALUE! | #VALUE! | #VALUE!
MO-BEM25.1 |  | CIV/AR Works | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-06-30 | 2026-07-30 | #VALUE! | #VALUE!
MO-BEM25.2 |  | E&M Works | ประธาน | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-06-30 | 2026-07-30 | #VALUE! | #VALUE!
MO-BEM26 | DN02B1720026 | Street Lighting system area between MRTA Fence and Depot slab | ประธาน | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-04-15 | 2026-05-15 | #VALUE! | #VALUE!
MO-BEM27 | DN02B1720027 | Compacted gravel walkway along the Test Track OR-BL 1.2 m. (ทางเดินเป็นแนวเอียง) | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-08-31 | 2026-09-30 | #VALUE! | #VALUE!
MO-BEM28 | DN02B1720028 | Walkway under the slab support Maintenance activity |  | #VALUE! | #VALUE! | #VALUE! | -30 | 0 | 2026-09-30 | 2026-10-30 | #VALUE! | #VALUE! | #VALUE!
MO-BEM28.1 |  | CIV/AR Works | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-09-30 | 2026-10-30 | #VALUE! | #VALUE!
MO-BEM28.2 |  | E&M Works | ประธาน | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-09-30 | 2026-10-30 | #VALUE! | #VALUE!
MO-BEM29 | DN02B1720029 | Walkway Bridge across the canal for Depot area inspection patrols 3 location | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-08-31 | 2026-09-30 | #VALUE! | #VALUE!
MO-BEM30 | DN02B1720030 | Cut down trees between Depot BL+ORL and MRTA Fence | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-10-30 | 2026-11-29 | #VALUE! | #VALUE!
MO-BEM31 | DN02B1720031 | Provide faciltiy system and interface to MMC room (Fire Alarm / CCTV / VMS / TEL / CASS / Radio / PA) | ประธาน | #VALUE! | #VALUE! | #VALUE!
MO-BEM32 | DN02B1720032 | Stainless Guard rail balustrade for waiting area | สหชาติ | #VALUE! | #VALUE! | #VALUE!
MO-BEM33 | DN02B1720033 | Concrete walkway 2 x 80 m. For fire escape route | สหชาติ | #VALUE! | #VALUE! | #VALUE!
MO-BEM34 | DN02B1720034 | Access Gate (Full Height Turnstile) at 1st floor admin ORL | มนตรี | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-10-30 | 2026-11-29 | #VALUE! | #VALUE!
MO-BEM35 | DN02B1720035 | Access Gate (Tripod with Swing Gate) at MWS Entrance | บัณฑิต | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-10-30 | 2026-11-29 | #VALUE! | #VALUE!
MO-BEM36 | DN02B1720036 | Access Gate (Tripod with Swing Gate) at Admin 2nd floor connect to OCC | บัณฑิต | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-10-30 | 2026-11-29 | #VALUE! | #VALUE!
MO-BEM37 | DN02B1720037 | Access Gate (Tripod with Swing Gate) on Klong Chourdyai bridge | บัณฑิต | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-10-30 | 2026-11-29 | #VALUE! | #VALUE!
MO-BEM38 | DN02B1720038 | Access Gate (Tripod with roof covering) at parking lot OCC | บัณฑิต | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-10-30 | 2026-11-29 | #VALUE! | #VALUE!
MO-BEM39 | DN02B1720039 | Access Gate (Tripod with roof covering) at Stair up to Depot slab | บัณฑิต | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-10-30 | 2026-11-29 | #VALUE! | #VALUE!
MO-BEM40 | DN02B1720040 | Access Control (2 Factors, Card+Finger Print) at High Security rooms -CCR/PTR/Store | บัณฑิต | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-10-30 | 2026-11-29 | #VALUE! | #VALUE!
MO-BEM41 | DN02B1720041 | Link CCTV Landscape of all depot ORL area for MMC BL monitoring. | บัณฑิต | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-10-30 | 2026-11-29 | #VALUE! | #VALUE!
MO-BEM42 | DN02B1720042 | Fire Suppression Control Panel Cover which located in tunnel | ประธาน | #VALUE! | #VALUE! | #VALUE!
MO-BEM43 | DN02B1720043 | Handrails for ladder at IVS and Vent buildings | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-04-01 | 2026-05-01 | #VALUE! | #VALUE!
MO-BEM44 | DN02B1720044 | Escalator Anti-Slide device for all station. | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-05-31 | 2026-06-30 | #VALUE! | #VALUE!
MO-BEM45 | DN02B1720045 | Roof for control panel on vent building | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-09-30 | 2026-10-30 | #VALUE! | #VALUE!
MO-BEM46 | DN02B1720046 | Provide Standing plate or ladder to access the Fire Valve in at Omega points for all underground stations. | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-09-30 | 2026-10-30 | #VALUE! | #VALUE!
MO-BEM47 | DN02B1720047 | Water drop protection above UPS cabinet at station and Depot | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-09-30 | 2026-10-30 | #VALUE! | #VALUE!
MO-BEM48 | DN02B1720048 | Fire alarm manual call point cover in public area at all station | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-09-30 | 2026-10-30 | #VALUE! | #VALUE!
MO-BEM49 | DN02B1720049 | Emergency stop button cover for escalator at all station. | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-09-30 | 2026-10-30 | #VALUE! | #VALUE!
MO-BEM50 | DN02B1720050 | Modify maintenance service door to the roof of OR13 vent building to easier access while maintaining safe operational standards | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-09-30 | 2026-10-30 | #VALUE! | #VALUE!
MO-BEM51 | DN02B1720051 | Modify existing car park to be 220 motorcycle parking lots including floor painting and parking roof | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-02-14 | 2026-03-16 | #VALUE! | #VALUE!
MO-BEM52 | DN02B1720052 | Modify the sidewalk for temporary parking at entrance | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-08-31 | 2026-09-30 | #VALUE! | #VALUE!
MO-BEM53 | DN02B1720053 | Security Guard Box and Electrical system At OCC Parking lot |  | #VALUE! | #VALUE! | #VALUE! | -30 | 0 | 2026-09-30 | 2026-10-30 | #VALUE! | #VALUE! | #VALUE!
MO-BEM53.1 |  | CIV/AR Works | สหชาติ | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-09-30 | 2026-10-30 | #VALUE! | #VALUE!
MO-BEM53.2 |  | E&M Works | ประธาน | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 2026-09-30 | 2026-10-30 | #VALUE! | #VALUE!
MO-BEM54 | DN02B1720054 | Strengthen the Maintenance Walkway of the TEF fan | สหชาติ | #VALUE! | #VALUE! | #VALUE!
Formulas:
ISO Plan = [PO/WO]-30
PO/WO = MAX([PO/WO, row below]:I7)
Minor Work Plan = [PO/WO]-30
PPR Status = IF([Total (List)]=[PPR Issued],"Completed",IF([ISO Plan]>TODAY(),"On Schedule",IF([Minor Work Plan]>=[ISO Plan],"On Schedule","Late")))
PO/WO Status = IF([Total (List)]=[PO/WO Issued],"Completed",IF([PO/WO]>TODAY(),"On Schedule",IF([PO/WO]>=[PO/WO],"On Schedule","Late")))

## Master Data Lot2 (hidden)
No | Item | BEM Item | Submission No. | Lot | Description | Expected Completion Month | Design % | Plan Finish (Design) | Status Design | Procurement % | Plan Finish (Procurement) | Status Procurement | Construction % | Plan Finish (Construction) | Status Construction | Overall Progress | Location Rev.01 | Location Rev.02 | CK Responsible Person | Type of Work | Detail
1 | MO-BEM1.1 | MDW1/2-1 | MDW-39506 | Lot02 | Walkway from Main Work Shop to Stabling Area - Building Services | 2026-08-31 | 100% | 2026-04-28 | Completed | 100% | 2026-05-29 | Completed | 75% | 2026-09-30 | On Schedule | 82.5% | Landscape on Depot Slab | Walkway | ประธาน | EE/ME | Walkway 1.5m(W) x 2m.(H) ระดับเดียวกับ platform | Design | Procurement | Construction
2 | MO-BEM1.2 | MDW1/2-1 | MDW-39505 | Lot02 | Walkway from Main Work Shop to Stabling Area - Civil & AR | 2026-08-31 | 100% | 2026-04-28 | Completed | 100% | 2026-05-29 | Completed | 0% | 2026-09-30 | On Schedule | 30% | Landscape on Depot Slab | Walkway | สหชาติ | CV/AR | Walkway 1.5m(W) x 2m.(H) ระดับเดียวกับ platform | 10% | 20% | 70%
3 | MO-BEM2 | MDW2-2 | MDW-39507 | Lot02 | High Roof at Main Work Shop Entrance and Store | 2026-08-31 | 100% | 2026-02-13 | Completed | 100% | 2026-03-31 | Completed | 100% | 2026-07-31 | Completed | 100% | Landscape on Depot Slab | High Roof | สหชาติ | CV/AR | 1.หลังคาสูงด้านหน้าทางเข้า MWS + Store -12x35x5.5m. = 420 sqm. 2.หลังคาสูงบน Roller Shutter หน้า Store -10x4x5.5m. = 40 sqm.
4 | MO-BEM3 | MDW2-3 | MDW-39509 | Lot02 | High Roof at the entance and exit of the under floor wheel lathe | 2026-08-31 | 100% | 2026-02-13 | Completed | 100% | 2026-03-31 | Completed | 100% | 2026-07-31 | Completed | 100% | Landscape on Depot Slab | High Roof | สหชาติ | CV/AR | หลังคาสูงด้านหน้าทางเข้าเคริ้องกลึงล้อ -5.2 wide x 20 m long x5.5 m.high for each side
5 | MO-BEM5 | MDW2-5 | MDW-39513 | Lot02 | Install Concrete car barrier along the walkway in front of MWS building | 2027-01-31 | 100% | 2026-10-14 | Completed | 100% | 2026-11-14 | Completed | 100% | 2026-12-31 | Completed | 100% | Landscape on Depot Slab | Other Landscape | สหชาติ | CV/AR | คันคอนกรีตทางเดินหน้า MWS
6 | MO-BEM18 | MDW1-10 | MDW-39519 MDW-39520 | Lot02 | Walkway roof over the footpath near depot slab (1.50 m.x 290 m.) and stair up to depot slap. | 2026-08-31 | 100% | 2026-06-15 | Completed | 30% | 2026-06-30 | Late | 30% | 2026-10-31 | On Schedule | 37% | Landscape on Depot Slab | Walkway | สหชาติ | CV/AR | ทำทางเดินฟุตบาทบริเวณ depot slab และบันไดทางขึ้น
7 | MO-BEM24 | MDW2-24 | MDW-39531 | Lot02 | Guard rail protection for Fire Hose Cabinet 8 set | 2026-06-30 | 100% | 2026-03-14 | Completed | 100% | 2026-04-14 | Completed | 100% | 2026-08-15 | Completed | 100% | Landscape on Depot Slab | Other Landscape | สหชาติ | CV/AR | Guard กันชนตู้ Fire Hose Cabinet สูง 1 ม. กว้าง 0.7 ม.
8 | MO-BEM25.1 | MDW1-9 | MDW-39520 | Lot02 | Chain Link Fence to divide controlled areas on Depot slab 3 m.x 485 m.- Building Services | 2026-10-31 | 100% | 2026-06-14 | Completed | 100% | 2026-07-30 | Completed | 0% | 2026-09-30 | On Schedule | 30% | Landscape on Depot Slab | Chain Link | ประธาน | EE/ME | ติดตั้งรั้ว Chain Link แบ่งกั้นพื้นที่ควบคุมบน Depot slab สูง 3 ม.ยาว 485 ม.
9 | MO-BEM25.2 | MDW1-9 | MDW-39519 | Lot02 | Chain Link Fence to divide controlled areas on Depot slab 3 m.x 485 m. - Civil & AR | 2026-10-31 | 100% | 2026-06-14 | Completed | 100% | 2026-07-30 | Completed | 0% | 2026-09-30 | On Schedule | 30% | Landscape on Depot Slab | Chain Link | สหชาติ | CV/AR | ติดตั้งรั้ว Chain Link แบ่งกั้นพื้นที่ควบคุมบน Depot slab สูง 3 ม.ยาว 485 ม.
10 | MO-CK10 | MDW2-50 | MDW-39544 | Lot02 | Barbed wire fence Viaduct CE CW | 2027-01-31 | 10% | 2026-08-30 | Late | 0% | 2026-09-30 | On Schedule | 0% | 2026-12-31 | On Schedule | 1% | Landscape Works around Depot | Other Landscape | บัณฑิต/สหชาติ | CV/AR | ติดตั้งรั้วลวดหนามหีบเพลง แนวรั้ว Viaduct CE CW ยกเลิก Barbed wire fence Viaduct CE CW มีกล้อง(ไม่มีfunction intrusion) ล้อมรอบพื้นที่ จำนวน 19 ตัว
11 | MO-CK11 | MDW2-51 | MDW-39545 | Lot02 | Chain Link at Cut & Cover 600m. | 2026-06-30 | 100% | 2026-02-27 | Completed | 100% | 2026-04-30 | Completed | 90% | 2026-08-31 | On Schedule | 93% | Landscape Works around Depot | Chain Link | สหชาติ | CV/AR | Chain Link ปิดด้านข้าง Cut & Cover
12 | MO-CK12 | MDW2-52 | MDW-39546 | Lot02 | Chain Link under slab high 1.70 m | 2027-01-31 | 100% | 2026-06-30 | Completed | 50% | 2026-07-31 | Late | 0% | 2026-12-31 | On Schedule | 20% | Landscape Works around Depot | Chain Link | สหชาติ | CV/AR | ติดตั้งรั้ว Chain Link ปิดใต้ slab สูง 1.70 ม. (3,047 ม.)
13 | MO-CK27 | MDW2-25 | MDW-39532 | Lot02 | Spike fence for Depot slab | 2027-01-31 | 10% | 2026-07-31 | On Schedule | 0% | 2026-08-31 | On Schedule | 0% | 2026-12-31 | On Schedule | 1% | Landscape Works around Depot | Other Landscape | บัณฑิต/สหชาติ | CV/AR | ติดตั้งรั้วเหล็กแหลม Depot slab (5,568 ม.) ยกเลิก Spike fence มีกล้องล้อมรอบ Depot platform เพิ่มรั้วหีบเพลงบริเวณจุดที่ใกล้ถนนกับจุดที่รั้วเตี้ย
14 | MO-BEM13 |  |  | Lot02 | Water gate for Waste water treatment holding pond | 2027-01-31 | 100% | 2026-08-30 | Completed | 100% | 2026-09-30 | Completed | 0% | 2026-12-31 | On Schedule | 30% | Landscape Works around Depot | Other Landscape | สหชาติ | CV/AR | จากwater treatment ไปลงบ่อใหม่ (บ่อปูน) ขุดบ่อเพิ่ม ขนาด 5x5 m.
15 | MO-BEM14.1 | MDW1-7 | MDW-39517 | Lot02 | Modification Works : Walkway Bridge between BL Depot and ORL Depot - Building Services | 2026-08-31 | 100% | 2026-02-28 | Completed | 100% | 2026-06-15 | Completed | 30% | 2026-09-30 | On Schedule | 51% | Landscape Works around Depot | Bridge | ประธาน | EE/ME | สะพานข้ามคลองขนาดเล็ก จาก Depot ORL มายัง Depot BL สะพาน3จุด ขนาด 2 m.
16 | MO-BEM14.2 | MDW1-7 | MDW-39516 | Lot02 | Modification Works : Walkway Bridge between BL Depot and ORL Depot - Civil & AR | 2026-08-31 | 100% | 2026-01-14 | Completed | 100% | 2026-03-01 | Completed | 10% | 2026-07-31 | Late | 37% | Landscape Works around Depot | Bridge | สหชาติ | CV/AR | สะพานข้ามคลองขนาดเล็ก จาก Depot ORL มายัง Depot BL สะพาน3จุด ขนาด 2 m.
17 | MO-BEM15.1 | MDW2-6 | MDW-39515 | Lot02 | Roof for cars parking lots area (184 car) - Building Services | 2026-08-31 | 100% | 2026-02-28 | Completed | 100% | 2026-03-31 | Completed | 100% | 2026-07-31 | Completed | 100% | Landscape Works around Depot | Other Landscape | ประธาน | EE/ME | ทำหลังคาสำหรับลานจอดรถ 184 คัน
18 | MO-BEM15.2 | MDW2-6 | MDW-39514 | Lot02 | Roof for cars parking lots area (184 car)t - Civil & AR | 2026-08-31 | 100% | 2026-02-28 | Completed | 100% | 2026-03-31 | Completed | 90% | 2026-07-31 | Late | 93% | Landscape Works around Depot | Other Landscape | สหชาติ | CV/AR | ทำหลังคาสำหรับลานจอดรถ 184 คัน
19 | MO-BEM16 | MDW2-15 | MDW-39519 MDW-39520 | Lot02 | Walkway roof and High roof across the road from Admin ORL to Depot slap | 2026-08-31 | 100% | 2026-06-15 | Completed | 30% | 2026-06-30 | Late | 30% | 2026-10-31 | On Schedule | 37% | Landscape Works around Depot | Walkway | สหชาติ | CV/AR | หลังคาสูงข้ามถนนจากอาคาร Admin ไปยัง Depot slab เพื่อเข้า MWS หลังคาสูง 5.5m.รวมคานเหล็กกันรถสูงผ่าน
20 | MO-BEM17 | MDW2-20 | MDW-39519 MDW-39520 | Lot02 | Walkway roof to car park in front of admin ORL(3x5m.) | 2026-08-31 | 100% | 2026-06-15 | Completed | 30% | 2026-06-30 | Late | 30% | 2026-10-31 | On Schedule | 37% | Landscape Works around Depot | Walkway | สหชาติ | CV/AR | หลังคากันฝนทางเดินลงลานจอดหน้าอาคารบริหาร ขนาด 3x5 ม.
21 | MO-BEM20 | MDW2-16 | MDW-39523 | Lot02 | Hose bib 1/2" 4 sets for Tree around Admin area | 2026-06-30 | 100% | 2026-04-23 | Completed | 100% | 2026-06-08 | Completed | 100% | 2026-07-31 | Completed | 100% | Landscape Works around Depot | Other Landscape | ประธาน | EE/ME
22 | MO-BEM21 | MDW2-31 | MDW-39534 MDW-39535 | Lot02 | Relocate Security Guard Box at Front Gate and Install Roof 3x5m. | 2027-01-31 | 100% | 2026-07-31 | Completed | 100% | 2026-09-30 | Completed | 0% | 2026-12-31 | On Schedule | 30% | Landscape Works around Depot | Other Landscape | สหชาติ | CV/AR | ย้ายป้อมรปภ.หน้าทางเข้า + ติดตั้งหลังคา 3x5 ม.
23 | MO-BEM22 | MDW2-25 | MDW-39532 | Lot02 | Addition Spike fence for MRTA fence and Chainlink at Klong Chourdyai 400m. | 2027-01-31 | 28% | 2026-08-30 | On Schedule | 0% | 2026-09-30 | On Schedule | 0% | 2026-12-31 | On Schedule | 2.8% | Landscape Works around Depot | Other Landscape | บัณฑิต/สหชาติ | CV/AR | ติดตั้งรั้วเหล็กแหลม แนวรั้วรฟม.+ แนวรั้ว Chainlink ฝั่งริมคลองชวดใหญ่ ไม่ทำเหล็กแหลม ทำรั้วหีบเพลงตลอดแนว + ติดกล้อง
24 | MO-BEM26 | MDW1-8 | MDW-39518 | Lot02 | Street Lighting system area between MRTA Fence and Depot slab | 2026-08-31 | 0% | 2026-04-14 | Late | 0% | 2026-05-15 | Late | 0% | 2026-07-31 | Late | 0% | Landscape Works around Depot | Other Landscape | ประธาน | EE/ME | ทางเดินหลัง MWS-Permanent way ค่า LUX. 25 Lux as minimum - 50 lux อ้างอิงกรมสวัสดิการคุ้มครองแรงงาน 2561 (ใกล้เคียงกับ BLE)
25 | MO-BEM27 | MDW2-12 |  | Lot02 | Compacted gravel walkway along the Test Track OR-BL 1.2 m. (ทางเดินเป็นแนวเอียง) | 2027-01-31 | 100% | 2026-08-30 | Completed | 10% | 2026-09-30 | On Schedule | 0% | 2026-12-31 | On Schedule | 12% | Landscape Works around Depot | Road and Walkway for Maintenance Service and Inspection | สหชาติ | CV/AR | ไม่ทำทางเดิน ทำรั้ว Chainlink ปิดต้น-ปลายทาง + ทำประตูเล็กแทน (ใส่กุญแจล็อก)
26 | MO-BEM28.1 | MDW2-12 | MDW-39525 | Lot02 | Walkway under Depot Slab for Maintenance Service - Building Services | 2027-01-31 | 100% | 2026-09-14 | Completed | 100% | 2026-10-30 | Completed | 84% | 2026-12-31 | On Schedule | 88.8% | Landscape Works around Depot | Walkway | ประธาน | EE/ME | -lighting for Waste water tank 7 set
27 | MO-BEM28.2 | MDW2-12 | MDW-39524 | Lot02 | Walkway under Depot Slab for Maintenance Service - Civil & AR | 2027-01-31 | 100% | 2026-09-14 | Completed | 100% | 2026-10-30 | Completed | 0% | 2026-12-31 | On Schedule | 30% | Landscape Works around Depot | Walkway | สหชาติ | CV/AR | -Walk way under slab 270m. -Walk way and support up to Waste water tank 8 set -Bridge over gutter 2 set
28 | MO-BEM29 | MDW2-11 | MDW-39521 | Lot02 | Walkway Bridge across the canal for Depot area inspection patrols 3 location | 2027-01-31 | 100% | 2026-08-15 | Completed | 100% | 2026-09-30 | Completed | 20% | 2026-12-31 | On Schedule | 44% | Landscape Works around Depot | Walkway | สหชาติ | CV/AR | Walkway Bridge over canal for Security patrol 3 set สะพานเหล็กกว้าง 2 ม. 3 จุด
29 | MO-BEM30 | MDW1/2-18 |  | Lot02 | Cut down trees between Depot BL+ORL and MRTA Fence | 2027-01-31 | 0% | 2026-10-29 | On Schedule | 0% | 2026-11-29 | On Schedule | 0% | 2026-12-31 | On Schedule | 0% | Landscape Works around Depot | Other Landscape | สหชาติ | CV/AR | ตัดต้นไม้ตลอดแนวรั้ว Depot BL+ORL ดำเนินการ 1 ครั้งก่อนเปิดเดินรถ
30 | MO-BEM34 | MDW2-27 |  | Lot02 | Access Gate (Full Height Turnstile) at 1st floor admin ORL | 2027-01-31 | 100% | 2026-11-28 | Completed | 100% | 2026-11-29 | Completed | 0% | 2026-12-31 | On Schedule | 30% | Works in Depot Building | Access Gate | สหชาติ | CV/AR | Access Gate (Full Height Turnstile) ที่ทางลงลานจอดรถใต้อาคารบริหาร
31 | MO-BEM35 | MDW2-29 |  | Lot02 | Access Gate (Tripod with Swing Gate) at MWS Entrance | 2027-01-31 | 100% | 2026-11-28 | Completed | 100% | 2026-11-29 | Completed | 0% | 2026-12-31 | On Schedule | 30% | Landscape Works around Depot | Access Gate | บัณฑิต | EE/ME | Access Gate (Tripod with Swing Gate)ที่โถงทางเข้าออก MWS
32 | MO-BEM36 | MDW2-29 |  | Lot02 | Access Gate (Tripod with Swing Gate) at Admin 2nd floor connect to OCC | 2027-01-31 | 100% | 2026-11-28 | Completed | 100% | 2026-11-29 | Completed | 0% | 2026-12-31 | On Schedule | 30% | Landscape Works around Depot | Access Gate | บัณฑิต | EE/ME | Access Gate (Tripod with Swing Gate) จากตึกAdminชั้น2 ไป OCC
33 | MO-BEM37 | MDW2-29 |  | Lot02 | Access Gate (Tripod with Swing Gate) on Klong Chourdyai bridge | 2027-01-31 | 100% | 2026-11-28 | Completed | 100% | 2026-11-29 | Completed | 0% | 2026-12-31 | On Schedule | 30% | Landscape Works around Depot | Access Gate | บัณฑิต | EE/ME | Access Gate (Tripod with Swing Gate) บนสะพานข้ามคลองชวดใหญ่
34 | MO-BEM38 | MDW2-29 |  | Lot02 | Access Gate (Tripod with roof covering) at parking lot OCC | 2027-01-31 | 100% | 2026-11-28 | Completed | 100% | 2026-11-29 | Completed | 0% | 2026-12-31 | On Schedule | 30% | Landscape Works around Depot | Access Gate | บัณฑิต | EE/ME | Access Gate (Tripod with roof covering) ที่ลานจอดรถพนักงานหลัง OCC
35 | MO-BEM39 | MDW2-29 |  | Lot02 | Access Gate (Tripod with roof covering) at Stair up to Depot slab | 2027-01-31 | 100% | 2026-11-28 | Completed | 100% | 2026-11-29 | Completed | 0% | 2026-12-31 | On Schedule | 30% | Landscape Works around Depot | Access Gate | บัณฑิต | EE/ME | Access Gate (Tripod with roof covering) ที่ทางขึ้นลง Depot slab
36 | MO-BEM51 | MDW2-6 | MDW-39514 MDW-39515 | Lot02 | Modify existiong car park to be 220 motorcycle parking lots including floor painting and parking roof | 2026-08-31 | 100% | 2026-01-29 | Completed | 100% | 2026-03-16 | Completed | 100% | 2026-07-31 | Completed | 100% | Landscape Works around Depot | Other Landscape | สหชาติ | CV/AR | ปรับลานจอดรถเป็นลานจอดมอเตอร์ไซค์ 220 คัน รวมทำหลังคา
37 | MO-BEM53.1 | MDW2-32 | MDW-39555 | Lot02 | Modification Works : Security Guard Box at OCC Parking Area - Building Services | 2027-01-31 | 100% | 2026-09-14 | Completed | 100% | 2026-10-30 | Completed | 0% | 2026-12-31 | On Schedule | 30% | Landscape Works around Depot | Other Landscape | ประธาน | EE/ME | ติดตั้งป้อมรปภ.สำเร็จรูปพร้อมเดินระบบไฟฟ้า ขนาด 1 x 2 ม ที่ลานจอดรถพนักงานหลัง OCC
38 | MO-BEM53.2 | MDW2-32 | MDW-39554 | Lot02 | Modification Works : Security Guard Box at OCC Parking Area - Civil & AR | 2027-01-31 | 100% | 2026-09-14 | Completed | 100% | 2026-10-30 | Completed | 10% | 2026-12-31 | On Schedule | 37% | Landscape Works around Depot | Other Landscape | สหชาติ | CV/AR | ติดตั้งป้อมรปภ.สำเร็จรูปพร้อมเดินระบบไฟฟ้า ขนาด 1 x 2 ม ที่ลานจอดรถพนักงานหลัง OCC
39 | MO-CK1.1 | MDW2-55 | MDW-39501 | Lot02 | Store Modification Works at Main Workshop - Building Services | 2026-06-30 | 100% | 2026-02-27 | Completed | 100% | 2026-03-30 | Completed | 100% | 2026-05-31 | Completed | 100% | Works in Depot Building | MWS | ประธาน | EE/ME | ปรับปรุงห้อง 1.ห้อง office store 2.two-tier shelf 3.main pallet storage 4.tool storage
40 | MO-CK1.2 | MDW2-55 | MDW-39500 | Lot02 | Store Modification Works at Main Workshop - Civil&AR | 2026-06-30 | 100% | 2026-02-12 | Completed | 100% | 2026-03-30 | Completed | 95% | 2026-05-28 | Late | 96.5% | Works in Depot Building | MWS | สหชาติ | CV/AR | ปรับปรุงห้อง 1.ห้อง office store 2.two-tier shelf 3.main pallet storage 4.tool storage
41 | MO-CK2.1 | MDW1/2-53 | MDW-39504 | Lot02 | New MMC at Admin Building - Building Services | 2026-08-31 | 100% | 2026-04-14 | Completed | 100% | 2026-05-15 | Completed | 100% | 2026-07-31 | Completed | 100% | Works in Depot Building | Admin | ประธาน | EE/ME | งานระบบประกอบอาคารย้ายตู้ Panel จากห้อง SCADA ไปที่ห้อง Storge ที่ MWS แล้ว Like ผ่านระบบ Backbone
42 | MO-CK2.2 | MDW1/2-53 | MDW-39503 | Lot02 | New MMC at Admin Building - Civil & AR | 2026-08-31 | 100% | 2026-02-28 | Completed | 100% | 2026-04-15 | Completed | 88% | 2026-08-31 | Late | 91.6% | Works in Depot Building | Admin | สหชาติ | CV/AR | ทำผนังกั้นห้องเป็นห้อง MMC (Lobby Admin)
43 | MO-CK4 | MDW1/2-49 | MDW-39543 | Lot02 | Bird & Rain Protetion for Open space Admin C | 2026-08-31 | 100% | 2026-04-29 | Completed | 100% | 2026-05-30 | Completed | 100% | 2026-07-31 | Completed | 100% | Works in Depot Building | Admin | สหชาติ | CV/AR | ผนังกันฝนสาด และกันนกเข้าอาคาร Admin C (9 ช่อง)
44 | MO-CK5 | MDW2-56 | MDW-39547 | Lot02 | Relocate door in front of toilet and build partition wall to conceal the view in side of toilet | 2026-08-31 | 100% | 2026-05-14 | Completed | 100% | 2026-06-14 | Completed | 90% | 2026-07-31 | Late | 93% | Works in Depot Building | Admin | สหชาติ | CV/AR | ย้ายประตูหน้าห้องน้ำและสร้างผนังกั้นเพื่อปิดบังมุมมองด้านข้างห้องน้ำ
45 | MO-CK6 | MDW2-57 | MDW-39547 | Lot02 | Modify Lockset the emergency door to be used for passage between the 2nd and 3rd floors inside the building. | 2026-08-31 | 100% | 2026-04-29 | Completed | 100% | 2026-06-14 | Completed | 100% | 2026-07-31 | Completed | 100% | Works in Depot Building | Admin | สหชาติ | CV/AR | ปรับเปลี่ยนประตูฉุกเฉินเพื่อใช้เป็นทางเดินระหว่างชั้น 2 และ 3 ภายในอาคาร
46 | MO-CK7 | MDW2-58 | MDW-39556 | Lot02 | Addition small power for lounge and pantry room at 2nd floor and Hall andobservation room at 3nd floor | 2026-08-31 | 100% | 2026-05-14 | Completed | 100% | 2026-06-14 | Completed | 100% | 2026-07-31 | Completed | 100% | Works in Depot Building | Admin | ประธาน | EE/ME | เพิ่มปลั๊กในห้องนั่งเล่นและห้องเตรียมอาหารชั้น 2 และห้องโถงและห้องสังเกตการณ์ชั้น 3
47 | MO-CK8 | MDW2-59 | MDW-39548 | Lot02 | Air Condition for using store room to be pantry room. 2nd floor | 2026-08-31 | 100% | 2026-04-29 | Completed | 100% | 2026-06-14 | Completed | 100% | 2026-07-31 | Completed | 100% | Works in Depot Building | Admin | ประธาน | EE/ME | แอร์สำหรับห้องเก็บของที่จะเป็นห้องเตรียมอาหาร ชั้น 2
48 | MO-CK9 | MDW1/2-60 | MDW-39552 | Lot02 | Walk Way Hand rail high 90 cm 1 side (144 m.x 7 route) | 2026-10-31 | 100% | 2026-05-30 | Completed | 100% | 2026-06-30 | Completed | 78% | 2026-09-30 | On Schedule | 84.6% | Works in Depot Building | Stabling yard | สหชาติ | CV/AR | ราวจับทางเดินสูง 90 ซม. 1 ด้าน
49 | MO-CK15.1 | ADW-1/2 | MDW-39296 | Lot02 | Change Electrical Equipment to be Explosion-proof type - Building Services | 2026-05-31 | 100% | 2026-01-27 | Completed | 100% | 2026-02-27 | Completed | 100% | 2026-04-30 | Completed | 100% | Works in Depot Building | MWS | ประธาน | EE/ME | ติดตั้งระบบดับเพลิงชนิดโฟม
50 | MO-CK15.2 | ADW-1/2 | MDW-39295 | Lot02 | Epoxy Floor Installation and Curb Installation at the Entrance - Civil & AR | 2026-05-31 | 100% | 2025-12-13 | Completed | 100% | 2026-01-28 | Completed | 75% | 2026-04-30 | Late | 82.5% | Works in Depot Building | MWS | สหชาติ | CV/AR | เทพื้น Epoxyและติดตั้ง Curb หน้าประตูทางเข้า
51 | MO-CK33 |  |  | Lot02 | Additional lighting in areas where the lux level does not meet occupational health standards | 2027-01-31 | 100% | 2026-09-14 | Completed | 100% | 2026-10-15 | Completed | 95% | 2026-12-31 | On Schedule | 96.5% | Works in Depot Building | MWS | ประธาน | EE/ME | เพิ่มแสงสว่างในพื้นที่ที่ระดับลักซ์ไม่ตรงตามมาตรฐานอาชีวอนามัย
52 | MO-BEM4.1 | MDW2-4 | MDW-39512 | Lot02 | Maintenance Office Rooms at Main Workshop - Building Services | 2026-07-31 | 100% | 2026-04-13 | Completed | 100% | 2026-05-14 | Completed | 100% | 2026-06-30 | Completed | 100% | Works in Depot Building | MWS | ประธาน | EE/ME | ติดตั้ง - ระบบแอร์ - ระบบไฟแสงสว่าง - ปลั๊กไฟ
53 | MO-BEM4.2 | MDW2-4 | MDW-39511 | Lot02 | Maintenance Office Rooms at Main Workshop - Civil & AR | 2026-07-31 | 100% | 2026-04-13 | Completed | 100% | 2026-05-14 | Completed | 80% | 2026-06-30 | Late | 86% | Works in Depot Building | MWS | สหชาติ | CV/AR | ติดตั้ง - หน้าต่าง - พื้นกระเบื้องเซรามิก
54 | MO-BEM6 | MDW2-47 | MDW-39543 | Lot02 | Handrail on top of the water tank on the rooftop of the Admin Building | 2027-01-31 | 100% | 2026-10-19 | Completed | 100% | 2026-11-19 | Completed | 0% | 2026-12-31 | On Schedule | 30% | Works in Depot Building | Admin | สหชาติ | CV/AR | ราวจับบนถังเก็บน้ำบนดาดฟ้าอาคาร Admin 1.รูปแบบทำเฉพาะจุด water tank 1 ด้าน 2.เสริมguard rail ของบันได 3.ทำตัวค้ำฝาเปิด water tank
55 | MO-BEM7 | MDW2-47/48 | MDW-39543 | Lot02 | Modify maintenance service door to the roof building to easier access while maintaining safe operational standards | 2027-01-31 | 0% | 2026-10-19 | On Schedule | 0% | 2026-11-19 | On Schedule | 0% | 2026-12-31 | On Schedule | 0% | Works in Depot Building | Admin | สหชาติ | CV/AR | - อาคาร admin: ถังน้ำบนหลังคา - เพิ่มราวกันตกประมาณ 6 เมตร, เหล็กค้ำฝา, เพิ่มเหล็กกันหลังบันไดลิง (ของเดิมห่าง)
56 | MO-BEM8 | MDW2-35 | MDW-39536 | Lot02 | Company logo and Central Control Room sign in CCR room. | 2026-05-31 | 100% | 2026-01-27 | Completed | 100% | 2026-03-14 | Completed | 100% | 2026-04-30 | Completed | 100% | Works in Depot Building | Admin | สหชาติ | CV/AR | ติตดั้งโลโก้บริษัทแลป้ายห้องควบคุมกลางในห้อง CCR
57 | MO-BEM9 | MDW2-33 | MDW-39536 | Lot02 | Soundproof insulation on the wall and structure and equipment in the CCR room. | 2026-05-31 | 100% | 2026-01-12 | Completed | 100% | 2026-02-27 | Completed | 100% | 2026-04-30 | Completed | 100% | Works in Depot Building | Admin | สหชาติ | CV/AR | ฉนวนกันเสียงบนผนังและอุปกรณ์ในห้อง CCR
58 | MO-BEM10 | MDW2-19 | MDW-39526 | Lot02 | Ralocate Fire Hose Cabinet to be outside of the clearance guage zone 17 set (E5 Not accepted as a defect because it follows the specified drawing) | 2026-05-31 | 100% | 2026-01-12 | Completed | 100% | 2026-02-27 | Completed | 100% | 2026-04-30 | Completed | 100% | Works in Depot Building | Stabling yard | ประธาน | EE/ME | ตู้ FHC ขยับหมุนให้สามารถเปิดตู้ใช้งานได้พอ (มีย้ายแค่1ตู้ที่มีปัญหาเปิดไม่ได้เลย) มีงานย้ายถังดับเพลิงด้วย
59 | MO-BEM11.1 | MDW2-22 | MDW-39529 | Lot02 | Washing Area in Cleaning Staff Room at Stabling Yard - Building Services | 2026-08-31 | 100% | 2026-06-03 | Completed | 100% | 2026-07-04 | Completed | 100% | 2026-07-31 | Completed | 100% | Works in Depot Building | Stabling yard | ประธาน | EE/ME | พื้นที่ซักล้าง มีระบบน้ำดี และระบายน้ำเสียเข้าระบบบำบัดของอาคาร
60 | MO-BEM11.2 | MDW2-22 | MDW-39528 | Lot02 | Washing Area in Cleaning Staff Room at Stabling Yard - Civil & AR | 2026-08-31 | 100% | 2026-04-14 | Completed | 100% | 2026-05-30 | Completed | 100% | 2026-07-31 | Completed | 100% | Works in Depot Building | Stabling yard | สหชาติ | CV/AR | พื้นที่ซักล้าง มีระบบน้ำดี และระบายน้ำเสียเข้าระบบบำบัดของอาคาร
61 | MO-BEM12 | MDW2-23 | MDW-39530 | Lot02 | Rain protection for Water treatment Building | 2026-08-31 | 100% | 2026-04-29 | Completed | 100% | 2026-05-30 | Completed | 100% | 2026-07-31 | Completed | 100% | Works in Depot Building | Water treatment Building | สหชาติ | CV/AR | ติดตั้งผนัง Louver กันฝนสาด
62 | MO-BEM19 | MDW2-14 | MDW-39519 MDW-39520 | Lot02 | Install Chain Link fence to enclose parking area | 2026-10-31 | 100% | 2026-06-29 | Completed | 100% | 2026-07-30 | Completed | 0% | 2026-09-30 | On Schedule | 30% | Works in Depot Building | Admin | สหชาติ | CV/AR | รั้ว Chain Link ปิดกั้นพื้นที่ลานจอดรถยาว 180 ม.x สูง 2.5 ม.
63 | MO-BEM23 | MDW2-21 | MDW-39527 | Lot02 | Hand sink with eye wash station(6set) | 2027-01-31 | 100% | 2026-08-30 | Completed | 100% | 2026-10-15 | Completed | 50% | 2026-12-31 | On Schedule | 65% | Works in Depot Building | MWS | ประธาน | EE/ME | รูปแบบเป็นแบบอ่างล้างสำเร็จรูป ไม่เป็นก่อปูน - Eye wash ทำเป็นถังไว้ให้ ไม่ต่อท่อ - Hand wash ทำท่อลงไปยังถังบำบัดจากห้องน้ำ (มีถังดักไขมัน)
64 | MO-BEM31 | MDW2-35/36 |  | Lot02 | Provide faciltiy system and interface to MMC room (Fire Alarm / CCTV / VMS / TEL / CASS / Radio / PA) | 2026-10-31 | 100% | 2026-04-30 | Completed | 100% | 2026-05-31 | Completed | 66% | 2026-09-30 | On Schedule | 76.2% | Works in Depot Building | Admin | บัณฑิต | EE/ME | เพิ่ม CCTV ที่ Dorm และ Link FA/CCTV/CASS ไปที่ MMC
65 | MO-BEM40 | MDW2-30 |  | Lot02 | Access Control (2 Factors, Card+Finger Print) at High Security rooms-CCR/PTR/Store | 2027-01-31 | 0% | 2026-11-28 | On Schedule | 0% | 2026-11-29 | On Schedule | 0% | 2026-12-31 | On Schedule | 0% | Works in Depot Building | Admin | บัณฑิต | EE/ME | ระบบตรวจสอบอัตลักษณ์ (2 Factors) บัตร+ลายนิ้วมือ หน้าห้องพื้นที่ Hight Security -CCR/PTR/Store
66 | MO-BEM41 | MDW2-28 |  | Lot02 | Link CCTV Landscape of all depot ORL area for MMC BL monitoring. | 2027-01-31 | 0% | 2026-11-28 | On Schedule | 0% | 2026-11-29 | On Schedule | 0% | 2026-12-31 | On Schedule | 0% | Works in Depot Building | Admin | บัณฑิต | EE/ME | Link ภาพ CCTV รอบนอก ORL มายัง MMC BL เพิ่ม Workstation ที่ MMC BL แล้ว Link CCTV ORL ไป
67 | MO-CK13.1 | MDW2-61 | MDW-39550 | Lot02 | Satellite Store at OR21 - Civil & AR | 2027-01-31 | 0% | 2026-08-30 | Completed | 0% | 2026-10-15 | Completed | 0% | 2026-12-31 | On Schedule | 0% | Works in ORL East Station/IVS/ VS/Mainline | Maintenance | สหชาติ | CV/AR | เพิ่ม Sink ล้างเครื่องมือที่ห้อง Cleaner จำนวน 6 สถานี
68 | MO-CK13.2 | MDW2-61 | MDW-39549 | Lot02 | Maintenance Room and Satellite Store at Stations - Building Services | 2027-01-31 | 100% | 2026-08-30 | On Schedule | 100% | 2026-10-15 | On Schedule | 65% | 2026-12-31 | On Schedule | 75.5% | Works in ORL East Station/IVS/ VS/Mainline | Maintenance | ประธาน | EE/ME | -ติดแอร์ห้องMaintenance และห้อง Cleaner จำนวน 6 สถานี '-มีระบบ LAN, TEL, CASS เป็น STEE Contract scope
69 | MO-CK14 | MDW2-62 | MDW-39551 | Lot02 | Modify Cleaner room at OR29 to be Train crew Standby office with facility system | 2026-07-31 | 100% | 2026-03-14 | Completed | 100% | 2026-04-29 | Completed | 90% | 2026-06-30 | Late | 93% | Works in ORL East Station/IVS/ VS/Mainline | Operattion | ประธาน | EE/ME | ห้อง Train crew Standby office พร้อม facility ที่ OR29 ชั้น concourse
70 | MO-CK30 |  |  | Lot02 | Lighting for sealed space under stairs and behind lift shaft at underground station | 2027-01-31 | 0% | 2026-10-14 | On Schedule | 0% | 2026-11-14 | On Schedule | 0% | 2026-12-31 | On Schedule | 0% | Works in ORL East Station/IVS/ VS/Mainline | Maintenance | ประธาน | EE/ME | ไฟส่องสว่างสำหรับพื้นที่ปิดใต้บันไดและด้านหลังช่องลิฟต์ที่สถานีรถไฟใต้ดิน
71 | MO-CK31 |  |  | Lot02 | Modify the access door of sealed space (under-stairs room) with a Sump Pump or ESPS cabinet by extend to the full door add lighting to the under stairs room | 2027-01-31 | 0% | 2026-07-16 | Late | 0% | 2026-08-16 | Late | 0% | 2026-12-31 | On Schedule | 0% | Works in ORL East Station/IVS/ VS/Mainline | Maintenance | สหชาติ | CV/AR | ปรับเปลี่ยนประตูทางเข้าพื้นที่ปิด (ห้องใต้บันได) ด้วยตู้ Sump Pump หรือ ESPS โดยขยายไปจนถึงประตูเต็ม เพิ่มแสงสว่างให้กับห้องใต้บันได
72 | MO-CK32 |  |  | Lot02 | Lighting to the sealed space (under-stairs room) with a Sump Pump or ESPS cabinet | 2027-01-31 | 0% | 2026-11-03 | On Schedule | 0% | 2026-12-04 | On Schedule | 0% | 2026-12-31 | On Schedule | 0% | Works in ORL East Station/IVS/ VS/Mainline | Maintenance | ประธาน | EE/ME | ซื้อสปอร์ตไลท์+แบต จำนวน 4 ชุด แทนการลากสายไฟ
73 | MO-BEM43 | MDW1-40 | MDW-39537 | Lot02 | Handrails for ladder at IVS and Vent buildings | 2026-09-30 | 0% | 2026-03-31 | Late | 0% | 2026-05-01 | Late | 0% | 2026-08-31 | Late | 0% | Works in ORL East Station/IVS/ VS/Mainline | Maintenance | สหชาติ | CV/AR | ราวบันไดอาคาร IVS และ Vent
74 | MO-BEM44 | MDW1-41 | MDW-39538 | Lot02 | Escalator Anti-Slide device for all station. | 2026-09-30 | 100% | 2026-05-30 | Completed | 100% | 2026-06-30 | Completed | 40% | 2026-08-31 | Late | 58% | Works in ORL East Station/IVS/ VS/Mainline | Operattion | สหชาติ | CV/AR | อุปกรณ์ป้องกันการเลื่อนบันไดเลื่อนสำหรับทุกสถานี
75 | MO-BEM45 | MDW2-42 | MDW-39543 | Lot02 | Roof for control panel on vent building | 2027-01-31 | 0% | 2026-09-14 | On Schedule | 0% | 2026-10-30 | On Schedule | 0% | 2026-12-31 | On Schedule | 0% | Works in ORL East Station/IVS/ VS/Mainline | Maintenance | สหชาติ | CV/AR
76 | MO-BEM46 | MDW1/2-43 | MDW-39553 | Lot02 | Provide Standing plate or ladder to access the Fire Valve in at Omega points for all underground stations. | 2027-01-31 | 0% | 2026-09-14 | On Schedule | 0% | 2026-10-30 | On Schedule | 0% | 2026-12-31 | On Schedule | 0% | Works in ORL East Station/IVS/ VS/Mainline | Maintenance | สหชาติ | CV/AR | จัดหาบันไดสแตนเลสชั่วคราว 1ชุด/1สถานี
77 | MO-BEM47 | MDW1/2-44 | MDW-39540 | Lot02 | Water drop protection above UPS cabinet at station and Depot | 2027-01-31 | 0% | 2026-09-14 | On Schedule | 0% | 2026-10-30 | On Schedule | 0% | 2026-12-31 | On Schedule | 0% | Works in ORL East Station/IVS/ VS/Mainline | Maintenance | สหชาติ | CV/AR | ระบบป้องกันน้ำหยดเหนือตู้ UPS ที่สถานี และ Depot
78 | MO-BEM48 | MDW2-45 | MDW-39541 | Lot02 | Fire alarm manual call point coverin public area at all station | 2027-01-31 | 0% | 2026-09-14 | On Schedule | 0% | 2026-10-30 | On Schedule | 0% | 2026-12-31 | On Schedule | 0% | Works in ORL East Station/IVS/ VS/Mainline | Operattion | ประธาน | EE/ME | ฝาครอบ Manual call point ทุกสถานี
79 | MO-BEM49 | ADW-16 | MDW-39542 | Lot02 | Emergency stop button cover for escalator at all station. | 2027-01-31 | 0% | 2026-09-14 | On Schedule | 0% | 2026-10-30 | On Schedule | 0% | 2026-12-31 | On Schedule | 0% | Works in ORL East Station/IVS/ VS/Mainline | Operattion | สหชาติ | CV/AR | ฝาครอบปุ่มหยุดฉุกเฉินสำหรับบันไดเลื่อนทุกสถานี
80 | MO-BEM50 | MDW2-47 | MDW-39539 | Lot02 | Modify maintenance service door to the roof of OR13 vent building to easier access while maintaining safe operational standards | 2027-01-31 | 0% | 2026-10-29 | On Schedule | 0% | 2026-10-30 | On Schedule | 0% | 2026-12-31 | On Schedule | 0% | Works in ORL East Station/IVS/ VS/Mainline | Maintenance | สู่โชค | CV/AR | - บริเวณ IVS OR13 ทางเข้าห้อง sump pump ปัจจุบันเปิดได้โดยการยก โมดิฟายเพิ่ม hinge หรือ รอกยก - ที่ ivs มีห้องบางห้อง มีช่องเปิดที่พื้นบริเวณหน้าประตู, ให้ทำราวกันตก หรือโซ่กั้นหน้าประตู
81 | MO-BEM54 |  |  | Lot02 | Strengthen the Maintenance Walkway of the TEF fan | 2027-01-31 | 0% | 2026-07-16 | Late | 0% | 2026-08-16 | Late | 0% | 2026-12-31 | On Schedule | 0% | Works in ORL East Station/IVS/ VS/Mainline | Maintenance | สหชาติ | CV/AR | เสริมความแข็งแรงทางเดินซ่อมบำรุงพัดลม TEF
82 | MO-CK17 | ADW-4 |  | Lot02 | Safety Sign all Depot Area building | 2026-05-31 | 70% | 2025-11-28 | Late | 100% | 2026-06-15 | Completed | 0% | 2026-07-31 | Late | 27% | Graphic Signage | Graphic Signage | สหชาติ | GRS | ติดตั้งป้าย Safety Sign ภายใน ภายนอกทุกอาคาร (2500 ป้าย)
83 | MO-CK18 | ADW-5 |  | Lot02 | Emergency escape route map | 2027-01-31 | 0% | 2026-09-29 | On Schedule | 0% | 2026-10-30 | On Schedule | 0% | 2026-12-31 | On Schedule | 0% | Graphic Signage | Graphic Signage | สหชาติ | GRS | แผนที่เส้นทางหนีไฟฉุกเฉิน
84 | MO-CK19 | ADW-6 |  | Lot02 | Traffice Line Marking (Thermoplastic Paint) | 2026-05-31 | 70% | 2026-04-30 | Late | 100% | 2026-06-15 | Completed | 0% | 2026-07-15 | Late | 27% | Graphic Signage | Graphic Signage | สหชาติ | GRS | ตีเส้นจราจรบนพื้นที่ slab ไปตามอาคารต่างๆ - ถนน 1 เลน 4,202 ม. - ถนน 2 เลน 1,115 ม.
85 | MO-CK20 | ADW-7 |  | Lot02 | Emergency Car Parking location Painting in front of MWS | 2026-05-31 | 70% | 2026-04-30 | Late | 100% | 2026-06-15 | Completed | 0% | 2026-07-15 | Late | 27% | Graphic Signage | Graphic Signage | สหชาติ | GRS | ตีเส้นจุดจอดรถชั่วคราว รถฉุกเฉิน หน้าอาคาร MWS จุดจอดรถฉุกเฉิน ขนาด 2.5 x 7 ม. (จำนวน 5 ช่อง) จุดจอดรถชั่วคราว ขนาด 2.5 x 5 ม. (จำนวน 4 ช่อง)
86 | MO-CK21 | ADW-8 |  | Lot02 | Safety Line painting in MWS, Stabling Area, P-way, Track | 2027-01-31 | 100% | 2026-06-01 | On Schedule | 100% | 2026-08-01 | Completed | 10% | 2026-12-31 | On Schedule | 37% | Graphic Signage | Graphic Signage | สหชาติ | GRS | Safety Line ใน MWS, Stabling Area, P-way และจุดที่มีความเสี่ยงอื่นๆ - safety line ใน MWS (6,658 m.) - Safety line ใน P-way (548 m.) - เส้นแดงข้าง Track (4,817 m.) - เส้นเหลืองดำ Walk way Stabling Yard (4,824 m.)
87 | MO-CK22 | ADW-9 |  | Lot02 | Fire escape stairs level signs in the Depot, VS and IVS areas | 2027-01-31 | 0% | 2026-09-04 | On Schedule | 0% | 2026-10-05 | On Schedule | 0% | 2026-12-31 | On Schedule | 0% | Graphic Signage | Graphic Signage | สหชาติ | GRS | ป้ายบันไดหนีไฟที่ Depot, VS และ IVS
88 | MO-CK24 | ADW-11 |  | Lot02 | Modify Traffic paint and traffic sign | 2026-05-31 | 70% | 2026-04-30 | Late | 100% | 2026-06-15 | Completed | 0% | 2026-07-15 | Late | 27% | Graphic Signage | Graphic Signage | สหชาติ | GRS | แก้ไขสัญลักษณ์ทิศทางจราจรบนถนน และป้ายจราจร
89 | MO-CK25 | ADW-15 |  | Lot02 | Station Area sign 28 stations | 2026-05-31 | 100% | 2026-06-15 | Completed | 50% | 2026-06-30 | Late | 0% | 2026-08-15 | Late | 20% | Graphic Signage | Graphic Signage | สหชาติ | GRS | ติดตั้งป้าย Station Area 28 สถานี (112 ป้าย)
90 | MO-CK26 | ADW-17 |  | Lot02 | Safety and warning signage for lift and escalator at all station | 2027-01-31 | 100% | 2026-06-16 | Completed | 100% | 2026-07-17 | Completed | 0% | 2026-12-31 | On Schedule | 30% | Graphic Signage | Graphic Signage | สหชาติ | GRS | ป้ายเตือนความปลอดภัยสำหรับลิฟต์และบันไดเลื่อนทุกสถานี
91 | MO-CK34 | ADW-14 |  | Lot02 | Provide and install comfined space signage for Station and Depot | 2027-01-31 | 100% | 2026-08-15 | Completed | 100% | 2026-09-15 | Completed | 0% | 2026-12-31 | On Schedule | 30% | Graphic Signage | Graphic Signage | สหชาติ | GRS

## Test Procedure&Report (hidden)
Stage 6 Submittal ADW
[11 empty] | Submit Plan |  |  |  | Punch List |  |  | Remark
| 9=Requirement Traceability Report 2=Additional Works-internal document | No. | Detailed Design | Submission No. | Work Code | Type of Work | System | Title | Originator | Submission PCOR | Submit Plan Rev.01 | Submit Plan Rev.02 | %Prog | Status | Forecast | %Prog | Status
1 | 6 | 17 | DWE-39023 | DWE-69023 | DN01B1800015 | DWE15 | DWE | Test Procedure - Provision of Civil Works and Building Services to support Train Washing Equipment | Sahachart S. |  | 2026-08-31 | 2026-08-31 | 100% | Completed | 2026-09-15 |  |  |  | CIV/AR | East
2 | 6 | 18 | DWE-39023 | DWE-69123 | DN01B1800015 | DWE15 | DWE | Test Report - Provision of Civil Works and Building Services to support Train Washing Equipment | Korkiat W. |  | 2026-10-15 | 2026-10-15 | 0% | On Schedule |  |  |  | รอส่งมอบงาน | CIV/AR | East | Atit S. | 1 | Bournbhrom CH. | 5 | Jaturong W. | 2 | Kamphol H. | 14
3 | 6 | 19 | DWE-39024 | DWE-69024 | DN01B1700007 | GEN7.1 | DWE | Test Procedure - Dangerous Waste Storage Building in Depot - Civil & AR | Sahachart S. |  | 2026-06-30 | 2026-06-30 | 100% | Completed | 2026-06-22 |  |  |  | CIV/AR | East
4 | 6 | 20 | DWE-39024 | DWE-69124 | DN01B1700007 | GEN7.1 | DWE | Test Report - Dangerous Waste Storage Building in Depot - Civil & AR | Korkiat W. |  | 2026-06-07 | 2026-09-30 | 90% | On Schedule |  |  |  | วนเซ็น/รอส่งมอบงาน | CIV/AR | East | Kiatiphon L. | 13 | Korkiat W. | 17 | Nopsiri S. | 1 | Pitoon P. | 4
5 | 6 | 23 | DWE-39026 | DWE-69026 | DN01B1700008 | GEN8.1 | DWE | Test Procedure - General Waste Storage Building in Depot - Civil & AR | Sahachart S. |  | 2026-06-30 | 2026-03-31 | 100% | Completed | 2026-06-22 |  |  |  | CIV/AR | East
6 | 6 | 24 | DWE-39026 | DWE-69126 | DN01B1700008 | GEN8.1 | DWE | Test Report - General Waste Storage Building in Depot - Civil & AR | Korkiat W. |  | 2026-06-07 | 2026-09-30 | 90% | On Schedule |  |  |  | วนเซ็น/รอส่งมอบงาน | CIV/AR | East | Sahachart S. | 123 | Sukree T. | 2 | Thinnaphat S. | 3
7 | 6 | 3 | MDW-39002 | MDW-69003 | DN01B1700051 | SIG1 | MDW | Test Procedure - Modification Motorized Gate and Shelters at Test Track Depot - Civil & AR | Sahachart S. | PCOR | 2026-04-25 | 2026-04-25 | 100% | Completed | 2026-06-22 |  |  |  | CIV/AR | East
8 | 6 | 4 | MDW-39002 | MDW-69004 | DN01B1700051 | SIG1 | MDW | Test Report - Modification Motorized Gate and Shelters at Test Track Depot - Civil & AR | Korkiat W. | PCOR | 2026-06-07 | 2026-09-30 | 90% | On Schedule |  |  |  | วนเซ็น/รอส่งมอบงาน | CIV/AR | East
9 | 6 | 43 | MDW-39233 | MDW-69234 | DN01B1700012 | GEN12 | MDW | Test Procedure - Main Line Cable Trough Modification on East Section for PSY and SIG/COM | Sahachart S. |  | 2026-05-31 | 2026-09-30 | 80% | On Schedule | 2026-07-30 |  |  |  | CIV/AR | East
10 | 6 | 44 | MDW-39233 | MDW-69235 | DN01B1700012 | GEN12 | MDW | Test Report - Main Line Cable Trough Modification on East Section (PSY) | Pitoon P. |  | 2026-07-15 | 2026-10-30 | 0% | On Schedule |  |  |  |  | CIV/AR | East
11 | 6 | 45 | MDW-39234 | MDW-69236 | DN01B1700012 | GEN12 | MDW | Test Report - Main Line Cable Trough Modification on East Section (SIG/COM) | Pitoon P. |  | 2026-07-15 | 2026-10-30 | 0% | On Schedule |  |  |  |  | CIV/AR | East
12 | 6 | 46 | MDW-39235 | MDW-69237 | DN01B1700005 | GEN5 | MDW | Test Procedure - Raised Floor Installation on East Section | Sahachart S. |  | 2026-05-31 | 2025-11-28 | 100% | Completed | 2026-07-30 |  |  |  | CIV/AR | East
13 | 6 | 47 | MDW-39235 | MDW-69238 | DN01B1700005 | GEN5 | MDW | Test Report - Raised Floor Installation on East Section | Sahachart S. |  | 2026-07-15 | 2026-10-21 | 0% | On Schedule |  |  |  | รอส่งมอบงาน | CIV/AR | East
14 | 6 | 48 | MDW-39236 | MDW-69239 | DN01B1700013 | GEN13 | MDW | Test Procedure - Bird Protection System at Depot Buildings | Sahachart S. |  | 2026-10-31 | 2025-12-27 | 100% | Completed | 2026-12-30 |  |  |  | CIV/AR | East
15 | 6 | 49 | MDW-39236 | MDW-69240 | DN01B1700013 | GEN13 | MDW | Test Report - Bird Protection System at Depot Buildings | Korkiat W. |  | 2026-12-15 | 2026-10-21 | 90% | On Schedule |  |  |  | วนเซ็น/รอส่งมอบงาน | CIV/AR | East
16 | 6 | 54 | MDW-39239 | MDW-69245 | DN01B1700015 | GEN15 | MDW | Test Procedure - Access Panel Closeout for Traction Substation Room in Main Workshop | Sahachart S. |  | 2026-03-01 | 2026-03-01 | 100% | Completed | 2026-06-22 |  |  |  | CIV/AR | East
17 | 6 | 55 | MDW-39239 | MDW-69246 | DN01B1700015 | GEN15 | MDW | Test Report - Access Panel Closeout for Traction Substation Room in Main Workshop | Korkiat W. |  | 2026-06-07 | 2026-10-21 | 90% | On Schedule |  |  |  | วนเซ็น/รอส่งมอบงาน | CIV/AR | East
18 | 6 | 56 | MDW-39240 | MDW-69247 | DN02B1710014 | GEN14.1 | MDW | Test Procedure - Driver Train Simulation Room and Train Crew Office at OR18 - Civil & AR | Sahachart S. |  | 2026-07-15 | 2026-07-15 | 100% | Completed | 2026-06-22 |  |  |  | CIV/AR | East
19 | 6 | 57 | MDW-39240 | MDW-69248 | DN02B1710014 | GEN14.1 | MDW | Test Report - Driver Train Simulation Room and Train Crew Office at OR18 - Civil & AR | Thinnaphat S. |  | 2026-06-07 | 2026-09-30 | 90% | On Schedule |  |  |  | วนเซ็น/รอส่งมอบงาน | CIV/AR | East
20 | 6 | 64 | MDW-39244 | MDW-69255 | DN01B1700019 | GEN4.1 | MDW | Test Procedure - AFC Training Room Modification - Civil & AR | Sahachart S. |  | 2026-08-01 | 2026-10-31 | 25% | On Schedule | 2026-09-30 |  |  | รอDetailed Design | CIV/AR | East
21 | 6 | 65 | MDW-39244 | MDW-69256 | DN01B1700019 | GEN4.1 | MDW | Test Report - AFC Training Room Modification - Civil & AR | Sahachart S. |  | 2026-09-15 | 2026-12-15 | 0% | On Schedule |  |  |  | รอDetailed Design | CIV/AR | East
22 | 6 | 72 | หน้างานปรับ Checklist | MDW-69263 | DN01B1700001 | GEN1 | MDW | Test Procedure - SOR Counter and Work station Hanging Support Installation on East Section | Sahachart S. |  | 2026-07-15 | 2026-07-15 | 100% | Completed | 2026-06-22 |  |  |  | CIV/AR | East
23 | 6 | 73 | หน้างานปรับ Checklist | MDW-69264 | DN01B1700001 | GEN1 | MDW | Test Report - SOR Counter and Work station Hanging Support Installation on East Section | Sahachart S. |  | 2026-06-07 | 2026-09-30 | 90% | On Schedule |  |  |  | วนเซ็น/รอส่งมอบงาน | CIV/AR | East
24 | 6 | 74 | MDW-39250 | MDW-69265 | DN01B1700001 | GEN1 | MDW | Test Procedure - Ticket Office Modification on East Section | Sahachart S. |  | 2026-07-15 | 2026-07-15 | 100% | Completed | 2026-08-15 |  |  |  | CIV/AR | East
25 | 6 | 75 | MDW-39250 | MDW-69266 | DN01B1700001 | GEN1 | MDW | Test Report - Ticket Office Modification on East Section | Sahachart S. |  | 2026-07-31 | 2026-10-15 | 0% | On Schedule |  |  |  | รอส่งมอบงาน | CIV/AR | East
26 | 6 | 78 | MDW-39253 | MDW-69271 | DN01B1700001 | GEN1 | MDW | Test Procedure - Modification of Civil Work in Telecommunication Room at OR14 | Sahachart S. |  | 2025-12-01 | 2026-03-24 | 100% | Completed | 2026-01-30 |  |  |  | CIV/AR | East
27 | 6 | 79 | MDW-39253 | MDW-69272 | DN01B1700001 | GEN1 | MDW | Test Report - Modification of Civil Work in Telecommunication Room at OR14 | Pitoon P. |  | 2026-01-15 | 2026-10-15 | 0% | On Schedule |  |  |  | รอส่งมอบงาน | CIV/AR | East
28 | 6 | 96 | - | MDW-69289 | DN01B1700002 | GEN2 | MDW | Test Procedure - Block-out and Holes Modification at Depot Platform | Sahachart S. |  |  | ยกเลิก |  |  | 1900-01-14
29 | 6 | 97 | - | MDW-69290 | DN01B1700002 | GEN2 | MDW | Test Report - Block-out and Holes Modification at Depot Platform | Pitoon P. |  |  | ยกเลิก
30 | 6 | 104 | MDW-39271 | MDW-69297 | DN01B1700006 | GEN6 | MDW | Test Procedure - Wayside Cable Trough in Depot | Sahachart S. |  | 2026-01-29 | 2026-08-26 | 100% | Completed | 2026-03-30 |  |  |  | CIV/AR | East
31 | 6 | 105 | MDW-39271 | MDW-69298 | DN01B1700006 | GEN6 | MDW | Test Report - Wayside Cable Trough in Depot | Korkiat W. |  | 2026-03-15 | 2026-10-21 | 0% | On Schedule |  |  |  | รอส่งมอบงาน | CIV/AR | East
32 | 6 | 106 | MDW-39272 | MDW-69299 | DN01B1700001 | GEN1 | MDW | Test Procedure - Modification of New M&E Room at IVS15 - Civil & AR | Sahachart S. |  | 2026-06-30 | 2026-03-24 | 100% | Completed | 2026-06-22 |  |  |  | CIV/AR | East
33 | 6 | 107 | MDW-39272 | MDW-69300 | DN01B1700001 | GEN1 | MDW | Test Report - Modification of New M&E Room at IVS15 - Civil & AR | Thinnaphat S. |  | 2026-06-07 | 2026-09-30 | 90% | On Schedule |  |  |  | วนเซ็น/รอส่งมอบงาน | CIV/AR | East
34 | 6 | 110 | MDW-39276 | MDW-69303 | DN01B1700042 | AFC2 | AFC | Test Procedure - Ticket Issuing Machine (TIM) Wall Opening and Closing East Section | Sahachart S. |  | 2026-08-31 | 2026-09-30 | 90% | On Schedule | 2026-10-30 |  |  | วนเซ็นเอกสาร | CIV/AR | East
35 | 6 | 111 | MDW-39276 | MDW-69304 | DN01B1700042 | AFC2 | AFC | Test Report - Ticket Issuing Machine (TIM) Wall Opening and Closing East Section | Sukree T. |  | 2026-10-15 | 2026-10-30 | 0% | On Schedule |  |  |  | รอส่งมอบงาน | CIV/AR | East
36 | 6 | 112 | MDW-39277 | MDW-69305 | DN01B1700043 | AFC3 | AFC | Test Procedure - Modification Works for AFC - Balustrade Modification Along AFC Gate Line East Section | Sahachart S. |  | 2026-08-31 | 2026-10-07 | 25% | On Schedule | 2026-10-30 |  |  | รอDetailed Design | CIV/AR | East
37 | 6 | 113 | MDW-39277 | MDW-69306 | DN01B1700043 | AFC3 | AFC | Test Report - Modification Works for AFC - Balustrade Modification Along AFC Gate Line East Section | Sahachart S. |  | 2026-10-15 | 2026-11-30 | 0% | On Schedule |  |  |  | รอDetailed Design | CIV/AR | East
38 | 6 | 114 | MDW-39278 | MDW-69307 | DN01B1700044 | AFC4 | AFC | Test Procedure - Underfloor Embedded Duct Modification for AFC Gates Line East Section | Sahachart S. |  | 2026-08-31 | 2026-09-30 | 25% | On Schedule | 2026-10-30 |  |  | รอDetailed Design | CIV/AR | East
39 | 6 | 115 | MDW-39278 | MDW-69308 | DN01B1700044 | AFC4 | AFC | Test Report - Underfloor Embedded Duct Modification for AFC Gates Line East Section | Sahachart S. |  | 2026-10-15 | 2026-10-24 | 0% | On Schedule |  |  |  | รอDetailed Design | CIV/AR | East
40 | 6 | 116 | MDW-39279 | MDW-69309 | DN01B1700043 | AFC3 | AFC | Test Procedure - Balustrade Modification Along AFC Gate Line East Section | Sahachart S. |  | 2026-08-31 | 2026-10-07 | 50% | On Schedule | 2026-10-30 |  |  | จัดทำ | CIV/AR | East
41 | 6 | 117 | MDW-39279 | MDW-69310 | DN01B1700043 | AFC3 | AFC | Test Report - Balustrade Modification Along AFC Gate Line East Section | Sahachart S. |  | 2026-10-15 | 2026-11-21 | 0% | On Schedule |  |  |  | รอDetailed Design | CIV/AR | East
42 | 6 | 146 | MDW-39294 | MDW-69339 | DN01B1700001 | GEN1 | MDW | Test Procedure - Provision of Architectural Work in new M&E UPS room at OR23 | Sahachart S. |  | 2026-06-30 | 2026-06-30 | 100% | Completed | 2026-06-22 |  |  |  | CIV/AR | East
43 | 6 | 147 |  | MDW-69340 | DN01B1700001 | GEN1 | MDW | Test Report - Provision of Architectural Work in new M&E UPS room at OR23 | Thinnaphat S. |  | 2026-06-07 | 2026-09-30 | 90% | On Schedule |  |  |  | วนเซ็น/รอส่งมอบงาน | CIV/AR | East
44 | 6 | 148 | MDW-39295 | MDW-69341 | DN01B1800005 | MO-CK15.1 | MDW | Test Procedure - Dangerous Goods Building in Depot - Civil & AR | Sahachart S. |  | 2026-03-31 | 2026-09-30 | 90% | On Schedule | 2026-05-30 |  |  | วนเซ็นเอกสาร | CIV/AR | East
45 | 6 | 149 |  | MDW-69342 | DN01B1800005 | MO-CK15.1 | MDW | Test Report - Dangerous Goods Building in Depot - Civil & AR | Korkiat W. |  | 2026-05-15 | 2026-10-30 | 0% | On Schedule |  |  |  | รอส่งมอบงาน | CIV/AR | East
46 | 6 | 152 | MDW-39297 | MDW-69345 | DN01B1700004 | GEN4 | MDW | Test Procedure - Training Room at Ratchada Station (Part 2) | Sahachart S. |  | 2026-03-31 | 2026-09-30 | 90% | On Schedule | 2026-05-30 |  |  | วนเซ็นเอกสาร | CIV/AR | East
47 | 6 | 153 |  | MDW-69346 | DN01B1700004 | GEN4 | MDW | Test Report - Training Room at Ratchada Station (Part 2) | Sahachart S. |  | 2026-05-15 | 2026-10-30 | 25% | On Schedule |  |  |  | รอDetailed Design | CIV/AR | East
48 | 6 | 168 | MDW-39305 | MDW-69361 | DN01B1800013 | DWE13 | MDW | Test Procedure - Safety Provision for Maintenance Pits | Sahachart S. |  | 2026-08-31 | 2026-09-30 | 90% | On Schedule | 2026-10-30 |  |  | วนเซ็นเอกสาร | CIV/AR | East
49 | 6 | 169 |  | MDW-69362 | DN01B1800013 | DWE13 | MDW | Test Report - Safety Provision for Maintenance Pits | Korkiat W. |  | 2026-10-15 | 2026-10-30 | 0% | On Schedule |  |  |  | รอส่งมอบงาน | CIV/AR | East
50 | 6 | 172 | MDW-39307 | MDW-69365 |  | ยังไม่มี Type of work | MDW | Test Procedure - Additional Fence at Back of House OR13 - OR22 and IVS East Section | Sahachart S. |  | 2026-08-01 | 2026-10-16 | 90% | On Schedule | 2026-09-30 |  |  | วนเซ็นเอกสาร | CIV/AR | East
51 | 6 | 173 |  | MDW-69366 |  | ยังไม่มี Type of work | MDW | Test Report - Additional Fence at Back of House OR13 - OR22 and IVS East Section | Sahachart S. |  | 2026-09-15 | 2026-11-30 | 0% | On Schedule |  |  |  | รอส่งมอบงาน | CIV/AR | East
52 | 6 | [5 empty] | AFC | Test Procedure - Ticket Issuing Machine (TIM) Wall Opening and Closing West Section |  |  |  | ยกเลิก
53 | 6 | [5 empty] | AFC | Test Report - Ticket Issuing Machine (TIM) Wall Opening and Closing West Section |  |  |  | ยกเลิก
54 | 6 | 1 | MDW-39500 | MDW-69500 | DN02B1710001 | MO-CK1.1 | MDW | Test Procedure - Modification Works : Storage Office in Main Workshop - Civil & AR | Sahachart S. |  | 2026-08-31 | 2026-09-30 | 90% | On Schedule | 2026-10-30 |  |  | วนเซ็นเอกสาร | CIV/AR | East
55 | 6 | 2 |  | MDW-69501 | DN02B1710001 | MO-CK1.1 | MDW | Test Report - Modification Works : Storage Office in Main Workshop - Civil & AR | Korkiat W. |  | 2026-10-15 | 2026-10-30 | 0% | On Schedule |  |  |  | รอส่งมอบงาน | CIV/AR | East
56 | 6 | 7 | MDW-39503 | MDW-69506 | DN02B1710002 | MO-CK2.1 | MDW | Test Procedure - Modification Works : New MMC at Admin Building - Civil & AR | Sahachart S. |  | 2026-06-30 | 2026-09-30 | 90% | On Schedule | 2026-08-29 |  |  | วนเซ็นเอกสาร | CIV/AR | East
57 | 6 | 8 |  | MDW-69507 | DN02B1710002 | MO-CK2.1 | MDW | Test Report - Modification Works : New MMC at Admin Building - Civil & AR | Kiatiphon L. |  | 2026-08-14 | 2026-10-30 | 0% | On Schedule |  |  |  | รอส่งมอบงาน | CIV/AR | East
58 | 6 | 11 | MDW-39505 | MDW-69510 | DN02B1720001 | MO-BEM1.1 | MDW | Test Procedure - Modification Works : Walkway with Roof from Main Workshop to Stabling Yard - Civil & AR | Sahachart S. |  | 2026-06-30 | 2026-08-31 | 100% | Completed | 2026-08-29 |  |  |  | CIV/AR | East
59 | 6 | 12 |  | MDW-69511 | DN02B1720001 | MO-BEM1.1 | MDW | Test Report - Modification Works : Walkway with Roof from Main Workshop to Stabling Yard - Civil & AR | Bournbhrom CH. |  | 2026-08-14 | 2026-10-15 | 0% | On Schedule |  |  |  | รอส่งมอบงาน | CIV/AR | East
60 | 6 | 15 | MDW-39507 | MDW-69514 | DN02B1720002 | MO-BEM2 | MDW | Test Procedure - Modification Works : High Roof in front of MWS Entrance and Store Entrance - Civil & AR | Sahachart S. |  | 2026-07-01 | 2026-07-01 | 100% | Completed | 2026-08-30 |  |  |  | CIV/AR | East
61 | 6 | 16 |  | MDW-69515 | DN02B1720002 | MO-BEM2 | MDW | Test Report - Modification Works : High Roof in front of MWS Entrance and Store Entrance - Civil & AR | Kiatiphon L. |  | 2026-08-15 | 2026-10-21 | 0% | On Schedule |  |  |  | รอส่งมอบงาน | CIV/AR | East
62 | 6 | 19 | MDW-39509 | MDW-69518 | DN02B1720003 | MO-BEM3 | MDW | Test Procedure - Modification Works : High Roof at Under Floor Wheel Lathe - Civil & AR | Sahachart S. |  | 2026-07-01 | 2026-07-01 | 100% | Completed | 2026-08-30 |  |  |  | CIV/AR | East
63 | 6 | 20 |  | MDW-69519 | DN02B1720003 | MO-BEM3 | MDW | Test Report - Modification Works : High Roof at Under Floor Wheel Lathe - Civil & AR | Kiatiphon L. |  | 2026-08-15 | 2026-10-21 | 0% | On Schedule |  |  |  | รอส่งมอบงาน | CIV/AR | East
64 | 6 | 23 | MDW-39511 | MDW-69522 | DN02B1720004 | MO-BEM4.1 | MDW | Test Procedure - Modification Works : Maintenance Office Rooms at Main Workshop - Civil & AR | Sahachart S. |  | 2026-05-31 | 2026-05-31 | 100% | Completed | 2026-07-30 |  |  |  | CIV/AR | East
65 | 6 | 24 |  | MDW-69523 | DN02B1720004 | MO-BEM4.1 | MDW | Test Report - Modification Works : Maintenance Office Rooms at Main Workshop - Civil & AR | Korkiat W. |  | 2026-07-15 | 2026-10-21 | 0% | On Schedule |  |  |  | รอส่งมอบงาน | CIV/AR | East
66 | 6 | 27 | MDW-39513 | MDW-69526 | DN02B1720005 | MO-BEM5 | MDW | Test Procedure - Modification Works : Concrete Car Barrier in front of Main Workshop | Sahachart S. |  | 2026-12-01 | 2026-12-01 | 90% | On Schedule | 2027-01-30 |  |  | วนเซ็นเอกสาร | CIV/AR | East
67 | 6 | 28 |  | MDW-69527 | DN02B1720005 | MO-BEM5 | MDW | Test Report - Modification Works : Concrete Car Barrier in front of Main Workshop | Korkiat W. |  | 2027-01-15 | 2027-01-28 | 0% | On Schedule |  |  |  | รอส่งมอบงาน | CIV/AR | East
68 | 6 | 29 | MDW-39514 | MDW-69528 | DN02B1720051 | MO-BEM51 | MDW | Test Procedure - Modification Works : Car Park Roof and Motorcycle in Depot - Civil & AR | Sahachart S. |  | 2026-07-01 | 2026-07-01 | 100% | Completed | 2026-08-30 |  |  |  | CIV/AR | East
69 | 6 | 30 |  | MDW-69529 | DN02B1720051 | MO-BEM51 | MDW | Test Report - Modification Works : Car Park Roof and Motorcycle in Depot - Civil & AR | Kiatiphon L. |  | 2026-08-15 | 2026-10-21 | 0% | On Schedule |  |  |  | รอส่งมอบงาน | CIV/AR | East
70 | 6 | 33 | MDW-39516 | MDW-69532 | DN02B1720014 | MO-BEM14.1 | MDW | Test Procedure - Modification Works : Walkway Bridge between BL Depot and ORL Depot - Civil & AR | Sahachart S. |  | 2026-07-01 | 2026-08-31 | 100% | Completed | 2026-08-30 |  |  |  | CIV/AR | East
71 | 6 | 34 |  | MDW-69533 | DN02B1720014 | MO-BEM14.1 | MDW | Test Report - Modification Works : Walkway Bridge between BL Depot and ORL Depot - Civil & AR | Kiatiphon L. |  | 2026-08-15 | 2026-10-21 | 0% | On Schedule |  |  |  | รอส่งมอบงาน | CIV/AR | East
72 | 6 | 39 | MDW-39519 | MDW-69538 | DN02B1720016-19 | MO-BEM16-18 | MDW | Test Procedure - Modification Works : Walkway with Roof in Depot Area - Civil & AR | Sahachart S. |  | 2026-07-01 | 2026-08-31 | 100% | Completed | 2026-08-30 |  |  |  | CIV/AR | East
73 | 6 | 40 |  | MDW-69539 | DN02B1720016-19 | MO-BEM16-18 | MDW | Test Report - Modification Works : Walkway with Roof in Depot Area - Civil & AR | Kiatiphon L. |  | 2026-08-15 | 2026-11-28 | 0% | On Schedule |  |  |  | รอส่งมอบงาน | CIV/AR | East
74 | 6 | 43 | MDW-39521 | MDW-69542 | DN02B1720029 | MO-BEM29 | MDW | Test Procedure - Modification Works : Walkway Bridge and Walkway over Canal in Depot | Sahachart S. |  | 2026-07-01 | 2026-12-01 | 100% | Completed | 2026-08-30 |  |  |  | CIV/AR | East
75 | 6 | 44 |  | MDW-69543 | DN02B1720029 | MO-BEM29 | MDW | Test Report - Modification Works : Walkway Bridge and Walkway over Canal in Depot | Kiatiphon L. |  | 2026-08-15 | 2027-01-15 | 0% | On Schedule |  |  |  | รอส่งมอบงาน | CIV/AR | East
76 | 6 | 45 | MDW-39522 | MDW-69544 | DN02B1720012 | MO-BEM12 | MDW | Test Procedure - Modification Works : Rain Protection and Zero Discharge Water treatment in Depot - Civil & AR | Sahachart S. |  | 2026-07-01 | 2026-07-01 | 100% | Completed | 2026-08-30 |  |  |  | CIV/AR | East
77 | 6 | 46 |  | MDW-69545 | DN02B1720012 | MO-BEM12 | MDW | Test Report - Modification Works : Rain Protection and Zero Discharge Water treatment in Depot - Civil & AR | Korkiat W. |  | 2026-08-15 | 2026-10-21 | 0% | On Schedule |  |  |  | รอส่งมอบงาน | CIV/AR | East
78 | 6 | 49 | MDW-39524 | MDW-69548 | DN02B1720028 | MO-BEM28.1 | MDW | Test Procedure - Modification Works : Walkway under Depot Slab for Maintenance Service - Civil & AR | Sahachart S. |  | 2026-12-01 | 2026-12-01 | 90% | On Schedule | 2027-01-30 |  |  | วนเซ็นเอกสาร | CIV/AR | East
79 | 6 | 50 |  | MDW-69549 | DN02B1720028 | MO-BEM28.1 | MDW | Test Report - Modification Works : Walkway under Depot Slab for Maintenance Service - Civil & AR | Korkiat W. |  | 2027-01-15 | 2027-01-28 | 0% | On Schedule |  |  |  | รอส่งมอบงาน | CIV/AR | East
80 | 6 | 57 | MDW-39528 | MDW-69556 | DN02B1720011 | MO-BEM11.1 | MDW | Test Procedure - Modification Works : Washing Area in Cleaning Staff Room at Stabling Yard - Civil & AR | Sahachart S. |  | 2026-07-01 | 2026-07-01 | 100% | Completed | 2026-08-30 |  |  |  | CIV/AR | East
81 | 6 | 58 |  | MDW-69557 | DN02B1720011 | MO-BEM11.2 | MDW | Test Report - Modification Works : Washing Area in Cleaning Staff Room at Stabling Yard - Civil & AR | Korkiat W. |  | 2026-08-15 | 2026-10-15 | 0% | On Schedule |  |  |  | รอส่งมอบงาน | CIV/AR | East
82 | 6 | 63 | MDW-39531 | MDW-69562 | DN02B1720024 | MO-BEM24 | MDW | Test Procedure - Modification Works : Guard rail protection for FHC in Depot Area | Sahachart S. |  | 2026-05-01 | 2026-07-16 | 100% | Completed | 2026-06-30 |  |  |  | CIV/AR | East
83 | 6 | 64 |  | MDW-69563 | DN02B1720024 | MO-BEM24 | MDW | Test Report - Modification Works : Guard rail protection for FHC in Depot Area | Korkiat W. |  | 2026-06-15 | 2026-10-21 | 0% | On Schedule |  |  |  | รอส่งมอบงาน | CIV/AR | East
84 | 6 | 65 | MDW-39532 | MDW-69564 | DN02B1710010 | MO-BEM22 MO-CK27 | MDW | Test Procedure - Modification Works : Barbed Wire Fences for MRTA Chain Link at Klong Chourdyai | Sahachart S. |  | 2026-12-01 | 2026-12-01 | 25% | On Schedule | 2027-01-30 |  |  | รอDetailed Design | CIV/AR | East
85 | 6 | 66 |  | MDW-69565 | DN02B1710010 | MO-BEM22 MO-CK27 | MDW | Test Report - Modification Works : Barbed Wire Fences for MRTA Chain Link at Klong Chourdyai | Sahachart S. |  | 2027-01-15 | 2027-01-28 | 0% | On Schedule |  |  |  | รอDetailed Design | CIV/AR | East
86 | 6 | 67 | MDW-39533 | MDW-69566 | DN02B1720005 | ยังไม่มี Type of work | MDW | Test Procedure - Modification Works : Car Barrier Gate at Depot Area | Sahachart S. |  | 2026-12-01 | 2026-12-01 | 90% | On Schedule | 2027-01-30 |  |  | วนเซ็นเอกสาร | CIV/AR | East
87 | 6 | 68 |  | MDW-69567 | DN02B1720005 | ยังไม่มี Type of work | MDW | Test Report - Modification Works : Car Barrier Gate at Depot Area | Sahachart S. |  | 2027-01-15 | 2027-01-15 | 0% | On Schedule |  |  |  | รอDetailed Design | CIV/AR | East
88 | 6 | 69 | MDW-39534 | MDW-69568 | DN02B1720053 | MO-BEM21.1 | MDW | Test Procedure - Modification Works : Security Guard Box at ORL Depot Entrance - Civil & AR | Sahachart S. |  | 2026-12-01 | 2026-12-01 | 90% | On Schedule | 2027-01-30 |  |  | วนเซ็นเอกสาร | CIV/AR | East
89 | 6 | 70 |  | MDW-69569 | DN02B1720053 | MO-BEM21.1 | MDW | Test Report - Modification Works : Security Guard Box at ORL Depot Entrance - Civil & AR | Kiatiphon L. |  | 2027-01-15 | 2027-01-28 | 0% | On Schedule |  |  |  | รอส่งมอบงาน | CIV/AR | East
90 | 6 | 73 | MDW-39536 | MDW-69572 | DN02B1720009 | MO-BEM9 | MDW | Test Procedure - Modification Works : Soundproof Installation and Company Logo at CCR Room | Sahachart S. |  | 2026-03-31 | 2026-09-30 | 90% | On Schedule | 2026-05-30 |  |  | วนเซ็นเอกสาร | CIV/AR | East
91 | 6 | 74 |  | MDW-69573 | DN02B1720009 | MO-BEM9 | MDW | Test Report - Modification Works : Soundproof Installation and Company Logo at CCR Room | Sahachart S. |  | 2026-05-15 | 2026-10-30 | 0% | On Schedule |  |  |  | รอDetailed Design | CIV/AR | East
92 | 6 | 75 | MDW-39537 | MDW-69574 | DN02B1720043 | MO-BEM43 | MDW | Test Procedure - Modification Works : Fence Installation at Ladder in VS, IVS Buildings | Sahachart S. |  | 2026-08-01 | 2026-10-31 | 25% | On Schedule | 2026-09-30 |  |  | รอDetailed Design | CIV/AR | East
93 | 6 | 76 |  | MDW-69575 | DN02B1720043 | MO-BEM43 | MDW | Test Report - Modification Works : Fence Installation at Ladder in VS, IVS Buildings | Sahachart S. |  | 2026-09-15 | 2026-11-30 | 0% | On Schedule |  |  |  | รอDetailed Design | CIV/AR | East
94 | 6 | 77 | MDW-39538 | MDW-69576 | DN02B1720044 | MO-BEM44 | MDW | Test Procedure - Modification Works : Anti-Slide Signage at Escalator for all Stations | Sahachart S. |  | 2026-08-01 | 2027-01-29 | 25% | On Schedule | 2026-09-30 |  |  | รอDetailed Design | CIV/AR | East
95 | 6 | 78 |  | MDW-69577 | DN02B1720044 | MO-BEM44 | MDW | Test Report - Modification Works : Anti-Slide Signage at Escalator for all Stations | Sahachart S. |  | 2026-09-15 | 2027-03-15 | 0% | On Schedule |  |  |  | รอDetailed Design | CIV/AR | East
96 | 6 | 79 | MDW-39539 | MDW-69578 | DN02B1720045 | MO-BEM45 | MDW | Test Procedure - Modification Works : Roofing over Control Panel Installation at VS, IVS Buildings | Sahachart S. |  | 2026-12-01 | 2026-12-01 | 25% | On Schedule | 2027-01-30 |  |  | รอDetailed Design | CIV/AR | East
97 | 6 | 80 |  | MDW-69579 | DN02B1720045 | MO-BEM45 | MDW | Test Report - Modification Works : Roofing over Control Panel Installation at VS, IVS Buildings | Sahachart S. |  | 2027-01-15 | 2027-01-28 | 0% | On Schedule |  |  |  | รอDetailed Design | CIV/AR | East
98 | 6 | 81 | MDW-39540 | MDW-69580 | DN02B1720047 | MO-BEM47 | MDW | Test Procedure - Modification Works : Water Drop Protection for UPS Cabinet for all Stations and Depot | Sahachart S. |  | 2026-12-01 | 2026-12-01 | 25% | On Schedule | 2027-01-30 |  |  | รอDetailed Design | CIV/AR | East
99 | 6 | 82 |  | MDW-69581 | DN02B1720047 | MO-BEM47 | MDW | Test Report - Modification Works : Water Drop Protection for UPS Cabinet for all Stations and Depot | Sahachart S. |  | 2027-01-15 | 2027-01-28 | 0% | On Schedule |  |  |  | รอDetailed Design | CIV/AR | East
100 | 6 | 83 | MDW-39541 | MDW-69582 | DN02B1720048 | MO-BEM48 | MDW | Test Procedure - Modification Works : Manual Call Point Cover in Public Area at all Stations | Sahachart S. |  | 2026-12-01 | 2026-12-01 | 25% | On Schedule | 2027-01-30 |  |  | รอDetailed Design | CIV/AR | East
101 | 6 | 84 |  | MDW-69583 | DN02B1720048 | MO-BEM48 | MDW | Test Report - Modification Works : Manual Call Point Cover in Public Area at all Stations | Sahachart S. |  | 2027-01-15 | 2027-01-28 | 0% | On Schedule |  |  |  | รอDetailed Design | CIV/AR | East
102 | 6 | 85 | MDW-39542 | MDW-69584 | DN02B1720049 | MO-BEM49 | MDW | Test Procedure - Modification Works : Emergency Stop Button Cover for Escalator at all Stations | Sahachart S. |  | 2026-12-01 | 2026-12-01 | 25% | On Schedule | 2027-01-30 |  |  | รอDetailed Design | CIV/AR | East
103 | 6 | 86 |  | MDW-69585 | DN02B1720049 | MO-BEM49 | MDW | Test Report - Modification Works : Emergency Stop Button Cover for Escalator at all Stations | Sahachart S. |  | 2027-01-15 | 2027-01-28 | 0% | On Schedule |  |  |  | รอDetailed Design | CIV/AR | East
104 | 6 | 87 | MDW-39543 | MDW-69586 | DN02B1710004 | MO-CK4 | MDW | Test Procedure - Modification Works : Bird & Rain Protetion, Safety Hand Rail Installation at Admin Building | Sahachart S. |  | 2026-07-01 | 2026-09-30 | 90% | On Schedule | 2026-08-30 |  |  | วนเซ็นเอกสาร | CIV/AR | East
105 | 6 | 88 |  | MDW-69587 | DN02B1710004 | MO-CK4 | MDW | Test Report - Modification Works : Bird & Rain Protetion, Safety Hand Rail Installation at Admin Building | Sahachart S. |  | 2026-08-15 | 2026-10-30 | 0% | On Schedule |  |  |  | รอDetailed Design | CIV/AR | East
106 | 6 | 89 | MDW-39544 | MDW-69588 | DN02B1710010 | MO-CK10 | MDW | Test Procedure - Modification Works : Barbed Wire Fences for Depot slab | Sahachart S. |  | 2026-12-01 | 2026-12-01 | 50% | On Schedule | 2027-01-30 |  |  | รอDetailed Design | CIV/AR | East
107 | 6 | 90 |  | MDW-69589 | DN02B1710010 | MO-CK10 | MDW | Test Report - Modification Works : Barbed Wire Fences for Depot slab | Sahachart S. |  | 2027-01-15 | 2027-01-28 | 0% | On Schedule |  |  |  | รอDetailed Design | CIV/AR | East
108 | 6 | 91 | MDW-39545 | MDW-69590 | DN02B1710011 | MO-CK11 | MDW | Test Procedure - Modification Works : Chain Link Installation at Cut & Cover Depot Access | Sahachart S. |  | 2026-05-01 | 2026-08-01 | 100% | Completed | 2026-06-30 |  |  |  | CIV/AR | East
109 | 6 | 92 |  | MDW-69591 | DN02B1710011 | MO-CK11 | MDW | Test Report - Modification Works : Chain Link Installation at Cut & Cover Depot Access | Korkiat W. |  | 2026-06-15 | 2026-10-21 | 0% | On Schedule |  |  |  | รอส่งมอบงาน | CIV/AR | East
110 | 6 | 93 | MDW-39546 | MDW-69592 | DN02B1710012 | MO-CK12 | MDW | Test Procedure - Modification Works : Chain Link Installation under Depot Slab | Sahachart S. |  | 2026-12-01 | 2026-12-01 | 90% | On Schedule | 2027-01-30 |  |  | วนเซ็นเอกสาร | CIV/AR | East
111 | 6 | 94 |  | MDW-69593 | DN02B1710012 | MO-CK12 | MDW | Test Report - Modification Works : Chain Link Installation under Depot Slab | Kiatiphon L. |  | 2027-01-15 | 2027-01-28 | 0% | On Schedule |  |  |  | รอส่งมอบงาน | CIV/AR | East
112 | 6 | 95 | MDW-39547 | MDW-69594 | DN02B1710006 | MO-CK6 | MDW | Test Procedure - Modification Works : Door and Lockset Modification at OCC Building | Sahachart S. |  | 2026-07-01 | 2026-07-01 | 100% | Completed | 2026-08-30 |  |  |  | CIV/AR | East
113 | 6 | 96 |  | MDW-69595 | DN02B1710006 | MO-CK6 | MDW | Test Report - Modification Works : Door and Lockset Modification at OCC Building | Sahachart S. |  | 2026-08-15 | 2026-10-21 | 0% | On Schedule |  |  |  | รอส่งมอบงาน | CIV/AR | East
114 | 6 | 101 | MDW-39550 | MDW-69600 | DN02B1710013 | MO-CK13.1 | MDW | Test Procedure - Modification Works : Satellite Store at OR21 - Civil & AR | Sahachart S. |  | 2026-12-01 | 2026-12-01 | 100% | Completed |  |  |  |  | CIV/AR | East
115 | 6 | 102 |  | MDW-69601 | DN02B1710013 | MO-CK13.1 | MDW | Test Report - Modification Works : Satellite Store at OR21 - Civil & AR | Sahachart S. |  | 2027-01-15 | 2027-01-28 | 0% | On Schedule |  |  |  |  | CIV/AR | East
116 | 6 | 105 | MDW-39552 | MDW-69604 | DN02B1710009 | MO-CK9 | MDW | Test Procedure - Modification Works : Hand Rail Installation at Walk Way in Stabling Yard | Sahachart S. |  | 2026-08-31 | 2026-09-30 | 90% | On Schedule | 2026-10-30 |  |  | วนเซ็นเอกสาร | CIV/AR | East
117 | 6 | 106 |  | MDW-69605 | DN02B1710009 | MO-CK9 | MDW | Test Report - Modification Works : Hand Rail Installation at Walk Way in Stabling Yard | Bournbhrom CH. |  | 2026-10-15 | 2026-10-30 | 0% | On Schedule |  |  |  | รอส่งมอบงาน | CIV/AR | East
118 | 6 | 107 | MDW-39553 | MDW-69606 | DN02B1720046 | MO-BEM46 | MDW | Test Procedure - Modification Works : Ladder to Access the Fire Valve at Omega Joints for all Underground Stations | Sahachart S. |  | 2026-12-01 | 2026-12-01 | 25% | On Schedule | 2027-01-30 |  |  | รอDetailed Design | CIV/AR | East
119 | 6 | 108 |  | MDW-69607 | DN02B1720046 | MO-BEM46 | MDW | Test Report - Modification Works : Ladder to Access the Fire Valve at Omega Joints for all Underground Stations | Sahachart S. |  | 2027-01-15 | 2027-01-28 | 0% | On Schedule |  |  |  | รอDetailed Design | CIV/AR | East
120 | 6 | 109 | MDW-39554 | MDW-69608 | DN02B1720053 | MO-BEM53.1 | MDW | Test Procedure - Modification Works : Security Guard Box at OCC Parking Area - Civil & AR | Sahachart S. |  | 2026-12-01 | 2026-12-01 | 90% | On Schedule | 2027-01-30 |  |  | วนเซ็นเอกสาร | CIV/AR | East
121 | 6 | 110 |  | MDW-69609 | DN02B1720053 | MO-BEM53.1 | MDW | Test Report - Modification Works : Security Guard Box at OCC Parking Area - Civil & AR | Kiatiphon L. |  | 2027-01-15 | 2027-01-28 | 0% | On Schedule |  |  |  | รอส่งมอบงาน | CIV/AR | East
122 | 6 | 115 | MDW-39557 | MDW-69614 | DN02B1720025 | MO-BEM25.1 | MDW | Test Procedure - Modification Works : Sliding Gate and Chain Link Fence in Depot Area - Civil & AR | Sahachart S. |  | 2026-08-31 | 2026-09-30 | 90% | On Schedule | 2026-10-30 |  |  | วนเซ็นเอกสาร | CIV/AR | East
123 | 6 | 116 |  | MDW-69615 | DN02B1720025 | MO-BEM25.1 | MDW | Test Report - Modification Works : Sliding Gate and Chain Link Fence in Depot Area - Civil & AR | Kiatiphon L. |  | 2026-10-15 | 2026-10-21 | 0% | On Schedule |  |  |  | รอส่งมอบงาน | CIV/AR | East
124 | 6 | 1 | PSY-39001 | PSY-69001 | DN01B1700062 | PSY2 | PSY | Test Procedure - BSS1 : Architectural Installation Drawing | Sahachart S. | PCOR | 2025-11-04 | 2025-11-04 | 100% | Completed | 2026-06-22 |  |  |  | CIV/AR | East
125 | 6 | 2 |  | PSY-69002 | DN01B1700062 | PSY2 | PSY | Test Report - BSS1 : Architectural Installation Drawing | Kiatiphon L. | PCOR | 2026-06-07 | 30/9/263 | 90% | On Schedule |  |  |  | วนเซ็น/รอส่งมอบงาน | CIV/AR | East
126 | 6 | 3 | PSY-39002 | PSY-69003 | DN01B1700062 | PSY2 | PSY | Test Procedure - BSS1 : Structural Installation Drawing | Sahachart S. | PCOR | 2025-09-30 | 2025-09-30 | 100% | Completed |  |  |  |  | CIV/AR | East
127 | 6 | 4 |  | PSY-69004 | DN01B1700062 | PSY2 | PSY | Test Report - BSS1 : Structural Installation Drawing | Kiatiphon L. | PCOR | 2026-06-07 | 2026-09-30 | 90% | On Schedule |  |  |  | วนเซ็น/รอส่งมอบงาน | CIV/AR | East
128 | 6 | 5 |  | PSY-69005 | DN01B1700062 | PSY2 | PSY | Test Procedure - BSS1 : Building Services Installation Drawing | Jaturong W. | PCOR | 2026-04-02 | 2026-04-02 | 100% | Completed |  |  |  |  | E&M | East
129 | 6 | 6 |  | PSY-69006 | DN01B1700062 | PSY2 | PSY | Test Report - BSS1 : Building Services Installation Drawing | Atit S. | PCOR | 2025-12-19 | 2026-10-15 | 0% | On Schedule |  |  |  |  | E&M | East
130 | 6 | 7 | PSY-39004 | PSY-69007 | DN01B1700062 | PSY2 | PSY | Test Procedure - BSS2 : Architectural Installation Drawing | Sahachart S. | PCOR | 2025-08-04 | 2025-08-04 | 100% | Completed | 2026-06-22 |  |  |  | CIV/AR | East
131 | 6 | 8 |  | PSY-69008 | DN01B1700062 | PSY2 | PSY | Test Report - BSS2 : Architectural Installation Drawing | Bournbhrom CH. | PCOR | 2026-06-07 | 2026-09-30 | 90% | On Schedule |  |  |  | วนเซ็น/รอส่งมอบงาน | CIV/AR | East
132 | 6 | 9 | PSY-39005 | PSY-69009 | DN01B1700062 | PSY2 | PSY | Test Procedure - BSS2 : Structural Installation Drawing | Sahachart S. | PCOR | 2025-06-04 | 2025-06-04 | 100% | Completed |  |  |  |  | CIV/AR | East
133 | 6 | 10 |  | PSY-69010 | DN01B1700062 | PSY2 | PSY | Test Report - BSS2 : Structural Installation Drawing | Bournbhrom CH. | PCOR | 2026-06-07 | 2026-09-30 | 90% | On Schedule |  |  |  | วนเซ็น/รอส่งมอบงาน | CIV/AR | East
134 | 6 | 11 |  | PSY-69011 | DN01B1700062 | PSY2 | PSY | Test Procedure - BSS2 : Building Services Installation Drawing | Jaturong W. | PCOR | 2026-03-18 | 2026-03-18 | 100% | Completed |  |  |  |  | E&M | East
135 | 6 | 12 |  | PSY-69012 | DN01B1700062 | PSY2 | PSY | Test Report - BSS2 : Building Services Installation Drawing | Nopsiri S. | PCOR | 2025-04-11 | 2025-04-11 | 100% | Completed |  |  |  |  | E&M | East
136 | 6 | 13 | PSY-39009 | PSY-69013 | DN01B1700062 | PSY2 | PSY | Test Procedure - HV Cable Ducts from MEA Interface Point to BSS1 | Sahachart S. | PCOR | 2025-11-04 | 2025-11-04 | 100% | Completed | 2026-06-22 |  |  |  | CIV/AR | East
137 | 6 | 14 |  | PSY-69014 | DN01B1700062 | PSY2 | PSY | Test Report - HV Cable Ducts from MEA Interface Point to BSS1 | Sukree T. | PCOR | 2026-06-07 | 2026-09-30 | 90% | On Schedule |  |  |  | วนเซ็น/รอส่งมอบงาน | CIV/AR | East
138 | 6 | 15 | PSY-39011 | PSY-69015 | DN01B1700063 | PSY3 | PSY | Test Procedure - Steel Grating Raised Floor for EE Panel on East Section | Sahachart S. | PCOR | 2026-03-01 | 2026-06-14 | 100% | Completed | 2026-04-30 |  |  |  | CIV/AR | East
139 | 6 | 16 |  | PSY-69016 | DN01B1700063 | PSY3 | PSY | Test Report - Steel Grating Raised Floor for EE Panel on East Section | Sahachart S. | PCOR | 2026-04-15 | 2026-10-21 | 0% | On Schedule |  |  |  | รอส่งมอบงาน | CIV/AR | East
140 | 6 | 1 | MDW-39001 | MDW-69001 | DN01B1700054 | SIG4 | MDW | Test Procedure - Modification of Depot Track Alignment at Stabling Yard | Kamphol H. | PCOR | 2026-05-30 | 2026-09-30 | 50% | On Schedule | 2026-07-15 |  |  |  | CIV/AR | East
141 | 6 | 2 |  | MDW-69002 | DN01B1700054 | SIG4 | MDW | Test Report - Modification of Depot Track Alignment at Stabling Yard | Kamphol H. | PCOR | 2026-06-30 | 2026-10-30 | 50% | On Schedule |  |  |  |  | CIV/AR | East
142 | 6 | 7 | MDW-39004 | MDW-69007 | DN01B1700032 | PSD2 | MDW | Test Procedure - Rubber Gap Fillers on Platform Edge on East Section | Kamphol H. | PCOR | 2026-06-10 | 2026-09-30 | 25% | On Schedule | 2026-07-25 |  |  |  | CIV/AR | East
143 | 6 | 8 |  | MDW-69008 | DN01B1700032 | PSD2 | MDW | Test Report - Rubber Gap Fillers on Platform Edge on East Section | Kamphol H. | PCOR | 2026-07-10 | 2026-10-30 | 90% | On Schedule |  |  |  |  | CIV/AR | East
144 | 6 | 41 |  | MDW-69232 |  |  | MDW | Test Procedure - Level Crossing at Turnout and Track Slab Crossing on Main Line East Section |  |  |  | ยกเลิก
145 | 6 | 42 |  | MDW-69233 |  |  | MDW | Test Report - Level Crossing at Turnout and Track Slab Crossing on Main Line East Section |  |  |  | ยกเลิก
146 | 6 | 118 | MDW-39280 | MDW-69311 | DN01B1700033 | PSD3 | PSD | Test Procedure - Platform Finishing on East Section | Kamphol H. |  | 2026-08-01 | 2026-08-17 | 100% | Completed | 2026-09-30 |  |  |  | CIV/AR | East
147 | 6 | 119 |  | MDW-69312 | DN01B1700033 | PSD3 | PSD | Test Report - Platform Finishing on East Section | Kamphol H. |  | 2026-09-15 | 2026-10-21 | 0% | On Schedule |  |  |  |  | CIV/AR | East
148 | 6 | 120 | MDW-39281 | MDW-69313 | DN01B1700034 | PSD4 | PSD | Test Procedure - Cladding Barrier between EWD and Station Structure on East Section | Kamphol H. |  | 2026-08-01 | 2026-09-23 | 0% | On Schedule | 2026-09-30 |  |  |  | CIV/AR | East
149 | 6 | 121 |  | MDW-69314 | DN01B1700034 | PSD4 | PSD | Test Report - Cladding Barrier between EWD and Station Structure on East Section | Kamphol H. |  | 2026-09-15 | 2026-10-21 | 0% | On Schedule |  |  |  |  | CIV/AR | East
150 | 6 | 122 |  | MDW-69315 |  |  | PSD | Test Procedure - Holes for PSD Cable Wiring on East Section |  |  |  | ยกเลิก
151 | 6 | 123 |  | MDW-69316 |  |  | PSD | Test Report - Holes for PSD Cable Wiring on East Section |  |  |  | ยกเลิก
152 | 6 | 134 | MDW-39288 | MDW-69327 | DN01B1700053 | SIG3 | MDW | Test Procedure - Point Machine Foundation Construction on East Section | Kamphol H. |  | 2026-08-01 | 2026-09-23 | 25% | On Schedule | 2026-09-30 |  |  |  | CIV/AR | East
153 | 6 | 135 |  | MDW-69328 | DN01B1700053 | SIG3 | MDW | Test Report - Point Machine Foundation Construction on East Section | Kamphol H. |  | 2026-09-15 | 2026-10-21 | 0% | On Schedule |  |  |  |  | CIV/AR | East
154 | 6 | 140 | MDW-39291 | MDW-69333 |  |  | MDW | Test Procedure - Conductor Rail Arrangement Modification at Main Line East Section | Kamphol H. |  | 2026-07-15 | 2026-09-30 | 50% | On Schedule | 2026-08-14 |  |  |  | CIV/AR | East
155 | 6 | 141 |  | MDW-69334 |  |  | MDW | Test Report - Conductor Rail Arrangement Modification at Main Line East Section | Kamphol H. |  | 2026-07-30 | 2026-10-30 | 50% | On Schedule |  |  |  |  | CIV/AR | East
156 | 6 | 142 | MDW-39292 | MDW-69335 |  |  | MDW | Test Procedure - Conductor Rail Arrangement Modification at Depot | Kamphol H. |  | 2026-07-15 | 2026-09-30 | 50% | On Schedule | 2026-08-14 |  |  |  | CIV/AR | East
157 | 6 | 143 |  | MDW-69336 |  |  | MDW | Test Report - Conductor Rail Arrangement Modification at Depot | Kamphol H. |  | 2026-07-30 | 2026-10-30 | 50% | On Schedule |  |  |  |  | CIV/AR | East
158 | 6 | 144 | MDW-39293 | MDW-69337 |  | SIG2 | MDW | Test Procedure - Stabling Walkway Modification at Stabling Yard - Civil & AR | Sahachart S. |  | 2026-05-31 | 2026-09-30 | 90% | On Schedule | 2026-07-30 |  |  | วนเซ็นเอกสาร | CIV/AR | East
159 | 6 | 145 |  | MDW-69338 |  | SIG2 | MDW | Test Report - Stabling Walkway Modification at Stabling Yard - Civil & AR | Bournbhrom CH. |  | 2026-07-15 | 2026-10-30 | 0% | On Schedule |  |  |  | รอส่งมอบงาน | CIV/AR | East
160 | 6 |  |  | AFC-69001 | DN01B1700087 | COM7 | AFC | Test Procedure - Mini Paging in Ticket Office East Section | Bandit |  | 2026-11-30 | 2026-10-31 | 0% | On Schedule |  |  |  |  | E&M | East
161 | 6 |  |  | AFC-69002 | DN01B1700087 | COM7 | AFC | Test Report - Mini Paging in Ticket Office East Section | Bandit |  | 2027-01-29 | 2026-12-30 | 0% | On Schedule |  |  |  |  | E&M | East
162 | 6 |  |  | AFC-69001 |  |  | AFC | Test Procedure - Mini Paging in Ticket Office West Section | TBA |  | 2029-08-01 | 2029-12-30 | 0% | On Schedule |  |  |  |  | E&M | West
163 | 6 |  |  | AFC-69004 |  |  | AFC | Test Report - Mini Paging in Ticket Office West Section | TBA |  | 2029-09-30 | 2030-02-28 | 0% | On Schedule |  |  |  |  | E&M | West
164 | 6 |  |  | COM-69001 | DN01B1700083 | COM3 | COM | Test Procedure - Walk-Through Metal Detector East Section | Montri |  | 2026-10-31 | 2027-01-29 | 0% | On Schedule |  |  |  |  | CIV/AR | East
165 | 6 |  |  | COM-69002 | DN01B1700083 | COM3 | COM | Test Report - Walk-Through Metal Detector East Section | Montri |  | 2026-12-30 | 2027-03-28 | 0% | On Schedule |  |  |  |  | CIV/AR | East
166 | 6 |  |  | COM-69003 |  |  | COM | Test Procedure - Walk-Through Metal Detector West Section | TBA |  | 2029-08-01 | 2029-12-31 | 0% | On Schedule |  |  |  |  | CIV/AR | West
167 | 6 |  |  | COM-69004 |  |  | COM | Test Report - Walk-Through Metal Detector West Section | TBA |  | 2029-09-30 | 2030-03-01 | 0% | On Schedule |  |  |  |  | CIV/AR | West
168 | 6 |  |  | COM-69005 |  |  | COM | Test Procedure - Main Cable Containment for M&E Dedicated communication link to MRTA Headquarter
169 | 6 |  |  | COM-69006 |  |  | COM | Test Report - Main Cable Containment for M&E Dedicated communication link to MRTA Headquarter
170 | 6 |  |  | COM-69007 |  |  | COM | Test Procedure - Power Distribution for M&E Systems at MRTA Headquarter
171 | 6 |  |  | COM-69008 |  |  | COM | Test Report - Power Distribution for M&E Systems at MRTA Headquarter
172 | 6 |  |  | COM-69200 | DN01B1700081 | COM1 | COM | Test Procedure - Magnetic Door Lock for East Section | Montri |  | 2026-08-01 | 2026-12-01 | 0% | On Schedule |  |  |  |  | E&M | East
173 | 6 |  |  | COM-69201 | DN01B1700081 | COM1 | COM | Test Report - Magnetic Door Lock for East Section | Montri |  | 2026-09-30 | 2027-01-30 | 0% | On Schedule |  |  |  |  | E&M | East
174 | 6 |  |  | COM-69202 | DN01B1700085 | COM5 | COM | Test Procedure - MEA Radio | Pratan |  | 2026-08-31 | 2026-09-23 | 0% | Late |  |  |  |  | E&M | East
175 | 6 |  |  | COM-69203 | DN01B1700085 | COM5 | COM | Test Report - MEA Radio | Pratan |  | 2026-10-30 | 2026-10-30 | 0% | On Schedule |  |  |  |  | E&M | East
176 | 6 |  |  | COM-69204 |  |  | COM | Test Procedure - Magnetic Door Lock for West Section | TBA |  | 2029-05-01 | 2029-03-27 | 0% | On Schedule |  |  |  |  | E&M | West
177 | 6 |  |  | COM-69205 |  |  | COM | Test Report - Magnetic Door Lock for West Section | TBA |  | 2029-06-30 | 2029-05-26 | 0% | On Schedule |  |  |  |  | E&M | West
178 | 6 |  |  | DWE-69001 | DN01B1800019 | DWE19 | DWE | Test Procedure - Shunting Locomotive | Somsak |  | 2026-08-31 | 2026-11-30 | 0% | On Schedule |  |  |  |  | E&M | East
179 | 6 |  |  | DWE-69101 | DN01B1800019 | DWE19 | DWE | Test Report - Shunting Locomotive | Somsak |  | 2026-10-30 | 2027-01-29 | 0% | On Schedule |  |  |  |  | E&M | East
180 | 6 |  |  | DWE-69002 | DN01B1800019 | DWE19 | DWE | Test Procedure - Tunnel Inspection and Cleaning Vehicle | Somsak |  | 2026-08-31 | 2026-09-11 | 0% | On Schedule |  |  |  |  | E&M | East
181 | 6 |  |  | DWE-69102 | DN01B1800019 | DWE19 | DWE | Test Report - Tunnel Inspection and Cleaning Vehicle | Somsak |  | 2026-10-30 | 2026-11-10 | 0% | On Schedule |  |  |  |  | E&M | East
182 | 6 |  |  | DWE-69003 | DN01B1800019 | DWE19 | DWE | Test Procedure - Rail Maintenance Vehicle | Somsak |  | 2026-08-31 | 2026-11-16 | 0% | On Schedule |  |  |  |  | E&M | East
183 | 6 |  |  | DWE-69103 | DN01B1800019 | DWE19 | DWE | Test Report - Rail Maintenance Vehicle | Somsak |  | 2026-10-30 | 2027-01-15 | 0% | On Schedule |  |  |  |  | E&M | East
184 | 6 |  |  | DWE-69004 | DN01B1800019 | DWE19 | DWE | Test Procedure - Flat Wagon | Somsak |  | 2026-08-31 | 2026-07-12 | 0% | Late |  |  |  |  | E&M | East
185 | 6 |  |  | DWE-69104 | DN01B1800019 | DWE19 | DWE | Test Report - Flat Wagon | Somsak |  | 2026-10-30 | 2026-09-10 | 0% | On Schedule |  |  |  |  | E&M | East
186 | 6 |  |  | DWE-69005 | DN01B1800019 | DWE19 | DWE | Test Procedure - Re-railing Equipment | Somsak |  | 2026-08-31 | 2026-08-01 | 0% | Late |  |  |  |  | E&M | East
187 | 6 |  |  | DWE-69105 | DN01B1800019 | DWE19 | DWE | Test Report - Re-railing Equipment | Somsak |  | 2026-10-30 | 2026-09-30 | 0% | On Schedule |  |  |  |  | E&M | East
188 | 6 |  |  | DWE-69006 | DN01B1800019 | DWE19 | DWE | Test Procedure - Self-propelled Rail Based Inspection Vehicle | Somsak |  | 2026-08-31 | 2026-11-16 | 0% | On Schedule |  |  |  |  | E&M | East
189 | 6 |  |  | DWE-69106 | DN01B1800019 | DWE19 | DWE | Test Report - Self-propelled Rail Based Inspection Vehicle | Somsak |  | 2026-10-30 | 2027-01-15 | 0% | On Schedule |  |  |  |  | E&M | East
190 | 6 |  |  | DWE-69007 | DN01B1800019 | DWE19 | DWE | Test Procedure - Rail-head Grinding Machine Vehicle | Somsak |  | 2026-08-31 | 2027-08-01 | 0% | On Schedule |  |  |  |  | E&M | East
191 | 6 |  |  | DWE-69107 | DN01B1800019 | DWE19 | DWE | Test Report - Rail-head Grinding Machine Vehicle | Somsak |  | 2026-10-30 | 2027-09-30 | 0% | On Schedule |  |  |  |  | E&M | East
192 | 6 |  |  | DWE-69008 |  |  | DWE | Test Procedure - Multi Measuring Rail Vehicle
193 | 6 |  |  | DWE-69108 |  |  | DWE | Test Report - Multi Measuring Rail Vehicle
194 | 6 |  |  | DWE-69009 | DN01B1800017 | DWE17 | DWE | Test Procedure - Rail / Road Shunting Vehicle | Somsak |  | 2026-08-31 | 2026-09-01 | 0% | Late |  |  |  |  | E&M | East
195 | 6 |  |  | DWE-69109 | DN01B1800017 | DWE17 | DWE | Test Report - Rail / Road Shunting Vehicle | Somsak |  | 2026-10-30 | 2026-10-31 | 0% | On Schedule |  |  |  |  | E&M | East
196 | 6 |  |  | DWE-69011 | DN01B1800002 | DWE2 | DWE | Test Procedure - Movable Height Maintenance Platform Vehicle | Somsak |  | 2026-08-31 | 2026-06-09 | 100% | Completed |  |  |  |  | E&M | East
197 | 6 |  |  | DWE-69111 | DN01B1800002 | DWE2 | DWE | Test Report - Movable Height Maintenance Platform Vehicle | Somsak |  | 2026-10-30 | 2026-08-08 | 0% | Late |  |  |  |  | E&M | East
198 | 6 |  |  | DWE-69012 | DN01B1800003 | DWE3 | DWE | Test Procedure - Forklifts | Somsak |  | 2026-08-31 | 2026-06-30 | 0% | Late |  |  |  |  | E&M | East
199 | 6 |  |  | DWE-69112 | DN01B1800003 | DWE3 | DWE | Test Report - Forklifts | Somsak |  | 2026-10-30 | 2026-08-29 | 0% | Late |  |  |  |  | E&M | East
200 | 6 |  |  | DWE-69013 | DN01B1800016 | DWE16 | DWE | Test Procedure - Overhead Traveling Crane | Somsak |  | 2026-10-01 | 2026-03-05 | 100% | Completed |  |  |  |  | E&M | East
201 | 6 |  |  | DWE-69013 | DN01B1800016 | DWE16 | DWE | Test Procedure - Overhead Traveling Crane | Somsak |  | 2026-10-01 | 2026-03-05 | 100% | Completed |  |  |  |  | E&M | East
202 | 6 |  |  | DWE-69013 | DN01B1800016 | DWE16 | DWE | Test Procedure - Overhead Traveling Crane | Somsak |  | 2026-10-01 | 2026-03-05 | 0% | Late |  |  |  |  | E&M | East
203 | 6 |  |  | DWE-69113 | DN01B1800016 | DWE16 | DWE | Test Report - Overhead Traveling Crane 10 tons | Somsak |  | 2026-11-30 | 2026-05-04 | 0% | Late |  |  |  |  | E&M | East
204 | 6 |  |  | DWE-69213 | DN01B1800016 | DWE16 | DWE | Test Report - Overhead Traveling Crane 5 tons | Somsak |  | 2026-11-30 | 2026-05-04 | 0% | Late |  |  |  |  | E&M | East
205 | 6 |  |  | DWE-69213 | DN01B1800016 | DWE16 | DWE | Test Report - Overhead Traveling Crane 5 tons | Somsak |  | 2026-11-30 | 2026-05-04 | 100% | Completed |  |  |  |  | E&M | East
206 | 6 |  |  | DWE-69313 | DN01B1800016 | DWE16 | DWE | Test Report - Overhead Traveling Crane 2 tons | Somsak |  | 2026-11-30 | 2026-05-04 | 0% | Late |  |  |  |  | E&M | East
207 | 6 |  |  | DWE-69413 | DN01B1800016 | DWE16 | DWE | Test Report - Overhead Traveling Crane 2x2 tons | Somsak |  | 2026-11-30 | 2026-05-04 | 0% | Late |  |  |  |  | E&M | East
208 | 6 |  |  | DWE-69513 | DN01B1800016 | DWE16 | DWE | Test Report - Overhead Traveling Crane 8 tons | Somsak |  | 2026-11-30 | 2026-05-04 | 0% | Late |  |  |  |  | E&M | East
209 | 6 |  |  | DWE-69014 | DN01B1800018 | DWE18 | DWE | Test Procedure - Trackwork Equpment | Somsak |  | 2026-10-01 | 2027-02-28 | 0% | On Schedule |  |  |  |  | E&M | East
210 | 6 |  |  | DWE-69114 | DN01B1800018 | DWE18 | DWE | Test Report - Trackwork Equpment | Somsak |  | 2026-11-30 | 2027-04-29 | 0% | On Schedule |  |  |  |  | E&M | East
211 | 6 |  |  | DWE-69015 | DN01B1800004 | DWE4 | DWE | Test Procedure - Compressed Air System and Portable Air Compressor for Depot | Somsak |  | 2026-08-31 | 2026-08-30 | 0% | Late |  |  |  |  | E&M | East
212 | 6 |  |  | DWE-69115 | DN01B1800004 | DWE4 | DWE | Test Report - Compressed Air System and Portable Air Compressor for Depot | Somsak |  | 2026-10-30 | 2026-10-29 | 0% | On Schedule |  |  |  |  | E&M | East
213 | 6 |  |  | DWE-69016 | DN01B1800001 | DWE1 | DWE | Test Procedure - Diesel Fuel Storage Tank for Maintenance Vehicle at Depot | Somsak |  | 2026-08-31 | 2026-07-10 | 0% | Late |  |  |  |  | E&M | East
214 | 6 |  |  | DWE-69116 | DN01B1800001 | DWE1 | DWE | Test Report - Diesel Fuel Storage Tank for Maintenance Vehicle at Depot | Somsak |  | 2026-10-30 | 2026-09-08 | 0% | On Schedule |  |  |  |  | E&M | East
215 | 6 |  |  | DWE-69017 | DN01B1800005 | DWE5 | DWE | Test Procedure - Pallet Shelves, Two-Tier Shelves and Tool Storage | Somsak |  | 2026-08-31 | 2026-05-06 | 100% | Completed |  |  |  |  | E&M | East
216 | 6 |  |  | DWE-69117 | DN01B1800005 | DWE5 | DWE | Test Report - Pallet Shelves, Two-Tier Shelves and Tool Storage | Somsak |  | 2026-10-30 | 2026-07-05 | 0% | Late |  |  |  |  | E&M | East
217 | 6 |  |  | DWE-69217 |  |  | DWE | Test Procedure - Pallet Storage Shelves in Dangerous Goods Building
218 | 6 |  |  | DWE-69317 |  |  | DWE | Test Report - Pallet Storage Shelves in Dangerous Goods Building
219 | 6 |  |  | DWE-69417 |  |  | DWE | Test Procedure - Two-Tier Shelf
220 | 6 |  |  | DWE-69517 |  |  | DWE | Test Report - Two-Tier Shelf
221 | 6 |  |  | DWE-69617 |  |  | DWE | Test Procedure - Tool Storage
222 | 6 |  |  | DWE-69717 |  |  | DWE | Test Report - Tool Storage
223 | 6 |  |  | DWE-69018 | DN01B1800009 | DWE9 | DWE | Test Procedure - Repair Equipment | Somsak |  | 2026-08-31 | 2027-03-03 | 0% | On Schedule |  |  |  |  | E&M | East
224 | 6 |  |  | DWE-69118 | DN01B1800009 | DWE9 | DWE | Test Report - Repair Equipment | Somsak |  | 2026-10-30 | 2027-05-02 | 0% | On Schedule |  |  |  |  | E&M | East
225 | 6 |  |  | DWE-69019 | DN01B1800009 | DWE9 | DWE | Test Procedure - Paint Shop Equipment | Somsak |  | 2026-08-31 | 2027-03-03 | 0% | On Schedule |  |  |  |  | E&M | East
226 | 6 |  |  | DWE-69119 | DN01B1800009 | DWE9 | DWE | Test Report - Paint Shop Equipment | Somsak |  | 2026-10-30 | 2027-05-02 | 0% | On Schedule |  |  |  |  | E&M | East
227 | 6 |  |  | DWE-69020 | DN01B1800010 | DWE10 | DWE | Test Procedure - Oil & Grease Disposal and Waste Disposal | Somsak |  | 2026-08-31 | 2026-06-05 | 0% | Late |  |  |  |  | E&M | East
228 | 6 |  |  | DWE-69120 | DN01B1800010 | DWE10 | DWE | Test Report - Oil & Grease Disposal and Waste Disposal | Somsak |  | 2026-10-30 | 2026-08-04 | 0% | Late |  |  |  |  | E&M | East
229 | 6 |  |  | DWE-69021 | DN01B1700009 | GEN9 | DWE | Test Procedure - Operation Support Equipment | Somsak |  | 2026-08-01 | 2026-10-17 | 0% | On Schedule |  |  |  |  | E&M | East
230 | 6 |  |  | DWE-69121 | DN01B1700009 | GEN9 | DWE | Test Report - Operation Support Equipment | Somsak |  | 2026-09-30 | 2026-12-16 | 0% | On Schedule |  |  |  |  | E&M | East
231 | 6 |  |  | DWE-69030 |  |  | DWE | Workshop Manual - DWE Part 2 Phase: Testing and Commissioning | Somsak |  |  |  | 100% | Completed |  |  |  |  | E&M | East
232 | 6 |  |  | DWE-69023 | DN01B1800015 | DWE15 | DWE | Test Procedure - Provision of Civil Works to support Train Washing Equipment | Somsak |  | 2026-08-31 | 2026-08-01 | 0% | Late |  |  |  |  | E&M | East
233 | 6 |  |  | DWE-69123 | DN01B1800015 | DWE15 | DWE | Test Report - Provision of Civil Works to support Train Washing Equipment | Somsak |  | 2026-10-30 | 2026-09-30 | 0% | On Schedule |  |  |  |  | E&M | East
234 | 6 |  |  | DWE-69024 | DN01B1700007 | GEN7.1 | DWE | Test Procedure - Dangerous Waste Storage Building in Depot - Civil & AR | Somsak |  | 2026-08-31 | 2026-05-31 | 100% | Completed |  |  |  |  | E&M | East
235 | 6 |  |  | DWE-69124 | DN01B1700007 | GEN7.1 | DWE | Test Report - Dangerous Waste Storage Building in Depot - Civil & AR | Somsak |  | 2026-10-30 | 2026-09-30 | 0% | Late |  |  |  |  | E&M | East
236 | 6 |  |  | DWE-69025 | DN01B1700007 | GEN7.2 GEN8.2 | DWE | Test Procedure - Dangerous Waste Storage Building and General Waste Storage Building in Depot - Building Service | Somsak |  | 2026-08-31 | 2026-05-31 | 100% | Completed |  |  |  |  | E&M | East
237 | 6 |  |  | DWE-69125 | DN01B1700007 | GEN7.2 GEN8.2 | DWE | Test Report - Dangerous Waste Storage Building and General Waste Storage Building in Depot - Building Service | Somsak |  | 2026-10-30 | 2026-09-30 | 0% | Late |  |  |  |  | E&M | East
238 | 6 |  |  | DWE-69026 | DN01B1700008 | GEN8.1 | DWE | Test Procedure - General Waste Storage Building in Depot - Civil & AR | Sahachart S. |  | 2026-08-31 | 2026-03-31 | 100% | Completed |  |  |  |  | CIV/AR | East
239 | 6 |  |  | DWE-69126 | DN01B1700008 | GEN8.1 | DWE | Test Report - General Waste Storage Building in Depot - Civil & AR | Sahachart S. |  | 2026-10-30 | 2026-09-30 | 0% | Late |  |  |  |  | CIV/AR | East
240 | 6 |  |  | DWE-69027 |  |  | DWE | Test Procedure - General Waste Storage Building in Depot - Building Service
241 | 6 |  |  | DWE-69127 |  |  | DWE | Test Report - General Waste Storage Building in Depot - Building Service
242 | 6 |  |  | EPS-69001 | DN01B1800001 | DWE1 | EPS | Test Procedure - Diesel Fuel Storage Tanks for Power Generators | Somsak |  | 2026-03-01 | 2026-06-10 | 0% | Late |  |  |  |  | E&M | East
243 | 6 |  |  | EPS-69002 | DN01B1800001 | DWE1 | EPS | Test Report - Diesel Fuel Storage Tanks for Power Generators | Somsak |  | 2026-04-30 | 2026-08-09 | 0% | Late |  |  |  |  | E&M | East
244 | 6 |  |  | EPS-69003 |  |  | EPS | Test Procedure - Diesel Fuel Storage Tanks for Power Generators - Building Services
245 | 6 |  |  | EPS-69004 |  |  | EPS | Test Report - Diesel Fuel Storage Tanks for Power Generators - Building Services
246 | 6 |  |  | GRS-69001 | DN01B1700010 | GEN10 | GRS | Test Procedure - Graphic and Signage | Sahachart S. |  | 2026-08-02 | 2027-01-29 | 0% | On Schedule |  |  |  |  | CIV/AR | East
247 | 6 |  | GRS-39001 | GRS-69002 | DN01B1700010 | GEN10 | GRS | Test Report - Graphic and Signage on East Section, OR13 | Sahachart S. |  | 2026-10-01 | 2027-03-30 | 0% | On Schedule |  |  |  |  | CIV/AR | East
248 | 6 |  | GRS-39002 | GRS-69003 | DN01B1700010 | GEN10 | GRS | Test Report - Graphic and Signage on East Section, OR14 | Sahachart S. |  | 2026-10-01 | 2027-03-30 | 0% | On Schedule |  |  |  |  | CIV/AR | East
249 | 6 |  | GRS-39003 | GRS-69004 | DN01B1700010 | GEN10 | GRS | Test Report - Graphic and Signage on East Section, OR15 | Sahachart S. |  | 2026-10-01 | 2027-03-30 | 0% | On Schedule |  |  |  |  | CIV/AR | East
250 | 6 |  | GRS-39004 | GRS-69005 | DN01B1700010 | GEN10 | GRS | Test Report - Graphic and Signage on East Section, OR16 | Sahachart S. |  | 2026-10-01 | 2027-03-30 | 0% | On Schedule |  |  |  |  | CIV/AR | East
251 | 6 |  | GRS-39005 | GRS-69006 | DN01B1700010 | GEN10 | GRS | Test Report - Graphic and Signage on East Section, OR17 | Sahachart S. |  | 2026-10-01 | 2027-03-30 | 0% | On Schedule |  |  |  |  | CIV/AR | East
252 | 6 |  | GRS-39006 | GRS-69007 | DN01B1700010 | GEN10 | GRS | Test Report - Graphic and Signage on East Section, OR18 | Sahachart S. |  | 2026-10-01 | 2027-03-30 | 0% | On Schedule |  |  |  |  | CIV/AR | East
253 | 6 |  | GRS-39007 | GRS-69008 | DN01B1700010 | GEN10 | GRS | Test Report - Graphic and Signage on East Section, OR19 | Sahachart S. |  | 2026-10-01 | 2027-03-30 | 0% | On Schedule |  |  |  |  | CIV/AR | East
254 | 6 |  | GRS-39008 | GRS-69009 | DN01B1700010 | GEN10 | GRS | Test Report - Graphic and Signage on East Section, OR20 | Sahachart S. |  | 2026-10-01 | 2027-03-30 | 0% | On Schedule |  |  |  |  | CIV/AR | East
255 | 6 |  | GRS-39009 | GRS-69010 | DN01B1700010 | GEN10 | GRS | Test Report - Graphic and Signage on East Section, OR21 | Sahachart S. |  | 2026-10-01 | 2027-03-30 | 0% | On Schedule |  |  |  |  | CIV/AR | East
256 | 6 |  | GRS-39010 | GRS-69011 | DN01B1700010 | GEN10 | GRS | Test Report - Graphic and Signage on East Section, OR22 | Sahachart S. |  | 2026-10-01 | 2027-03-30 | 0% | On Schedule |  |  |  |  | CIV/AR | East
257 | 6 |  | GRS-39011 | GRS-69012 | DN01B1700010 | GEN10 | GRS | Test Report - Graphic and Signage on East Section, OR23 | Sahachart S. |  | 2026-10-01 | 2027-03-30 | 0% | On Schedule |  |  |  |  | CIV/AR | East
258 | 6 |  | GRS-39012 | GRS-69013 | DN01B1700010 | GEN10 | GRS | Test Report - Graphic and Signage on East Section, OR24 | Sahachart S. |  | 2026-10-01 | 2027-03-30 | 0% | On Schedule |  |  |  |  | CIV/AR | East
259 | 6 |  | GRS-39013 | GRS-69014 | DN01B1700010 | GEN10 | GRS | Test Report - Graphic and Signage on East Section, OR25 | Sahachart S. |  | 2026-10-01 | 2027-03-30 | 0% | On Schedule |  |  |  |  | CIV/AR | East
260 | 6 |  | GRS-39014 | GRS-69015 | DN01B1700010 | GEN10 | GRS | Test Report - Graphic and Signage on East Section, OR26 | Sahachart S. |  | 2026-10-01 | 2027-03-30 | 0% | On Schedule |  |  |  |  | CIV/AR | East
261 | 6 |  | GRS-39015 | GRS-69016 | DN01B1700010 | GEN10 | GRS | Test Report - Graphic and Signage on East Section, OR27 | Sahachart S. |  | 2026-10-01 | 2027-03-30 | 0% | On Schedule |  |  |  |  | CIV/AR | East
262 | 6 |  | GRS-39016 | GRS-69017 | DN01B1700010 | GEN10 | GRS | Test Report - Graphic and Signage on East Section, OR28 | Sahachart S. |  | 2026-10-01 | 2027-03-30 | 0% | On Schedule |  |  |  |  | CIV/AR | East
263 | 6 |  | GRS-39017 | GRS-69018 | DN01B1700010 | GEN10 | GRS | Test Report - Graphic and Signage on East Section, OR29 | Sahachart S. |  | 2026-10-01 | 2027-03-30 | 0% | On Schedule |  |  |  |  | CIV/AR | East
264 | 6 |  | GRS-39018 | GRS-69019 | DN02B1710022 | MO-CK22 | GRS | Test Report - Graphic and Signage on East Section, IVS, VS, EEEN and Transition Area | Sahachart S. |  | 2026-10-01 | 2027-01-30 | 0% | On Schedule |  |  |  |  | CIV/AR | East
265 | 6 |  | GRS-39019 | GRS-69020 | DN02B1710017 DN02B1710018 DN02B1710019 DN02B1710020 DN02B1710022 DN02B1710024 | MO-CK17 MO-CK18 MO-CK19 MO-CK20 MO-CK22 MO-CK24 | GRS | Test Report - Graphic and Signage at Depot, Main Workshop and Other Buildings | Sahachart S. |  | 2026-10-01 | 2026-11-30 | 0% | On Schedule |  |  |  |  | CIV/AR | East
266 | 6 |  | GRS-39020 | GRS-69021 | DN02B1710017 DN02B1710018 DN02B1710019 DN02B1710020 DN02B1710022 DN02B1710024 | MO-CK17 MO-CK18 MO-CK19 MO-CK20 MO-CK22 MO-CK24 | GRS | Test Report - Graphic and Signage at Depot, OCC and Admin Building | Sahachart S. |  | 2026-10-01 | 2026-11-30 | 0% | On Schedule |  |  |  |  | CIV/AR | East
267 | 6 |  | GRS-39021 | GRS-69022 | DN02B1710021 | MO-CK21 | GRS | Test Report - Graphic and Signage on East Section, Safety Line for Depot Buildings | Sahachart S. |  | 2026-10-01 | 2026-11-30 | 0% | On Schedule |  |  |  |  | CIV/AR | East
268 | 6 |  | GRS-39022 | GRS-69023 | DN01B1700010 | GEN10 | GRS | Test Report - Graphic and Signage on East Section, at BSS1, BSS2 and Generator Building | Sahachart S. |  | 2026-10-01 | 2026-05-30 | 0% | Late |  |  |  |  | CIV/AR | East
269 | 6 |  | GRS-39023 | GRS-69024 | DN01B1700010 DN02B1710017 DN02B1710021 | GEN10 MO-CK17 MO-CK21 | GRS | Test Report - Graphic and Signage on East Section, Track Area at Depot | Sahachart S. |  | 2026-10-01 | 2026-11-30 | 0% | On Schedule |  |  |  |  | CIV/AR | East
270 | 6 |  | GRS-39024 | GRS-69025 | DN02B1710025 | MO-CK25 | GRS | Test Report - Graphic and Signage on East Section, Track Area at Main Line | Sahachart S. |  | 2026-10-01 | 2027-01-30 | 0% | On Schedule |  |  |  |  | CIV/AR | East
271 | 6 |  | GRS-39025 | GRS-69026 | DN01B1700010 | GEN10 | GRS | Test Report - Graphic and Signage on East Section, Power Supply for Signage | Sahachart S. |  | 2026-10-01 | 2026-11-30 | 0% | On Schedule |  |  |  |  | CIV/AR | East
272 | 6 |  |  | GRS-69027 |  |  | GRS | Test Report - Graphic and Signage on West Section, OR02 | TBA |  | 2029-04-30 | 2029-04-25 | 0% | On Schedule |  |  |  |  | CIV/AR | West
273 | 6 |  |  | GRS-69028 |  |  | GRS | Test Report - Graphic and Signage on West Section, OR03 | TBA |  | 2029-04-30 | 2029-04-25 | 0% | On Schedule |  |  |  |  | CIV/AR | West
274 | 6 |  |  | GRS-69029 |  |  | GRS | Test Report - Graphic and Signage on West Section, OR04 | TBA |  | 2029-04-30 | 2029-04-25 | 0% | On Schedule |  |  |  |  | CIV/AR | West
275 | 6 |  |  | GRS-69030 |  |  | GRS | Test Report - Graphic and Signage on West Section, OR05 | TBA |  | 2029-04-30 | 2029-04-25 | 0% | On Schedule |  |  |  |  | CIV/AR | West
276 | 6 |  |  | GRS-69031 |  |  | GRS | Test Report - Graphic and Signage on West Section, OR06 | TBA |  | 2029-04-30 | 2029-04-25 | 0% | On Schedule |  |  |  |  | CIV/AR | West
277 | 6 |  |  | GRS-69032 |  |  | GRS | Test Report - Graphic and Signage on West Section, OR07 | TBA |  | 2029-04-30 | 2029-04-25 | 0% | On Schedule |  |  |  |  | CIV/AR | West
278 | 6 |  |  | GRS-69033 |  |  | GRS | Test Report - Graphic and Signage on West Section, OR08 | TBA |  | 2029-04-30 | 2029-04-25 | 0% | On Schedule |  |  |  |  | CIV/AR | West
279 | 6 |  |  | GRS-69034 |  |  | GRS | Test Report - Graphic and Signage on West Section, OR09 | TBA |  | 2029-04-30 | 2029-04-25 | 0% | On Schedule |  |  |  |  | CIV/AR | West
280 | 6 |  |  | GRS-69035 |  |  | GRS | Test Report - Graphic and Signage on West Section, OR10 | TBA |  | 2029-04-30 | 2029-04-25 | 0% | On Schedule |  |  |  |  | CIV/AR | West
281 | 6 |  |  | GRS-69036 |  |  | GRS | Test Report - Graphic and Signage on West Section, OR11 | TBA |  | 2029-04-30 | 2029-04-25 | 0% | On Schedule |  |  |  |  | CIV/AR | West
282 | 6 |  |  | GRS-69037 |  |  | GRS | Test Report - Graphic and Signage on West Section, OR12 | TBA |  | 2029-04-30 | 2029-04-25 | 0% | On Schedule |  |  |  |  | CIV/AR | West
283 | 6 |  |  | GRS-69038 |  |  | GRS | Test Report - Graphic and Signage on West Section, IVS and EEEN | TBA |  | 2029-04-30 | 2029-04-25 | 0% | On Schedule |  |  |  |  | CIV/AR | West
284 | 6 |  |  | GRS-69039 |  |  | GRS | Test Report - Graphic and Signage on West Section, at BSS3 | TBA |  | 2029-04-30 | 2029-04-25 | 0% | On Schedule |  |  |  |  | CIV/AR | West
285 | 6 |  |  | GRS-69040 |  |  | GRS | Test Report - Graphic and Signage on West Section, Track Area at Main Line | TBA |  | 2029-04-30 | 2029-04-25 | 0% | On Schedule |  |  |  |  | CIV/AR | West
286 | 6 |  |  | GRS-69041 |  |  | GRS | Test Report - Graphic and Signage on West Section, Power Supply for Signage | TBA |  | 2029-04-30 | 2029-04-25 | 0% | On Schedule |  |  |  |  | CIV/AR | West
287 | 6 |  |  | PSY-69013 | DN01B1700062 | PSY2 | PSY | Test Procedure - HV Cable Ducts from MEA Interface Point to BSS1 | Pratan |  | 2026-03-01 | 2025-11-04 | 0% | Late |  |  |  |  | E&M | East
288 | 6 |  |  | PSY-69014 | DN01B1700062 | PSY2 | PSY | Test Report - HV Cable Ducts from MEA Interface Point to BSS1 | Pratan |  | 2026-04-30 | 2026-01-03 | 0% | Late |  |  |  |  | E&M | East
289 | 6 |  |  | PSY-690XX |  |  | PSY | Test Procedure - Earthing and Bonding Modification on East Section
290 | 6 |  |  | PSY-690XX |  |  | PSY | Test Report - Earthing and Bonding Modification on East Section
291 | 6 |  |  | PSY-69015 | DN01B1700063 | PSY3 | PSY | Test Procedure - Steel Grating Raised Floor for EE Panel on East Section | Sahachart S. |  | 2026-03-01 | 2025-06-14 | 0% | Late |  |  |  |  | CIV/AR | East
292 | 6 |  |  | PSY-69016 | DN01B1700063 | PSY3 | PSY | Test Report - Steel Grating Raised Floor for EE Panel on East Section | Sahachart S. |  | 2026-04-30 | 2025-08-13 | 0% | Late |  |  |  |  | CIV/AR | East
293 | 6 |  |  | PSY-69017 | DN01B1700062 | PSY2 | PSY | Test Procedure - Overhead Travelling Crane for BSS1 and BSS2 | Sahachart S. |  | 2026-03-01 | 2025-11-04 | 100% | Completed |  |  |  |  | CIV/AR | East
294 | 6 |  |  | PSY-69018 | DN01B1700062 | PSY2 | PSY | Test Report - Overhead Travelling Crane for BSS1 and BSS2 | Sahachart S. |  | 2026-04-30 | 2026-01-03 | 100% | Completed |  |  |  |  | CIV/AR | East
295 | 6 |  |  | PSY-69019 |  |  | PSY | Test Procedure - Overhead Travelling Crane for BSS3 | TBA |  | 2028-10-31 | 2028-01-30 | 0% | On Schedule |  |  |  |  | CIV/AR | West
296 | 6 |  |  | PSY-69020 |  |  | PSY | Test Report - Overhead Travelling Crane for BSS3 | TBA |  | 2028-12-30 | 2028-03-30 | 0% | On Schedule |  |  |  |  | CIV/AR | West
297 | 6 |  |  | PSY-690XX | DN01B1700011 | GEN11 | PSY | Test Procedure - Earthing and Bonding Modification on West Section | Montri |  | 2026-03-01 | 2026-02-28 | 0% | Late |  |  |  |  | E&M | West
298 | 6 |  |  | PSY-690XX | DN01B1700011 | GEN11 | PSY | Test Report - Earthing and Bonding Modification on West Section | Montri |  | 2026-04-30 | 2026-04-29 | 0% | Late |  |  |  |  | E&M | West
299 | 6 |  |  | PSY-690XX |  |  | PSY | Test Procedure - Steel Grating Raised Floor for EE Panel on West Section | TBA |  | 2029-01-29 | 2027-08-28 | 0% | On Schedule |  |  |  |  | CIV/AR | West
300 | 6 |  |  | PSY-690XX |  |  | PSY | Test Report - Steel Grating Raised Floor for EE Panel on West Section | TBA |  | 2029-03-30 | 2027-10-27 | 0% | On Schedule |  |  |  |  | CIV/AR | West
301 | 6 |  |  | SCA-69200 |  |  | SCA | Test Procedure - Modification of BEMS to receive PSD Signal on East Section
302 | 6 |  |  | SCA-69201 |  |  | SCA | Test Report - Modification of BEMS to receive PSD Signal on East Section
303 | 6 |  |  | SCA-69202 |  |  | SCA | Test Procedure - Modification of Escalator Interface Point with CCTV and SCADA on East Section
304 | 6 |  |  | SCA-69203 |  |  | SCA | Test Report - Modification of Escalator Interface Point with CCTV and SCADA on East Section
305 | 6 |  |  | SCA-69204 |  |  | SCA | Test Procedure - Modification of Fire Alarm System Interface Point with CCTV and SCADA on East Section
306 | 6 |  |  | SCA-69205 |  |  | SCA | Test Report - Modification of Fire Alarm System Interface Point with CCTV and SCADA on East Section
307 | 6 |  |  | SCA-69206 |  |  | SCA | Test Procedure - Modification of SCADA Hardwire on East Section
308 | 6 |  |  | SCA-69207 |  |  | SCA | Test Report - Modification of SCADA Hardwire on East Section
Formulas:
Submit Plan Rev.02 = [Punch List]-7
Note on N6: USER: Check %Prog. จากไฟล์พี่บิ๊ก, พี่ต่อ

## 04 Test Procedure&Report
| 9=Requirement Traceability Report 2=Additional Works-internal document | Submission No. | Document No. (QA) | Issued Date | Rev. | Letter No. | Description/Title | Orignator | Submit Plan by CK | Status | Submission No. | Description/Title
| 6 | OPM-69001 | OLW-ME-24/0007 | 2025-03-01 | A | BEM/M/ORM/S0062/68 | On-Site Inspection and Test Procedure of Modification Work - Civil & AR in MRT Orange Line Project (East Section) |  |  | submitted |  | Modification Work - Civil & AR in MRT Orange Line Project (East Section) | Test Procedure
| 6 | OPM-69001 | OLW-ME-24/0007 | 2025-10-02 | B | BEM/M/ORM/S0097/69 | On-Site Inspection and Test Procedure of Modification Work - Civil & AR in MRT Orange Line Project (East Section) |  |  | submitted |  | Modification Work - Civil & AR in MRT Orange Line Project (East Section) | Test Procedure
| 6 | OPM-69002 | OLW-ME-24/0108 | 2025-07-18 | A | BEM/M/ORM/S0509/68 | On-Site Inspection and Test Procedure of Modification Work - Building Service (Electrical System) in MRT Orange Line Project (East Section) |  |  | submitted |  | Building Service (Electrical System) in MRT Orange Line Project (East Section) | Test Procedure
| 6 | OPM-69002 | OLW-ME-24/0108 | 2026-02-18 | B | BEM/M/ORM/S0554/69 | On-Site Inspection and Test Procedure of Modification Work - Building Service (Electrical System) in MRT Orange Line Project (East Section) |  |  | submitted |  | Modification Work - Building Service (Electrical System) in MRT Orange Line Project (East Section) | Test Procedure
| 6 | OPM-69003 | OLW-ME-24/0129 | 2025-09-12 | A | BEM/M/ORM/S0960/68 | On-Site Inspection and Test Procedure of Modification Work - Building Service (Mechanical System) in MRT Orange Line Project (East Section) |  |  | submitted |  | Modification Work - Building Service (Mechanical System) in MRT Orange Line Project (East Section) | Test Procedure
| 6 | OPM-69003 | OLW-ME-24/0129 | 2026-02-18 | B | BEM/M/ORM/S0500/69 | On-Site Inspection and Test Procedure of Modification Work - Building Service (Mechanical System) in MRT Orange Line Project (East Section) |  |  | submitted |  | Modification Work - Building Service (Mechanical System) in MRT Orange Line Project (East Section) | Test Procedure
| 6 | AFC-69001 |  |  |  |  | Test Procedure - Mini Paging in Ticket Office East Section |  |  |  | AFC-39001 | Mini Paging in Ticket Office East Section | Test Procedure
| 6 | AFC-69003 |  |  |  |  | Test Procedure - Mini Paging in Ticket Office West Section |  |  |  | AFC-39002 | Mini Paging in Ticket Office West Section | Test Procedure
| 6 | AFC-69002 |  |  |  |  | Test Report - Mini Paging in Ticket Office East Section |  |  |  | AFC-39001 | Mini Paging in Ticket Office East Section | Test Report
| 6 | AFC-69004 |  |  |  |  | Test Report - Mini Paging in Ticket Office West Section |  |  |  | AFC-39002 | Mini Paging in Ticket Office West Section | Test Report
| 6 | COM-69001 |  |  |  |  | Test Procedure - Walk-Through Metal Detector East Section |  |  |  | COM-39001 | Walk-Through Metal Detector East Section | Test Procedure
| 6 | COM-69003 |  |  |  |  | Test Procedure - Walk-Through Metal Detector West Section |  |  |  | COM-39002 | Walk-Through Metal Detector West Section | Test Procedure
| 6 | COM-69005 |  |  |  |  | Test Procedure - Main Cable Containment for M&E Dedicated communication link to MRTA Headquarter |  |  | CANCLE | COM-39004 | Main Cable Containment for M&E Dedicated communication link to MRTA Headquarter | Test Procedure
| 6 | COM-69007 |  |  |  |  | Test Procedure - Power Distribution for M&E Systems at MRTA Headquarter |  |  | CANCLE | COM-39005 | Power Distribution for M&E Systems at MRTA Headquarter | Test Procedure
| 6 | COM-69200 |  |  |  |  | Test Procedure - Magnetic Door Lock for East Section |  |  |  | COM-39200 | Magnetic Door Lock for East Section | Test Procedure
| 6 | COM-69202 |  |  |  |  | Test Procedure - MEA Radio |  |  |  | MDW-39304 | MEA Radio | Test Procedure
| 6 | COM-69204 |  |  |  |  | Test Procedure - Magnetic Door Lock for West Section |  |  |  | COM-39203 | Magnetic Door Lock for West Section | Test Procedure
| 6 | COM-69002 |  |  |  |  | Test Report - Walk-Through Metal Detector East Section |  |  |  | COM-39001 | Walk-Through Metal Detector East Section | Test Report
| 6 | COM-69004 |  |  |  |  | Test Report - Walk-Through Metal Detector West Section |  |  |  | COM-39002 | Walk-Through Metal Detector West Section | Test Report
| 6 | COM-69006 |  |  |  |  | Test Report - Main Cable Containment for M&E Dedicated communication link to MRTA Headquarter |  |  | CANCLE | COM-39004 | Main Cable Containment for M&E Dedicated communication link to MRTA Headquarter | Test Report
| 6 | COM-69008 |  |  |  |  | Test Report - Power Distribution for M&E Systems at MRTA Headquarter |  |  | CANCLE | COM-39005 | Power Distribution for M&E Systems at MRTA Headquarter | Test Report
| 6 | COM-69201 |  |  |  |  | Test Report - Magnetic Door Lock for East Section |  |  |  | COM-39200 | Magnetic Door Lock for East Section | Test Report
| 6 | COM-69203 |  |  |  |  | Test Report - MEA Radio |  |  |  | MDW-39304 | MEA Radio | Test Report
| 6 | COM-69205 |  |  |  |  | Test Report - Magnetic Door Lock for West Section |  |  |  | COM-39203 | Magnetic Door Lock for West Section | Test Report
| 6 | DWE-69001 |  |  |  |  | Test Procedure - Shunting Locomotive |  |  |  | DWE-39001 | Shunting Locomotive | Test Procedure
| 6 | DWE-69002 |  |  |  |  | Test Procedure - Tunnel Inspection and Cleaning Vehicle |  |  |  | DWE-39002 | Tunnel Inspection and Cleaning Vehicle | Test Procedure
| 6 | DWE-69003 |  |  |  |  | Test Procedure - Rail Maintenance Vehicle |  |  |  | DWE-39003 | Rail Maintenance Vehicle | Test Procedure
| 6 | DWE-69004 |  |  |  |  | Test Procedure - Flat Wagon |  |  |  | DWE-39004 | Flat Wagon | Test Procedure
| 6 | DWE-69005 |  |  |  |  | Test Procedure - Re-railing Equipment |  |  |  | DWE-39005 | Re-railing Equipment | Test Procedure
| 6 | DWE-69006 |  |  |  |  | Test Procedure - Self-propelled Rail Based Inspection Vehicle |  |  |  | DWE-39006 | Self-propelled Rail Based Inspection Vehicle | Test Procedure
| 6 | DWE-69007 |  |  |  |  | Test Procedure - Rail-head Grinding Machine Vehicle |  |  |  | DWE-39007 | Rail-head Grinding Machine Vehicle | Test Procedure
| 6 | DWE-69008 |  |  |  |  | Test Procedure - Multi Measuring Rail Vehicle |  |  | CANCLE | DWE-39008 | Multi Measuring Rail Vehicle | Test Procedure
| 6 | DWE-69009 |  |  |  |  | Test Procedure - Rail / Road Shunting Vehicle |  |  |  | DWE-39009 | Rail / Road Shunting Vehicle | Test Procedure
| 6 | DWE-69011 | OLW-ME-24/0392 | 2026-05-22 | A | BEM/M/ORM/S1390/69 | Test Procedure - Movable Height Maintenance Platform Vehicle |  |  | submitted | DWE-39011 | Movable Height Maintenance Platform Vehicle | Test Procedure
| 6 | DWE-69012 |  |  |  |  | Test Procedure - Forklifts |  |  |  | DWE-39012 | Forklifts | Test Procedure
| 6 | DWE-69013 | OLW-ME-24/0367 | 2026-04-10 | A | BEM/M/ORM/S0902/69 | Test Procedure - Overhead Traveling Crane |  |  | submitted | DWE-39013 | Overhead Traveling Crane | Test Procedure
| 6 | DWE-69013 | OLW-ME-24/0367 | 2026-05-26 | B | BEM/M/ORM/S1388/69 | Test Procedure - Overhead Traveling Crane |  |  | submitted | DWE-39013 | Overhead Traveling Crane | Test Procedure
| 6 | DWE-69013 | OLW-ME-24/0367 | เตรียมออก 8/6/26 1/8/26 | C | (323 หน้า) | Test Procedure - Overhead Traveling Crane |  |  |  | DWE-39013 | Overhead Traveling Crane | Test Procedure
| 6 | DWE-69014 |  |  |  |  | Test Procedure - Trackwork Equpment |  |  |  | DWE-39014 | Trackwork Equpment | Test Procedure
| 6 | DWE-69015 |  |  |  |  | Test Procedure - Compressed Air System and Portable Air Compressor for Depot |  |  |  | DWE-39015 | Compressed Air System and Portable Air Compressor for Depot | Test Procedure
| 6 | DWE-69016 |  |  |  |  | Test Procedure - Diesel Fuel Storage Tank for Maintenance Vehicle at Depot |  |  |  | DWE-39016 | Diesel Fuel Storage Tank for Maintenance Vehicle at Depot | Test Procedure
| 6 | DWE-69017 | OLW-ME-24/0474 Total 32 pages | 2026-07-17 | A | BEM/M/ORM/S2292/69 | Test Procedure - Pallet Shelves, Two-Tier Shelves and Tool Storage |  |  | submitted | DWE-39017 | Pallet Shelves, Two-Tier Shelves and Tool Storage | Test Procedure
| 6 | DWE-69217 | OLW-ME-24/0474 Total 32 pages |  |  |  | Test Procedure - Pallet Storage Shelves in Dangerous Goods Building |  |  | CANCLE | DWE-39117 | Pallet Storage Shelves in Dangerous Goods Building | Test Procedure
| 6 | DWE-69417 | OLW-ME-24/0474 Total 32 pages |  |  |  | Test Procedure - Two-Tier Shelf |  |  | CANCLE | DWE-39217 | Two-Tier Shelf | Test Procedure
| 6 | DWE-69617 | OLW-ME-24/0474 Total 32 pages |  |  |  | Test Procedure - Tool Storage |  |  | CANCLE | DWE-39317 | Tool Storage | Test Procedure
| 6 | DWE-69018 | OLW-ME-24/0474 Total 32 pages |  |  |  | Test Procedure - Repair Equipment |  |  |  | DWE-39018 | Repair Equipment | Test Procedure
| 6 | DWE-69019 | OLW-ME-24/0474 Total 32 pages |  |  |  | Test Procedure - Paint Shop Equipment |  |  |  | DWE-39019 | Paint Shop Equipment | Test Procedure
| 6 | DWE-69020 | OLW-ME-24/0474 Total 32 pages |  |  |  | Test Procedure - Oil & Grease Disposal and Waste Disposal |  |  |  | DWE-39020 | Oil & Grease Disposal and Waste Disposal | Test Procedure
| 6 | DWE-69021 | OLW-ME-24/0474 Total 32 pages |  |  |  | Test Procedure - Operation Support Equipment |  |  |  | DWE-39021 | Operation Support Equipment | Test Procedure
| 6 | DWE-69030 | OLW-ME-24/0413 | 2026-06-05 | A | BEM/M/ORM/S1768/69 | Workshop Manual - DWE Part 2 Phase: Testing and Commissioning |  |  | submitted |  | DWE Part 2 Phase: Testing and Commissioning | Workshop Manual
| 6 | DWE-69023 | เตรียมออก 7/7/26 OLW-ME-24/0438 16 pages |  |  |  | Test Procedure - Provision of Civil Works to support Train Washing Equipment |  |  |  | DWE-39023 | Provision of Civil Works to support Train Washing Equipment | Test Procedure
| 6 | DWE-69024 | OLW-ME-24/0439 22 pages | 2026-07-15 | A | Internal | Test Procedure - Dangerous Waste Storage Building in Depot - Civil & AR |  |  | submitted | DWE-39024 | Dangerous Waste Storage Building in Depot - Civil & AR | Test Procedure
| 6 | DWE-69025 | OLW-ME-24/0370 | 2026-04-20 | A | Internal | Test Procedure - Dangerous Waste Storage Building and General Waste Storage Building in Depot - Building Service |  |  | submitted | DWE-39025 | Dangerous Waste Storage Building and General Waste Storage Building in Depot - Building Service | Test Procedure
| 6 | DWE-69026 | OLW-ME-24/0440 24 pages | 2026-07-15 | A | Internal | Test Procedure - General Waste Storage Building in Depot - Civil & AR |  |  | submitted | DWE-39026 | General Waste Storage Building in Depot - Civil & AR | Test Procedure
| 6 | DWE-69027 |  |  |  |  | Test Procedure - General Waste Storage Building in Depot - Building Service |  |  | CANCLE | DWE-39027 | General Waste Storage Building in Depot - Building Service | Test Procedure
| 6 | DWE-69101 |  |  |  |  | Test Report - Shunting Locomotive |  |  |  | DWE-39001 | Shunting Locomotive | Test Report
| 6 | DWE-69102 |  |  |  |  | Test Report - Tunnel Inspection and Cleaning Vehicle |  |  |  | DWE-39002 | Tunnel Inspection and Cleaning Vehicle | Test Report
| 6 | DWE-69103 |  |  |  |  | Test Report - Rail Maintenance Vehicle |  |  |  | DWE-39003 | Rail Maintenance Vehicle | Test Report
| 6 | DWE-69104 |  |  |  |  | Test Report - Flat Wagon |  |  |  | DWE-39004 | Flat Wagon | Test Report
| 6 | DWE-69105 |  |  |  |  | Test Report - Re-railing Equipment |  |  |  | DWE-39005 | Re-railing Equipment | Test Report
| 6 | DWE-69106 |  |  |  |  | Test Report - Self-propelled Rail Based Inspection Vehicle |  |  |  | DWE-39006 | Self-propelled Rail Based Inspection Vehicle | Test Report
| 6 | DWE-69107 |  |  |  |  | Test Report - Rail-head Grinding Machine Vehicle |  |  |  | DWE-39007 | Rail-head Grinding Machine Vehicle | Test Report
| 6 | DWE-69108 |  |  |  |  | Test Report - Multi Measuring Rail Vehicle |  |  | CANCLE | DWE-39008 | Multi Measuring Rail Vehicle | Test Report
| 6 | DWE-69109 |  |  |  |  | Test Report - Rail / Road Shunting Vehicle |  |  |  | DWE-39009 | Rail / Road Shunting Vehicle | Test Report
| 6 | DWE-69111 |  |  |  |  | Test Report - Movable Height Maintenance Platform Vehicle |  |  |  | DWE-39011 | Movable Height Maintenance Platform Vehicle | Test Report
| 6 | DWE-69112 |  |  |  |  | Test Report - Forklifts |  |  |  | DWE-39012 | Forklifts | Test Report
| 6 | DWE-69113 | เตรียมออก 5/8/26 OLW-ME-24/0523 total 177 pages |  | A |  | Test Report - Overhead Traveling Crane 10 tons |  |  |  | DWE-39013 | Overhead Traveling Crane 10 tons | Test Report
| 6 | DWE-69213 | OLW-ME-24/0423 | 2026-06-23 | A | BEM/M/ORM/S1833/69 | Test Report - Overhead Traveling Crane 5 tons |  |  | submitted | DWE-39013 | Overhead Traveling Crane 5 tons | Test Report
| 6 | DWE-69213 | เตรียมออก 5/8/26 total 177 pages |  | B |  | Test Report - Overhead Traveling Crane 5 tons |  |  |  | DWE-39013 | Overhead Traveling Crane 5 tons | Test Report
| 6 | DWE-69313 | เตรียมออก 5/8/26 OLW-ME-24/0524 total 277 pages |  | A |  | Test Report - Overhead Traveling Crane 2 tons |  |  |  | DWE-39013 | Overhead Traveling Crane 2 tons | Test Report
| 6 | DWE-69413 | เตรียมออก 5/8/26 OLW-ME-24/0525 total 119 pages |  | A |  | Test Report - Overhead Traveling Crane 2x2 tons |  |  |  | DWE-39013 | Overhead Traveling Crane 2x2 tons | Test Report
| 6 | DWE-69513 | เตรียมออก 25/6/26 5/8/26 OLW-ME-24/0424 total 129 pages |  | A |  | Test Report - Overhead Traveling Crane 8 tons |  |  |  | DWE-39013 | Overhead Traveling Crane 8 tons | Test Report
| 6 | DWE-69114 |  |  |  |  | Test Report - Trackwork Equpment |  |  |  | DWE-39014 | Trackwork Equpment | Test Report
| 6 | DWE-69115 |  |  |  |  | Test Report - Compressed Air System and Portable Air Compressor for Depot |  |  |  | DWE-39015 | Compressed Air System and Portable Air Compressor for Depot | Test Report
| 6 | DWE-69116 |  |  |  |  | Test Report - Diesel Fuel Storage Tank for Maintenance Vehicle at Depot |  |  |  | DWE-39016 | Diesel Fuel Storage Tank for Maintenance Vehicle at Depot | Test Report
| 6 | DWE-69117 |  |  |  |  | Test Report - Pallet Shelves, Two-Tier Shelves and Tool Storage |  |  |  | DWE-39017 | Pallet Shelves, Two-Tier Shelves and Tool Storage | Test Report
| 6 | DWE-69317 |  |  |  |  | Test Report - Pallet Storage Shelves in Dangerous Goods Building |  |  | CANCLE | DWE-39117 | Pallet Storage Shelves in Dangerous Goods Building | Test Report
| 6 | DWE-69517 |  |  |  |  | Test Report - Two-Tier Shelf |  |  | CANCLE | DWE-39217 | Two-Tier Shelf | Test Report
| 6 | DWE-69717 |  |  |  |  | Test Report - Tool Storage |  |  | CANCLE | DWE-39317 | Tool Storage | Test Report
| 6 | DWE-69118 |  |  |  |  | Test Report - Repair Equipment |  |  |  | DWE-39018 | Repair Equipment | Test Report
| 6 | DWE-69119 |  |  |  |  | Test Report - Paint Shop Equipment |  |  |  | DWE-39019 | Paint Shop Equipment | Test Report
| 6 | DWE-69120 |  |  |  |  | Test Report - Oil & Grease Disposal and Waste Disposal |  |  |  | DWE-39020 | Oil & Grease Disposal and Waste Disposal | Test Report
| 6 | DWE-69121 |  |  |  |  | Test Report - Operation Support Equipment |  |  |  | DWE-39021 | Operation Support Equipment | Test Report
| 6 | DWE-69123 |  |  |  |  | Test Report - Provision of Civil Works to support Train Washing Equipment |  |  |  | DWE-39023 | Provision of Civil Works to support Train Washing Equipment | Test Report
| 6 | DWE-69124 |  |  |  |  | Test Report - Dangerous Waste Storage Building in Depot - Civil & AR |  |  |  | DWE-39024 | Dangerous Waste Storage Building in Depot - Civil & AR | Test Report
| 6 | DWE-69125 |  |  |  |  | Test Report - Dangerous Waste Storage Building and General Waste Storage Building in Depot - Building Service |  |  |  | DWE-39025 | Dangerous Waste Storage Building and General Waste Storage Building in Depot - Building Service | Test Report
| 6 | DWE-69126 |  |  |  |  | Test Report - General Waste Storage Building in Depot - Civil & AR |  |  |  | DWE-39026 | General Waste Storage Building in Depot - Civil & AR | Test Report
| 6 | DWE-69127 |  |  |  |  | Test Report - General Waste Storage Building in Depot - Building Service |  |  | CANCLE | DWE-39027 | General Waste Storage Building in Depot - Building Service | Test Report
| 6 | EPS-69001 |  |  |  |  | Test Procedure - Diesel Fuel Storage Tanks for Power Generators |  |  |  | EPS-39001 | Diesel Fuel Storage Tanks for Power Generators | Test Procedure
| 6 | EPS-69002 |  |  |  |  | Test Report - Diesel Fuel Storage Tanks for Power Generators |  |  |  | EPS-39001 | Diesel Fuel Storage Tanks for Power Generators | Test Report
| 6 | EPS-69003 |  |  |  |  | Test Procedure - Diesel Fuel Storage Tanks for Power Generators - Building Services |  |  | CANCLE | EPS-39002 | Diesel Fuel Storage Tanks for Power Generators - Building Services | Test Procedure
| 6 | EPS-69004 |  |  |  |  | Test Report - Diesel Fuel Storage Tanks for Power Generators - Building Services |  |  | CANCLE | EPS-39002 | Diesel Fuel Storage Tanks for Power Generators - Building Services | Test Report
| 6 | GRS-69001 |  |  |  |  | Test Procedure - Graphic and Signage |  |  |  | GRS-39001-40 | Graphic and Signage | Test Procedure
| 6 | GRS-69002 |  |  |  |  | Test Report - Graphic and Signage on East Section, OR13 |  |  |  | GRS-39001 | Graphic and Signage on East Section, OR13 | Test Report
| 6 | GRS-69003 |  |  |  |  | Test Report - Graphic and Signage on East Section, OR14 |  |  |  | GRS-39002 | Graphic and Signage on East Section, OR14 | Test Report
| 6 | GRS-69004 |  |  |  |  | Test Report - Graphic and Signage on East Section, OR15 |  |  |  | GRS-39003 | Graphic and Signage on East Section, OR15 | Test Report
| 6 | GRS-69005 |  |  |  |  | Test Report - Graphic and Signage on East Section, OR16 |  |  |  | GRS-39004 | Graphic and Signage on East Section, OR16 | Test Report
| 6 | GRS-69006 |  |  |  |  | Test Report - Graphic and Signage on East Section, OR17 |  |  |  | GRS-39005 | Graphic and Signage on East Section, OR17 | Test Report
| 6 | GRS-69007 |  |  |  |  | Test Report - Graphic and Signage on East Section, OR18 |  |  |  | GRS-39006 | Graphic and Signage on East Section, OR18 | Test Report
| 6 | GRS-69008 |  |  |  |  | Test Report - Graphic and Signage on East Section, OR19 |  |  |  | GRS-39007 | Graphic and Signage on East Section, OR19 | Test Report
| 6 | GRS-69009 |  |  |  |  | Test Report - Graphic and Signage on East Section, OR20 |  |  |  | GRS-39008 | Graphic and Signage on East Section, OR20 | Test Report
| 6 | GRS-69010 |  |  |  |  | Test Report - Graphic and Signage on East Section, OR21 |  |  |  | GRS-39009 | Graphic and Signage on East Section, OR21 | Test Report
| 6 | GRS-69011 |  |  |  |  | Test Report - Graphic and Signage on East Section, OR22 |  |  |  | GRS-39010 | Graphic and Signage on East Section, OR22 | Test Report
| 6 | GRS-69012 |  |  |  |  | Test Report - Graphic and Signage on East Section, OR23 |  |  |  | GRS-39011 | Graphic and Signage on East Section, OR23 | Test Report
| 6 | GRS-69013 |  |  |  |  | Test Report - Graphic and Signage on East Section, OR24 |  |  |  | GRS-39012 | Graphic and Signage on East Section, OR24 | Test Report
| 6 | GRS-69014 |  |  |  |  | Test Report - Graphic and Signage on East Section, OR25 |  |  |  | GRS-39013 | Graphic and Signage on East Section, OR25 | Test Report
| 6 | GRS-69015 |  |  |  |  | Test Report - Graphic and Signage on East Section, OR26 |  |  |  | GRS-39014 | Graphic and Signage on East Section, OR26 | Test Report
| 6 | GRS-69016 |  |  |  |  | Test Report - Graphic and Signage on East Section, OR27 |  |  |  | GRS-39015 | Graphic and Signage on East Section, OR27 | Test Report
| 6 | GRS-69017 |  |  |  |  | Test Report - Graphic and Signage on East Section, OR28 |  |  |  | GRS-39016 | Graphic and Signage on East Section, OR28 | Test Report
| 6 | GRS-69018 |  |  |  |  | Test Report - Graphic and Signage on East Section, OR29 |  |  |  | GRS-39017 | Graphic and Signage on East Section, OR29 | Test Report
| 6 | GRS-69019 |  |  |  |  | Test Report - Graphic and Signage on East Section, IVS, VS, EEEN and Transition Area |  |  |  | GRS-39018 | Graphic and Signage on East Section, IVS, VS, EEEN and Transition Area | Test Report
| 6 | GRS-69020 |  |  |  |  | Test Report - Graphic and Signage at Depot, Main Workshop and Other Buildings |  |  |  | GRS-39019 | Graphic and Signage at Depot, Main Workshop and Other Buildings | Test Report
| 6 | GRS-69021 |  |  |  |  | Test Report - Graphic and Signage at Depot, OCC and Admin Building |  |  |  | GRS-39020 | Graphic and Signage at Depot, OCC and Admin Building | Test Report
| 6 | GRS-69022 |  |  |  |  | Test Report - Graphic and Signage on East Section, Safety Line for Depot Buildings |  |  |  | GRS-39022 | Graphic and Signage on East Section, Safety Line for Depot Buildings | Test Report
| 6 | GRS-69023 |  |  |  |  | Test Report - Graphic and Signage on East Section, at BSS1, BSS2 and Generator Building |  |  |  | GRS-39021 | Graphic and Signage on East Section, at BSS1, BSS2 and Generator Building | Test Report
| 6 | GRS-69024 |  |  |  |  | Test Report - Graphic and Signage on East Section, Track Area at Depot |  |  |  | GRS-39023 | Graphic and Signage on East Section, Track Area at Depot | Test Report
| 6 | GRS-69025 |  |  |  |  | Test Report - Graphic and Signage on East Section, Track Area at Main Line |  |  |  | GRS-39024 | Graphic and Signage on East Section, Track Area at Main Line | Test Report
| 6 | GRS-69026 |  |  |  |  | Test Report - Graphic and Signage on East Section, Power Supply for Signage |  |  |  | GRS-39025 | Graphic and Signage on East Section, Power Supply for Signage | Test Report
| 6 | GRS-69027 |  |  |  |  | Test Report - Graphic and Signage on West Section, OR02 |  |  |  | GRS-39026 | Graphic and Signage on West Section, OR02 | Test Report
| 6 | GRS-69028 |  |  |  |  | Test Report - Graphic and Signage on West Section, OR03 |  |  |  | GRS-39027 | Graphic and Signage on West Section, OR03 | Test Report
| 6 | GRS-69029 |  |  |  |  | Test Report - Graphic and Signage on West Section, OR04 |  |  |  | GRS-39028 | Graphic and Signage on West Section, OR04 | Test Report
| 6 | GRS-69030 |  |  |  |  | Test Report - Graphic and Signage on West Section, OR05 |  |  |  | GRS-39029 | Graphic and Signage on West Section, OR05 | Test Report
| 6 | GRS-69031 |  |  |  |  | Test Report - Graphic and Signage on West Section, OR06 |  |  |  | GRS-39030 | Graphic and Signage on West Section, OR06 | Test Report
| 6 | GRS-69032 |  |  |  |  | Test Report - Graphic and Signage on West Section, OR07 |  |  |  | GRS-39031 | Graphic and Signage on West Section, OR07 | Test Report
| 6 | GRS-69033 |  |  |  |  | Test Report - Graphic and Signage on West Section, OR08 |  |  |  | GRS-39032 | Graphic and Signage on West Section, OR08 | Test Report
| 6 | GRS-69034 |  |  |  |  | Test Report - Graphic and Signage on West Section, OR09 |  |  |  | GRS-39033 | Graphic and Signage on West Section, OR09 | Test Report
| 6 | GRS-69035 |  |  |  |  | Test Report - Graphic and Signage on West Section, OR10 |  |  |  | GRS-39034 | Graphic and Signage on West Section, OR10 | Test Report
| 6 | GRS-69036 |  |  |  |  | Test Report - Graphic and Signage on West Section, OR11 |  |  |  | GRS-39035 | Graphic and Signage on West Section, OR11 | Test Report
| 6 | GRS-69037 |  |  |  |  | Test Report - Graphic and Signage on West Section, OR12 |  |  |  | GRS-39036 | Graphic and Signage on West Section, OR12 | Test Report
| 6 | GRS-69038 |  |  |  |  | Test Report - Graphic and Signage on West Section, IVS and EEEN |  |  |  | GRS-39037 | Graphic and Signage on West Section, IVS and EEEN | Test Report
| 6 | GRS-69039 |  |  |  |  | Test Report - Graphic and Signage on West Section, at BSS3 |  |  |  | GRS-39038 | Graphic and Signage on West Section, at BSS3 | Test Report
| 6 | GRS-69040 |  |  |  |  | Test Report - Graphic and Signage on West Section, Track Area at Main Line |  |  |  | GRS-39039 | Graphic and Signage on West Section, Track Area at Main Line | Test Report
| 6 | GRS-69041 |  |  |  |  | Test Report - Graphic and Signage on West Section, Power Supply for Signage |  |  |  | GRS-39040 | Graphic and Signage on West Section, Power Supply for Signage | Test Report
| 6 | PSY-69001 | เตรียมออก 29/6/26 OLW-ME-24/0428 | 27 pages |  |  | Test Procedure - BSS1 : Architectural |  |  |  | PSY-39001 | BSS1 : Architectural | Test Procedure
| 6 | PSY-69003 | เตรียมออก 26/6/26 OLW-ME-24/0429 | 16 pages |  |  | Test Procedure - BSS1 : Structural |  |  |  | PSY-39002 | BSS1 : Structural | Test Procedure
| 6 | PSY-69005 | OLW-ME-24/0300 | 2026-02-18 | A | BEM/M/ORM/S0514/69 | Test Procedure - BSS1 : Building Services Installation Drawing |  |  | submitted | PSY-39003 | BSS1 : Building Services Installation Drawing | Test Procedure
| 6 | PSY-69007 | เตรียมออก 26/6/26 OLW-ME-24/0430 | 27 pages |  |  | Test Procedure - BSS2 : Architectural |  |  |  | PSY-39004 | BSS2 : Architectural | Test Procedure
| 6 | PSY-69009 | เตรียมออก 26/6/26 OLW-ME-24/0431 | 16 pages |  |  | Test Procedure - BSS2 : Structural |  |  |  | PSY-39005 | BSS2 : Structural | Test Procedure
| 6 | PSY-69011 | OLW-ME-24/0326 | 2026-03-18 | A | BEM/M/ORM/S0877/69 | Test Procedure - BSS2 : Building Services Installation Drawing |  |  | submitted | PSY-39006 | BSS2 : Building Services Installation Drawing | Test Procedure
| 6 | PSY-69013 | OLW-ME-24/0432 9 pages |  |  |  | Test Procedure - HV Cable Ducts from MEA Interface Point to BSS1 |  |  |  | PSY-39009 | HV Cable Ducts from MEA Interface Point to BSS1 | Test Procedure
| 6 | PSY-690XX |  |  |  |  | Test Procedure - Earthing and Bonding Modification on East Section |  |  | CANCLE | PSY-39010 | Earthing and Bonding Modification on East Section | Test Procedure
| 6 | PSY-69015 | เตรียมออก 29/6/2026 OLW-ME-24/0433 | 9 pages |  |  | Test Procedure - Steel Grating Raised Floor for EE Panel on East Section |  |  |  | PSY-39011 | Steel Grating Raised Floor for EE Panel on East Section | Test Procedure
| 6 | PSY-69017 | OLW-ME-24/0285 | 2026-02-12 | A | BEM/M/ORM/S0407/69 | Test Procedure - Overhead Travelling Crane for BSS1 and BSS2 |  |  | submitted | PSY-39012-13 | Overhead Travelling Crane for BSS1 and BSS2 | Test Procedure
| 6 | PSY-69019 |  |  |  |  | Test Procedure - Overhead Travelling Crane for BSS3 |  |  |  | PSY-39014 | Overhead Travelling Crane for BSS3 | Test Procedure
| 6 | PSY-690XX |  |  |  |  | Test Procedure - Earthing and Bonding Modification on West Section |  |  |  | PSY-390xx | Earthing and Bonding Modification on West Section | Test Procedure
| 6 | PSY-690XX |  |  |  |  | Test Procedure - Steel Grating Raised Floor for EE Panel on West Section |  |  |  | PSY-390xx | Steel Grating Raised Floor for EE Panel on West Section | Test Procedure
| 6 | PSY-69002 |  |  |  |  | Test Report - BSS1 : Architectural Installation |  |  |  | PSY-39001 | BSS1 : Architectural Installation | Test Report
| 6 | PSY-69004 |  |  |  |  | Test Report - BSS1 : Structural Installation |  |  |  | PSY-39002 | BSS1 : Structural Installation | Test Report
| 6 | PSY-69006 |  |  |  |  | Test Report - BSS1 : Building Services Installation |  |  |  | PSY-39003 | BSS1 : Building Services Installation | Test Report
| 6 | PSY-69008 |  |  |  |  | Test Report - BSS2 : Architectural Installation |  |  |  | PSY-39004 | BSS2 : Architectural Installation | Test Report
| 6 | PSY-69010 |  |  |  |  | Test Report - BSS2 : Structural Installation |  |  |  | PSY-39005 | BSS2 : Structural Installation | Test Report
| 6 | PSY-69012 |  |  |  |  | Test Report - BSS2 : Building Services Installation |  |  |  | PSY-39006 | BSS2 : Building Services Installation | Test Report
| 6 | PSY-69014 |  |  |  |  | Test Report - HV Cable Ducts from MEA Interface Point to BSS1 |  |  |  | PSY-39009 | HV Cable Ducts from MEA Interface Point to BSS1 | Test Report
| 6 | PSY-690XX |  |  |  |  | Test Report - Earthing and Bonding Modification on East Section |  |  | CANCLE | PSY-39010 | Earthing and Bonding Modification on East Section | Test Report
| 6 | PSY-69016 |  |  |  |  | Test Report - Steel Grating Raised Floor for EE Panel on East Section |  |  |  | PSY-39011 | Steel Grating Raised Floor for EE Panel on East Section | Test Report
| 6 | PSY-69018 | OLW-ME-24/0323 | 2026-03-17 | A | BEM/M/ORM/S0884/69 | Test Report - Overhead Travelling Crane for BSS1 and BSS2 |  |  | submitted | PSY-39012-13 | Overhead Travelling Crane for BSS1 and BSS2 | Test Report
| 6 | PSY-69020 |  |  |  |  | Test Report - Overhead Travelling Crane for BSS3 |  |  |  | PSY-39014 | Overhead Travelling Crane for BSS3 | Test Report
| 6 | PSY-690XX |  |  |  |  | Test Report - Earthing and Bonding Modification on West Section |  |  |  | PSY-390xx | Earthing and Bonding Modification on West Section | Test Report
| 6 | PSY-690XX |  |  |  |  | Test Report - Steel Grating Raised Floor for EE Panel on West Section |  |  |  | PSY-390xx | Steel Grating Raised Floor for EE Panel on West Section | Test Report
| 6 | SCA-69200 |  |  |  |  | Test Procedure - Modification of BEMS to receive PSD Signal on East Section |  |  | CANCLE | SCA-39200 | Modification of BEMS to receive PSD Signal on East Section | Test Procedure
| 6 | SCA-69202 |  |  |  |  | Test Procedure - Modification of Escalator Interface Point with CCTV and SCADA on East Section |  |  | CANCLE | SCA-39201 | Modification of Escalator Interface Point with CCTV and SCADA on East Section | Test Procedure
| 6 | SCA-69204 |  |  |  |  | Test Procedure - Modification of Fire Alarm System Interface Point with CCTV and SCADA on East Section |  |  | CANCLE | SCA-39202 | Modification of Fire Alarm System Interface Point with CCTV and SCADA on East Section | Test Procedure
| 6 | SCA-69206 |  |  |  |  | Test Procedure - Modification of SCADA Hardwire on East Section |  |  | CANCLE | SCA-39203 | Modification of SCADA Hardwire on East Section | Test Procedure
| 6 | SCA-69201 |  |  |  |  | Test Report - Modification of BEMS to receive PSD Signal on East Section |  |  | CANCLE | SCA-39200 | Modification of BEMS to receive PSD Signal on East Section | Test Report
| 6 | SCA-69203 |  |  |  |  | Test Report - Modification of Escalator Interface Point with CCTV and SCADA on East Section |  |  | CANCLE | SCA-39201 | Modification of Escalator Interface Point with CCTV and SCADA on East Section | Test Report
| 6 | SCA-69205 |  |  |  |  | Test Report - Modification of Fire Alarm System Interface Point with CCTV and SCADA on East Section |  |  | CANCLE | SCA-39202 | Modification of Fire Alarm System Interface Point with CCTV and SCADA on East Section | Test Report
| 6 | SCA-69207 |  |  |  |  | Test Report - Modification of SCADA Hardwire on East Section |  |  | CANCLE | SCA-39203 | Modification of SCADA Hardwire on East Section | Test Report
| 6 | MDW-69001 | เตรียมออก 1/7/26 OLW-ME-24/0434 | 10 pages |  |  | Test Procedure - Modification of Depot Track Alignment at Stabling Yard |  |  |  | MDW-39001 | Modification of Depot Track Alignment at Stabling Yard | Test Procedure
| 6 | MDW-69003 | เตรียมออก 29/6/2026 24/7/26 OLW-ME-24/0427 | 14 pages |  |  | Test Procedure - Modification Motorized Gate and Shelters at Test Track Depot - Civil & AR |  |  |  | MDW-39002 | Modification Motorized Gate and Shelters at Test Track Depot - Civil & AR | Test Procedure
| 6 | MDW-69005 | OLW-ME-24/0386 | 2026-05-15 | A | BEM/M/ORM/S1394/69 | Test Procedure - Modification Motorized Gate and Shelters at Test Track Depot - Building Service |  |  | submitted | MDW-39003 | Modification Motorized Gate and Shelters at Test Track Depot - Building Service | Test Procedure
| 6 | MDW-69007 | เตรียมออก 9/7/2026 OLW-ME-24/035 |  |  |  | Test Procedure - Rubber Gap Fillers on Platform Edge on East Section |  |  |  | MDW-39004 | Rubber Gap Fillers on Platform Edge on East Section | Test Procedure
| 6 | MDW-69200 |  |  |  | Internal Only | Test Procedure - Modification Work of M&E Cable Containment for East Section stations, VS, IVS, EEEN and Depot |  |  |  | MDW-39201-31 | Modification Work of M&E Cable Containment for East Section stations, VS, IVS, EEEN and Depot | Test Procedure
| 6 | MDW-69232 |  |  |  | Internal Only | Test Procedure - Level Crossing at Turnout and Track Slab Crossing on Main Line East Section |  |  |  | MDW-39232 | Level Crossing at Turnout and Track Slab Crossing on Main Line East Section | Test Procedure
| 6 | MDW-69234 |  |  |  | Internal Only | Test Procedure - Main Line Cable Trough Modification on East Section for PSY and SIG/COM |  |  |  | MDW-39233-4 | Main Line Cable Trough Modification on East Section for PSY and SIG/COM | Test Procedure
| 6 | MDW-69237 | เตรียมออก 3/7/26 OLW-ME-24/0442 |  |  | Internal Only | Test Procedure - Raised Floor Installation on East Section |  |  |  | MDW-39235 | Raised Floor Installation on East Section | Test Procedure
| 6 | MDW-69239 | OLW-ME-24/0443 8 pages | 2026-07-15 | A | Internal Only | Test Procedure - Bird Protection System at Depot Buildings |  |  | submitted | MDW-39236 | Bird Protection System at Depot Buildings | Test Procedure
| 6 | MDW-69241 |  |  |  |  | Test Procedure - Central BEMS for the MRT Orange Line System East Section |  |  |  | MDW-39237 | Central BEMS for the MRT Orange Line System East Section | Test Procedure
| 6 | MDW-69243 |  |  |  |  | Test Procedure - Central BEMS for the MRT Orange Line System West Section |  |  |  | MDW-39238 | Central BEMS for the MRT Orange Line System West Section | Test Procedure
| 6 | MDW-69245 | OLW-ME-24/0444 14 pages | 2026-07-15 | A | Internal Only | Test Procedure - Access Panel Closeout for Traction Substation Room in Main Workshop |  |  | submitted | MDW-39239 | Access Panel Closeout for Traction Substation Room in Main Workshop | Test Procedure
| 6 | MDW-69247 | OLW-ME-24/0445 18 pages | 2026-07-15 | A | Internal Only | Test Procedure - Driver Train Simulation Room and Train Crew Office at OR18 - Civil & AR |  |  | submitted | MDW-39240 | Driver Train Simulation Room and Train Crew Office at OR18 - Civil & AR | Test Procedure
| 6 | MDW-69249 | OLW-ME-24/0318 | 2026-03-12 | A | Internal Only | Test Procedure - Driver Train Simulation Room and Train Crew Office at OR18 - Building Services |  |  | submitted | MDW-39241 | Driver Train Simulation Room and Train Crew Office at OR18 - Building Services | Test Procedure
| 6 | MDW-69251 | OLW-ME-24/0324 | 2026-03-16 | A | Internal Only | Test Procedure - Modification Works for Training Room at Ratchada Station |  |  | submitted | MDW-39242 | Modification Works for Training Room at Ratchada Station | Test Procedure
| 6 | MDW-69253 | OLW-ME-24/0297 | 2026-02-18 | A | Internal Only | Test Procedure - Eye Adaptation Lighting at Transition Area and Depot Approach |  |  | submitted | MDW-39001 | Eye Adaptation Lighting at Transition Area and Depot Approach | Test Procedure
| 6 | MDW-69255 |  |  |  |  | Test Procedure - AFC Training Room Modification - Civil & AR |  |  |  | MDW-39244 | AFC Training Room Modification - Civil & AR | Test Procedure
| 6 | MDW-69257 | OLW-ME-24/0342 | 2026-03-24 | A | Internal Only | Test Procedure - AFC Training Room Modification - Building Services |  |  | submitted | MDW-39245 | AFC Training Room Modification - Building Services | Test Procedure
| 6 | MDW-69259 | OLW-ME-24/0363 | 2026-04-20 | A | Internal Only | Test Procedure - Power Outlet Installation in SOR, Ticket Office and Cash Handling OR13 - OR29 |  |  | submitted | MDW-39246-8 | Power Outlet Installation in SOR, Ticket Office and Cash Handling OR13 - OR29 | Test Procedure
| 6 | MDW-69263 | OLW-ME-24/0446 9 pages | 2026-07-15 | A | Internal Only | Test Procedure - SOR Counter and Workstation Hanging Support Installation on East Section |  |  | submitted | MDW-39249 | SOR Counter and Workstation Hanging Support Installation on East Section | Test Procedure
| 6 | MDW-69265 | OLW-ME-24/0447 8 pages | 2026-07-15 | A | Internal Only | Test Procedure - Ticket Office Modification on East Section |  |  | submitted | MDW-39250 | Ticket Office Modification on East Section | Test Procedure
| 6 | MDW-69267 |  |  |  |  | Test Procedure - Modification of Eletrical System in Telecommunication Room at OR14 |  |  | CANCLE | MDW-39251 | Modification of Eletrical System in Telecommunication Room at OR14 | Test Procedure
| 6 | MDW-69269 | OLW-ME-24/0334 | 2026-03-23 | A | Internal Only | Test Procedure - Modification of Ventilation System, Fire Suspression System (N2) in Telecommunication Room at OR14 |  |  | submitted | MDW-39252 | Modification of Ventilation System, Fire Suspression System (N2) in Telecommunication Room at OR14 | Test Procedure
| 6 | MDW-69271 | OLW-ME-24/0458 15 pages | 2026-07-15 | A | Internal Only | Test Procedure - Modification of Civil Work in Telecommunication Room at OR14 |  |  | submitted | MDW-39253 | Modification of Civil Work in Telecommunication Room at OR14 | Test Procedure
| 6 | MDW-69273 | OLW-ME-24/0364 | 2026-04-20 | A | Internal Only | Test Procedure - Modification in Staff Mess Room at OR13-OR29 |  |  | submitted | MDW-39254-6 | Modification in Staff Mess Room at OR13-OR29 | Test Procedure
| 6 | MDW-69277 | OLW-ME-24/0337 | 2026-03-24 | A | Internal Only | Test Procedure - Modification of Air Conditioning in CER and SER at OR13-OR29 |  |  | submitted | MDW-39257-9 | Modification of Air Conditioning in CER and SER at OR13-OR29 | Test Procedure
| 6 | MDW-69281 | OLW-ME-24/0340 | 2026-03-24 | A | Internal Only | Test Procedure - Modification of Air Conditioning in M&E Room at OCC Building |  |  | submitted | MDW-39260 | Modification of Air Conditioning in M&E Room at OCC Building | Test Procedure
| 6 | MDW-69283 | OLW-ME-24/0310 | 2026-02-25 | A | Internal Only | Test Procedure - Provision of UPS for MDB Control at Main Workshop, OCC Building, Admin Building, Stabling Yard and Train Washing Plant |  |  | submitted | MDW-39261 | Provision of UPS for MDB Control at Main Workshop, OCC Building, Admin Building, Stabling Yard and Train Washing Plant | Test Procedure
| 6 | MDW-69285 | OLW-ME-24/0304 | 2026-02-18 | A | Internal Only | Test Procedure - Provision of Redundant MDB at OCC Building, Admin Building and Canteen |  |  | submitted | MDW-39262 | Provision of Redundant MDB at OCC Building, Admin Building and Canteen | Test Procedure
| 6 | MDW-69287 | OLW-ME-24/0322 | 2026-03-14 | A | Internal Only | Test Procedure - Additonal Lighting System at Depot Area |  |  | submitted | MDW-39263 | Additonal Lighting System at Depot Area | Test Procedure
| 6 | MDW-69289 |  |  |  |  | Test Procedure - Block-out and Holes Modification at Depot Platform |  |  | CANCLE | MDW-39264 | Block-out and Holes Modification at Depot Platform | Test Procedure
| 6 | MDW-69291 |  |  |  |  | Test Procedure - Main Cable Containment Modification at Depot |  |  |  | MDW-39231 | Main Cable Containment Modification at Depot | Test Procedure
| 6 | MDW-69293 |  |  |  |  | Test Procedure - PSY Wayside Cable Containment for 24 KV Cable under Depot slab |  |  | CANCLE | MDW-39269 | PSY Wayside Cable Containment for 24 KV Cable under Depot slab | Test Procedure
| 6 | MDW-69295 |  |  |  |  | Test Procedure - SIG/COM Wayside Cable Containment in Depot |  |  |  | MDW-39270 | SIG/COM Wayside Cable Containment in Depot | Test Procedure
| 6 | MDW-69297 | OLW-ME-24/0460 11 pages | 2026-07-15 | A | Internal Only | Test Procedure - Wayside Cable Trough in Depot |  |  | submitted | MDW-39271 | Wayside Cable Trough in Depot | Test Procedure
| 6 | MDW-69299 | OLW-ME-24/0461 13 pages | 2026-07-15 | A | Internal Only | Test Procedure - Modification of New M&E Room at IVS15 - IVS17 Civil & AR |  |  | submitted | MDW-39272 | Modification of New M&E Room at IVS15 - IVS17 Civil & AR | Test Procedure
| 6 | MDW-69301 | OLW-ME-24/0343 | 2026-03-24 | A | Internal Only | Test Procedure - Modification of New M&E UPS Room at IVS15-IVS17 - Building Services |  |  | submitted | MDW-39273 | Modification of New M&E UPS Room at IVS15-IVS17 - Building Services | Test Procedure
| 6 | MDW-69303 | เตรียมออก 7/8/26 OLW-ME-24/0513 total 10 pages |  | A | Internal Only | Test Procedure - Ticket Issuing Machine (TIM) Wall Opening and Closing East Section |  |  |  | MDW-39276 | Ticket Issuing Machine (TIM) Wall Opening and Closing East Section | Test Procedure
| 6 | MDW-69305 |  |  |  | Internal Only | Test Procedure - Modification Works for AFC - Balustrade Modification Along AFC Gate Line East Section |  |  |  | MDW-39277 | Modification Works for AFC - Balustrade Modification Along AFC Gate Line East Section | Test Procedure
| 6 | MDW-69307 |  |  |  | Internal Only | Test Procedure - Underfloor Embedded Duct Modification for AFC Gates Line East Section |  |  |  | MDW-39278 | Underfloor Embedded Duct Modification for AFC Gates Line East Section | Test Procedure
| 6 | MDW-69309 |  |  |  | Internal Only | Test Procedure - Balustrade Modification Along AFC Gate Line East Section |  |  |  | MDW-39279 | Balustrade Modification Along AFC Gate Line East Section | Test Procedure
| 6 | MDW-69311 |  |  |  | Internal Only | Test Procedure - Platform Finishing on East Section |  |  |  | MDW-39280 | Platform Finishing on East Section | Test Procedure
| 6 | MDW-69313 |  |  |  | Internal Only | Test Procedure - Cladding Barrier between EWD and Station Structure on East Section |  |  |  | MDW-39281 | Cladding Barrier between EWD and Station Structure on East Section | Test Procedure
| 6 | MDW-69315 |  |  |  | Internal Only | Test Procedure - Holes for PSD Cable Wiring on East Section |  |  |  | MDW-39282 | Holes for PSD Cable Wiring on East Section | Test Procedure
| 6 | MDW-69317 |  |  |  | Internal Only | Test Procedure - Intercom System in Cash Handling Room East Section |  |  |  | MDW-39283 | Intercom System in Cash Handling Room East Section | Test Procedure
| 6 | MDW-69319 |  |  |  |  | Test Procedure - Power Cable and Conduits Modification for Walk-Through Metal Detector East Section |  |  | CANCLE | MDW-39284 | Power Cable and Conduits Modification for Walk-Through Metal Detector East Section | Test Procedure
| 6 | MDW-69321 |  |  |  |  | Test Procedure - Underground Cable Containment at Station Public Areas East Section |  |  | CANCLE | MDW-39286 | Underground Cable Containment at Station Public Areas East Section | Test Procedure
| 6 | MDW-69323 |  |  |  |  | Test Procedure - Strobe Light at Buffer Stops East Section |  |  | CANCLE | MDW-39287 | Strobe Light at Buffer Stops East Section | Test Procedure
| 6 | MDW-69325 | OLW-ME-24/0319 | 2026-03-14 | A | Internal Only | Test Procedure - Strobe Light at Buffer Stops East Section |  |  | submitted | MDW-39287 | Strobe Light at Buffer Stops East Section | Test Procedure
| 6 | MDW-69327 |  |  |  | Internal Only | Test Procedure - Point Machine Foundation Construction on East Section |  |  |  | MDW-39288 | Point Machine Foundation Construction on East Section | Test Procedure
| 6 | MDW-69329 | OLW-ME-24/0315 | 2026-03-09 | A | Internal Only | Test Procedure - Earthing and Bonding for Raised Floor on East Section |  |  | submitted | MDW-39289 | Earthing and Bonding for Raised Floor on East Section | Test Procedure
| 6 | MDW-69331 | OLW-ME-24/0333 | 2026-03-23 | A | Internal Only | Test Procedure - Modification Room for PSY at Depot Buildings - Building Services |  |  | submitted | MDW-39290 | Modification Room for PSY at Depot Buildings - Building Services | Test Procedure
| 6 | MDW-69333 | เตรียมออก 10/7/26 OLW-ME-24/0472 |  |  | Internal Only | Test Procedure - Conductor Rail Arrangement Modification at Main Line East Section |  |  |  | MDW-39291 | Conductor Rail Arrangement Modification at Main Line East Section | Test Procedure
| 6 | MDW-69335 |  |  |  | Internal Only | Test Procedure - Conductor Rail Arrangement Modification at Depot |  |  |  | MDW-39292 | Conductor Rail Arrangement Modification at Depot | Test Procedure
| 6 | MDW-69337 |  |  |  | Internal Only | Test Procedure - Stabling Walkway Modification at Stabling Yard - Civil & AR |  |  |  | MDW-39293 | Stabling Walkway Modification at Stabling Yard - Civil & AR | Test Procedure
| 6 | MDW-69339 | OLW-ME-24/0462 11 pages | 2026-07-15 | A | Internal Only | Test Procedure - Provision of Architectural Work in new M&E UPS room at OR23 |  |  | submitted | MDW-39294 | Provision of Architectural Work in new M&E UPS room at OR23 | Test Procedure
| 6 | MDW-69341 | เตรียมออก 7/8/26 OLW-ME-24/0514 11 pages |  | A | Internal Only | Test Procedure - Dangerous Goods Building in Depot - Civil & AR |  |  |  | MDW-39295 | Dangerous Goods Building in Depot - Civil & AR | Test Procedure
| 6 | MDW-69343 | OLW-ME-24/0358 | 2026-04-01 | A | Internal Only | Test Procedure - Dangerous Goods Building in Depot - Building Services |  |  | submitted | MDW-39296 | Dangerous Goods Building in Depot - Building Services | Test Procedure
| 6 | MDW-69345 | เตรียมออก 21/7/26 OLW-ME-24/0463 11 pages |  |  | Internal Only | Test Procedure - Training Room at Ratchada Station (Part 2) |  |  |  | MDW-39297 | Training Room at Ratchada Station (Part 2) | Test Procedure
| 6 | MDW-69347 |  |  |  | Internal Only | Test Procedure - Training Room at Ratchada Station (Part 2) - Building Services |  |  | CANCLE | MDW-39298 | Training Room at Ratchada Station (Part 2) - Building Services | Test Procedure
| 6 | MDW-69349 | OLW-ME-24/0357 | 2026-04-01 | A | Internal Only | Test Procedure - Provision of Air Conditioning System in Commercial Room at OR13-OR19 |  |  | submitted | MDW-39299 | Provision of Air Conditioning System in Commercial Room at OR13-OR19 | Test Procedure
| 6 | MDW-69351 | OLW-ME-24/0345 | 2026-03-24 | A | Internal Only | Test Procedure - Modification SIG-PSD Office at Main Workshop - Building Services |  |  | submitted | MDW-39300 | Modification SIG-PSD Office at Main Workshop - Building Services | Test Procedure
| 6 | MDW-69353 | OLW-ME-24/0346 | 2026-03-24 | A | Internal Only | Test Procedure - Modification Backup CCR Room at Main Workshop - Building Services |  |  | submitted | MDW-39301 | Modification Backup CCR Room at Main Workshop - Building Services | Test Procedure
| 6 | MDW-69355 | OLW-ME-24/0347 | 2026-03-24 | A | Internal Only | Test Procedure - Modification SER at Main Workshop - Building Services |  |  | submitted | MDW-39302 | Modification SER at Main Workshop - Building Services | Test Procedure
| 6 | MDW-69357 | OLW-ME-24/0348 | 2026-03-31 | A | Internal Only | Test Procedure - Modification CER & SCADA Room at Main Workshop - Building Services |  |  | submitted | MDW-39303 | Modification CER & SCADA Room at Main Workshop - Building Services | Test Procedure
| 6 | MDW-69359 |  |  |  | Internal Only | Test Procedure - MEA Radio |  |  |  | MDW-39304 | MEA Radio | Test Procedure
| 6 | MDW-69361 | เตรียมออก 7/8/26 OLW-ME-24/0515 total 8 pages |  | A | Internal Only | Test Procedure - Safety Provision for Maintenance Pits |  |  |  | DWE-39xxx | Safety Provision for Maintenance Pits | Test Procedure
| 6 | MDW-69363 | OLW-ME-24/0414 | 2026-06-10 | A | Internal Only | Test Procedure - Modification CER and First Aid Room at OR14 - Building Services |  |  | submitted | MDW-39306 | Modification CER and First Aid Room at OR14 - Building Services | Test Procedure
| 6 | MDW-69365 | เตรียมออก 7/8/26 OLW-ME-24/0516 total 8 pages |  | A | Internal Only | Test Procedure - Additional Fence at Back of House OR13 - OR22 and IVS East Section |  |  |  | MDW-39307 | Additional Fence at Back of House OR13 - OR22 and IVS East Section | Test Procedure
| 6 | MDW-69367 |  |  |  | Internal Only | Test Procedure - Additional Locking Devices for Main Line Tandem Turnouts 2007, 2010 & 2013 and Depot Turnout D16 |  |  |  | MDW-39308 | Additional Locking Devices for Main Line Tandem Turnouts 2007, 2010 & 2013 and Depot Turnout D16 | Test Procedure
| 6 | MDW-69369 |  |  |  |  | Test Procedure - Modification Air Conditioning System at CCR |  |  |  | MDW-39309 | Modification Air Conditioning System at CCR | Test Procedure
| 6 | MDW-69371 |  |  |  |  | Test Procedure - Modification AFC Training Center at OR19 - Civil & AR |  |  |  | MDW-39310 | Modification AFC Training Center at OR19 - Civil & AR | Test Procedure
| 6 | MDW-69373 |  |  |  |  | Test Procedure - Modification AFC Training Center at OR19 - Building Services |  |  |  | MDW-39311 | Modification AFC Training Center at OR19 - Building Services | Test Procedure
| 6 | MDW-69375 |  |  |  |  | Test Procedure - Modification Electronic Workshop at Main Workshop - Building Services |  |  |  | MDW-39312 | Modification Electronic Workshop at Main Workshop - Building Services | Test Procedure
| 6 | MDW-69377 |  |  |  |  | Test Procedure - Modification Battery Charger Room at Main Workshop - Building Services |  |  |  | MDW-39313 | Modification Battery Charger Room at Main Workshop - Building Services | Test Procedure
| 6 | MDW-69379 |  |  |  |  | Test Procedure - Modification Machining Room at Main Workshop - Building Services |  |  |  | MDW-39314 | Modification Machining Room at Main Workshop - Building Services | Test Procedure
| 6 | MDW-69381 |  |  |  |  | Test Procedure - Modification Paint Shop Room at Main Workshop - Building Services |  |  |  | MDW-39315 | Modification Paint Shop Room at Main Workshop - Building Services | Test Procedure
| 6 | MDW-69383 |  |  |  |  | Test Procedure - Modification Electronic Workshop, Battery Charger, Machining and Paint Shop at Main Workshop - Civil & AR |  |  |  | MDW-39316 | Modification Electronic Workshop, Battery Charger, Machining and Paint Shop at Main Workshop - Civil & AR | Test Procedure
| 6 | MDW-69500 | เตรียมออก 7/8/26 OLW-ME-24/0517 total 19 pages |  | A | Internal Only | Test Procedure - Modification Works : Storage Office in Main Workshop - Civil & AR |  |  |  | MDW-39500 | Modification Works : Storage Office in Main Workshop - Civil & AR | Test Procedure
| 6 | MDW-69502 | OLW-ME-24/374 | 2026-05-05 | A | Internal Only | Test Procedure - Modification Works : Storage Office in Main Workshop - Building Services |  |  | submitted | MDW-39501 | Modification Works : Storage Office in Main Workshop - Building Services | Test Procedure
| 6 | MDW-69504 |  |  |  | Internal Only | Test Procedure - Modification Works : all Fire Alarm System Controller in Depot |  |  | CANCLE | MDW-39502 | Modification Works : all Fire Alarm System Controller in Depot | Test Procedure
| 6 | MDW-69506 | เตรียมออก 7/8/26 OLW-ME-24/0518 total 12 pages |  |  | Internal Only | Test Procedure - Modification Works : New MMC at Admin Building - Civil & AR |  |  |  | MDW-39503 | Modification Works : New MMC at Admin Building - Civil & AR | Test Procedure
| 6 | MDW-69508 | เตรียมออก 31/7/26 OLW-ME-24/0477 Total 41 pages |  |  | Internal Only | Test Procedure - Modification Works : New MMC at Admin Building - Building Services |  |  |  | MDW-39504 | Modification Works : New MMC at Admin Building - Building Services | Test Procedure
| 6 | MDW-69510 | OLW-ME-24/0485 total 22 pages | 2026-07-24 | A | Internal Only | Test Procedure - Modification Works : Walkway with Roof from Main Workshop to Stabling Yard - Civil & AR |  |  | submitted | MDW-39505 | Modification Works : Walkway with Roof from Main Workshop to Stabling Yard - Civil & AR | Test Procedure
| 6 | MDW-69512 | OLW-ME-24/0373 | 2026-05-05 | A | Internal Only | Test Procedure - Modification Works : Walkway with Roof from Main Workshop to Stabling Yard - Building Services |  |  | submitted | MDW-39506 | Modification Works : Walkway with Roof from Main Workshop to Stabling Yard - Building Services | Test Procedure
| 6 | MDW-69514 | OLW-ME-24/0486 10 pages | 2026-07-24 | A | Internal Only | Test Procedure - Modification Works : High Roof in front of MWS Entrance and Store Entrance - Civil & AR |  |  | submitted | MDW-39507 | Modification Works : High Roof in front of MWS Entrance and Store Entrance - Civil & AR | Test Procedure
| 6 | MDW-69516 |  |  |  | Internal Only | Test Procedure - Modification Works : High Roof in front of MWS Entrance and Store Entrance - Building Services |  |  | CANCLE | MDW-39508 | Modification Works : High Roof in front of MWS Entrance and Store Entrance - Building Services | Test Procedure
| 6 | MDW-69518 | OLW-ME-24/0487 10 pages | 2026-07-24 | A | Internal Only | Test Procedure - Modification Works : High Roof at Under Floor Wheel Lathe - Civil & AR |  |  | submitted | MDW-39509 | Modification Works : High Roof at Under Floor Wheel Lathe - Civil & AR | Test Procedure
| 6 | MDW-69520 |  |  |  | Internal Only | Test Procedure - Modification Works : High Roof at Under Floor Wheel Lathe - Building Services |  |  | CANCLE | MDW-39510 | Modification Works : High Roof at Under Floor Wheel Lathe - Building Services | Test Procedure
| 6 | MDW-69522 | OLW-ME-24/0464 11 pages | 2026-07-15 | A | Internal Only | Test Procedure - Modification Works : Maintenance Office Rooms at Main Workshop - Civil & AR |  |  | submitted | MDW-39511 | Modification Works : Maintenance Office Rooms at Main Workshop - Civil & AR | Test Procedure
| 6 | MDW-69524 | OLW-ME-24/0415 | 2026-06-10 | A | Internal Only | Test Procedure - Modification Works : Maintenance Office Rooms at Main Workshop - Building Services |  |  | submitted | MDW-39512 | Modification Works : Maintenance Office Rooms at Main Workshop - Building Services | Test Procedure
| 6 | MDW-69526 |  |  |  | Internal Only | Test Procedure - Modification Works : Concrete Car Barrier in front of Main Workshop |  |  |  | MDW-39513 | Modification Works : Concrete Car Barrier in front of Main Workshop | Test Procedure
| 6 | MDW-69528 | OLW-ME-24/0488 total 12 pages | 2026-07-24 | A | Internal Only | Test Procedure - Modification Works : Car Park Roof and Motorcycle in Depot - Civil & AR |  |  | submitted | MDW-39514 | Modification Works : Car Park Roof and Motorcycle in Depot - Civil & AR | Test Procedure
| 6 | MDW-69530 | OLW-ME-24/0391 | 2026-05-18 | A | Internal Only | Test Procedure - Modification Works : Car Park Roof and Motorcycle in Depot - Building Services |  |  | submitted | MDW-39515 | Modification Works : Car Park Roof and Motorcycle in Depot - Building Services | Test Procedure
| 6 | MDW-69532 | OLW-ME-24/0489 total 16 pages | 2026-07-24 | A | Internal Only | Test Procedure - Modification Works : Walkway Bridge between BL Depot and ORL Depot - Civil & AR |  |  | submitted | MDW-39516 | Modification Works : Walkway Bridge between BL Depot and ORL Depot - Civil & AR | Test Procedure
| 6 | MDW-69534 | OLW-ME-24/0417 | 2025-06-16 | A | Internal Only | Test Procedure - Modification Works : Walkway Bridge between BL Depot and ORL Depot - Building Services |  |  | submitted | MDW-39517 | Modification Works : Walkway Bridge between BL Depot and ORL Depot - Building Services | Test Procedure
| 6 | MDW-69536 | OLW-ME-24/0332 | 2026-03-23 | A | Internal Only | Test Procedure - Modification Works : Street Lighting between MRTA Fence and Depot Slab |  |  | submitted | MDW-39518 | Modification Works : Street Lighting between MRTA Fence and Depot Slab | Test Procedure
| 6 | MDW-69538 | OLW-ME-24/0490 total 17 pages | 2026-07-24 | A | Internal Only | Test Procedure - Modification Works : Walkway with Roof in Depot Area - Civil & AR |  |  | submitted | MDW-39519 | Modification Works : Walkway with Roof in Depot Area - Civil & AR | Test Procedure
| 6 | MDW-69540 | OLW-ME-24/0478 22 pages | 2026-07-15 | A | Internal Only | Test Procedure - Modification Works : Sliding Gate, Chain Link Fence and Walkway with Roof in Depot Area - Building Services |  |  | submitted | MDW-39520 | Modification Works : Sliding Gate, Chain Link Fence and Walkway with Roof in Depot Area - Building Services | Test Procedure
| 6 | MDW-69542 | OLW-ME-24/0491 total 10 pages | 2026-07-24 | A | Internal Only | Test Procedure - Modification Works : Walkway Bridge and Walkway over Canal in Depot |  |  | submitted | MDW-39521 | Modification Works : Walkway Bridge and Walkway over Canal in Depot | Test Procedure
| 6 | MDW-69544 | OLW-ME-24/0492 total 16 pages | 2026-07-24 | A | Internal Only | Test Procedure - Modification Works : Rain Protection and Zero Discharge Water treatment in Depot - Civil & AR |  |  | submitted | MDW-39522 | Modification Works : Rain Protection and Zero Discharge Water treatment in Depot - Civil & AR | Test Procedure
| 6 | MDW-69546 | OLW-ME-24/0349 | 2026-03-31 | A | Internal Only | Test Procedure - Modification Works : Cold Water System at Admin Building Landscape |  |  | submitted | MDW-39523 | Modification Works : Cold Water System at Admin Building Landscape | Test Procedure
| 6 | MDW-69548 |  |  |  | Internal Only | Test Procedure - Modification Works : Walkway under Depot Slab for Maintenance Service - Civil & AR |  |  |  | MDW-39524 | Modification Works : Walkway under Depot Slab for Maintenance Service - Civil & AR | Test Procedure
| 6 | MDW-69550 | OLW-ME-24/0418 | 2026-06-10 | A | Internal Only | Test Procedure - Modification Works : Walkway under Depot Slab for Maintenance Service - Building Services |  |  | submitted | MDW-39525 | Modification Works : Walkway under Depot Slab for Maintenance Service - Building Services | Test Procedure
| 6 | MDW-69552 | OLW-ME-24/0328 | 2026-03-18 | A | Internal Only | Test Procedure - Modification Works : FHC Modification at Stabling Yard |  |  | submitted | MDW-39526 | Modification Works : FHC Modification at Stabling Yard | Test Procedure
| 6 | MDW-69554 | OLW-ME-24/0361 | 2026-04-01 | A | Internal Only | Test Procedure - Modification Works : Hand Sink with Emergency Eye Wash Installation in Depot |  |  | submitted | MDW-39527 | Modification Works : Hand Sink with Emergency Eye Wash Installation in Depot | Test Procedure
| 6 | MDW-69556 | OLW-ME-24/0493 9 pages | 2026-07-24 | A | Internal Only | Test Procedure - Modification Works : Washing Area in Cleaning Staff Room at Stabling Yard - Civil & AR |  |  | submitted | MDW-39528 | Modification Works : Washing Area in Cleaning Staff Room at Stabling Yard - Civil & AR | Test Procedure
| 6 | MDW-69558 | OLW-ME-24/0350 | 2026-03-31 | A | Internal Only | Test Procedure - Modification Works : Washing Area in Cleaning Staff Room at Stabling Yard - Building Services |  |  | submitted | MDW-39529 | Modification Works : Washing Area in Cleaning Staff Room at Stabling Yard - Building Services | Test Procedure
| 6 | MDW-69560 | OLW-ME-24/0360 | 2026-04-01 | A | Internal Only | Test Procedure - Modification Works : Zero Discharge Water treatment in Depot - Building Services |  |  | submitted | MDW-39530 | Modification Works : Zero Discharge Water treatment in Depot - Building Services | Test Procedure
| 6 | MDW-69562 | OLW-ME-24/0465 8 pages | 2026-07-15 | A | Internal Only | Test Procedure - Modification Works : Guard rail protection for FHC in Depot Area |  |  | submitted | MDW-39531 | Modification Works : Guard rail protection for FHC in Depot Area | Test Procedure
| 6 | MDW-69564 | เตรียมออก 1/7/26 OLW-ME-24/0421 |  |  | Internal Only | Test Procedure - Modification Works : Barbed Wire Fences for MRTA Chain Link at Klong Chourdyai |  |  |  | MDW-39532 | Modification Works : Barbed Wire Fences for MRTA Chain Link at Klong Chourdyai | Test Procedure
| 6 | MDW-69566 | เตรียมออก 26/6/26 OLW-ME-24/0422 | 11 หน้า |  | Internal Only | Test Procedure - Modification Works : Car Barrier Gate at Depot Area |  |  |  | MDW-39533 | Modification Works : Car Barrier Gate at Depot Area | Test Procedure
| 6 | MDW-69568 |  |  |  | Internal Only | Test Procedure - Modification Works : Security Guard Box at ORL Depot Entrance - Civil & AR |  |  |  | MDW-39534 | Modification Works : Security Guard Box at ORL Depot Entrance - Civil & AR | Test Procedure
| 6 | MDW-69570 | OLW-ME-24/0479 24 pages | 2026-07-15 | A | Internal Only | Test Procedure - Modification Works : Security Guard Box at ORL Depot Entrance - Building Services |  |  | submitted | MDW-39535 | Modification Works : Security Guard Box at ORL Depot Entrance - Building Services | Test Procedure
| 6 | MDW-69572 |  |  |  | Internal Only | Test Procedure - Modification Works : Soundproof Installation and Company Logo at CCR Room |  |  |  | MDW-39536 | Modification Works : Soundproof Installation and Company Logo at CCR Room | Test Procedure
| 6 | MDW-69574 |  |  |  | Internal Only | Test Procedure - Modification Works : Fence Installation at Ladder in VS, IVS Buildings |  |  |  | MDW-39537 | Modification Works : Fence Installation at Ladder in VS, IVS Buildings | Test Procedure
| 6 | MDW-69576 |  |  |  | Internal Only | Test Procedure - Modification Works : Anti-Slide Signage at Escalator for all Stations |  |  |  | MDW-39538 | Modification Works : Anti-Slide Signage at Escalator for all Stations | Test Procedure
| 6 | MDW-69578 |  |  |  | Internal Only | Test Procedure - Modification Works : Roofing over Control Panel Installation at VS, IVS Buildings |  |  |  | MDW-39539 | Modification Works : Roofing over Control Panel Installation at VS, IVS Buildings | Test Procedure
| 6 | MDW-69580 |  |  |  | Internal Only | Test Procedure - Modification Works : Water Drop Protection for UPS Cabinet for all Stations and Depot |  |  |  | MDW-39540 | Modification Works : Water Drop Protection for UPS Cabinet for all Stations and Depot | Test Procedure
| 6 | MDW-69582 |  |  |  | Internal Only | Test Procedure - Modification Works : Manual Call Point Cover in Public Area at all Stations |  |  |  | MDW-39541 | Modification Works : Manual Call Point Cover in Public Area at all Stations | Test Procedure
| 6 | MDW-69584 |  |  |  | Internal Only | Test Procedure - Modification Works : Emergency Stop Button Cover for Escalator at all Stations |  |  |  | MDW-39542 | Modification Works : Emergency Stop Button Cover for Escalator at all Stations | Test Procedure
| 6 | MDW-69586 |  |  |  | Internal Only | Test Procedure - Modification Works : Bird & Rain Protetion, Safety Hand Rail Installation at Admin Building |  |  |  | MDW-39543 | Modification Works : Bird & Rain Protetion, Safety Hand Rail Installation at Admin Building | Test Procedure
| 6 | MDW-69588 |  |  |  | Internal Only | Test Procedure - Modification Works : Barbed Wire Fences for Depot slab |  |  |  | MDW-39544 | Modification Works : Barbed Wire Fences for Depot slab | Test Procedure
| 6 | MDW-69590 | OLW-ME-24/0494 total 8 pages | 2026-07-24 | A | Internal Only | Test Procedure - Modification Works : Chain Link Installation at Cut & Cover Depot Access |  |  | submitted | MDW-39545 | Modification Works : Chain Link Installation at Cut & Cover Depot Access | Test Procedure
| 6 | MDW-69592 |  |  |  | Internal Only | Test Procedure - Modification Works : Chain Link Installation under Depot Slab |  |  |  | MDW-39546 | Modification Works : Chain Link Installation under Depot Slab | Test Procedure
| 6 | MDW-69594 | OLW-ME-24/0467 13 pages | 2026-07-15 | A | Internal Only | Test Procedure - Modification Works : Door and Lockset Modification at OCC Building |  |  | submitted | MDW-39547 | Modification Works : Door and Lockset Modification at OCC Building | Test Procedure
| 6 | MDW-69596 | OLW-ME-24/0351 | 2026-03-31 | A | Internal Only | Test Procedure - Modification Works : Air Conditioning System Installation at Pantry room OCC Building |  |  | submitted | MDW-39548 | Modification Works : Air Conditioning System Installation at Pantry room OCC Building | Test Procedure
| 6 | MDW-69598 | OLW-ME-24/0362 | 2026-04-01 | A | Internal Only | Test Procedure - Maintenance Room and Satellite Store at Stations - Building Services |  |  | submitted | MDW-39549 | Maintenance Room and Satellite Store at Stations - Building Services | Test Procedure
| 6 | MDW-69600 |  |  |  | Internal Only | Test Procedure - Satellite Store at OR21 - Civil & AR |  |  |  | MDW-39550 | Satellite Store at OR21 - Civil & AR | Test Procedure
| 6 | MDW-69602 | OLW-ME-24/0359 | 2026-04-01 | A | Internal Only | Test Procedure - Modification Works : Train Crew Office at OR29 |  |  | submitted | MDW-39551 | Modification Works : Train Crew Office at OR29 | Test Procedure
| 6 | MDW-69604 | เตรียมออก 6/8/26 OLW-ME-24/0520 total 8 pages |  | A | Internal Only | Test Procedure - Modification Works : Hand Rail Installation at Walk Way in Stabling Yard |  |  |  | MDW-39552 | Modification Works : Hand Rail Installation at Walk Way in Stabling Yard | Test Procedure
298 | 6 | MDW-69606 |  |  |  | Internal Only | Test Procedure - Modification Works : Ladder to Access the Fire Valve at Omega Joints for all Underground Stations |  |  |  | MDW-39553 | Modification Works : Ladder to Access the Fire Valve at Omega Joints for all Underground Stations | Test Procedure
| 6 | MDW-69608 |  |  |  | Internal Only | Test Procedure - Modification Works : Security Guard Box at OCC Parking Area - Civil & AR |  |  |  | MDW-39554 | Modification Works : Security Guard Box at OCC Parking Area - Civil & AR | Test Procedure
| 6 | MDW-69610 |  |  |  | Internal Only | Test Procedure - Modification Works : Security Guard Box at OCC Parking Area - Building Services |  |  |  | MDW-39555 | Modification Works : Security Guard Box at OCC Parking Area - Building Services | Test Procedure
| 6 | MDW-69612 | OLW-ME-24/0372 | 2026-05-05 | A | Internal Only | Test Procedure - Modification Works : Addition Small Power System at OCC Building |  |  | submitted | MDW-39556 | Modification Works : Addition Small Power System at OCC Building | Test Procedure
| 6 | MDW-69614 | เตรียมออก 6/8/26 OLW-ME-24/0521 9 pages |  | A | Internal Only | Test Procedure - Modification Works : Sliding Gate and Chain Link Fence in Depot Area - Civil & AR |  |  |  | MDW-39557 | Modification Works : Sliding Gate and Chain Link Fence in Depot Area - Civil & AR | Test Procedure
| 6 | MDW-69002 |  |  |  |  | Test Report - Modification of Depot Track Alignment at Stabling Yard |  |  |  | MDW-39001 | Modification of Depot Track Alignment at Stabling Yard | Test Report
| 6 | MDW-69004 |  |  |  |  | Test Report - Modification Motorized Gate and Shelters at Test Track Depot - Civil & AR |  |  |  | MDW-39002 | Modification Motorized Gate and Shelters at Test Track Depot - Civil & AR | Test Report
| 6 | MDW-69006 |  |  |  |  | Test Report - Modification Motorized Gate and Shelters at Test Track Depot - Building Service |  |  |  | MDW-39003 | Modification Motorized Gate and Shelters at Test Track Depot - Building Service | Test Report
| 6 | MDW-69008 |  |  |  |  | Test Report - Rubber Gap Fillers on Platform Edge on East Section |  |  |  | MDW-39004 | Rubber Gap Fillers on Platform Edge on East Section | Test Report
| 6 | MDW-69201 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of OR13 |  |  |  | MDW-39201 | Modification Work of M&E Cable Containment of OR13 | Test Report
| 6 | MDW-69202 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of OR14 |  |  |  | MDW-39202 | Modification Work of M&E Cable Containment of OR14 | Test Report
| 6 | MDW-69203 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of OR15 |  |  |  | MDW-39203 | Modification Work of M&E Cable Containment of OR15 | Test Report
| 6 | MDW-69204 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of OR16 |  |  |  | MDW-39204 | Modification Work of M&E Cable Containment of OR16 | Test Report
| 6 | MDW-69205 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of OR17 |  |  |  | MDW-39205 | Modification Work of M&E Cable Containment of OR17 | Test Report
| 6 | MDW-69206 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of OR18 |  |  |  | MDW-39206 | Modification Work of M&E Cable Containment of OR18 | Test Report
| 6 | MDW-69207 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of OR19 |  |  |  | MDW-39207 | Modification Work of M&E Cable Containment of OR19 | Test Report
| 6 | MDW-69208 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of OR20 |  |  |  | MDW-39208 | Modification Work of M&E Cable Containment of OR20 | Test Report
| 6 | MDW-69209 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of OR21 |  |  |  | MDW-39209 | Modification Work of M&E Cable Containment of OR21 | Test Report
| 6 | MDW-69210 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of OR22 |  |  |  | MDW-39210 | Modification Work of M&E Cable Containment of OR22 | Test Report
| 6 | MDW-69211 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of OR23 |  |  |  | MDW-39211 | Modification Work of M&E Cable Containment of OR23 | Test Report
| 6 | MDW-69212 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of OR24 |  |  |  | MDW-39212 | Modification Work of M&E Cable Containment of OR24 | Test Report
| 6 | MDW-69213 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of OR25 |  |  |  | MDW-39213 | Modification Work of M&E Cable Containment of OR25 | Test Report
| 6 | MDW-69214 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of OR26 |  |  |  | MDW-39214 | Modification Work of M&E Cable Containment of OR26 | Test Report
| 6 | MDW-69215 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of OR27 |  |  |  | MDW-39215 | Modification Work of M&E Cable Containment of OR27 | Test Report
| 6 | MDW-69216 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of OR28 |  |  |  | MDW-39216 | Modification Work of M&E Cable Containment of OR28 | Test Report
| 6 | MDW-69217 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of OR29 |  |  |  | MDW-39217 | Modification Work of M&E Cable Containment of OR29 | Test Report
| 6 | MDW-69218 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of VS02 |  |  |  | MDW-39218 | Modification Work of M&E Cable Containment of VS02 | Test Report
| 6 | MDW-69219 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of VS03 |  |  |  | MDW-39219 | Modification Work of M&E Cable Containment of VS03 | Test Report
| 6 | MDW-69220 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of IVS08 |  |  |  | MDW-39220 | Modification Work of M&E Cable Containment of IVS08 | Test Report
| 6 | MDW-69221 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of IVS09 |  |  |  | MDW-39221 | Modification Work of M&E Cable Containment of IVS09 | Test Report
| 6 | MDW-69222 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of IVS10 |  |  |  | MDW-39222 | Modification Work of M&E Cable Containment of IVS10 | Test Report
| 6 | MDW-69223 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of IVS11 |  |  |  | MDW-39223 | Modification Work of M&E Cable Containment of IVS11 | Test Report
| 6 | MDW-69224 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of IVS12 |  |  |  | MDW-39224 | Modification Work of M&E Cable Containment of IVS12 | Test Report
| 6 | MDW-69225 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of IVS13 |  |  |  | MDW-39225 | Modification Work of M&E Cable Containment of IVS13 | Test Report
| 6 | MDW-69226 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of IVS14 |  |  |  | MDW-39226 | Modification Work of M&E Cable Containment of IVS14 | Test Report
| 6 | MDW-69227 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of IVS15 |  |  |  | MDW-39227 | Modification Work of M&E Cable Containment of IVS15 | Test Report
| 6 | MDW-69228 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of IVS16 |  |  |  | MDW-39228 | Modification Work of M&E Cable Containment of IVS16 | Test Report
| 6 | MDW-69229 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of IVS17 |  |  |  | MDW-39229 | Modification Work of M&E Cable Containment of IVS17 | Test Report
| 6 | MDW-69230 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of EEEN |  |  |  | MDW-39230 | Modification Work of M&E Cable Containment of EEEN | Test Report
| 6 | MDW-69231 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of Orange Line - Depot |  |  |  | MDW-39231 | Modification Work of M&E Cable Containment of Orange Line - Depot | Test Report
| 6 | MDW-69233 |  |  |  |  | Test Report - Level Crossing at Turnout and Track Slab Crossing on Main Line East Section |  |  |  | MDW-39232 | Level Crossing at Turnout and Track Slab Crossing on Main Line East Section | Test Report
| 6 | MDW-69235 |  |  |  |  | Test Report - Main Line Cable Trough Modification on East Section (PSY) |  |  |  | MDW-39233 | Main Line Cable Trough Modification on East Section (PSY) | Test Report
| 6 | MDW-69236 |  |  |  |  | Test Report - Main Line Cable Trough Modification on East Section (SIG/COM) |  |  |  | MDW-39234 | Main Line Cable Trough Modification on East Section (SIG/COM) | Test Report
| 6 | MDW-69238 |  |  |  |  | Test Report - Raised Floor Installation on East Section |  |  |  | MDW-39235 | Raised Floor Installation on East Section | Test Report
| 6 | MDW-69240 |  |  |  |  | Test Report - Bird Protection System at Depot Buildings |  |  |  | MDW-39236 | Bird Protection System at Depot Buildings | Test Report
| 6 | MDW-69242 |  |  |  |  | Test Report - Central BEMS for the MRT Orange Line System East Section |  |  |  | MDW-39237 | Central BEMS for the MRT Orange Line System East Section | Test Report
| 6 | MDW-69244 |  |  |  |  | Test Report - Central BEMS for the MRT Orange Line System West Section |  |  |  | MDW-39238 | Central BEMS for the MRT Orange Line System West Section | Test Report
| 6 | MDW-69246 |  |  |  |  | Test Report - Access Panel Closeout for Traction Substation Room in Main Workshop |  |  |  | MDW-39239 | Access Panel Closeout for Traction Substation Room in Main Workshop | Test Report
| 6 | MDW-69248 |  |  |  |  | Test Report - Driver Train Simulation Room and Train Crew Office at OR18 - Civil & AR |  |  |  | MDW-39240 | Driver Train Simulation Room and Train Crew Office at OR18 - Civil & AR | Test Report
| 6 | MDW-69250 |  |  |  |  | Test Report - Driver Train Simulation Room and Train Crew Office at OR18 - Building Services |  |  |  | MDW-39241 | Driver Train Simulation Room and Train Crew Office at OR18 - Building Services | Test Report
| 6 | MDW-69252 | OLW-ME-24/0408 | 2026-05-24 | A |  | Test Report - Modification Works for Training Room at Ratchada Station |  |  | submitted | MDW-39242 | Modification Works for Training Room at Ratchada Station | Test Report
| 6 | MDW-69254 |  |  |  |  | Test Report - Eye Adaptation Lighting at Transition Area and Depot Approach |  |  |  | MDW-39001 | Eye Adaptation Lighting at Transition Area and Depot Approach | Test Report
| 6 | MDW-69256 |  |  |  |  | Test Report - AFC Training Room Modification - Civil & AR |  |  |  | MDW-39244 | AFC Training Room Modification - Civil & AR | Test Report
| 6 | MDW-69258 |  |  |  |  | Test Report - AFC Training Room Modification - Building Services |  |  |  | MDW-39245 | AFC Training Room Modification - Building Services | Test Report
| 6 | MDW-69260 |  |  |  |  | Test Report - Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR13 - OR17 |  |  |  | MDW-39246 | Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR13 - OR17 | Test Report
| 6 | MDW-69261 |  |  |  |  | Test Report - Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR18 - OR22 |  |  |  | MDW-39247 | Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR18 - OR22 | Test Report
| 6 | MDW-69262 |  |  |  |  | Test Report - Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR22 - OR29 |  |  |  | MDW-39248 | Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR22 - OR29 | Test Report
| 6 | MDW-69264 |  |  |  |  | Test Report - SOR Counter and Workstation Hanging Support Installation on East Section |  |  |  | MDW-39249 | SOR Counter and Workstation Hanging Support Installation on East Section | Test Report
| 6 | MDW-69266 |  |  |  |  | Test Report - Ticket Office Modification on East Section |  |  |  | MDW-39250 | Ticket Office Modification on East Section | Test Report
| 6 | MDW-69268 |  |  |  |  | Test Report - Modification of Eletrical System in Telecommunication Room at OR14 |  |  | CANCLE | MDW-39251 | Modification of Eletrical System in Telecommunication Room at OR14 | Test Report
| 6 | MDW-69270 |  |  |  |  | Test Report - Modification of Ventilation System, Fire Suspression System (N2) in Telecommunication Room at OR14 |  |  |  | MDW-39252 | Modification of Ventilation System, Fire Suspression System (N2) in Telecommunication Room at OR14 | Test Report
| 6 | MDW-69272 |  |  |  |  | Test Report - Modification of Civil Work in Telecommunication Room at OR14 |  |  |  | MDW-39253 | Modification of Civil Work in Telecommunication Room at OR14 | Test Report
| 6 | MDW-69274 |  |  |  |  | Test Report - Modification in Staff Mess Room at OR13-OR17 |  |  |  | MDW-39254 | Modification in Staff Mess Room at OR13-OR17 | Test Report
| 6 | MDW-69275 |  |  |  |  | Test Report - Modification in Staff Mess Room at OR18-OR22 |  |  |  | MDW-39255 | Modification in Staff Mess Room at OR18-OR22 | Test Report
| 6 | MDW-69276 |  |  |  |  | Test Report - Modification in Staff Mess Room at OR23-OR29 |  |  |  | MDW-39256 | Modification in Staff Mess Room at OR23-OR29 | Test Report
| 6 | MDW-69278 |  |  |  |  | Test Report - Modification of Air Conditioning in CER and SER at OR13-OR19 |  |  |  | MDW-39257 | Modification of Air Conditioning in CER and SER at OR13-OR19 | Test Report
| 6 | MDW-69279 |  |  |  |  | Test Report - Modification of Air Conditioning in CER and SER at OR20-OR22 |  |  |  | MDW-39258 | Modification of Air Conditioning in CER and SER at OR20-OR22 | Test Report
| 6 | MDW-69280 |  |  |  |  | Test Report - Modification of Air Conditioning in CER and SER at OR23-OR29 |  |  |  | MDW-39259 | Modification of Air Conditioning in CER and SER at OR23-OR29 | Test Report
| 6 | MDW-69282 |  |  |  |  | Test Report - Modification of Air Conditioning in M&E Room at OCC Building |  |  |  | MDW-39260 | Modification of Air Conditioning in M&E Room at OCC Building | Test Report
| 6 | MDW-69284 |  |  |  |  | Test Report - Provision of UPS for MDB Control at Main Workshop, OCC Building, Admin Building, Stabling Yard and Train Washing Plant |  |  |  | MDW-39261 | Provision of UPS for MDB Control at Main Workshop, OCC Building, Admin Building, Stabling Yard and Train Washing Plant | Test Report
| 6 | MDW-69286 |  |  |  |  | Test Report - Provision of Redundant MDB at OCC Building, Admin Building and Canteen |  |  |  | MDW-39262 | Provision of Redundant MDB at OCC Building, Admin Building and Canteen | Test Report
| 6 | MDW-69288 |  |  |  |  | Test Report - Additonal Lighting System at Depot Area |  |  |  | MDW-39263 | Additonal Lighting System at Depot Area | Test Report
| 6 | MDW-69290 |  |  |  |  | Test Report - Block-out and Holes Modification at Depot Platform |  |  | CANCLE | MDW-39264 | Block-out and Holes Modification at Depot Platform | Test Report
| 6 | MDW-69292 |  |  |  |  | Test Report - Main Cable Containment Modification at Depot |  |  |  | MDW-39268 | Main Cable Containment Modification at Depot | Test Report
| 6 | MDW-69294 |  |  |  |  | Test Report - PSY Wayside Cable Containment for 24 KV Cable under Depot slab |  |  | CANCLE | MDW-39269 | PSY Wayside Cable Containment for 24 KV Cable under Depot slab | Test Report
| 6 | MDW-69296 |  |  |  |  | Test Report - SIG/COM Wayside Cable Containment in Depot |  |  |  | MDW-39270 | SIG/COM Wayside Cable Containment in Depot | Test Report
| 6 | MDW-69298 |  |  |  |  | Test Report - Wayside Cable Trough in Depot |  |  |  | MDW-39271 | Wayside Cable Trough in Depot | Test Report
| 6 | MDW-69300 |  |  |  |  | Test Report - Modification of New M&E Room at IVS15 - IVS17 Civil & AR |  |  |  | MDW-39272 | Modification of New M&E Room at IVS15 - IVS17 Civil & AR | Test Report
| 6 | MDW-69302 |  |  |  |  | Test Report - Modification of New M&E UPS Room at IVS15-IVS17 - Building Services |  |  |  | MDW-39273 | Modification of New M&E UPS Room at IVS15-IVS17 - Building Services | Test Report
| 6 | MDW-69304 |  |  |  |  | Test Report - Ticket Issuing Machine (TIM) Wall Opening and Closing East Section |  |  |  | MDW-39276 | Ticket Issuing Machine (TIM) Wall Opening and Closing East Section | Test Report
| 6 | MDW-69306 |  |  |  |  | Test Report - Modification Works for AFC - Balustrade Modification Along AFC Gate Line East Section |  |  |  | MDW-39277 | Modification Works for AFC - Balustrade Modification Along AFC Gate Line East Section | Test Report
| 6 | MDW-69308 |  |  |  |  | Test Report - Underfloor Embedded Duct Modification for AFC Gates Line East Section |  |  |  | MDW-39278 | Underfloor Embedded Duct Modification for AFC Gates Line East Section | Test Report
| 6 | MDW-69310 |  |  |  |  | Test Report - Balustrade Modification Along AFC Gate Line East Section |  |  |  | MDW-39279 | Balustrade Modification Along AFC Gate Line East Section | Test Report
| 6 | MDW-69312 |  |  |  |  | Test Report - Platform Finishing on East Section |  |  |  | MDW-39280 | Platform Finishing on East Section | Test Report
| 6 | MDW-69314 |  |  |  |  | Test Report - Cladding Barrier between EWD and Station Structure on East Section |  |  |  | MDW-39281 | Cladding Barrier between EWD and Station Structure on East Section | Test Report
| 6 | MDW-69316 |  |  |  |  | Test Report - Holes for PSD Cable Wiring on East Section |  |  |  | MDW-39282 | Holes for PSD Cable Wiring on East Section | Test Report
| 6 | MDW-69318 |  |  |  |  | Test Report - Intercom System in Cash Handling Room East Section |  |  |  | MDW-39283 | Intercom System in Cash Handling Room East Section | Test Report
| 6 | MDW-69320 |  |  |  |  | Test Report - Power Cable and Conduits Modification for Walk-Through Metal Detector East Section |  |  | CANCLE | MDW-39284 | Power Cable and Conduits Modification for Walk-Through Metal Detector East Section | Test Report
| 6 | MDW-69322 |  |  |  |  | Test Report - Underground Cable Containment at Station Public Areas East Section |  |  | CANCLE | MDW-39286 | Underground Cable Containment at Station Public Areas East Section | Test Report
| 6 | MDW-69324 |  |  |  |  | Test Report - Strobe Light at Buffer Stops East Section |  |  | CANCLE | MDW-39287 | Strobe Light at Buffer Stops East Section | Test Report
| 6 | MDW-69326 |  |  |  |  | Test Report - Strobe Light at Buffer Stops East Section |  |  |  | MDW-39287 | Strobe Light at Buffer Stops East Section | Test Report
| 6 | MDW-69328 |  |  |  |  | Test Report - Point Machine Foundation Construction on East Section |  |  |  | MDW-39288 | Point Machine Foundation Construction on East Section | Test Report
| 6 | MDW-69330 |  |  |  |  | Test Report - Earthing and Bonding for Raised Floor on East Section |  |  |  | MDW-39289 | Earthing and Bonding for Raised Floor on East Section | Test Report
| 6 | MDW-69332 |  |  |  |  | Test Report - Modification Room for PSY at Depot Buildings - Building Services |  |  |  | MDW-39290 | Modification Room for PSY at Depot Buildings - Building Services | Test Report
| 6 | MDW-69334 |  |  |  |  | Test Report - Conductor Arrangement Modification at Main Line East Section |  |  |  | MDW-39291 | Conductor Arrangement Modification at Main Line East Section | Test Report
| 6 | MDW-69336 |  |  |  |  | Test Report - Conductor Rail Arrangement Modification at Depot |  |  |  | MDW-39292 | Conductor Rail Arrangement Modification at Depot | Test Report
| 6 | MDW-69338 |  |  |  |  | Test Report - Stabling Walkway Modification at Stabling Yard - Civil & AR |  |  |  | MDW-39293 | Stabling Walkway Modification at Stabling Yard - Civil & AR | Test Report
| 6 | MDW-69340 |  |  |  |  | Test Report - Provision of Architectural Work in new M&E UPS room at OR23 |  |  |  | MDW-39294 | Provision of Architectural Work in new M&E UPS room at OR23 | Test Report
| 6 | MDW-69342 |  |  |  |  | Test Report - Dangerous Goods Building in Depot - Civil & AR |  |  |  | MDW-39295 | Dangerous Goods Building in Depot - Civil & AR | Test Report
| 6 | MDW-69344 |  |  |  |  | Test Report - Dangerous Goods Building in Depot - Building Services |  |  |  | MDW-39296 | Dangerous Goods Building in Depot - Building Services | Test Report
| 6 | MDW-69346 |  |  |  |  | Test Report - Training Room at Ratchada Station (Part 2) |  |  |  | MDW-39297 | Training Room at Ratchada Station (Part 2) | Test Report
| 6 | MDW-69348 |  |  |  |  | Test Report - Training Room at Ratchada Station (Part 2) - Building Services |  |  | CANCLE | MDW-39298 | Training Room at Ratchada Station (Part 2) - Building Services | Test Report
| 6 | MDW-69350 |  |  |  |  | Test Report - Provision of Air Conditioning System in Commercial Room at OR13-OR19 |  |  |  | MDW-39299 | Provision of Air Conditioning System in Commercial Room at OR13-OR19 | Test Report
| 6 | MDW-69352 |  |  |  |  | Test Report - Modification SIG-PSD Office at Main Workshop - Building Services |  |  |  | MDW-39300 | Modification SIG-PSD Office at Main Workshop - Building Services | Test Report
| 6 | MDW-69354 |  |  |  |  | Test Report - Modification Backup CCR Room at Main Workshop - Building Services |  |  |  | MDW-39301 | Modification Backup CCR Room at Main Workshop - Building Services | Test Report
| 6 | MDW-69356 |  |  |  |  | Test Report - Modification SER at Main Workshop - Building Services |  |  |  | MDW-39302 | Modification SER at Main Workshop - Building Services | Test Report
| 6 | MDW-69358 |  |  |  |  | Test Report - Modification CER & SCADA Room at Main Workshop - Building Services |  |  |  | MDW-39303 | Modification CER & SCADA Room at Main Workshop - Building Services | Test Report
| 6 | MDW-69360 |  |  |  |  | Test Report - MEA Radio |  |  |  | MDW-39304 | MEA Radio | Test Report
| 6 | MDW-69362 |  |  |  |  | Test Report - Safety Provision for Maintenance Pits |  |  |  | DWE-39xxx | Safety Provision for Maintenance Pits | Test Report
| 6 | MDW-69364 |  |  |  |  | Test Report - Modification CER and First Aid Room at OR14 - Building Services |  |  |  | MDW-39306 | Modification CER and First Aid Room at OR14 - Building Services | Test Report
| 6 | MDW-69366 |  |  |  |  | Test Report - Additional Fence at Back of House OR13 - OR22 and IVS East Section |  |  |  | MDW-39307 | Additional Fence at Back of House OR13 - OR22 and IVS East Section | Test Report
| 6 | MDW-69368 |  |  |  |  | Test Report - Additional Locking Devices for Main Line Tandem Turnouts 2007, 2010 & 2013 and Depot Turnout D16 |  |  |  | MDW-39308 | Additional Locking Devices for Main Line Tandem Turnouts 2007, 2010 & 2013 and Depot Turnout D16 | Test Report
| 6 | MDW-69370 |  |  |  |  | Test Report - Modification Air Conditioning System at CCR |  |  |  | MDW-39309 | Modification Air Conditioning System at CCR | Test Report
| 6 | MDW-69372 |  |  |  |  | Test Report - Modification AFC Training Center at OR19 - Civil & AR |  |  |  | MDW-39310 | Modification AFC Training Center at OR19 - Civil & AR | Test Report
| 6 | MDW-69374 |  |  |  |  | Test Report - Modification AFC Training Center at OR19 - Building Services |  |  |  | MDW-39311 | Modification AFC Training Center at OR19 - Building Services | Test Report
| 6 | MDW-69376 |  |  |  |  | Test Report - Modification Electronic Workshop at Main Workshop - Building Services |  |  |  | MDW-39312 | Modification Electronic Workshop at Main Workshop - Building Services | Test Report
| 6 | MDW-69378 |  |  |  |  | Test Report - Modification Battery Charger Room at Main Workshop - Building Services |  |  |  | MDW-39313 | Modification Battery Charger Room at Main Workshop - Building Services | Test Report
| 6 | MDW-69380 |  |  |  |  | Test Report - Modification Machining Room at Main Workshop - Building Services |  |  |  | MDW-39314 | Modification Machining Room at Main Workshop - Building Services | Test Report
| 6 | MDW-69382 |  |  |  |  | Test Report - Modification Paint Shop Room at Main Workshop - Building Services |  |  |  | MDW-39315 | Modification Paint Shop Room at Main Workshop - Building Services | Test Report
| 6 | MDW-69384 |  |  |  |  | Test Report - Modification Electronic Workshop, Battery Charger, Machining and Paint Shop at Main Workshop - Civil & AR |  |  |  | MDW-39316 | Modification Electronic Workshop, Battery Charger, Machining and Paint Shop at Main Workshop - Civil & AR | Test Report
| 6 | MDW-69501 |  |  |  |  | Test Report - Modification Works : Storage Office in Main Workshop - Civil & AR |  |  |  | MDW-39500 | Modification Works : Storage Office in Main Workshop - Civil & AR | Test Report
| 6 | MDW-69503 |  |  |  |  | Test Report - Modification Works : Storage Office in Main Workshop - Building Services |  |  |  | MDW-39501 | Modification Works : Storage Office in Main Workshop - Building Services | Test Report
| 6 | MDW-69505 |  |  |  |  | Test Report - Modification Works : all Fire Alarm System Controller in Depot |  |  | CANCLE | MDW-39502 | Modification Works : all Fire Alarm System Controller in Depot | Test Report
| 6 | MDW-69507 |  |  |  |  | Test Report - Modification Works : New MMC at Admin Building - Civil & AR |  |  |  | MDW-39503 | Modification Works : New MMC at Admin Building - Civil & AR | Test Report
| 6 | MDW-69509 |  |  |  |  | Test Report - Modification Works : New MMC at Admin Building - Building Services |  |  |  | MDW-39504 | Modification Works : New MMC at Admin Building - Building Services | Test Report
| 6 | MDW-69511 |  |  |  |  | Test Report - Modification Works : Walkway with Roof from Main Workshop to Stabling Yard - Civil & AR |  |  |  | MDW-39505 | Modification Works : Walkway with Roof from Main Workshop to Stabling Yard - Civil & AR | Test Report
| 6 | MDW-69513 |  |  |  |  | Test Report - Modification Works : Walkway with Roof from Main Workshop to Stabling Yard - Building Services |  |  |  | MDW-39506 | Modification Works : Walkway with Roof from Main Workshop to Stabling Yard - Building Services | Test Report
| 6 | MDW-69515 |  |  |  |  | Test Report - Modification Works : High Roof in front of MWS Entrance and Store Entrance - Civil & AR |  |  |  | MDW-39507 | Modification Works : High Roof in front of MWS Entrance and Store Entrance - Civil & AR | Test Report
| 6 | MDW-69523 |  |  |  |  | Test Report - Modification Works : Maintenance Office Rooms at Main Workshop - Civil & AR |  |  |  | MDW-39511 | Modification Works : Maintenance Office Rooms at Main Workshop - Civil & AR | Test Report
| 6 | MDW-69525 |  |  |  |  | Test Report - Modification Works : Maintenance Office Rooms at Main Workshop - Building Services |  |  |  | MDW-39512 | Modification Works : Maintenance Office Rooms at Main Workshop - Building Services | Test Report
| 6 | MDW-69527 |  |  |  |  | Test Report - Modification Works : Concrete Car Barrier in front of Main Workshop |  |  |  | MDW-39513 | Modification Works : Concrete Car Barrier in front of Main Workshop | Test Report
| 6 | MDW-69529 |  |  |  |  | Test Report - Modification Works : Car Park Roof and Motorcycle in Depot - Civil & AR |  |  |  | MDW-39514 | Modification Works : Car Park Roof and Motorcycle in Depot - Civil & AR | Test Report
| 6 | MDW-69531 |  |  |  |  | Test Report - Modification Works : Car Park Roof and Motorcycle in Depot - Building Services |  |  |  | MDW-39515 | Modification Works : Car Park Roof and Motorcycle in Depot - Building Services | Test Report
| 6 | MDW-69533 |  |  |  |  | Test Report - Modification Works : Walkway Bridge between BL Depot and ORL Depot - Civil & AR |  |  |  | MDW-39516 | Modification Works : Walkway Bridge between BL Depot and ORL Depot - Civil & AR | Test Report
| 6 | MDW-69535 |  |  |  |  | Test Report - Modification Works : Walkway Bridge between BL Depot and ORL Depot - Building Services |  |  |  | MDW-39517 | Modification Works : Walkway Bridge between BL Depot and ORL Depot - Building Services | Test Report
| 6 | MDW-69537 |  |  |  |  | Test Report - Modification Works : Street Lighting between MRTA Fence and Depot Slab |  |  |  | MDW-39518 | Modification Works : Street Lighting between MRTA Fence and Depot Slab | Test Report
| 6 | MDW-69539 |  |  |  |  | Test Report - Modification Works : Walkway with Roof in Depot Area - Civil & AR |  |  |  | MDW-39519 | Modification Works : Walkway with Roof in Depot Area - Civil & AR | Test Report
| 6 | MDW-69541 |  |  |  |  | Test Report - Modification Works : Sliding Gate, Chain Link Fence and Walkway with Roof in Depot Area - Building Services |  |  |  | MDW-39520 | Modification Works : Sliding Gate, Chain Link Fence and Walkway with Roof in Depot Area - Building Services | Test Report
| 6 | MDW-69543 |  |  |  |  | Test Report - Modification Works : Walkway Bridge and Walkway over Canal in Depot |  |  |  | MDW-39521 | Modification Works : Walkway Bridge and Walkway over Canal in Depot | Test Report
| 6 | MDW-69545 |  |  |  |  | Test Report - Modification Works : Rain Protection and Zero Discharge Water treatment in Depot - Civil & AR |  |  |  | MDW-39522 | Modification Works : Rain Protection and Zero Discharge Water treatment in Depot - Civil & AR | Test Report
| 6 | MDW-69547 | OLW-ME-24/0471 20 pages | 2026-07-10 | A |  | Test Report - Modification Works : Cold Water System at Admin Building Landscape |  |  | submitted | MDW-39523 | Modification Works : Cold Water System at Admin Building Landscape | Test Report
| 6 | MDW-69549 |  |  |  |  | Test Report - Modification Works : Walkway under Depot Slab for Maintenance Service - Civil & AR |  |  |  | MDW-39524 | Modification Works : Walkway under Depot Slab for Maintenance Service - Civil & AR | Test Report
| 6 | MDW-69551 |  |  |  |  | Test Report - Modification Works : Walkway under Depot Slab for Maintenance Service - Building Services |  |  |  | MDW-39525 | Modification Works : Walkway under Depot Slab for Maintenance Service - Building Services | Test Report
| 6 | MDW-69553 | OLW-ME-24/0387 | 2026-05-15 | A |  | Test Report - Modification Works : FHC Modification at Stabling Yard |  |  | submitted | MDW-39526 | Modification Works : FHC Modification at Stabling Yard | Test Report
| 6 | MDW-69555 |  |  |  |  | Test Report - Modification Works : Hand Sink with Emergency Eye Wash Installation in Depot |  |  |  | MDW-39527 | Modification Works : Hand Sink with Emergency Eye Wash Installation in Depot | Test Report
| 6 | MDW-69557 |  |  |  |  | Test Report - Modification Works : Washing Area in Cleaning Staff Room at Stabling Yard - Civil & AR |  |  |  | MDW-39528 | Modification Works : Washing Area in Cleaning Staff Room at Stabling Yard - Civil & AR | Test Report
| 6 | MDW-69559 | OLW-ME-24/0470 13 pages | 2026-07-10 | A |  | Test Report - Modification Works : Washing Area in Cleaning Staff Room at Stabling Yard - Building Services |  |  | submitted | MDW-39529 | Modification Works : Washing Area in Cleaning Staff Room at Stabling Yard - Building Services | Test Report
| 6 | MDW-69561 |  |  |  |  | Test Report - Modification Works : Zero Discharge Water treatment in Depot - Building Services |  |  |  | MDW-39530 | Modification Works : Zero Discharge Water treatment in Depot - Building Services | Test Report
| 6 | MDW-69563 |  |  |  |  | Test Report - Modification Works : Guard rail protection for FHC in Depot Area |  |  |  | MDW-39531 | Modification Works : Guard rail protection for FHC in Depot Area | Test Report
| 6 | MDW-69565 |  |  |  |  | Test Report - Modification Works : Barbed Wire Fences for MRTA Chain Link at Klong Chourdyai |  |  |  | MDW-39532 | Modification Works : Barbed Wire Fences for MRTA Chain Link at Klong Chourdyai | Test Report
| 6 | MDW-69567 |  |  |  |  | Test Report - Modification Works : Car Barrier Gate at Depot Area |  |  |  | MDW-39533 | Modification Works : Car Barrier Gate at Depot Area | Test Report
| 6 | MDW-69569 |  |  |  |  | Test Report - Modification Works : Security Guard Box at ORL Depot Entrance - Civil & AR |  |  |  | MDW-39534 | Modification Works : Security Guard Box at ORL Depot Entrance - Civil & AR | Test Report
| 6 | MDW-69571 |  |  |  |  | Test Report - Modification Works : Security Guard Box at ORL Depot Entrance - Building Services |  |  |  | MDW-39535 | Modification Works : Security Guard Box at ORL Depot Entrance - Building Services | Test Report
| 6 | MDW-69573 |  |  |  |  | Test Report - Modification Works : Soundproof Installation and Company Logo at CCR Room |  |  |  | MDW-39536 | Modification Works : Soundproof Installation and Company Logo at CCR Room | Test Report
| 6 | MDW-69575 |  |  |  |  | Test Report - Modification Works : Fence Installation at Ladder in VS, IVS Buildings |  |  |  | MDW-39537 | Modification Works : Fence Installation at Ladder in VS, IVS Buildings | Test Report
| 6 | MDW-69577 |  |  |  |  | Test Report - Modification Works : Anti-Slide Signage at Escalator for all Stations |  |  |  | MDW-39538 | Modification Works : Anti-Slide Signage at Escalator for all Stations | Test Report
| 6 | MDW-69579 |  |  |  |  | Test Report - Modification Works : Roofing over Control Panel Installation at VS, IVS Buildings |  |  |  | MDW-39539 | Modification Works : Roofing over Control Panel Installation at VS, IVS Buildings | Test Report
| 6 | MDW-69581 |  |  |  |  | Test Report - Modification Works : Water Drop Protection for UPS Cabinet for all Stations and Depot |  |  |  | MDW-39540 | Modification Works : Water Drop Protection for UPS Cabinet for all Stations and Depot | Test Report
| 6 | MDW-69583 |  |  |  |  | Test Report - Modification Works : Manual Call Point Cover in Public Area at all Stations |  |  |  | MDW-39541 | Modification Works : Manual Call Point Cover in Public Area at all Stations | Test Report
| 6 | MDW-69585 |  |  |  |  | Test Report - Modification Works : Emergency Stop Button Cover for Escalator at all Stations |  |  |  | MDW-39542 | Modification Works : Emergency Stop Button Cover for Escalator at all Stations | Test Report
| 6 | MDW-69587 |  |  |  |  | Test Report - Modification Works : Bird & Rain Protetion, Safety Hand Rail Installation at Admin Building |  |  |  | MDW-39543 | Modification Works : Bird & Rain Protetion, Safety Hand Rail Installation at Admin Building | Test Report
| 6 | MDW-69589 |  |  |  |  | Test Report - Modification Works : Barbed Wire Fences for Depot slab |  |  |  | MDW-39544 | Modification Works : Barbed Wire Fences for Depot slab | Test Report
| 6 | MDW-69591 |  |  |  |  | Test Report - Modification Works : Chain Link Installation at Cut & Cover Depot Access |  |  |  | MDW-39545 | Modification Works : Chain Link Installation at Cut & Cover Depot Access | Test Report
| 6 | MDW-69593 |  |  |  |  | Test Report - Modification Works : Chain Link Installation under Depot Slab |  |  |  | MDW-39546 | Modification Works : Chain Link Installation under Depot Slab | Test Report
| 6 | MDW-69595 |  |  |  |  | Test Report - Modification Works : Door and Lockset Modification at OCC Building |  |  |  | MDW-39547 | Modification Works : Door and Lockset Modification at OCC Building | Test Report
| 6 | MDW-69597 | OLW-ME-24/0469 40 pages | 2026-07-10 | A |  | Test Report - Modification Works : Air Conditioning System Installation at Pantry room OCC Building |  |  | submitted | MDW-39548 | Modification Works : Air Conditioning System Installation at Pantry room OCC Building | Test Report
| 6 | MDW-69599 |  |  |  |  | Test Report - Maintenance Room and Satellite Store at Stations - Building Services |  |  |  | MDW-39549 | Maintenance Room and Satellite Store at Stations - Building Services | Test Report
| 6 | MDW-695601 |  |  |  |  | Test Report - Satellite Store at OR21 - Civil & AR |  |  |  | MDW-39550 | Satellite Store at OR21 - Civil & AR | Test Report
| 6 | MDW-69603 |  |  |  |  | Test Report - Modification Works : Train Crew Office at OR29 |  |  |  | MDW-39551 | Modification Works : Train Crew Office at OR29 | Test Report
| 6 | MDW-69605 |  |  |  |  | Test Report - Modification Works : Hand Rail Installation at Walk Way in Stabling Yard |  |  |  | MDW-39552 | Modification Works : Hand Rail Installation at Walk Way in Stabling Yard | Test Report
| 6 | MDW-69607 |  |  |  |  | Test Report - Modification Works : Ladder to Access the Fire Valve at Omega Joints for all Underground Stations |  |  |  | MDW-39553 | Modification Works : Ladder to Access the Fire Valve at Omega Joints for all Underground Stations | Test Report
| 6 | MDW-69609 |  |  |  |  | Test Report - Modification Works : Security Guard Box at OCC Parking Area - Civil & AR |  |  |  | MDW-39554 | Modification Works : Security Guard Box at OCC Parking Area - Civil & AR | Test Report
| 6 | MDW-69611 |  |  |  |  | Test Report - Modification Works : Security Guard Box at OCC Parking Area - Building Services |  |  |  | MDW-39555 | Modification Works : Security Guard Box at OCC Parking Area - Building Services | Test Report
| 6 | MDW-69613 | เตรียมออก 6/8/26 OLW-ME-24/0507 Total 45 pages | A |  |  | Test Report - Modification Works : Addition Small Power System at OCC Building |  |  |  | MDW-39556 | Modification Works : Addition Small Power System at OCC Building | Test Report
| 6 | MDW-69615 |  |  |  |  | Test Report - Modification Works : Sliding Gate and Chain Link Fence in Depot Area - Civil & AR |  |  |  | MDW-39557 | Modification Works : Sliding Gate and Chain Link Fence in Depot Area - Civil & AR | Test Report
| 6 | RST-69001 |  |  |  |  | On-site Inspection and Test Report - Walk-Through Metal Detector East Section |  |  |  |  | Walk-Through Metal Detector East Section | Test Report
| 6 | RST-69002 |  |  |  |  | On-site Inspection and Test Report - Walk-Through Metal Detector West Section |  |  |  |  | Walk-Through Metal Detector West Section | Test Report
| 6 | RST-69003 |  |  |  |  | On-site Inspection and Testing Procedure - Driver Training Simulator |  |  |  | RST-39001 | Driver Training Simulator | Test Procedure
| 6 | RST-69004 |  |  |  |  | On-site Inspection and Test Report - Driver Training Simulator |  |  |  | RST-39001 | Driver Training Simulator | Test Report
| 6 | RST-69005 |  |  |  |  | On-site Inspection and Test Report - Traceability Report - Driver Training Simulator |  |  |  |  | Traceability Report - Driver Training Simulator | Test Report
| 6 | RST-69006 |  |  |  |  | On-site Inspection and Test Report - Taking Over Certificate Application - Driver Training Simulator |  |  |  |  | Taking Over Certificate Application - Driver Training Simulator | Test Report
| 6 | RST-69007 |  |  |  |  | On-site Inspection and Test Report - Taking Over Certificate DRACAS Report - Driver Training Simulator |  |  |  |  | Taking Over Certificate DRACAS Report - Driver Training Simulator | Test Report
| 6 | RST-69008 |  |  |  |  | On-site Inspection and Test Report - Provisional Acceptance Certificate DRACAS Report - Driver Training Simulator |  |  |  |  | Provisional Acceptance Certificate DRACAS Report - Driver Training Simulator | Test Report

## ADW_Doc.
|  | 9=Requirement Traceability Report 2=Additional Works-internal document | Submission No. | Document No. (QA) | Issued Date | Rev. | Letter No. | Description/Title | Item | System | CK Doc Ctrl | CK Prep by | CK DWG | CK Leader CC | M&E Leader Review | CK Prepare | M&E reviewed | Released | Orignator | Submit Plan by CK | Status
1
2
3 | [7 empty] | OPM
4 | [7 empty] | Outline Design
5 | [7 empty] | Definitive Design
6 | [7 empty] | Detailed Design
7 | [7 empty] | Procurement / Manufacturing / Delivery Stage / FAT
8 | [7 empty] | Installation Menthod Statement
9 |  | 5 | OPM-59001 | OLW-ME-24/0042 | 2025-03-26 | A | BEM/M/ORM/S0063/68 | Installation Method Statement of Modification Work - CIV & AR in MRT Orange Line Project (East Section) |  |  | Wijittra M. | Chadin R. | - | Tanyawit K. | Werachai J. | Chadin R. | Tanyawit K. | Suraphong S. |  |  | submitted
10 |  | 5 | OPM-59001 | OLW-ME-24/0042 | 2025-07-07 | B | BEM/M/ORM/S0553/68 | Installation Method Statement of Modification Work - CIV & AR in MRT Orange Line Project (East Section) |  |  | Wijittra M. | Chadin R. | - | Tanyawit K. | Werachai J. | Chadin R. | Tanyawit K. | Suraphong S. |  |  | submitted
11 |  | 5 | OPM-59001 | OLW-ME-24/0042 | 2025-10-02 | C | BEM/M/ORM/S0072/69 | Installation Method Statement of Modification Work - CIV & AR in MRT Orange Line Project (East Section) |  |  | Wijittra M. | Chadin R. | - | Tanyawit K. | Werachai J. | Chadin R. | Tanyawit K. | Suraphong S. |  |  | submitted
12 |  | 5 | OPM-59002 | OLW-ME-24/0022 | 2025-03-01 | A | BEM/M/ORM/S0040/68 | Installation Method Statement of Modification Work - Building Service (Electrical System) in MRT Orange Line Project (East Section) |  |  | Nichapa P. | Sek J. | - | Pratan L. | Werachai J. | Sek J. | Pratan L. | Suraphong S. |  |  | submitted
13 |  | 5 | OPM-59003 | OLW-ME-24/0021 | 2025-05-15 | A | BEM/M/ORM/S0203/68 | Installation Method Statement of Modification Work - Building Service (Mechanical System) in MRT Orange Line Project (East Section) |  |  | Nichapa P. | Sek J. | - | Pratan L. | Werachai J. | Sek J. | Pratan L. | Suraphong S. |  |  | submitted
14 |  | 5 | OPM-59004 | OLW-ME-24/0079 | 2025-05-09 | A | BEM/M/ORM/S0135/68 | Installation Method Statement of Modification Work - Cable Ducts Bank from MEA Interface Point to BSS1 |  |  | Wijittra M. | Chadin R. | - | Tanyawit K. | Werachai J. | Chadin R. | K. Werachai J. | Suraphong S. |  |  | submitted
15 | [7 empty] | Testing and Commissioning Procedure
16 |  | 6 | OPM-69001 | OLW-ME-24/0007 | 2025-03-01 | A | BEM/M/ORM/S0062/68 | On-Site Inspection and Test Procedure of Modification Work - Civil & AR in MRT Orange Line Project (East Section) |  |  | Wijittra M. | Chadin R. | - | Tanyawit K. | Werachai J. | Chadin R. | Tanyawit K. | Suraphong S. |  |  | submitted
17 |  | 6 | OPM-69001 | OLW-ME-24/0007 | 2025-10-02 | B | BEM/M/ORM/S0097/69 | On-Site Inspection and Test Procedure of Modification Work - Civil & AR in MRT Orange Line Project (East Section) |  |  | Wijittra M. | Chadin R. | - | Tanyawit K. | Werachai J. | Chadin R. | Tanyawit K. | Suraphong S. |  |  | submitted
18 |  | 6 | OPM-69002 | OLW-ME-24/0108 | 2025-07-18 | A | BEM/M/ORM/S0509/68 | On-Site Inspection and Test Procedure of Modification Work - Building Service (Electrical System) in MRT Orange Line Project (East Section) |  |  | Nichapa P. | Sek J. | Sub | Pratan L. | Werachai J. | Sek J. | Pratan L. | Suraphong S. |  |  | submitted
19 |  | 6 | OPM-69002 | OLW-ME-24/0108 | 2026-02-18 | B | BEM/M/ORM/S0554/69 | On-Site Inspection and Test Procedure of Modification Work - Building Service (Electrical System) in MRT Orange Line Project (East Section) |  |  | Nichapa P. | Sek J. | Sub | Pratan L. | Werachai J. | Sek J. | Pratan L. | Suraphong S. |  |  | submitted
20 |  | 6 | OPM-69003 | OLW-ME-24/0129 | 2025-09-12 | A | BEM/M/ORM/S0960/68 | On-Site Inspection and Test Procedure of Modification Work - Building Service (Mechanical System) in MRT Orange Line Project (East Section) |  |  | Nichapa P. | Sek J. | Sub | Pratan L. | Werachai J. | Sek J. | Pratan L. | Suraphong S. |  |  | submitted
21 |  | 6 | OPM-69003 | OLW-ME-24/0129 | 2026-02-18 | B | BEM/M/ORM/S0500/69 | On-Site Inspection and Test Procedure of Modification Work - Building Service (Mechanical System) in MRT Orange Line Project (East Section) |  |  | Nichapa P. | Sek J. | Sub | Pratan L. | Werachai J. | Sek J. | Pratan L. | Suraphong S. |  |  | submitted
22 | [7 empty] | Testing and Commissioning Stage / System Integration and Handover Report
23 | [7 empty] | Training
24 | [7 empty] | As-Built Drawing, As-Built Configuration Data
25 | [7 empty] | O&M Manual
26
27
28 | [7 empty] | AFC
29 | [7 empty] | Outline Design
30 |  | 1 | AFC-19001 | OLW-ME-24/0017 | 2026-03-12 | C | BEM/M/ORM/S0609/69 | Outline Design - Automatic Fare Collection Systems | [12 empty] | submitted
31 | [7 empty] | Definitive Design
32 |  | 3 | AFC-39011 | OLW-ME-24/0365 | 2026-04-10 | A | BEM/M/ORM/S0879/69 | Detailed Design - EMV & QR - Central Ticketing System (CTS) | [12 empty] | submitted
33 |  | 3 | AFC-39012 | OLW-ME-24/0366 | 2026-04-10 | A | BEM/M/ORM/S0876/69 | Detailed Design - Central Computer System (CCS) | [12 empty] | submitted
34 | [7 empty] | Detailed Design
35 |  | 3 | AFC-39001 |  |  |  |  | Detailed Design - Park and Ride System | 5.1 | AFC | Wijittra | Peerapat | Peerapat | Sahachart S. | [6 empty] | CANCLE
36 |  | 3 | AFC-39001 | OLW-ME-24/0090 | 2025-09-08 | A | BEM/M/ORM/S0770/68 | Detailed Design - Mini Paging in Ticket Office East Section | 10.7 | COM | Kusuma K. | Sorawit P. | Sub | Pratan L. | Anat U. / Supajak S. | Sorawit P. | Anat U. | Suraphong S. |  |  | submitted
37 |  | 3 | AFC-39002 |  |  |  |  | Detailed Design - Mini Paging in Ticket Office West Section |  |  | Nichapa P. | Sorawit P. | Sub | Pratan L. | Anat U. / Supajak S. | Sorawit P. | Anat U. | Suraphong S.
38 |  | 3 | AFC-39003 | OLW-ME-24/0253 | 2026-01-09 | A | BEM/M/ORM/S0045/69 | Detailed Design - Cash Handling Equipment |  |  |  |  | Sub |  | Anat U. / Supajak S. |  | Anat U. | Suraphong S. |  |  | submitted
39 |  | 3 | AFC-39003 | OLW-ME-24/0253 | 2026-02-17 | B | BEM/M/ORM/S0315/69 | Detailed Design - Cash Handling Equipment |  |  |  |  | Sub |  | Anat U. / Supajak S. |  | Anat U. | Suraphong S. |  |  | submitted
40 | [7 empty] | Procurement / Manufacturing / Delivery Stage / FAT
41 | [7 empty] | Installation Menthod Statement
42 |  | 5 | AFC-59001 |  |  |  |  | Installation Method Statement - Mini Paging in Ticket Office East Section | [12 empty] | CANCLE
43 |  | 5 | AFC-59002 |  |  |  |  | Installation Method Statement - Mini Paging in Ticket Office West Section | [12 empty] | CANCLE
44 | [7 empty] | Testing and Commissioning Procedure
45 |  | 6 | AFC-69001 |  |  |  |  | Test Procedure - Mini Paging in Ticket Office East Section
46 |  | 6 | AFC-69003 |  |  |  |  | Test Procedure - Mini Paging in Ticket Office West Section
47 | [7 empty] | Testing and Commissioning Stage / System Integration and Handover Report
48 |  | 6 | AFC-69002 |  |  |  |  | Test Report - Mini Paging in Ticket Office East Section
49 |  | 6 | AFC-69004 |  |  |  |  | Test Report - Mini Paging in Ticket Office West Section
50 | [7 empty] | Training
51 | [7 empty] | As-Built Drawing, As-Built Configuration Data
52 |  | 8 | AFC-89001 |  |  |  |  | As-Built - Mini Paging in Ticket Office East Section
53 |  | 8 | AFC-89002 |  |  |  |  | As-Built - Mini Paging in Ticket Office West Section
54 | [7 empty] | O&M Manual
55 |  | 9 | AFC-99001 |  |  |  |  | O&M Manual - Mini Paging in Ticket Office - English
56 |  | 9 | AFC-99002 |  |  |  |  | O&M Manual - Mini Paging in Ticket Office - Thai Translation
57 |  | 9 | AFC-99003 |  |  |  |  | O&M Manual - Mini Paging in Ticket Office West Section - English | [12 empty] | CANCLE
58 |  | 9 | AFC-99004 |  |  |  |  | O&M Manual - Mini Paging in Ticket Office West Section - Thai Translation | [12 empty] | CANCLE
59
60
61 | [7 empty] | COM
62 | [7 empty] | Outline Design
63 |  | 1 | COM-19200 |  |  |  |  | Outline Design - Orange Line CCTV System interface to existing Blue Line CCTV System
64 |  | 1 | COM-19201 |  |  |  |  | Outline Design - Orange Line Digital Radio System Interface to existing Blue Line Digital Radio System
65 |  | 1 | COM-19204 |  |  |  |  | Outline Design - ORL CASS Interface to existing BL CASS
66 |  | 1 | COM-19202 |  |  |  |  | Outline Design - Orange Line Telephone System interface to existing Blue Line Telephone System | [12 empty] | CANCLE
67 |  | 1 | COM-19203 |  |  |  |  | Outline Design - Orange Line IT System interface to existing IT System | [12 empty] | CANCLE
68 | [7 empty] | Definitive Design
69 |  | 2 | COM-29001 | OLW-ME-24/0026 | 2025-03-03 | A | BEM/M/ORM/S0036/68 | Definitive Design - Walk-Through Metal Detector | [12 empty] | submitted
70 |  | 2 | COM-29001 | OLW-ME-24/0026 | 2025-05-07 | B | BEM/M/ORM/S0136/68 | Definitive Design - Walk-Through Metal Detector | [12 empty] | submitted
71 |  | 2 | COM-29001 | OLW-ME-24/0026 | 2025-07-04 | C | BEM/M/ORM/S0415/68 | Definitive Design - Walk-Through Metal Detector | [12 empty] | submitted
72 | [7 empty] | Detailed Design
73 |  | 3 | COM-39001 |  |  |  |  | Detailed Design - Walk-Through Metal Detector - Installation Drawing East Section | 10.3 | COM | Kusuma K. | Montri S. | Sub | Pratan L. | Sukij U. | Montri S. | Sukij U. | Suraphong S.
74 |  | 3 | COM-39002 |  |  |  |  | Detailed Design - Walk-Through Metal Detector - Installation Drawing West Section |  |  | Kusuma K. | Montri S. | Sub | Pratan L. | Sukij U. | Montri S. | Sukij U. | Suraphong S.
75 |  | 3 | COM-39003 |  |  |  |  | Detailed Design - Walk-Through Metal Detector - Material Approval |  |  | Kusuma K. | Montri S. | Sub | Pratan L. | Sukij U. | Montri S. | Sukij U. | Suraphong S.
76 |  | 3 | COM-39004 |  |  |  |  | Detailed Design - Main Cable Containment for M&E Dedicated communication link to MRTA Headquarter |  |  | Kusuma K. | Montri S. | Sub | Pratan L. | Sukij U. / Supajak S. | Montri S. | Sukij U. | Suraphong S. |  |  | CANCLE
77 |  | 3 | COM-39005 |  |  |  |  | Detailed Design - Power Distribution for M&E Systems at MRTA Headquarter | 10.9 | COM | Kusuma K. | Montri S. | Sub | Pratan L. | Sukij U. / Supajak S. | Montri S. | Sukij U. | Suraphong S. |  |  | CANCLE
78 |  | 3 | COM-39200 |  |  |  |  | Detailed Design - Magnetic Door Lock for East Section | 10.1 | COM | Kusuma K. | Montri S. | Sub | Pratan L. | Sukij U. / Supajak S. | Montri S. | Sukij U. | Suraphong S.
79 |  | 3 | COM-39201 | OLW-ME-24/0141 | 2025-08-27 | A |  | Detailed Design - Magnetic Door Lock - Material Approval | 10.1 | COM | Kusuma K. | Montri S. | Sub | Pratan L. | Sukij U. / Supajak S. | Montri S. | Sukij U. | Suraphong S. |  |  | submitted
80 |  | 3 | COM-39201 | OLW-ME-24/0141 | 2026-01-19 | B |  | Detailed Design - Magnetic Door Lock - Material Approval | 10.1 | COM | Kusuma K. | Montri S. | Sub | Pratan L. | Sukij U. / Supajak S. | Montri S. | Sukij U. | Suraphong S. |  |  | submitted
81 |  | 3 | COM-39203 |  |  |  |  | Detailed Design - Magnetic Door Lock for West Section | 10.1 | COM | Kusuma K. | Montri S. | Sub | Pratan L. | Sukij U. / Supajak S. | Montri S. | Sukij U. | Suraphong S.
82 | [7 empty] | Procurement / Manufacturing / Delivery Stage / FAT
83 |  | 4 | COM-49001 |  |  |  |  | Factory Routine Test Procedure - Walk-Through Metal Detector
84 |  | 4 | COM-49002 |  |  |  |  | Factory Routine Test Report - Walk-Through Metal Detector
85 | [7 empty] | Installation Menthod Statement
86 |  | 5 | COM-59001 |  |  |  |  | Installation Method Statement - Walk-Through Metal Detector East Section
87 |  | 5 | COM-59002 |  |  |  |  | Installation Method Statement - Walk-Through Metal Detector West Section
88 |  | 5 | COM-59003 |  |  |  |  | Installation Method Statement - Main Cable Containment for M&E Dedicated communication link to MRTA Headquarter | [12 empty] | CANCLE
89 |  | 5 | COM-59004 |  |  |  |  | Installation Method Statement - Power Distribution for M&E Systems at MRTA Headquarter | [12 empty] | CANCLE
90 |  | 5 | COM-59200 |  |  |  |  | Installation Method Statement - MEA Radio
91 | [7 empty] | Testing and Commissioning Procedure
92 |  | 6 | COM-69001 |  |  |  |  | Test Procedure - Walk-Through Metal Detector East Section
93 |  | 6 | COM-69003 |  |  |  |  | Test Procedure - Walk-Through Metal Detector West Section
94 |  | 6 | COM-69005 |  |  |  |  | Test Procedure - Main Cable Containment for M&E Dedicated communication link to MRTA Headquarter | [12 empty] | CANCLE
95 |  | 6 | COM-69007 |  |  |  |  | Test Procedure - Power Distribution for M&E Systems at MRTA Headquarter | [12 empty] | CANCLE
96 |  | 6 | COM-69200 |  |  |  |  | Test Procedure - Magnetic Door Lock for East Section
97 |  | 6 | COM-69202 |  |  |  |  | Test Procedure - MEA Radio
98 |  | 6 | COM-69204 |  |  |  |  | Test Procedure - Magnetic Door Lock for West Section
99 | [7 empty] | Testing and Commissioning Stage / System Integration and Handover Report
100 |  | 6 | COM-69002 |  |  |  |  | Test Report - Walk-Through Metal Detector East Section
101 |  | 6 | COM-69004 |  |  |  |  | Test Report - Walk-Through Metal Detector West Section
102 |  | 6 | COM-69006 |  |  |  |  | Test Report - Main Cable Containment for M&E Dedicated communication link to MRTA Headquarter | [12 empty] | CANCLE
103 |  | 6 | COM-69008 |  |  |  |  | Test Report - Power Distribution for M&E Systems at MRTA Headquarter | [12 empty] | CANCLE
104 |  | 6 | COM-69201 |  |  |  |  | Test Report - Magnetic Door Lock for East Section
105 |  | 6 | COM-69203 |  |  |  |  | Test Report - MEA Radio
106 |  | 6 | COM-69205 |  |  |  |  | Test Report - Magnetic Door Lock for West Section
107 | [7 empty] | Training
108 |  | 7 | COM-79001 |  |  |  |  | Training Manual - Walk-Through Metal Detector - English
109 |  | 7 | COM-79002 |  |  |  |  | Training Manual - Walk-Through Metal Detector - Thai Translation
110 | [7 empty] | As-Built Drawing, As-Built Configuration Data
111 |  | 8 | COM-89001 |  |  |  |  | As-Built - Walk-Through Metal Detector East Section
112 |  | 8 | COM-89002 |  |  |  |  | As-Built - Walk-Through Metal Detector West Section
113 |  | 8 | COM-89004 |  |  |  |  | As-Built - Main Cable Containment for M&E Dedicated communication link to MRTA Headquarter | [12 empty] | CANCLE
114 |  | 8 | COM-89005 |  |  |  |  | As-Built - Power Distribution for M&E Systems at MRTA Headquarter | [12 empty] | CANCLE
115 |  | 8 | COM-89200 |  |  |  |  | As-Built - Magnetic Door Lock for East Section
116 |  | 8 | COM-89201 |  |  |  |  | As-Built - MEA Radio
117 |  | 8 | COM-89202 |  |  |  |  | As-Built - Magnetic Door Lock for West Section
118 |  | 8 | COM-89203 |  |  |  |  | As-Built - Walk-Through Metal Detector Functional Location Data (FLD) East Section
119 |  | 8 | COM-89204 |  |  |  |  | As-Built - Walk-Through Metal Detector FLD On-Site Verificatrion Report East Section
120 |  | 8 | COM-89205 |  |  |  |  | As-Built - Walk-Through Metal Detector Functional Location Data (FLD) West Section
121 |  | 8 | COM-89206 |  |  |  |  | As-Built - Walk-Through Metal Detector FLD On-Site Verificatrion Report West Section
122 | [7 empty] | O&M Manual
123 |  | 9 | COM-99001 |  |  |  |  | O&M Manual - Walk-Through Metal Detector - English
124 |  | 9 | COM-99002 |  |  |  |  | O&M Manual - Walk-Through Metal Detector - Thai Translation
125 |  | 9 | COM-99003 |  |  |  |  | O&M Manual - Walk-Through Metal Detector West Section - English | [12 empty] | CANCLE
126 |  | 9 | COM-99004 |  |  |  |  | O&M Manual - Walk-Through Metal Detector West Section - Thai Translation | [12 empty] | CANCLE
127 |  | 9 | COM-99200 |  |  |  |  | O&M Manual - MEA Radio - English
128 |  | 9 | COM-99201 |  |  |  |  | O&M Manual - MEA Radio - Thai Translation
129
130
131
132
133 | [7 empty] | DWE
134 | [7 empty] | Outline Design
135 | [7 empty] | General
136 |  | 0 | DWE-09001 | OLW-ME-24/0255 | 2026-01-13 | A | Internal Only | DWE - System Assurance Plan | [12 empty] | submitted
137 |  | 0 | DWE-09002 |  |  |  |  | DWE Part 2 - RAM Plan
138 |  | 0 | DWE-09003 | OLW-ME-24/0329 | 2026-03-23 | A | Internal Only | DWE Part 2 - System Safety Plan | [12 empty] | submitted
139 |  | 0 | DWE-09004 |  |  |  |  | DWE Part 2 - RAM Report
140 |  | 0 | DWE-09005 | OLW-ME-24/0448 | 2026-07-01 | A | Internal Only | DWE- Design Management Plan | [12 empty] | submitted
141 |  | 0 | DWE-09006 |  |  |  |  | DWE - System Engineering Management Plan
142 |  | 0 | DWE-09007 |  |  |  |  | DWE - Interface management Plan
143 |  | 0 | DWE-09008 |  |  |  |  | DWE - Verification & Validation Plan
144 | [7 empty] | Definitive Design
145 |  | 2 | DWE-29001 | OLW-ME-24/0152 | 2025-08-25 | A | BEM/M/ORM/S0682/68 | Definitive Design - Shunting Locomotive | [12 empty] | submitted
146 |  | 2 | DWE-29001 | OLW-ME-24/0152 | 2026-05-05 | B | BEM/M/ORM/S1039/69 | Definitive Design - Shunting Locomotive | [12 empty] | submitted
147 |  | 2 | DWE-29001 | OLW-ME-24/0152 | 2026-06-26 | C | BEM/M/ORM/S1787/69 | Definitive Design - Shunting Locomotive | [12 empty] | submitted
148 |  | 2 | DWE-29002 | OLW-ME-24/0155 | 2025-08-28 | A | BEM/M/ORM/S0714/68 | Definitive Design - Tunnel Inspection and Cleaning Vehicle | [12 empty] | submitted
149 |  | 2 | DWE-29002 | OLW-ME-24/0155 | 2026-05-18 | B | BEM/M/ORM/S1204/69 | Definitive Design - Tunnel Inspection and Cleaning Vehicle | [12 empty] | submitted
150 |  | 2 | DWE-29002 | OLW-ME-24/0155 | 2026-07-07 | C | BEM/M/ORM/S1924/69 | Definitive Design - Tunnel Inspection and Cleaning Vehicle | [12 empty] | submitted
151 |  | 2 | DWE-29003 | OLW-ME-24/0156 | 1968-08-28 | A | BEM/M/ORM/S0716/68 | Definitive Design - Rail Maintenance Vehicle | [12 empty] | submitted
152 |  | 2 | DWE-29003 | OLW-ME-24/0156 | 2026-04-28 | B | BEM/M/ORM/S1024/69 | Definitive Design - Rail Maintenance Vehicle | [12 empty] | submitted
153 |  | 2 | DWE-29003 | OLW-ME-24/0156 | 2026-06-29 | C | BEM//M/ORM/S1810/69 | Definitive Design - Rail Maintenance Vehicle | [12 empty] | submitted
154 |  | 2 | DWE-29004 | OLW-ME-24/0157 | 2025-08-28 | A | BEM/M/ORM/S0712/68 | Definitive Design - Flat Wagon | [12 empty] | submitted
155 |  | 2 | DWE-29004 | OLW-ME-24/0157 | 2026-05-02 | B | BEM/M/ORM/S1023/69 | Definitive Design - Flat Wagon | [12 empty] | submitted
156 |  | 2 | DWE-29004 | OLW-ME-24/0157 | 2026-06-24 | C | BEM/M/ORM/S1748/69 | Definitive Design - Flat Wagon | [12 empty] | submitted
157 |  | 2 | DWE-29005 | OLW-ME-24/0125 | 2025-07-30 | A | BEM/M/ORM/S0510/68 | Definitive Design - Re-railing Equipment | [12 empty] | submitted
158 |  | 2 | DWE-29005 | OLW-ME-24/0125 | 2026-03-09 | B | BEM/M/ORM/S0594/69 | Definitive Design - Re-railing Equipment | [12 empty] | submitted
159 |  | 2 | DWE-29006 | OLW-ME-24/0158 | 2025-08-28 | A | BEM/M/ORM/S0715/68 | Definitive Design - Rail - based Inspection Vehicle | [12 empty] | submitted
160 |  | 2 | DWE-29006 | OLW-ME-24/0158 |  | B | BEM/M/ORM/S1015/69 | Definitive Design - Rail - based Inspection Vehicle
161 |  | 2 | DWE-29006 | OLW-ME-24/0158 | 2026-06-29 | C | BEM/M/ORM/S1811/69 | Definitive Design - Rail - based Inspection Vehicle | [12 empty] | submitted
162 |  | 2 | DWE-29007 | OLW-ME-24/0159 | 2025-08-28 | A | BEM/M/ORM/S0713/68 | Definitive Design - Rail-head Grinding Machine Vehicle | [12 empty] | submitted
163 |  | 2 | DWE-29008 |  |  |  |  | Definitive Design - Multi Measuring Rail Vehicle | [12 empty] | CANCLE
164 |  | 2 | DWE-29009 | OLW-ME-24/0122 | 2025-07-24 | A | BEM/M/ORM/S0496/68 | Definitive Design - Rail / Road Shunting Vehicle | [12 empty] | submitted
165 |  | 2 | DWE-29009 | OLW-ME-24/0122 | 2026-03-23 | B | BEM/M/ORM/S0701/69 | Definitive Design - Rail / Road Shunting Vehicle | [12 empty] | submitted
166 |  | 2 | DWE-29010 |  |  |  |  | Definitive Design - High Work Inspection Vehicle | [12 empty] | CANCLE
167 |  | 2 | DWE-29011 | OLW-ME-24/0103 | 2025-06-16 | A | BEM/M/ORM/S0227/68 | Definitive Design - Movable Height Maintenance Platform Vehicle | [12 empty] | submitted
168 |  | 2 | DWE-29011 | OLW-ME-24/0103 |  | B |  | Definitive Design - Movable Height Maintenance Platform Vehicle
169 |  | 2 | DWE-29011 | OLW-ME-24/0103 |  | C |  | Definitive Design - Movable Height Maintenance Platform Vehicle
170 |  | 2 | DWE-29012 | OLW-ME-24/0111 | 2025-07-02 | A | BEM/M/ORM/S0365/68 | Definitive Design - Forklifts | [12 empty] | submitted
171 |  | 2 | DWE-29013 | OLW-ME-24/0091 | 2025-06-12 | A | BEM/M/ORM/S0216/68 | Definitive Design - Overhead Traveling Crane | [12 empty] | submitted
172 |  | 2 | DWE-29014 | OLW-ME-24/0138 | 2025-08-08 | A | BEM/M/ORM/S0559/68 | Definitive Design - Trackwork Equipment | [12 empty] | submitted
173 |  | 2 | DWE-29014 | OLW-ME-24/0138 | 2026-03-11 | B | BEM/M/ORM/S0566/69 | Definitive Design - Trackwork Equipment | [12 empty] | submitted
174 |  | 2 | DWE-29015 | OLW-ME-24/0127 | 2025-08-01 | A | BEM/M/ORM/S0518/68 | Definitive Design - Compressed Air System and Portable Air Compressor for Depot | [12 empty] | submitted
175 |  | 2 | DWE-29015 | OLW-ME-24/0127 | 2026-04-23 | B | BEM/M/ORM/S0942/69 | Definitive Design - Compressed Air System and Portable Air Compressor for Depot | [12 empty] | submitted
176 |  | 2 | DWE-29016 | OLW-ME-24/0112 | 2025-07-31 | A | BEM/M/ORM/S0512/68 | Definitive Design - Diesel Fuel Storage Tank for Maintenance Vehicle at Depot | [12 empty] | submitted
177 |  | 2 | DWE-29016 | OLW-ME-24/0112 | 2026-02-18 | B | BEM/M/ORM/S0356/69 | Definitive Design - Diesel Fuel Storage Tank for Maintenance Vehicle at Depot | [12 empty] | submitted
178 |  | 2 | DWE-29017 | OLW-ME-24/0113 | 2025-07-21 | A | BEM/M/ORM/S0468/68 | Definitive Design - Pallet Storage and Tool Storage System at Depot | [12 empty] | submitted
179 |  | 2 | DWE-29017 | OLW-ME-24/0113 | 2026-03-23 | B | BEM/M/ORM/S0699/69 | Definitive Design - Pallet Storage and Tool Storage System at Depot | [12 empty] | submitted
180 |  | 2 | DWE-29018 | OLW-ME-24/0114 | 2025-07-09 | A | BEM/M/ORM/S0423/68 | Definitive Design - Repair Equipment | [12 empty] | submitted
181 |  | 2 | DWE-29018 | OLW-ME-24/0114 | 2026-03-23 | B | BEM/M/ORM/S0700/69 | Definitive Design - Repair Equipment | [12 empty] | submitted
182 |  | 2 | DWE-29019 | OLW-ME-24/0115 | 2025-07-21 | A | BEM/M/ORM/S0469/68 | Definitive Design - Paint Shop Equipment | [12 empty] | submitted
183 |  | 2 | DWE-29019 | OLW-ME-24/0115 | 2026-03-06 | B | BEM/M/ORM/S0525/69 | Definitive Design - Paint Shop Equipment | [12 empty] | submitted
184 |  | 2 | DWE-29020 | OLW-ME-24/0116 | 2025-07-11 | A | BEM/M/ORM/S0424/68 | Definitive Design - Oil & Grease Disposal and Waste Disposal | [12 empty] | submitted
185 |  | 2 | DWE-29020 | OLW-ME-24/0116 | 2026-03-06 | B | BEM/M/ORM/S0526/69 | Definitive Design - Oil & Grease Disposal and Waste Disposal | [12 empty] | submitted
186 |  | 2 | DWE-29021 | OLW-ME-24/0124 | 2025-07-30 | A | BEM/M/ORM/S0507/68 | Definitive Design - Operation Support Equipment | [12 empty] | submitted
187 |  | 2 | DWE-29021 | OLW-ME-24/0124 | 2026-02-20 | B | BEM/M/ORM/S0496/69 | Definitive Design - Operation Support Equipment | [12 empty] | submitted
188 | [7 empty] | Detailed Design
189 |  | 3 | DWE-39001 |  |  |  |  | Detailed Design - Shunting Locomotive |  | DWE | Nichapa P. | Somsak S. | Sub | Suchock P. | Komsun N. / Supajak S. | Somsak S. | Komsun N. | Suraphong S.
190 |  | 3 | DWE-39002 |  |  |  |  | Detailed Design - Tunnel Inspection and Cleaning Vehicle |  | DWE | Nichapa P. | Somsak S. | Sub | Suchock P. | Komsun N. / Supajak S. | Somsak S. | Komsun N. | Suraphong S.
191 |  | 3 | DWE-39003 |  |  |  |  | Detailed Design - Rail Maintenance Vehicle |  | DWE | Nichapa P. | Somsak S. | Sub | Suchock P. | Komsun N. / Supajak S. | Somsak S. | Komsun N. | Suraphong S.
192 |  | 3 | DWE-39004 |  |  |  |  | Detailed Design - Flat Wagon |  | DWE | Nichapa P. | Somsak S. | Sub | Suchock P. | Komsun N. / Supajak S. | Somsak S. | Komsun N. | Suraphong S.
193 |  | 3 | DWE-39005 |  |  |  |  | Detailed Design - Re-railing Equipment |  | DWE | Nichapa P. | Somsak S. | Sub | Suchock P. | Komsun N. / Supajak S. | Somsak S. | Komsun N. | Suraphong S.
194 |  | 3 | DWE-39006 |  |  |  |  | Detailed Design - Self-propelled Rail Based Inspection Vehicle |  | DWE | Nichapa P. | Somsak S. | Sub | Suchock P. | Komsun N. / Supajak S. | Somsak S. | Komsun N. | Suraphong S.
195 |  | 3 | DWE-39007 |  |  |  |  | Detailed Design - Rail-head Grinding Machine Vehicle |  | DWE | Nichapa P. | Somsak S. | Sub | Suchock P. | Komsun N. / Supajak S. | Somsak S. | Komsun N. | Suraphong S.
196 |  | 3 | DWE-39008 |  |  |  |  | Detailed Design - Multi Measuring Rail Vehicle |  | DWE | Nichapa P. | Somsak S. | Sub | 0 | Komsun N. / Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  | CANCLE
197 |  | 3 | DWE-39009 | OLW-ME-24/0291 | 2026-03-26 | A | BEM/M/ORM/S0834/69 | Detailed Design - Rail / Road Shunting Vehicle |  | DWE | Nichapa P. | Somsak S. | Sub | 0 | Komsun N. / Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  | submitted
198 |  | 3 | DWE-39010 |  |  |  |  | Detailed Design - High Work Inspection Vehicle |  | DWE | Nichapa P. | Somsak S. | Sub | 0 | Komsun N. / Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  | CANCLE
199 |  | 3 | DWE-39011 | OLW-ME-24/0263 | 2026-05-15 | A | BEM/M/ORM/S1393/69 | Detailed Design - Movable Height Maintenance Platform Vehicle |  | DWE | Nichapa P. | Somsak S. | Sub | 0 | Komsun N. / Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  | submitted
200 |  | 3 | DWE-39012 | OLW-ME-24/0395 | 2026-05-20 | A | BEM/M/ORM/S1391/69 | Detailed Design - Forklifts |  | DWE | Nichapa P. | Somsak S. | Sub | 0 | Komsun N. / Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  | submitted
201 |  | 3 | DWE-39013 | OLW-ME-24/0102 | 2025-07-01 | A | BEM/M/ORM/S0441/68 | Detailed Design - Overhead Traveling Crane | 7.16 | DWE | Nichapa P. | Somsak S. | Sub | 0 | Komsun N. / Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  | submitted
202 |  | 3 | DWE-39013 | OLW-ME-24/0102 | 2025-11-10 | B | BEM/M/ORM/S1272/68 | Detailed Design - Overhead Traveling Crane | 7.16 | DWE | Nichapa P. | Somsak S. | Sub | 0 | Komsun N. / Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  | submitted
203 |  | 3 | DWE-39013 | OLW-ME-24/0102 | 2026-03-23 | C | BEM/M/ORM/S0833/69 | Detailed Design - Overhead Traveling Crane | 7.16 | DWE | Nichapa P. | Somsak S. | Sub | 0 | Komsun N. / Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  | submitted
204 |  | 3 | DWE-39014 | เตรียมออก 25/7/26 OLW-ME-24/0292 |  |  |  | Detailed Design - Trackwork Equipment |  | DWE | Nichapa P. | Somsak S. | Sub | #REF! | Komsun N. / Supajak S. | Somsak S. | #REF! | Suraphong S.
205 |  | 3 | DWE-39015 |  |  |  |  | Detailed Design - Compressed Air System and Portable Air Compressor for Depot |  | DWE | Nichapa P. | Somsak S. | Sub | 0 | Komsun N. / Supajak S. | Somsak S. | #REF! | Suraphong S.
206 |  | 3 | DWE-39016 | OLW-ME-24/0376 | 2026-05-14 | A | BEM/M/ORM/S1259/69 | Detailed Design - Diesel Fuel Storage Tank for Maintenance Vehicle at Depot |  | DWE | Nichapa P. | Somsak S. | Sub | 0 | Komsun N. / Supajak S. | Somsak S. | #REF! | Suraphong S. |  |  | submitted
207 |  | 3 | DWE-39017 | OLW-ME-24/0352 | 2026-03-26 | A | BEM/M/ORM/S0835/69 | Detailed Design - Pallet Shelves, Two - Tier Shelves and Tool Storage | 7.5 | DWE | Nichapa P. | Somsak S. | Sub | 0 | Komsun N. / Supajak S. | Somsak S. | #REF! | Suraphong S. |  |  | submitted
208 |  | 3 | DWE-39017 | OLW-ME-24/0352 | 2026-05-12 | B | BEM/M/ORM/S1258/69 | Detailed Design - Pallet Shelves, Two - Tier Shelves and Tool Storage | 7.5 | DWE | Nichapa P. | Somsak S. | Sub | 0 | Komsun N. / Supajak S. | Somsak S. | #REF! | Suraphong S. |  |  | submitted
209 |  | 3 | DWE-39017 | OLW-ME-24/0352 | 2026-07-17 | C | BEM/M/ORM/S2293/69 | Detailed Design - Pallet Shelves, Two - Tier Shelves and Tool Storage | 7.5 | DWE | Nichapa P. | Somsak S. | Sub | 0 | Komsun N. / Supajak S. | Somsak S. | #REF! | Suraphong S. |  |  | submitted
210 |  | 3 | DWE-39117 | Include in submission DWE-39017 |  |  |  | Detailed Design - Pallet Storage Shelves in Dangerous Goods Building | 7.6 | DWE | Nichapa P. | Somsak S. | Sub | Suchock P. | Komsun N. / Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  | CANCLE
211 |  | 3 | DWE-39217 | Include in submission DWE-39018 |  |  |  | Detailed Design - Two-Tier Shelf | 7.7 | DWE | Nichapa P. | Somsak S. | Sub | 0 | Komsun N. / Supajak S. | Somsak S. | #REF! | Suraphong S. |  |  | CANCLE
212 |  | 3 | DWE-39317 | Include in submission DWE-39019 |  |  |  | Detailed Design - Tool Storage | 7.8 | DWE | Nichapa P. | Somsak S. | Sub | 0 | Komsun N. / Supajak S. | Somsak S. | #REF! | Suraphong S. |  |  | CANCLE
213 |  | 3 | DWE-39018 |  |  |  |  | Detailed Design - Repair Equipment | 7.9 | DWE | Nichapa P. | Somsak S. | Sub | 0 | Komsun N. / Supajak S. | Somsak S. | #REF! | Suraphong S.
214 |  | 3 | DWE-39019 | เตรียมออก 27/7/26 OLW-ME-24/0510 |  |  |  | Detailed Design - Paint Shop Equipment |  | DWE | Nichapa P. | Somsak S. | Sub | 0 | Komsun N. / Supajak S. | Somsak S. | #REF! | Suraphong S.
215 |  | 3 | DWE-39020 |  |  |  |  | Detailed Design - Oil & Grease Disposal and Waste Disposal | 7.10,7.11,7.12 | DWE | Nichapa P. | Somsak S. | Sub | 0 | Komsun N. / Supajak S. | Somsak S. | #REF! | Suraphong S.
216 |  | 3 | DWE-39021 | OLW-ME-24/0293 | 2026-03-26 | A | BEM/M/ORM/S0836/69 | Detailed Design - Operation Support Equipment | 3.6 | EE/ME | Nichapa P. | Somsak S. | Sub | Suchock P. | Komsun N. / Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  | submitted
217 |  | 3 | DWE-39022 |  |  |  |  | Detailed Design - DWE - List of Spare Parts, Consumables, Special Tools and Test Equipment, List of Critical Spare Parts |  | DWE | Nichapa P. | Somsak S. | Sub | #REF! | Komsun N. / Supajak S. | Somsak S. | Komsun N. | Suraphong S.
218 |  | 3 | DWE-39028
219 |  | 3 | DWE-39029
220 |  | 3 | DWE-39030 | OLW-ME-24/0161 | 2025-09-01 | A | BEM/M/ORM/S0784/68 | Workshop Manual - DWE Part 2 Phase: Outline,Definitive and Detailed Design | [6 empty] | Komsun N. / Supajak S. | [5 empty] | submitted
221 |  | 3 | DWE-39xxx |  |  |  |  | Detailed Design - Safety Provision for Maintenance Pits | 7.13 | DWE | Wijittra M. | Sahachart S. | Tanyawit | Tanyawit K. | Komsun N. / Supajak S. | Sahachart S. | Komsun N. | Suraphong S.
222 |  | 3 | DWE-39xxx |  |  |  |  | Detailed Design - Pit Drainage System in Main Workshop | 7.14 | DWE | Nichapa P. | Somsak S. | Sub |  | Komsun N. / Supajak S. | Somsak S. | Komsun N. | Suraphong S.
223 |  | 3 | DWE-39023 | OLW-ME-24/0242 | 2025-01-29 | A | Internal Only | Detailed Design - Provision of Civil Works to support Train Washing Equipment | 7.15 | DWE | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Komsun N. / Supajak S. | Sahachart S. | Komsun N. | Suraphong S. |  |  | submitted
224 |  | 3 | DWE-39024 | OLW-ME-24/0049 | 2025-10-08 | A | Internal Only | Detailed Design - Dangerous Waste Storage Building in Depot - Civil & AR | 3.5 | ST/AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Komsun N. / Supajak S. | Sahachart S. | Komsun N. | Suraphong S. |  |  | submitted
225 |  | 3 | DWE-39025 | OLW-ME-24/0264 | 2026-01-15 | A | Internal Only | Detailed Design - Dangerous Waste Storage Building and General Waste Storage Building in Depot - Building Service | 3.5 | EE/ME | Nichapa P. | Atiraj K. | Sub | Pratan L. | Komsun N. / Supajak S. | Atiraj K. | Komsun N. | Suraphong S. |  |  | submitted
226 |  | 3 | DWE-39026 | OLW-ME-24/0050 | 2025-10-08 | A | Internal Only | Detailed Design - General Waste Storage Building in Depot - Civil & AR | 3.6 | ST/AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Komsun N. / Supajak S. | Sahachart S. | Komsun N. | Suraphong S. |  |  | submitted
227 |  | 3 | DWE-39027 |  |  |  | Internal Only | Detailed Design - General Waste Storage Building in Depot - Building Service | 3.5 | EE/ME | Nichapa P. | Atiraj K. | Sub | Pratan L. | Komsun N. / Supajak S. | Atiraj K. | Komsun N. | Suraphong S. |  |  | CANCLE
228 | [7 empty] | Procurement / Manufacturing / Delivery Stage / FAT
229 |  | 4 | DWE-49001 |  |  |  |  | FAT Procedure - Shunting Locomotive
230 |  | 4 | DWE-49002 |  |  |  |  | FAT Procedure - Tunnel Inspection and Cleaning Vehicle
231 |  | 4 | DWE-49003 |  |  |  |  | FAT Procedure - Rail Maintenance Vehicle
232 |  | 4 | DWE-49004 |  |  |  |  | FAT Procedure - Flat Wagon
233 |  | 4 | DWE-49005 | OLW-ME-24/0355 | 2026-06-29 | A | BEM/M/ORM/S1853/69 | FAT Procedure - Re-railing Equipment | [12 empty] | submitted
234 |  | 4 | DWE-49006 |  |  |  |  | FAT Procedure - Self-propelled Rail Based Inspection Vehicle
235 |  | 4 | DWE-49007 |  |  |  |  | FAT Procedure - Rail-head Grinding Machine Vehicle
236 |  | 4 | DWE-49008 |  |  |  |  | FAT Procedure - Multi Measuring Rail Vehicle | [12 empty] | CANCLE
237 |  | 4 | DWE-49009 | OLW-ME-24/0356 | 2026-06-29 | A | BEM/M/ORM/S1877/69 | FAT Procedure - Rail / Road Shunting Vehicle | [12 empty] | submitted
238 |  | 4 | DWE-49011 | OLW-ME-24/0406 | 2026-05-27 | A | BEM/M/ORM/S1511/69 | FAT Procedure - Movable Height Maintenance Platform Vehicle | [12 empty] | submitted
239 |  | 4 | DWE-49012 | OLW-ME-24/0401 | 2026-05-25 | A | BEM/M/ORM/S1512/69 | FAT Procedure - Forklifts | [12 empty] | submitted
240 |  | 4 | DWE-49013 | OLW-ME-24/0131 | 2025-08-08 | A | BEM/M/ORM/S0602/68 | FAT Procedure - Overhead Traveling Crane | [12 empty] | submitted
241 |  | 4 | DWE-49013 | OLW-ME-24/0131 | 2025-09-04 | B | BEM/M/ORM/S0771/68 | FAT Procedure - Overhead Traveling Crane | [12 empty] | submitted
242 |  | 4 | DWE-49013 | OLW-ME-24/0131 | 2025-10-08 | C | BEM/M/ORM/S1091/68 | FAT Procedure - Overhead Traveling Crane | [12 empty] | submitted
243 |  | 4 | DWE-49013 | OLW-ME-24/0131 | 2026-02-04 | D | BEM/M/ORM/S0211/69 | FAT Procedure - Overhead Traveling Crane | [12 empty] | submitted
244 |  | 4 | DWE-49101 |  |  |  |  | FAT Report - Shunting Locomotive
245 |  | 4 | DWE-49102 |  |  |  |  | FAT Report - Tunnel Inspection and Cleaning Vehicle
246 |  | 4 | DWE-49103 |  |  |  |  | FAT Report - Rail Maintenance Vehicle
247 |  | 4 | DWE-49104 |  |  |  |  | FAT Report - Flat Wagon
248 |  | 4 | DWE-49105 |  |  |  |  | FAT Report - Re-railing Equipment
249 |  | 4 | DWE-49106 |  |  |  |  | FAT Report - Self-propelled Rail Based Inspection Vehicle
250 |  | 4 | DWE-49107 |  |  |  |  | FAT Report - Rail-head Grinding Machine Vehicle
251 |  | 4 | DWE-49108 |  |  |  |  | FAT Report - Multi Measuring Rail Vehicle | [12 empty] | CANCLE
252 |  | 4 | DWE-49109 |  |  |  |  | FAT Report - Rail / Road Shunting Vehicle
253 |  | 4 | DWE-49112 |  |  |  |  | FAT Report - Forklifts
254 |  | 4 | DWE-49113 |  |  |  |  | FAT Report - Overhead Traveling Crane 10 tons
255 |  | 4 | DWE-49213 | OLW-ME-24/0218 | 2025-12-05 | A | BEM/M/ORM/S1452/68 | FAT Report - Overhead Traveling Crane 5 tons | [12 empty] | submitted
256 |  | 4 | DWE-49213 | OLW-ME-24/0218 | 2026-03-23 | B | BEM/M/ORM/S0716/69 | FAT Report - Overhead Traveling Crane 5 tons | [12 empty] | submitted
257 |  | 4 | DWE-49313 |  |  |  |  | FAT Report - Overhead Traveling Crane 2 tons
258 |  | 4 | DWE-49413 |  |  |  |  | FAT Report - Overhead Traveling Crane 2x2 tons
259 |  | 4 | DWE-49513 | OLW-ME-24/0278 | 2026-03-09 | A | BEM/M/ORM/S0626/69 | FAT Report - Overhead Traveling Crane 8 tons | [12 empty] | submitted
260 |  | 4 | DWE-49030 |  |  |  |  | Workshop Manual - DWE Part 2 Phase: Manufacturing and Supply and Delivery
261 |  | 4 | DWE-49123 | OLW-ME-24/0260 | 2026-01-27 | A | BEM/M/ORM/S0203/69 | DWE - Overall Test Plan | [12 empty] | submitted
262 |  | 4 | DWE-49123 | OLW-ME-24/0260 | 2026-06-04 | B | BEM/M/ORM/S1608/69 | DWE - Overall Test Plan | [12 empty] | submitted
263 |  | 4 | DWE-49123 | OLW-ME-24/0260 | 2026-07-16 | C | BEM/M/ORM/S2075/69 | DWE - Overall Test Plan | [12 empty] | submitted
264 | [7 empty] | Installation Menthod Statement
265 |  | 5 | DWE-59013 | OLW-ME-25/0139 | 2025-08-18 | A | BEM/M/ORM/S0656/68 | Installation Method Statement - Overhead Traveling Crane | [12 empty] | submitted
266 |  | 5 | DWE-59013 | OLW-ME-25/0139 | 2026-04-02 | B | BEM/M/ORM/S0799/69 | Installation Method Statement - Overhead Traveling Crane | [12 empty] | submitted
267 |  | 5 | DWE-59015 |  |  |  |  | Installation Method Statement - Compressed Air System and Portable Air Compressor for Depot
268 |  | 5 | DWE-59016 | OLW-ME-24/0377 | 2026-05-11 | A | BEM/M/ORM/S1257/69 | Installation Method Statement - Diesel Fuel Storage Tank for Maintenance Vehicle at Depot | [12 empty] | submitted
269 |  | 5 | DWE-59017 | OLW-ME-24/0353 | 2026-03-30 | A | BEM/M/ORM/S0798/69 | Installation Method Statement - Pallet Shelves, Two-Tier Shelves and Tool Storage | [12 empty] | submitted
270 |  | 5 | DWE-59117 |  |  |  |  | Installation Method Statement - Pallet Storage Shelves in Dangerous Goods Building | [12 empty] | CANCLE
271 |  | 5 | DWE-59217 |  |  |  |  | Installation Method Statement - Two-Tier Shelf | [12 empty] | CANCLE
272 |  | 5 | DWE-59030 | OLW-ME-24/0412 | 2026-06-05 | A | BEM/M/ORM/S1769/69 | Workshop Manual - DWE Part 2 Phase: Construction and Installation | [12 empty] | submitted
273 | [7 empty] | Testing and Commissioning Procedure
274 |  | 6 | DWE-69001 |  |  |  |  | Test Procedure - Shunting Locomotive
275 |  | 6 | DWE-69002 |  |  |  |  | Test Procedure - Tunnel Inspection and Cleaning Vehicle
276 |  | 6 | DWE-69003 |  |  |  |  | Test Procedure - Rail Maintenance Vehicle
277 |  | 6 | DWE-69004 |  |  |  |  | Test Procedure - Flat Wagon
278 |  | 6 | DWE-69005 |  |  |  |  | Test Procedure - Re-railing Equipment
279 |  | 6 | DWE-69006 |  |  |  |  | Test Procedure - Self-propelled Rail Based Inspection Vehicle
280 |  | 6 | DWE-69007 |  |  |  |  | Test Procedure - Rail-head Grinding Machine Vehicle
281 |  | 6 | DWE-69008 |  |  |  |  | Test Procedure - Multi Measuring Rail Vehicle | [12 empty] | CANCLE
282 |  | 6 | DWE-69009 |  |  |  |  | Test Procedure - Rail / Road Shunting Vehicle
283 | DWE2 | 6 | DWE-69011 | OLW-ME-24/0392 | 2026-05-22 | A | BEM/M/ORM/S1390/69 | Test Procedure - Movable Height Maintenance Platform Vehicle | [12 empty] | submitted
284 |  | 6 | DWE-69012 |  |  |  |  | Test Procedure - Forklifts
285 |  | 6 | DWE-69013 | OLW-ME-24/0367 | 2026-04-10 | A | BEM/M/ORM/S0902/69 | Test Procedure - Overhead Traveling Crane | [12 empty] | submitted
286 |  | 6 | DWE-69013 | OLW-ME-24/0367 | 2026-05-26 | B | BEM/M/ORM/S1388/69 | Test Procedure - Overhead Traveling Crane | [12 empty] | submitted
287 |  | 6 | DWE-69013 | OLW-ME-24/0367 | เตรียมออก 8/6/26 1/8/26 | C | (323 หน้า) | Test Procedure - Overhead Traveling Crane
288 |  | 6 | DWE-69014 |  |  |  |  | Test Procedure - Trackwork Equpment
289 |  | 6 | DWE-69015 |  |  |  |  | Test Procedure - Compressed Air System and Portable Air Compressor for Depot
290 |  | 6 | DWE-69016 |  |  |  |  | Test Procedure - Diesel Fuel Storage Tank for Maintenance Vehicle at Depot
291 |  | 6 | DWE-69017 | OLW-ME-24/0474 Total 32 pages | 2026-07-17 | A | BEM/M/ORM/S2292/69 | Test Procedure - Pallet Shelves, Two-Tier Shelves and Tool Storage | [12 empty] | submitted
292 |  | 6 | DWE-69217 | OLW-ME-24/0474 Total 32 pages |  |  |  | Test Procedure - Pallet Storage Shelves in Dangerous Goods Building | [12 empty] | CANCLE
293 |  | 6 | DWE-69417 | OLW-ME-24/0474 Total 32 pages |  |  |  | Test Procedure - Two-Tier Shelf | [12 empty] | CANCLE
294 |  | 6 | DWE-69617 | OLW-ME-24/0474 Total 32 pages |  |  |  | Test Procedure - Tool Storage | [12 empty] | CANCLE
295 |  | 6 | DWE-69018 | OLW-ME-24/0474 Total 32 pages |  |  |  | Test Procedure - Repair Equipment
296 |  | 6 | DWE-69019 | OLW-ME-24/0474 Total 32 pages |  |  |  | Test Procedure - Paint Shop Equipment
297 |  | 6 | DWE-69020 | OLW-ME-24/0474 Total 32 pages |  |  |  | Test Procedure - Oil & Grease Disposal and Waste Disposal
298 |  | 6 | DWE-69021 | OLW-ME-24/0474 Total 32 pages |  |  |  | Test Procedure - Operation Support Equipment
299 |  | 6 | DWE-69030 | OLW-ME-24/0413 | 2026-06-05 | A | BEM/M/ORM/S1768/69 | Workshop Manual - DWE Part 2 Phase: Testing and Commissioning | [12 empty] | submitted
300 |  | 6 | DWE-69023 | เตรียมออก 7/7/26 OLW-ME-24/0438 16 pages |  |  |  | Test Procedure - Provision of Civil Works to support Train Washing Equipment
301 |  | 6 | DWE-69024 | OLW-ME-24/0439 22 pages | 2026-07-15 | A | Internal | Test Procedure - Dangerous Waste Storage Building in Depot - Civil & AR | [12 empty] | submitted
302 |  | 6 | DWE-69025 | OLW-ME-24/0370 | 2026-04-20 | A | Internal | Test Procedure - Dangerous Waste Storage Building and General Waste Storage Building in Depot - Building Service | [12 empty] | submitted
303 |  | 6 | DWE-69026 | OLW-ME-24/0440 24 pages | 2026-07-15 | A | Internal | Test Procedure - General Waste Storage Building in Depot - Civil & AR | [12 empty] | submitted
304 |  | 6 | DWE-69027 |  |  |  |  | Test Procedure - General Waste Storage Building in Depot - Building Service | [12 empty] | CANCLE
305 | [7 empty] | Testing and Commissioning Stage / System Integration and Handover Report
306 |  | 6 | DWE-69101 |  |  |  |  | Test Report - Shunting Locomotive
307 |  | 6 | DWE-69102 |  |  |  |  | Test Report - Tunnel Inspection and Cleaning Vehicle
308 |  | 6 | DWE-69103 |  |  |  |  | Test Report - Rail Maintenance Vehicle
309 |  | 6 | DWE-69104 |  |  |  |  | Test Report - Flat Wagon
310 |  | 6 | DWE-69105 |  |  |  |  | Test Report - Re-railing Equipment
311 |  | 6 | DWE-69106 |  |  |  |  | Test Report - Self-propelled Rail Based Inspection Vehicle
312 |  | 6 | DWE-69107 |  |  |  |  | Test Report - Rail-head Grinding Machine Vehicle
313 |  | 6 | DWE-69108 |  |  |  |  | Test Report - Multi Measuring Rail Vehicle | [12 empty] | CANCLE
314 |  | 6 | DWE-69109 |  |  |  |  | Test Report - Rail / Road Shunting Vehicle
315 |  | 6 | DWE-69111 |  |  |  |  | Test Report - Movable Height Maintenance Platform Vehicle
316 |  | 6 | DWE-69112 |  |  |  |  | Test Report - Forklifts
317 |  | 6 | DWE-69113 | เตรียมออก 5/8/26 OLW-ME-24/0523 total 177 pages |  | A |  | Test Report - Overhead Traveling Crane 10 tons
318 |  | 6 | DWE-69213 | OLW-ME-24/0423 | 2026-06-23 | A | BEM/M/ORM/S1833/69 | Test Report - Overhead Traveling Crane 5 tons | [12 empty] | submitted
319 |  | 6 | DWE-69213 | เตรียมออก 5/8/26 total 177 pages |  | B |  | Test Report - Overhead Traveling Crane 5 tons
320 |  | 6 | DWE-69313 | เตรียมออก 5/8/26 OLW-ME-24/0524 total 277 pages |  | A |  | Test Report - Overhead Traveling Crane 2 tons
321 |  | 6 | DWE-69413 | เตรียมออก 5/8/26 OLW-ME-24/0525 total 119 pages |  | A |  | Test Report - Overhead Traveling Crane 2x2 tons
322 |  | 6 | DWE-69513 | เตรียมออก 25/6/26 5/8/26 OLW-ME-24/0424 total 129 pages |  | A |  | Test Report - Overhead Traveling Crane 8 tons
323 |  | 6 | DWE-69114 |  |  |  |  | Test Report - Trackwork Equpment
324 |  | 6 | DWE-69115 |  |  |  |  | Test Report - Compressed Air System and Portable Air Compressor for Depot
325 |  | 6 | DWE-69116 |  |  |  |  | Test Report - Diesel Fuel Storage Tank for Maintenance Vehicle at Depot
326 |  | 6 | DWE-69117 |  |  |  |  | Test Report - Pallet Shelves, Two-Tier Shelves and Tool Storage
327 |  | 6 | DWE-69317 |  |  |  |  | Test Report - Pallet Storage Shelves in Dangerous Goods Building | [12 empty] | CANCLE
328 |  | 6 | DWE-69517 |  |  |  |  | Test Report - Two-Tier Shelf | [12 empty] | CANCLE
329 |  | 6 | DWE-69717 |  |  |  |  | Test Report - Tool Storage | [12 empty] | CANCLE
330 |  | 6 | DWE-69118 |  |  |  |  | Test Report - Repair Equipment
331 |  | 6 | DWE-69119 |  |  |  |  | Test Report - Paint Shop Equipment
332 |  | 6 | DWE-69120 |  |  |  |  | Test Report - Oil & Grease Disposal and Waste Disposal
333 |  | 6 | DWE-69121 |  |  |  |  | Test Report - Operation Support Equipment
334 |  | 6 | DWE-69123 |  |  |  |  | Test Report - Provision of Civil Works to support Train Washing Equipment
335 |  | 6 | DWE-69124 |  |  |  |  | Test Report - Dangerous Waste Storage Building in Depot - Civil & AR
336 |  | 6 | DWE-69125 |  |  |  |  | Test Report - Dangerous Waste Storage Building and General Waste Storage Building in Depot - Building Service
337 |  | 6 | DWE-69126 |  |  |  |  | Test Report - General Waste Storage Building in Depot - Civil & AR
338 |  | 6 | DWE-69127 |  |  |  |  | Test Report - General Waste Storage Building in Depot - Building Service | [12 empty] | CANCLE
339 | [7 empty] | Training
340 |  | 7 | DWE-79001 |  |  |  |  | Training Manual - Shunting Locomotive - English
341 |  | 7 | DWE-79002 |  |  |  |  | Training Manual - Tunnel Inspection and Cleaning Vehicle - English
342 |  | 7 | DWE-79003 |  |  |  |  | Training Manual - Rail Maintenance Vehicle - English
343 |  | 7 | DWE-79004 |  |  |  |  | Training Manual - Flat Wagon - English
344 |  | 7 | DWE-79005 |  |  |  |  | Training Manual - Re-railing Equipment - English
345 |  | 7 | DWE-79006 |  |  |  |  | Training Manual - Self-propelled Rail Based Inspection Vehicle - English
346 |  | 7 | DWE-79007 |  |  |  |  | Training Manual - Rail-head Grinding Machine Vehicle - English
347 |  | 7 | DWE-79008 |  |  |  |  | Training Manual - Multi Measuring Rail Vehicle | [12 empty] | CANCLE
348 |  | 7 | DWE-79009 |  |  |  |  | Training Manual - Rail / Road Shunting Vehicle - English
349 |  | 7 | DWE-79011 |  |  |  |  | Training Manual - Movable Height Maintenance Platform Vehicle - English
350 |  | 7 | DWE-79012 |  |  |  |  | Training Manual - Forklifts - English
351 |  | 7 | DWE-79013 |  |  |  |  | Training Manual - Overhead Traveling Crane - English
352 |  | 7 | DWE-79014 |  |  |  |  | Training Manual - Trackwork Equpment - English
353 |  | 7 | DWE-79015 |  |  |  |  | Training Manual - Compressed Air System and Portable Air Compressor for Depot - English
354 |  | 7 | DWE-79016 |  |  |  |  | Training Manual - Diesel Fuel Storage Tank for Maintenance Vehicle at Depot - English
355 |  | 7 | DWE-79018 |  |  |  |  | Training Manual - Repair Equipment - English
356 |  | 7 | DWE-79019 |  |  |  |  | Training Manual - Paint Shop Equipment - English
357 |  | 7 | DWE-79020 |  |  |  |  | Training Manual - Oil & Grease Disposal and Waste Disposal | [12 empty] | CANCLE
358 |  | 7 | DWE-79021 |  |  |  |  | Training Manual - Operation Support Equpment - English
359 |  | 7 | DWE-79040 |  |  |  |  | Training - DWE Part 2 Individual Training Plan (ITP)
360 |  | 7 | DWE-79101 |  |  |  |  | Training Manual - Shunting LocomotiveThai Translation
361 |  | 7 | DWE-79102 |  |  |  |  | Training Manual - Tunnel Inspection and Cleaning Vehicle - Thai Translation
362 |  | 7 | DWE-79103 |  |  |  |  | Training Manual - Rail Maintenance Vehicle - Thai Translation
363 |  | 7 | DWE-79104 |  |  |  |  | Training Manual - Flat Wagon - Thai Translation
364 |  | 7 | DWE-79105 |  |  |  |  | Training Manual - Re-railing Equipment - Thai Translation
365 |  | 7 | DWE-79106 |  |  |  |  | Training Manual - Self-propelled Rail Based Inspection Vehicle - Thai Translation
366 |  | 7 | DWE-79107 |  |  |  |  | Training Manual - Rail-head Grinding Machine Vehicle - Thai Translation
367 |  | 7 | DWE-79108 |  |  |  |  | Training Manual - Multi Measuring Rail Vehicle | [12 empty] | CANCLE
368 |  | 7 | DWE-79109 |  |  |  |  | Training Manual - Rail / Road Shunting Vehicle - Thai Translation
369 |  | 7 | DWE-79111 |  |  |  |  | Training Manual - Movable Height Maintenance Platform Vehicle - Thai Translation
370 |  | 7 | DWE-79112 |  |  |  |  | Training Manual - Forklifts - Thai Translation
371 |  | 7 | DWE-79113 |  |  |  |  | Training Manual - Overhead Traveling Crane - Thai Translation
372 |  | 7 | DWE-79114 |  |  |  |  | Training Manual - Trackwork Equpment - Thai Translation
373 |  | 7 | DWE-79115 |  |  |  |  | Training Manual - Compressed Air System and Portable Air Compressor for Depot - Thai Translation
374 |  | 7 | DWE-79116 |  |  |  |  | Training Manual - Diesel Fuel Storage Tank for Maintenance Vehicle at Depot - Thai Translation
375 |  | 7 | DWE-79118 |  |  |  |  | Training Manual - Repair Equipment - Thai Translation
376 |  | 7 | DWE-79119 |  |  |  |  | Training Manual - Paint Shop Equipment - Thai Translation
377 |  | 7 | DWE-79020 |  |  |  |  | Training Manual - Oil & Grease Disposal and Waste Disposal | [12 empty] | CANCLE
378 |  | 7 | DWE-79121 |  |  |  |  | Training Manual - Operation Support Equpment - Thai Translation
379 | [7 empty] | As-Built Drawing, As-Built Configuration Data
380 |  | 8 | DWE-89001 |  |  |  |  | As-Built - Shunting Locomotive
381 |  | 8 | DWE-89002 |  |  |  |  | As-Built - Tunnel Inspection and Cleaning Vehicle
382 |  | 8 | DWE-89003 |  |  |  |  | As-Built - Rail Maintenance Vehicle
383 |  | 8 | DWE-89004 |  |  |  |  | As-Built - Flat Wagon
384 |  | 8 | DWE-89005 |  |  |  |  | As-Built - Re-railing Equipment
385 |  | 8 | DWE-89006 |  |  |  |  | As-Built - Self-propelled Rail Based Inspection Vehicle
386 |  | 8 | DWE-89007 |  |  |  |  | As-Built - Rail-head Grinding Machine Vehicle
387 |  | 8 | DWE-89008 |  |  |  |  | As-Built - Multi Measuring Rail Vehicle | [12 empty] | CANCLE
388 |  | 8 | DWE-89009 |  |  |  |  | As-Built - Rail / Road Shunting Vehicle
389 |  | 8 | DWE-89011 |  |  |  |  | As-Built - Movable Height Maintenance Platform Vehicle
390 |  | 8 | DWE-89012 |  |  |  |  | As-Built - Forklifts
391 |  | 8 | DWE-89013 |  |  |  |  | As-Built - Overhead Traveling Crane
392 |  | 8 | DWE-89014 |  |  |  |  | As-Built - Trackwork Equpment
393 |  | 8 | DWE-89015 |  |  |  |  | As-Built - Compressed Air System and Portable Air Compressor for Depot
394 |  | 8 | DWE-89016 |  |  |  |  | As-Built - Diesel Fuel Storage Tank for Maintenance Vehicle at Depot
395 |  | 8 | DWE-89017 |  |  |  |  | As-Built - Pallet Shelves, Two-Tier Shelves and Tool Storage
396 |  | 8 | DWE-89117 |  |  |  |  | As-Built - Pallet Storage Shelves in Dangerous Goods Building | [12 empty] | CANCLE
397 |  | 8 | DWE-89217 |  |  |  |  | As-Built - Two-Tier Shelf | [12 empty] | CANCLE
398 |  | 8 | DWE-89317 |  |  |  |  | As-Built - Tool Storage | [12 empty] | CANCLE
399 |  | 8 | DWE-89018 |  |  |  |  | As-Built - Repair Equipment
400 |  | 8 | DWE-89019 |  |  |  |  | As-Built - Paint Shop Equipment
401 |  | 8 | DWE-89020 |  |  |  |  | As-Built - Oil & Grease Disposal and Waste Disposal
402 |  | 8 | DWE-89021 |  |  |  |  | As-Built - Operation Support Equipment
403 |  | 8 | DWE-89023 |  |  |  |  | As-Built - Provision of Civil Works to support Train Washing Equipment
404 |  | 8 | DWE-89024 |  |  |  |  | As-Built - Dangerous Waste Storage Building in Depot - Civil & AR
405 |  | 8 | DWE-89025 |  |  |  |  | As-Built - Dangerous Waste Storage Building and General Waste Storage Building in Depot - Building Service
406 |  | 8 | DWE-89026 |  |  |  |  | As-Built - General Waste Storage Building in Depot - Civil & AR
407 |  | 8 | DWE-89027 |  |  |  |  | As-Built - General Waste Storage Building in Depot - Building Service | [12 empty] | CANCLE
408 |  | 8 | DWE-89031 |  |  |  |  | As-Built - DWE - Material Management Data (MMD)
409 |  | 8 | DWE-89032 |  |  |  |  | As-Built - CSW, DWE CMMS Mapping Table
410 |  | 8 | DWE-89033 |  |  |  |  | As-Built - DWE - Functional Location Data (FLD)
411 |  | 8 | DWE-89034 |  |  |  |  | As-Built - DWE - FLD On-Site Verification Report
412 | [7 empty] | O&M Manual
413 |  | 9 | DWE-99001 |  |  |  |  | O&M Manual - Shunting Locomotive - English
414 |  | 9 | DWE-99002 |  |  |  |  | O&M Manual - Tunnel Inspection and Cleaning Vehicle - English
415 |  | 9 | DWE-99003 |  |  |  |  | O&M Manual - Rail Maintenance Vehicle - English
416 |  | 9 | DWE-99004 |  |  |  |  | O&M Manual - Flat Wagon - English
417 |  | 9 | DWE-99005 |  |  |  |  | O&M Manual - Re-railing Equipment - English
418 |  | 9 | DWE-99006 |  |  |  |  | O&M Manual - Self-propelled Rail Based Inspection Vehicle - English
419 |  | 9 | DWE-99007 |  |  |  |  | O&M Manual - Rail-head Grinding Machine Vehicle - English
420 |  | 9 | DWE-99008 |  |  |  |  | O&M Manual - Multi Measuring Rail Vehicle | [12 empty] | CANCLE
421 |  | 9 | DWE-99009 |  |  |  |  | O&M Manual - Rail / Road Shunting Vehicle - English
422 |  | 9 | DWE-99011 |  |  |  |  | O&M Manual - Movable Height Maintenance Platform Vehicle - English
423 |  | 9 | DWE-99012 |  |  |  |  | O&M Manual - Forklifts - English
424 |  | 9 | DWE-99013 |  |  |  |  | O&M Manual - Overhead Traveling Crane - English
425 |  | 9 | DWE-99014 |  |  |  |  | O&M Manual - Trackwork Equpment - English
426 |  | 9 | DWE-99015 |  |  |  |  | O&M Manual - Compressed Air System and Portable Air Compressor for Depot - English
427 |  | 9 | DWE-99016 |  |  |  |  | O&M Manual - Diesel Fuel Storage Tank for Maintenance Vehicle at Depot - English
428 |  | 9 | DWE-99017 |  |  |  |  | O&M Manual - Pallet Storage and Tool Storage System at Depot - English | [12 empty] | CANCLE
429 |  | 9 | DWE-99018 |  |  |  |  | O&M Manual - Repair Equipment - English
430 |  | 9 | DWE-99019 |  |  |  |  | O&M Manual - Paint Shop Equipment - English
431 |  | 9 | DWE-99020 |  |  |  |  | O&M Manual - Oil & Grease Disposal and Waste Disposal - English
432 |  | 9 | DWE-99021 |  |  |  |  | O&M Manual - Operation Support Equipment - English
433 |  | 9 | DWE-99101 |  |  |  |  | O&M Manual - Shunting Locomotive - Thai Translation
434 |  | 9 | DWE-99102 |  |  |  |  | O&M Manual - Tunnel Inspection and Cleaning Vehicle - Thai Translation
435 |  | 9 | DWE-99103 |  |  |  |  | O&M Manual - Rail Maintenance Vehicle - Thai Translation
436 |  | 9 | DWE-99104 |  |  |  |  | O&M Manual - Flat Wagon - Thai Translation
437 |  | 9 | DWE-99105 |  |  |  |  | O&M Manual - Re-railing Equipment - Thai Translation
438 |  | 9 | DWE-99106 |  |  |  |  | O&M Manual - Self-propelled Rail Based Inspection Vehicle - Thai Translation
439 |  | 9 | DWE-99107 |  |  |  |  | O&M Manual - Rail-head Grinding Machine Vehicle - Thai Translation
440 |  | 9 | DWE-99108 |  |  |  |  | O&M Manual - Multi Measuring Rail Vehicle - Thai | [12 empty] | CANCLE
441 |  | 9 | DWE-99109 |  |  |  |  | O&M Manual - Rail / Road Shunting Vehicle - Thai Translation
442 |  | 9 | DWE-99111 |  |  |  |  | O&M Manual - Movable Height Maintenance Platform Vehicle - Thai Translation
443 |  | 9 | DWE-99112 |  |  |  |  | O&M Manual - Forklifts - Thai Translation
444 |  | 9 | DWE-99113 |  |  |  |  | O&M Manual - Overhead Traveling Crane - Thai Translation
445 |  | 9 | DWE-99114 |  |  |  |  | O&M Manual - Trackwork Equpment - Thai Translation
446 |  | 9 | DWE-99115 |  |  |  |  | O&M Manual - Compressed Air System and Portable Air Compressor for Depot - Thai Translation
447 |  | 9 | DWE-99116 |  |  |  |  | O&M Manual - Diesel Fuel Storage Tank for Maintenance Vehicle at Depot - Thai Translation
448 |  | 9 | DWE-99117 |  |  |  |  | O&M Manual - Pallet Storage and Tool Storage System at Depot - Thai Translation | [12 empty] | CANCLE
449 |  | 9 | DWE-99118 |  |  |  |  | O&M Manual - Repair Equipment - Thai Translation
450 |  | 9 | DWE-99119 |  |  |  |  | O&M Manual - Paint Shop Equipment - Thai Translation
451 |  | 9 | DWE-99120 |  |  |  |  | O&M Manual - Oil & Grease Disposal and Waste Disposal - Thai Translation
452 |  | 9 | DWE-99121 |  |  |  |  | O&M Manual - Operation Support Equipment - Thai Translation
453
454
455
456
457 | [7 empty] | EPS
458 | [7 empty] | Outline Design
459 | [7 empty] | Definitive Design
460 | [7 empty] | Detailed Design
461 |  | 3 | EPS-39001 | OLW-ME-24/0382 | 2026-05-18 | A | BEM/M/ORM/S1474/69 | Detailed Design - Diesel Fuel Storage Tanks for Power Generators |  | CIV/AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Praphat M./ Supajak S. | Sahachart S. | Praphat M. | Suraphong S. |  |  | submitted
462 |  | 3 | EPS-39002 | Include in submission EPS-39001 |  |  |  | Detailed Design - Diesel Fuel Storage Tanks for Power Generators - Building Services |  | EE/ME | Nichapa P. | Jaturong W. | Sub | Pratan L. | Praphat M./ Supajak S. | Jaturong W. | Praphat M. | Suraphong S. |  |  | CANCLE
463 |  | 3 | EPS-39003 | Include in submission EPS-39001 |  |  |  | Detailed Design - Diesel Fuel Storage Tanks for Power Generators : Material Approval - Civil & AR |  |  | Nichapa P. | Somsak S. | Sub | Pratan L. | Praphat M./ Supajak S. | Somsak S. | Praphat M. | Suraphong S. |  |  | CANCLE
464 |  | 3 | EPS-39004 | Include in submission EPS-39001 |  |  |  | Detailed Design - Diesel Fuel Storage Tanks for Power Generators : Material Approval - Building Service |  |  | Nichapa P. | Somsak S. | Sub | Pratan L. | Praphat M./ Supajak S. | Somsak S. | Praphat M. | Suraphong S. |  |  | CANCLE
465 | [7 empty] | Procurement / Manufacturing / Delivery Stage / FAT
466 | [7 empty] | Installation Menthod Statement
467 |  | 5 | EPS-59001 | OLW-ME-24/0383 | 2026-05-11 | A | BEM/M/ORM/S1475/69 | Installation Method Statement - Diesel Fuel Storage Tanks for Power Generators | [12 empty] | submitted
468 |  | 5 | EPS-59002 |  |  |  |  | Installation Method Statement - Diesel Fuel Storage Tanks for Power Generators - Building Services | [12 empty] | CANCLE
469 | [7 empty] | Testing and Commissioning Procedure
470 |  | 6 | EPS-69001 |  |  |  |  | Test Procedure - Diesel Fuel Storage Tanks for Power Generators
471 |  | 6 | EPS-69002 |  |  |  |  | Test Report - Diesel Fuel Storage Tanks for Power Generators
472 |  | 6 | EPS-69003 |  |  |  |  | Test Procedure - Diesel Fuel Storage Tanks for Power Generators - Building Services | [12 empty] | CANCLE
473 |  | 6 | EPS-69004 |  |  |  |  | Test Report - Diesel Fuel Storage Tanks for Power Generators - Building Services | [12 empty] | CANCLE
474 | [7 empty] | Training
475 | [7 empty] | As-Built Drawing, As-Built Configuration Data
476 |  | 8 | EPS-89001 |  |  |  |  | As-Built - Diesel Fuel Storage Tanks for Power Generators
477 |  | 8 | EPS-89002 |  |  |  |  | As-Built - Diesel Fuel Storage Tanks for Power Generators - Building Services | [12 empty] | CANCLE
478 | [7 empty] | O&M Manual
479 |  | 9 | EPS-99001 |  |  |  |  | O&M Manual - Diesel Fuel Storage Tanks for Power Generators - English
480 |  | 9 | EPS-99002 |  |  |  |  | O&M Manual - Diesel Fuel Storage Tanks for Power Generators - Thai Translation
481
482
483
484 | [7 empty] | GRS
485 | [7 empty] | Outline Design
486 | [7 empty] | Definitive Design
487 |  | 2 | GRS-29001 |  |  |  |  | Definitive Design - Graphic and Signage
488 | [7 empty] | Detailed Design
489 |  | 3 | GRS-39001 | OLW-ME-24/0222 | 2025-11-24 | A | BEM/M/ORM/S1433/68 | Detailed Design - Graphic and Signage on East Section, OR13 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. |  |  | submitted
490 |  | 3 | GRS-39001 | OLW-ME-24/0222 | 2026-03-05 | B | BEM/M/ORM/S1328/69 | Detailed Design - Graphic and Signage on East Section, OR13 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. |  |  | submitted
491 |  | 3 | GRS-39002 | OLW-ME-24/0325 | 2026-04-23 | A | BEM/M/ORM/S1329/69 | Detailed Design - Graphic and Signage on East Section, OR14 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. |  |  | submitted
492 |  | 3 | GRS-39003 | OLW-ME-24/0379 | 2026-05-06 | A | BEM/M/ORM/S1771/69 | Detailed Design - Graphic and Signage on East Section, OR15 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. |  |  | submitted
493 |  | 3 | GRS-39004 | OLW-ME-24/0385 | 2026-05-12 | A | BEM/M/ORM/S1770/69 | Detailed Design - Graphic and Signage on East Section, OR16 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. |  |  | submitted
494 |  | 3 | GRS-39005 | OLW-ME-24/0394 | 2026-05-21 | A | BEM/M/ORM/S1772/69 | Detailed Design - Graphic and Signage on East Section, OR17 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. |  |  | submitted
495 |  | 3 | GRS-39006 | OLW-ME-24/0403 | 2026-06-12 | A | BEM/M/ORM/S2000/69 | Detailed Design - Graphic and Signage on East Section, OR18 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. |  |  | submitted
496 |  | 3 | GRS-39007 | OLW-ME-24/0410 | 2026-06-15 | A | BEM/M/ORM/S1999/69 | Detailed Design - Graphic and Signage on East Section, OR19 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. |  |  | submitted
497 |  | 3 | GRS-39008 | Total 48 pages, A3 - 39 sheets |  |  |  | Detailed Design - Graphic and Signage on East Section, OR20 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S.
498 |  | 3 | GRS-39009 | Total 41 pages, A3 - 33 sheets |  |  |  | Detailed Design - Graphic and Signage on East Section, OR21 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S.
499 |  | 3 | GRS-39010 | Total 40 pages, A3 - 32 sheets |  |  |  | Detailed Design - Graphic and Signage on East Section, OR22 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S.
500 |  | 3 | GRS-39011 | Total 37 pages, A3 - 29 sheets |  |  |  | Detailed Design - Graphic and Signage on East Section, OR23 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S.
501 |  | 3 | GRS-39012 | OLW-ME-24/0416 | 2026-06-18 | A | BEM/M/ORM/S1998/69 | Detailed Design - Graphic and Signage on East Section, OR24 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. |  |  | submitted
502 |  | 3 | GRS-39013 | Total 50 pages, A3 - 41 sheets |  |  |  | Detailed Design - Graphic and Signage on East Section, OR25 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S.
503 |  | 3 | GRS-39014 | Total 48 pages, dwg. 39 sheets |  |  |  | Detailed Design - Graphic and Signage on East Section, OR26 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S.
504 |  | 3 | GRS-39015 | Total 73 pages, dwg. 40 sheets |  |  |  | Detailed Design - Graphic and Signage on East Section, OR27 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S.
505 |  | 3 | GRS-39016 | OLW-ME-24/0237 | 2025-12-11 | A | BEM/M/ORM/S1577/68 | Detailed Design - Graphic and Signage on East Section, OR28 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S. |  |  | submitted
506 |  | 3 | GRS-39016 |  | Total 42 pages 34 pages - A3 | B |  | Detailed Design - Graphic and Signage on East Section, OR28 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S.
507 |  | 3 | GRS-39017 |  | Total 41 pages 33 pages - A3 |  |  | Detailed Design - Graphic and Signage on East Section, OR29 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S.
508 |  | 3 | GRS-39018 |  |  |  |  | Detailed Design - Graphic and Signage on East Section, IVS, VS, EEEN and Transition Area | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S.
509 |  | 3 | GRS-39019 |  |  |  |  | Detailed Design - Graphic and Signage at Depot, Main Workshop and Other Buildings | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S.
510 |  | 3 | GRS-39020 |  |  |  |  | Detailed Design - Graphic and Signage at Depot, OCC and Admin Building | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S.
511 |  | 3 | GRS-39021 |  |  |  |  | Detailed Design - Graphic and Signage on East Section, at BSS1, BSS2 and Generator Building | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S.
512 |  | 3 | GRS-39022 |  |  |  |  | Detailed Design - Graphic and Signage on East Section, Safety Line for Depot Buildings | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S.
513 |  | 3 | GRS-39023 |  |  |  |  | Detailed Design - Graphic and Signage on East Section, Track Area at Depot | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S.
514 |  | 3 | GRS-39024 |  |  |  |  | Detailed Design - Graphic and Signage on East Section, Track Area at Main Line | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S.
515 |  | 3 | GRS-39025 |  |  |  |  | Detailed Design - Graphic and Signage on East Section, Power Supply for Signage | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S.
516 |  | 3 | GRS-39026 |  |  |  |  | Detailed Design - Graphic and Signage on West Section, OR02 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S.
517 |  | 3 | GRS-39027 |  |  |  |  | Detailed Design - Graphic and Signage on West Section, OR03 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S.
518 |  | 3 | GRS-39028 |  |  |  |  | Detailed Design - Graphic and Signage on West Section, OR04 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S.
519 |  | 3 | GRS-39029 |  |  |  |  | Detailed Design - Graphic and Signage on West Section, OR05 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S.
520 |  | 3 | GRS-39030 |  |  |  |  | Detailed Design - Graphic and Signage on West Section, OR06 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S.
521 |  | 3 | GRS-39031 |  |  |  |  | Detailed Design - Graphic and Signage on West Section, OR07 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S.
522 |  | 3 | GRS-39032 |  |  |  |  | Detailed Design - Graphic and Signage on West Section, OR08 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S.
523 |  | 3 | GRS-39033 |  |  |  |  | Detailed Design - Graphic and Signage on West Section, OR09 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S.
524 |  | 3 | GRS-39034 |  |  |  |  | Detailed Design - Graphic and Signage on West Section, OR10 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S.
525 |  | 3 | GRS-39035 |  |  |  |  | Detailed Design - Graphic and Signage on West Section, OR11 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S.
526 |  | 3 | GRS-39036 |  |  |  |  | Detailed Design - Graphic and Signage on West Section, OR12 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S.
527 |  | 3 | GRS-39037 |  |  |  |  | Detailed Design - Graphic and Signage on West Section, IVS and EEEN | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S.
528 |  | 3 | GRS-39038 |  |  |  |  | Detailed Design - Graphic and Signage on West Section, at BSS3 | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S.
529 |  | 3 | GRS-39039 |  |  |  |  | Detailed Design - Graphic and Signage on West Section, Track Area at Main Line | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S.
530 |  | 3 | GRS-39040 |  |  |  |  | Detailed Design - Graphic and Signage on West Section, Power Supply for Signage | 3.8 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Piyawat C. / Supajak S. | Sahachart S. | Brian C. | Suraphong S.
531 | [7 empty] | Procurement / Manufacturing / Delivery Stage / FAT
532 | [7 empty] | Installation Menthod Statement
533 |  | 5 | GRS-59001 |  |  |  |  | Installation Menthod Statement - Graphic and Signage
534 | [7 empty] | Testing and Commissioning Procedure
535 |  | 6 | GRS-69001 |  |  |  |  | Test Procedure - Graphic and Signage
536 | [7 empty] | Testing and Commissioning Stage / System Integration and Handover Report
537 |  | 6 | GRS-69002 |  |  |  |  | Test Report - Graphic and Signage on East Section, OR13
538 |  | 6 | GRS-69003 |  |  |  |  | Test Report - Graphic and Signage on East Section, OR14
539 |  | 6 | GRS-69004 |  |  |  |  | Test Report - Graphic and Signage on East Section, OR15
540 |  | 6 | GRS-69005 |  |  |  |  | Test Report - Graphic and Signage on East Section, OR16
541 |  | 6 | GRS-69006 |  |  |  |  | Test Report - Graphic and Signage on East Section, OR17
542 |  | 6 | GRS-69007 |  |  |  |  | Test Report - Graphic and Signage on East Section, OR18
543 |  | 6 | GRS-69008 |  |  |  |  | Test Report - Graphic and Signage on East Section, OR19
544 |  | 6 | GRS-69009 |  |  |  |  | Test Report - Graphic and Signage on East Section, OR20
545 |  | 6 | GRS-69010 |  |  |  |  | Test Report - Graphic and Signage on East Section, OR21
546 |  | 6 | GRS-69011 |  |  |  |  | Test Report - Graphic and Signage on East Section, OR22
547 |  | 6 | GRS-69012 |  |  |  |  | Test Report - Graphic and Signage on East Section, OR23
548 |  | 6 | GRS-69013 |  |  |  |  | Test Report - Graphic and Signage on East Section, OR24
549 |  | 6 | GRS-69014 |  |  |  |  | Test Report - Graphic and Signage on East Section, OR25
550 |  | 6 | GRS-69015 |  |  |  |  | Test Report - Graphic and Signage on East Section, OR26
551 |  | 6 | GRS-69016 |  |  |  |  | Test Report - Graphic and Signage on East Section, OR27
552 |  | 6 | GRS-69017 |  |  |  |  | Test Report - Graphic and Signage on East Section, OR28
553 |  | 6 | GRS-69018 |  |  |  |  | Test Report - Graphic and Signage on East Section, OR29
554 |  | 6 | GRS-69019 |  |  |  |  | Test Report - Graphic and Signage on East Section, IVS, VS, EEEN and Transition Area
555 |  | 6 | GRS-69020 |  |  |  |  | Test Report - Graphic and Signage at Depot, Main Workshop and Other Buildings
556 |  | 6 | GRS-69021 |  |  |  |  | Test Report - Graphic and Signage at Depot, OCC and Admin Building
557 |  | 6 | GRS-69022 |  |  |  |  | Test Report - Graphic and Signage on East Section, Safety Line for Depot Buildings
558 |  | 6 | GRS-69023 |  |  |  |  | Test Report - Graphic and Signage on East Section, at BSS1, BSS2 and Generator Building
559 |  | 6 | GRS-69024 |  |  |  |  | Test Report - Graphic and Signage on East Section, Track Area at Depot
560 |  | 6 | GRS-69025 |  |  |  |  | Test Report - Graphic and Signage on East Section, Track Area at Main Line
561 |  | 6 | GRS-69026 |  |  |  |  | Test Report - Graphic and Signage on East Section, Power Supply for Signage
562 |  | 6 | GRS-69027 |  |  |  |  | Test Report - Graphic and Signage on West Section, OR02
563 |  | 6 | GRS-69028 |  |  |  |  | Test Report - Graphic and Signage on West Section, OR03
564 |  | 6 | GRS-69029 |  |  |  |  | Test Report - Graphic and Signage on West Section, OR04
565 |  | 6 | GRS-69030 |  |  |  |  | Test Report - Graphic and Signage on West Section, OR05
566 |  | 6 | GRS-69031 |  |  |  |  | Test Report - Graphic and Signage on West Section, OR06
567 |  | 6 | GRS-69032 |  |  |  |  | Test Report - Graphic and Signage on West Section, OR07
568 |  | 6 | GRS-69033 |  |  |  |  | Test Report - Graphic and Signage on West Section, OR08
569 |  | 6 | GRS-69034 |  |  |  |  | Test Report - Graphic and Signage on West Section, OR09
570 |  | 6 | GRS-69035 |  |  |  |  | Test Report - Graphic and Signage on West Section, OR10
571 |  | 6 | GRS-69036 |  |  |  |  | Test Report - Graphic and Signage on West Section, OR11
572 |  | 6 | GRS-69037 |  |  |  |  | Test Report - Graphic and Signage on West Section, OR12
573 |  | 6 | GRS-69038 |  |  |  |  | Test Report - Graphic and Signage on West Section, IVS and EEEN
574 |  | 6 | GRS-69039 |  |  |  |  | Test Report - Graphic and Signage on West Section, at BSS3
575 |  | 6 | GRS-69040 |  |  |  |  | Test Report - Graphic and Signage on West Section, Track Area at Main Line
576 |  | 6 | GRS-69041 |  |  |  |  | Test Report - Graphic and Signage on West Section, Power Supply for Signage
577 | [7 empty] | Training
578
579 | [7 empty] | As-Built Drawing, As-Built Configuration Data
580 |  | 8 | GRS-89001 |  |  |  |  | As-Built - Graphic and Signage on East Section, OR13
581 |  | 8 | GRS-89002 |  |  |  |  | As-Built - Graphic and Signage on East Section, OR14
582 |  | 8 | GRS-89003 |  |  |  |  | As-Built - Graphic and Signage on East Section, OR15
583 |  | 8 | GRS-89004 |  |  |  |  | As-Built - Graphic and Signage on East Section, OR16
584 |  | 8 | GRS-89005 |  |  |  |  | As-Built - Graphic and Signage on East Section, OR17
585 |  | 8 | GRS-89006 |  |  |  |  | As-Built - Graphic and Signage on East Section, OR18
586 |  | 8 | GRS-89007 |  |  |  |  | As-Built - Graphic and Signage on East Section, OR19
587 |  | 8 | GRS-89008 |  |  |  |  | As-Built - Graphic and Signage on East Section, OR20
588 |  | 8 | GRS-89009 |  |  |  |  | As-Built - Graphic and Signage on East Section, OR21
589 |  | 8 | GRS-89010 |  |  |  |  | As-Built - Graphic and Signage on East Section, OR22
590 |  | 8 | GRS-89011 |  |  |  |  | As-Built - Graphic and Signage on East Section, OR23
591 |  | 8 | GRS-89012 |  |  |  |  | As-Built - Graphic and Signage on East Section, OR24
592 |  | 8 | GRS-89013 |  |  |  |  | As-Built - Graphic and Signage on East Section, OR25
593 |  | 8 | GRS-89014 |  |  |  |  | As-Built - Graphic and Signage on East Section, OR26
594 |  | 8 | GRS-89015 |  |  |  |  | As-Built - Graphic and Signage on East Section, OR27
595 |  | 8 | GRS-89016 |  |  |  |  | As-Built - Graphic and Signage on East Section, OR28
596 |  | 8 | GRS-89017 |  |  |  |  | As-Built - Graphic and Signage on East Section, OR29
597 |  | 8 | GRS-89018 |  |  |  |  | As-Built - Graphic and Signage on East Section, IVS, VS, EEEN and Transition Area
598 |  | 8 | GRS-89019 |  |  |  |  | As-Built - Graphic and Signage at Depot, Main Workshop and Other Buildings
599 |  | 8 | GRS-89020 |  |  |  |  | As-Built - Graphic and Signage at Depot, OCC and Admin Building
600 |  | 8 | GRS-89021 |  |  |  |  | As-Built - Graphic and Signage on East Section, at BSS1, BSS2 and Generator Building
601 |  | 8 | GRS-89022 |  |  |  |  | As-Built - Graphic and Signage on East Section, Safety Line for Depot Buildings
602 |  | 8 | GRS-89023 |  |  |  |  | As-Built - Graphic and Signage on East Section, Track Area at Depot
603 |  | 8 | GRS-89024 |  |  |  |  | As-Built - Graphic and Signage on East Section, Track Area at Main Line
604 |  | 8 | GRS-89025 |  |  |  |  | As-Built - Graphic and Signage on East Section, Power Supply for Signage
605 |  | 8 | GRS-89026 |  |  |  |  | As-Built - Graphic and Signage on West Section, OR02
606 |  | 8 | GRS-89027 |  |  |  |  | As-Built - Graphic and Signage on West Section, OR03
607 |  | 8 | GRS-89028 |  |  |  |  | As-Built - Graphic and Signage on West Section, OR04
608 |  | 8 | GRS-89029 |  |  |  |  | As-Built - Graphic and Signage on West Section, OR05
609 |  | 8 | GRS-89030 |  |  |  |  | As-Built - Graphic and Signage on West Section, OR06
610 |  | 8 | GRS-89031 |  |  |  |  | As-Built - Graphic and Signage on West Section, OR07
611 |  | 8 | GRS-89032 |  |  |  |  | As-Built - Graphic and Signage on West Section, OR08
612 |  | 8 | GRS-89033 |  |  |  |  | As-Built - Graphic and Signage on West Section, OR09
613 |  | 8 | GRS-89034 |  |  |  |  | As-Built - Graphic and Signage on West Section, OR10
614 |  | 8 | GRS-89035 |  |  |  |  | As-Built - Graphic and Signage on West Section, OR11
615 |  | 8 | GRS-89036 |  |  |  |  | As-Built - Graphic and Signage on West Section, OR12
616 |  | 8 | GRS-89037 |  |  |  |  | As-Built - Graphic and Signage on West Section, IVS and EEEN
617 |  | 8 | GRS-89038 |  |  |  |  | As-Built - Graphic and Signage on West Section, at BSS3
618 |  | 8 | GRS-89039 |  |  |  |  | As-Built - Graphic and Signage on West Section, Track Area at Main Line
619 |  | 8 | GRS-89040 |  |  |  |  | As-Built - Graphic and Signage on West Section, Power Supply for Signage
620 | [7 empty] | O&M Manual
621 |  | 9 | GRS-99001 |  |  |  |  | O&M Manual - Graphic and Signage - English
622 |  | 9 | GRS-99002 |  |  |  |  | O&M Manual - Graphic and Signage - Thai Translation
623
624
625
626 | [7 empty] | PSY
627 | [7 empty] | Outline Design
628 | [7 empty] | Definitive Design
629 | [7 empty] | Detailed Design
630 |  | 3 | PSY-39001 | OLW-ME-24/0038 | 2025-03-26 | A | BEM/M/ORM/S0065/68 | Detailed Design - BSS1 : Architectural Installation Drawing | 8.2 | ST/AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Praphat M. / Supajak S, | Sahachart S. | Praphat M. | Suraphong S. |  |  | submitted
631 |  | 3 | PSY-39001 | OLW-ME-24/0038 | 2025-08-01 | B | BEM/M/ORM/S0688/68 | Detailed Design - BSS1 : Architectural Installation Drawing | 8.2 | ST/AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Praphat M. / Supajak S, | Sahachart S. | Praphat M. | Suraphong S. |  |  | submitted
632 |  | 3 | PSY-39002 | OLW-ME-24/0039 | 2025-03-26 | A | BEM/M/ORM/S0066/68 | Detailed Design - BSS1 : Structural Installation Drawing | 8.2 | ST/AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Praphat M. / Supajak S, | Sahachart S. | Praphat M. | Suraphong S. |  |  | submitted
633 |  | 3 | PSY-39002 | OLW-ME-24/0039 | 2025-06-04 | B | BEM/M/ORM/S0357/68 | Detailed Design - BSS1 : Structural Installation Drawing | 8.2 | ST/AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Praphat M. / Supajak S, | Sahachart S. | Praphat M. | Suraphong S. |  |  | submitted
634 |  | 3 | PSY-39003 | OLW-ME-24/0181 | 2025-09-17 | A | BEM/M/ORM/S1033/68 | Detailed Design - BSS1 : Building Services Installation Drawing | 8.2 | EE/ME | Nichapa P. | Jaturong W. | Sub | Pratan L. | Praphat M. / Supajak S, | Jaturong W. | Praphat M. | Suraphong S. |  |  | submitted
635 |  | 3 | PSY-39004 | OLW-ME-24/0040 | 2025-03-17 | A | BEM/M/ORM/S0054/68 | Detailed Design - BSS2 : Architectural Installation Drawing | 8.2 | ST/AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Praphat M. / Supajak S, | Sahachart S. | Praphat M. | Suraphong S. |  |  | submitted
636 |  | 3 | PSY-39004 | OLW-ME-24/0040 | 2025-08-15 | B | BEM/M/ORM/S0651/68 | Detailed Design - BSS2 : Architectural Installation Drawing | 8.2 | ST/AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Praphat M. / Supajak S, | Sahachart S. | Praphat M. | Suraphong S. |  |  | submitted
637 |  | 3 | PSY-39005 | OLW-ME-24/0041 | 2025-03-17 | A | BEM/M/ORM/S0053/68 | Detailed Design - BSS2 : Structural Installation Drawing | 8.2 | ST/AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Praphat M. / Supajak S, | Sahachart S. | Praphat M. | Suraphong S. |  |  | submitted
638 |  | 3 | PSY-39005 | OLW-ME-24/0041 | 2025-07-18 | B | BEM/M/ORM/S0562/68 | Detailed Design - BSS2 : Structural Installation Drawing | 8.2 | ST/AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Praphat M. / Supajak S, | Sahachart S. | Praphat M. | Suraphong S. |  |  | submitted
639 |  | 3 | PSY-39006 | OLW-ME-24/0086 | 2025-05-19 | A | BEM/M/ORM/S0261/68 | Detailed Design - BSS2 : Building Services Installation Drawing | 8.2 | EE/ME | Nichapa P. | Jaturong W. | Sub | Pratan L. | Praphat M. / Supajak S, | Jaturong W. | Praphat M. | Suraphong S. |  |  | submitted
640 |  | 3 | PSY-39007 |  |  |  |  | Detailed Design - BSS1,2 : Material Approval - Civil & AR |  | ST/AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Praphat M. / Supajak S, | Sahachart S. | Praphat M. | Suraphong S.
641 |  | 3 | PSY-39008 | OLW-ME-24/0282 | 2026-02-09 | A | BEM/M/ORM/S0289/69 | Detailed Design - BSS1,2 : Material Approval - Building Services |  | EE/ME | Nichapa P. | Jaturong W. | Sub | Pratan L. | Praphat M. / Supajak S, | Jaturong W. | Praphat M. | Suraphong S. |  |  | submitted
642 |  | 3 | PSY-39009 | OLW-ME-24/0054 | 2025-04-05 | A | BEM/M/ORM/S0084/68 | Detailed Design - HV Cable Ducts from MEA Interface Point to BSS1 | 8.2 | ST/AR | Nichapa P. | Jaturong W. | Sub | Pratan L. | Praphat M. / Supajak S, | Jaturong W. | Praphat M. | Suraphong S. |  |  | submitted
643 | [7 empty] | Detailed Design - HV Cable Ducts from MEA Interface Point to BSS2 | 8.2 | ST/AR | Nichapa P. | Jaturong W. | Sub | Pratan L. | Praphat M. / Supajak S, | Jaturong W. | Praphat M. | Suraphong S. |  |  | CANCLE
644 |  | 3 | PSY-39010 | MOVE TO MDW MDW-39289 |  |  |  | Detailed Design - Earthing and Bonding Modification on East Section |  | EE/ME | Nichapa P. | Jaturong W. | Sub | Pratan L. | Praphat M. / Supajak S, | Jaturong W. | Praphat M. | Suraphong S. |  |  | CANCLE
645 |  | 3 | PSY-39011 | OLW-ME-24/0052 | 2025-03-26 | A | BEM/M/ORM/S0064/68 | Detailed Design - Steel Grating Raised Floor for EE Panel on East Section | 8.3 | ST/AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Praphat M. / Supajak S, | Sahachart S. | Praphat M. | Suraphong S. |  |  | submitted
646 | [7 empty] | Detailed Design - Steel Grating Raised Floor for EE Panel
647 | [7 empty] | Detailed Design - Steel grating raised floor support for all PSY switchgear panels and PSY cabinets in TSS and SSS rooms
648 | [7 empty] | Detailed Design - Steel Grating
649 | [7 empty] | Detailed Design - Podium
650 | [7 empty] | Detailed Design - Chainlink
651 | [7 empty] | Detailed Design - Support Transformer
652 |  | 3 | PSY-39012 | OLW-ME-24/0197 | 2025-10-17 | A | BEM/M/ORM/S1206/68 | Detailed Design - Overhead Traveling Crane for BSS1 | [6 empty] | Praphat M. / Supajak S, | 0 | Praphat M. | Suraphong S. |  |  | submitted
653 |  | 3 | PSY-39013 | OLW-ME-24/0162 | 2025-09-01 | A | BEM/M/ORM/S0912/68 | Detailed Design - Overhead Traveling Crane for BSS2 | [6 empty] | Praphat M. / Supajak S, | 0 | Praphat M. | Suraphong S. |  |  | submitted
654 |  | 3 | PSY-39014 |  |  |  |  | Detailed Design - Overhead Traveling Crane for BSS3 | [6 empty] | Praphat M. / Supajak S, | 0 | Praphat M. | Suraphong S.
655 |  | 3 | PSY-39015 | เตรียมออก 24/7/26 OLW-ME-24/0453 | Total page 75 page, A3 - 65 sheets |  |  | Detailed Design - BSS3 : Architectural Installation Drawing
656 |  | 3 | PSY-39016 |  |  |  |  | Detailed Design - BSS3 : Structural Installation Drawing
657 |  | 3 | PSY-39017 |  |  |  |  | Detailed Design - BSS3 : Building Services Installation Drawing
658 |  | 3 | PSY-39018 |  |  |  |  | Detailed Design - BSS3 : Material Approval - Civil & AR
659 |  | 3 | PSY-39019 |  |  |  |  | Detailed Design - BSS3 : Material Approval - Building Services
660 | [7 empty] | Detailed Design - Earthing and Bonding Modification on West Section
661 | [7 empty] | Detailed Design - Steel Grating Raised Floor for EE Panel on West Section
662 | [7 empty] | Procurement / Manufacturing / Delivery Stage / FAT
663 |  | 4 | PSY-49001 | OLW-ME-24/0193 | 2025-10-10 | A | BEM/M/ORM/S1109/68 | Factory Routine Test - Overhead Travelling Crane for BSS1 and BSS2 | [12 empty] | submitted
664 |  | 4 | PSY-49002 |  |  |  |  | Factory Routine Test - Overhead Travelling Crane for BSS3
665 | [7 empty] | Installation Menthod Statement
666 |  | 5 | PSY-59001 | OLW-ME-24/0272 | 2026-02-09 | A | BEM/M/ORM/S0318/69 | Installation Method Statement - Overhead Traveling Crane for BSS1 | [12 empty] | submitted
667 |  | 5 | PSY-59002 | OLW-ME-24/0224 | 2025-11-17 | A | BEM/M/ORM/S1352/68 | Installation Method Statement - Overhead Traveling Crane for BSS2 | [12 empty] | submitted
668 |  | 5 | PSY-59003 |  |  |  |  | Installation Method Statement - Overhead Traveling Crane for BSS3
669 | [7 empty] | Testing and Commissioning Procedure
670 |  | 6 | PSY-69001 | เตรียมออก 29/6/26 OLW-ME-24/0428 | 27 pages |  |  | Test Procedure - BSS1 : Architectural
671 |  | 6 | PSY-69003 | เตรียมออก 26/6/26 OLW-ME-24/0429 | 16 pages |  |  | Test Procedure - BSS1 : Structural
672 |  | 6 | PSY-69005 | OLW-ME-24/0300 | 2026-02-18 | A | BEM/M/ORM/S0514/69 | Test Procedure - BSS1 : Building Services Installation Drawing | [12 empty] | submitted
673 |  | 6 | PSY-69007 | เตรียมออก 26/6/26 OLW-ME-24/0430 | 27 pages |  |  | Test Procedure - BSS2 : Architectural
674 |  | 6 | PSY-69009 | เตรียมออก 26/6/26 OLW-ME-24/0431 | 16 pages |  |  | Test Procedure - BSS2 : Structural
675 |  | 6 | PSY-69011 | OLW-ME-24/0326 | 2026-03-18 | A | BEM/M/ORM/S0877/69 | Test Procedure - BSS2 : Building Services Installation Drawing | [12 empty] | submitted
676 |  | 6 | PSY-69013 | OLW-ME-24/0432 9 pages |  |  |  | Test Procedure - HV Cable Ducts from MEA Interface Point to BSS1
677 |  | 6 | PSY-690XX |  |  |  |  | Test Procedure - Earthing and Bonding Modification on East Section | [12 empty] | CANCLE
678 |  | 6 | PSY-69015 | เตรียมออก 29/6/2026 OLW-ME-24/0433 | 9 pages |  |  | Test Procedure - Steel Grating Raised Floor for EE Panel on East Section
679 |  | 6 | PSY-69017 | OLW-ME-24/0285 | 2026-02-12 | A | BEM/M/ORM/S0407/69 | Test Procedure - Overhead Travelling Crane for BSS1 and BSS2 | [12 empty] | submitted
680 |  | 6 | PSY-69019 |  |  |  |  | Test Procedure - Overhead Travelling Crane for BSS3
681 |  | 6 | PSY-690XX |  |  |  |  | Test Procedure - Earthing and Bonding Modification on West Section
682 |  | 6 | PSY-690XX |  |  |  |  | Test Procedure - Steel Grating Raised Floor for EE Panel on West Section
683 | [7 empty] | Testing and Commissioning Stage / System Integration and Handover Report
684 |  | 6 | PSY-69002 |  |  |  |  | Test Report - BSS1 : Architectural Installation
685 |  | 6 | PSY-69004 |  |  |  |  | Test Report - BSS1 : Structural Installation
686 |  | 6 | PSY-69006 |  |  |  |  | Test Report - BSS1 : Building Services Installation
687 |  | 6 | PSY-69008 |  |  |  |  | Test Report - BSS2 : Architectural Installation
688 |  | 6 | PSY-69010 |  |  |  |  | Test Report - BSS2 : Structural Installation
689 |  | 6 | PSY-69012 |  |  |  |  | Test Report - BSS2 : Building Services Installation
690 |  | 6 | PSY-69014 |  |  |  |  | Test Report - HV Cable Ducts from MEA Interface Point to BSS1
691 |  | 6 | PSY-690XX |  |  |  |  | Test Report - Earthing and Bonding Modification on East Section | [12 empty] | CANCLE
692 |  | 6 | PSY-69016 |  |  |  |  | Test Report - Steel Grating Raised Floor for EE Panel on East Section
693 |  | 6 | PSY-69018 | OLW-ME-24/0323 | 2026-03-17 | A | BEM/M/ORM/S0884/69 | Test Report - Overhead Travelling Crane for BSS1 and BSS2 | [12 empty] | submitted
694 |  | 6 | PSY-69020 |  |  |  |  | Test Report - Overhead Travelling Crane for BSS3
695 |  | 6 | PSY-690XX |  |  |  |  | Test Report - Earthing and Bonding Modification on West Section
696 |  | 6 | PSY-690XX |  |  |  |  | Test Report - Steel Grating Raised Floor for EE Panel on West Section
697 | [7 empty] | Training
698 |  | 7 | PSY-79001 | Delete, crane is provided for installation phase of ORL project. |  |  |  | Training Manual - Overhead Travelling Crane for BSS1 and BSS2 - English | [12 empty] | CANCLE
699 |  | 7 | PSY-79002 | Delete, crane is provided for installation phase of ORL project. |  |  |  | Training Manual - Overhead Travelling Crane for BSS1 and BSS2 - Thai Translation | [12 empty] | CANCLE
700 |  | 7 | PSY-79003 | Delete, crane is provided for installation phase of ORL project. |  |  |  | Training Manual - Overhead Travelling Crane for BSS3 - English | [12 empty] | CANCLE
701 |  | 7 | PSY-79004 | Delete, crane is provided for installation phase of ORL project. |  |  |  | Training Manual - Overhead Travelling Crane for BSS3 - Thai Translation | [12 empty] | CANCLE
702 | [7 empty] | As-Built Drawing, As-Built Configuration Data
703 |  | 8 | PSY-89001 |  |  |  |  | As-Built - BSS1 : Architectural Installation Drawing
704 |  | 8 | PSY-89002 |  |  |  |  | As-Built - BSS1 : Structural Installation Drawing
705 |  | 8 | PSY-89003 |  |  |  |  | As-Built - BSS1 : Building Services Installation Drawing
706 |  | 8 | PSY-89004 |  |  |  |  | As-Built - BSS2 : Architectural Installation Drawing
707 |  | 8 | PSY-89005 |  |  |  |  | As-Built - BSS2 : Structural Installation Drawing
708 |  | 8 | PSY-89006 |  |  |  |  | As-Built - BSS2 : Building Services Installation Drawing
709 |  | 8 | PSY-89007 |  |  |  |  | As-Built - HV Cable Ducts from MEA Interface Point to BSS1
710 |  | 8 | PSY-890XX |  |  |  |  | As-Built - Earthing and Bonding Modification on East Section | [12 empty] | CANCLE
711 |  | 8 | PSY-89008 |  |  |  |  | As-Built - Steel Grating Raised Floor for EE Panel on East Section
712 |  | 8 | PSY-89009 |  |  |  |  | As-Built - Overhead Traveling Crane for BSS1
713 |  | 8 | PSY-89010 |  |  |  |  | As-Built - Overhead Traveling Crane for BSS2
714 |  | 8 | PSY-89011 |  |  |  |  | As-Built - Overhead Traveling Crane for BSS3
715 |  | 8 | PSY-890XX |  |  |  |  | As-Built - Earthing and Bonding Modification on West Section
716 |  | 8 | PSY-890XX |  |  |  |  | As-Built - Steel Grating Raised Floor for EE Panel on West Section
717 | [7 empty] | O&M Manual
718 |  | 9 | PSY-99001 |  |  |  |  | O&M Manual - Overhead Travelling Crane for BSS1 and BSS2 - English
719 |  | 9 | PSY-99002 |  |  |  |  | O&M Manual - Overhead Travelling Crane for BSS1 and BSS2 - Thai Translation
720 |  | 9 | PSY-99003 |  |  |  |  | O&M Manual - Overhead Travelling Crane for BSS3 - English
721 |  | 9 | PSY-99004 |  |  |  |  | O&M Manual - Overhead Travelling Crane for BSS3 - Thai Translation
722
723
724
725 | [7 empty] | SCADA
726 | [7 empty] | Outline Design
727 | [7 empty] | Definitive Design
728 | [7 empty] | Detailed Design
729 |  | 3 | SCA-39200 |  |  |  |  | Detailed Design - Modification of BEMS to receive PSD Signal on East Section | 9.1 | SCA | Kusuma K. | Thanthip S. | Sub | Pratan L. | Wanlop W./ K.Supajak S. | Thanthip S. | Wanlop W. | Suraphong S. |  |  | CANCLE
730 |  | 3 | SCA-39201 |  |  |  |  | Detailed Design - Modification of Escalator Interface Point with CCTV and SCADA on East Section | 9.3 | SCA | Kusuma K. | Thanthip S. | Sub | Pratan L. | Wanlop W./ K.Supajak S. | Thanthip S. | Wanlop W. | Suraphong S. |  |  | CANCLE
731 |  | 3 | SCA-39202 |  |  |  |  | Detailed Design - Modification of Fire Alarm System Interface Point with CCTV and SCADA on East Section |  |  | Kusuma K. | Thanthip S. | Sub | Pratan L. | Wanlop W./ K.Supajak S. | Thanthip S. | Wanlop W. | Suraphong S. |  |  | CANCLE
732 |  | 3 | SCA-39203 |  |  |  |  | Detailed Design - Modification of SCADA Hardwire on East Section | *NEW* | SCA | Kusuma K. | Thanthip S. | Sub | Pratan L. | Wanlop W./ K.Supajak S. | Thanthip S. | Wanlop W. | Suraphong S. |  |  | CANCLE
733 | [7 empty] | Procurement / Manufacturing / Delivery Stage / FAT
734 | [7 empty] | Installation Menthod Statement
735 | [7 empty] | Testing and Commissioning Procedure
736 |  | 6 | SCA-69200 |  |  |  |  | Test Procedure - Modification of BEMS to receive PSD Signal on East Section | [12 empty] | CANCLE
737 |  | 6 | SCA-69202 |  |  |  |  | Test Procedure - Modification of Escalator Interface Point with CCTV and SCADA on East Section | [12 empty] | CANCLE
738 |  | 6 | SCA-69204 |  |  |  |  | Test Procedure - Modification of Fire Alarm System Interface Point with CCTV and SCADA on East Section | [12 empty] | CANCLE
739 |  | 6 | SCA-69206 |  |  |  |  | Test Procedure - Modification of SCADA Hardwire on East Section | [12 empty] | CANCLE
740 | [7 empty] | Testing and Commissioning Stage / System Integration and Handover Report
741 |  | 6 | SCA-69201 |  |  |  |  | Test Report - Modification of BEMS to receive PSD Signal on East Section | [12 empty] | CANCLE
742 |  | 6 | SCA-69203 |  |  |  |  | Test Report - Modification of Escalator Interface Point with CCTV and SCADA on East Section | [12 empty] | CANCLE
743 |  | 6 | SCA-69205 |  |  |  |  | Test Report - Modification of Fire Alarm System Interface Point with CCTV and SCADA on East Section | [12 empty] | CANCLE
744 |  | 6 | SCA-69207 |  |  |  |  | Test Report - Modification of SCADA Hardwire on East Section | [12 empty] | CANCLE
745 | [7 empty] | Training
746 | [7 empty] | As-Built Drawing, As-Built Configuration Data
747 |  | 8 | SCA-89200 |  |  |  |  | As-Built - Modification of BEMS to receive PSD Signal on East Section | [12 empty] | CANCLE
748 |  | 8 | SCA-89201 |  |  |  |  | As-Built - Modification of Escalator Interface Point with CCTV and SCADA on East Section | [12 empty] | CANCLE
749 |  | 8 | SCA-89202 |  |  |  |  | As-Built - Modification of Fire Alarm System Interface Point with CCTV and SCADA on East Section | [12 empty] | CANCLE
750 |  | 8 | SCA-89203 |  |  |  |  | As-Built - Modification of SCADA Hardwire on East Section | [12 empty] | CANCLE
751 | [7 empty] | O&M Manual
752
753
754
755 | [7 empty] | MDW
756 | [7 empty] | Outline Design
757 |  | 1 | MDW-19242 |  |  |  |  | Outline Design - Modification Works for Training Room at Ratchada Station
758 |  | 1 | MDW-19297 |  |  |  |  | Outline Design - Training Room at Ratchada Station (Part 2)
759 | [7 empty] | Definitive Design
760 |  | 2 | MDW-29001 |  |  |  |  | Definitive Design - Modification Works at Station and Depot | [12 empty] | CANCLE
761 |  | 2 | MDW-29200 |  |  |  |  | Definitive Design - Driver Train Simulation Room and Train Crew Office at MRT Blue Line Thailand Cultural Centre Station
762 |  | 2 | MDW-29002 |  |  |  |  | Definitive Design - Train Crew Office at MRT Blue Line Thailand Cultural Centre Station | [12 empty] | CANCLE
763 |  | 2 | MDW-29001 |  |  |  |  | Definitive Design - Modification Works for Training Room at MRT Blue Line Ratchada Station
764 | [7 empty] | Detailed Design
765 |  | 3 | MDW-39001 | OLW-ME-24/0150 | 2025-10-01 | A | BEM/M/ORM/S1135/68 | Detailed Design - Modification of Depot Track Alignment at Stabling Yard | 6.4 | ST | Nichapa P. | Kamphol H. | Sub | Suchock P. | Supajak S. | Kamphol H. | Supajak S. | Suraphong S. |  |  | submitted
766 |  | 3 | MDW-39002 | OLW-ME-24/0208 | 2025-11-07 | A | BEM/M/ORM/S1309/68 | Detailed Design - Modification Motorized Gate and Shelters at Test Track Depot - Civil & AR | 6.1 | ST | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Eddy / Supajak S. | Sahachart S. | Supajak S. | Suraphong S. |  |  | submitted
767 |  | 3 | MDW-39002 | OLW-ME-24/0208 | 2026-02-16 | B | BEM/M/ORM/S0668/69 | Detailed Design - Modification Motorized Gate and Shelters at Test Track Depot - Civil & AR | 6.1 | ST | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Eddy / Supajak S. | Sahachart S. | Supajak S. | Suraphong S. |  |  | submitted
768 |  | 3 | MDW-39003 | OLW-ME-24/0180 | 2025-10-07 | A | BEM/M/ORM/S1136/68 | Detailed Design - Modification Motorized Gate and Shelters at Test Track Depot - Building Service | 6.1 | ST | Nichapa P. | Atiraj K. | Sub | Pratan L. | Eddy / Supajak S. | Atiraj K. | Supajak S. | Suraphong S. |  |  | submitted
769 |  | 3 | MDW-39004 | OLW-ME-24/0419 | 2026-07-09 | A | BEM/M/ORM/S2140/69 | Detailed Design - Rubber Gap Fillers on Platform Edge on East Section | 4.2 | ST/AR | Nichapa P. | Kamphol H. | Sub | Suchock P. | Supajak S. | Kamphol H. | Supajak S. | Suraphong S. |  |  | submitted
770 |  | 3 | MDW-39001 |  |  |  |  | Detailed Design - Eye Adaptation Lighting at Transition Area and Depot Approach | 3.16 | EE | Nichapa | Jaturong | Sub | Pratan | Supajak S. | [5 empty] | CANCLE
771 |  | 3 | MDW-39002 |  |  |  |  | Detailed Design - Dangerous Waste Storage Building in Depot | 3.5 | ST/AR | Wijittra | Peerapat | Peerapat | Sahachart | Supajak S. | [5 empty] | CANCLE
772 |  | 3 | MDW-39003 |  |  |  |  | Detailed Design - General Waste Storage Building in Depot | 3.6 | ST/AR | Wijittra | Peerapat | Peerapat | Sahachart | Supajak S. | [5 empty] | CANCLE
773 |  | 3 | MDW-39004 |  |  |  |  | Detailed Design - Wayside Cable Containment in Depot | [12 empty] | CANCLE
774 | [7 empty] | Detailed Design - PSY Wayside Cable Containment for 24 Kv Cable under the Depot slab | 3.4 | EE | Kusuma | Monchai | Peerapat | Pratan
775 | [7 empty] | Detailed Design - COM/SIG Wayside Cable Containment in the Depot | 3.4 | EE | Kusuma | Montri | Peerapat | Pratan
776 |  | 3 | MDW-39005 |  |  |  |  | Detailed Design - Driver Train Simulation Room and AFC Training Room Modification - Civil & AR |  | ST/AR | Wijittra | Somsak | Peerapat | Suchock | Supajak S. | [5 empty] | CANCLE
777 |  | 3 | MDW-39006 |  |  |  |  | Detailed Design - Driver Train Simulation Room and AFC Training Room Modification - Building Services |  | EE/ME | Nichapa | Jaturong | Sub | Pratan | Supajak S. | [5 empty] | CANCLE
778 |  | 3 | MDW-39200 | OLW-ME-24/0024 | 2025-03-03 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment Material for Approval | 3.4 | EE | Kusuma K. | Montri S. | Sub | Pratan L. | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted
779 |  | 3 | MDW-39201 | OLW-ME-24/0077 | 2025-03-24 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of OR13 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted
780 |  | 3 | MDW-39202 | OLW-ME-24/0078 | 2025-03-24 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of OR14 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted
781 |  | 3 | MDW-39203 | OLW-ME-24/0109 | 2025-06-20 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of OR15 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted
782 |  | 3 | MDW-39204 | OLW-ME-24/0106 | 2025-06-20 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of OR16 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted
783 |  | 3 | MDW-39205 | OLW-ME-24/0107 | 2025-06-20 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of OR17 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted
784 |  | 3 | MDW-39206 | OLW-ME-24/0027 | 2025-03-03 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of OR18 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted
785 |  | 3 | MDW-39207 | OLW-ME-24/0028 | 2025-03-03 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of OR19 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted
786 |  | 3 | MDW-39208 | OLW-ME-24/0029 | 2025-03-03 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of OR20 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted
787 |  | 3 | MDW-39209 | OLW-ME-24/0030 | 2025-03-03 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of OR21 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted
788 |  | 3 | MDW-39210 | OLW-ME-24/0031 | 2025-03-03 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of OR22 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted
789 |  | 3 | MDW-39211 | OLW-ME-24/0036 | 2025-03-06 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of OR23 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted
790 |  | 3 | MDW-39212 | OLW-ME-24/0037 | 2025-03-06 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of OR24 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted
791 |  | 3 | MDW-39213 | OLW-ME-24/0046 | 2025-03-06 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of OR25 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted
792 |  | 3 | MDW-39214 | OLW-ME-24/0047 | 2025-03-06 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of OR26 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted
793 |  | 3 | MDW-39215 | OLW-ME-24/0048 | 2025-03-06 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of OR27 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted
794 |  | 3 | MDW-39216 | OLW-ME-24/0032 | 2025-03-03 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of OR28 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted
795 |  | 3 | MDW-39217 | OLW-ME-24/0033 | 2025-03-03 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of OR29 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted
796 |  | 3 | MDW-39218 | OLW-ME-24/0168 | 2025-09-03 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of VS02 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted
797 |  | 3 | MDW-39219 | OLW-ME-24/0169 | 2025-09-03 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of VS03 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted
798 |  | 3 | MDW-39220 | OLW-ME-24/0170 | 2025-09-03 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of IVS08 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted
799 |  | 3 | MDW-39221 | OLW-ME-24/0171 | 2025-09-03 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of IVS09 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted
800 |  | 3 | MDW-39222 | OLW-ME-24/0172 | 2025-09-03 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of IVS10 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted
801 |  | 3 | MDW-39223 | OLW-ME-24/0173 | 2025-09-03 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of IVS11 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted
802 |  | 3 | MDW-39224 | OLW-ME-24/0174 | 2025-11-07 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of IVS12 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted
803 |  | 3 | MDW-39225 | OLW-ME-24/0034 | 2025-03-03 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of IVS13 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted
804 |  | 3 | MDW-39226 | OLW-ME-24/0083 | 2025-05-14 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of IVS14 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted
805 |  | 3 | MDW-39227 | OLW-ME-24/0084 | 2025-05-14 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of IVS15 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted
806 |  | 3 | MDW-39228 | OLW-ME-24/0088 | 2025-05-20 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of IVS16 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted
807 |  | 3 | MDW-39229 | OLW-ME-24/0089 | 2025-05-20 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of IVS17 | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted
808 |  | 3 | MDW-39230 | OLW-ME-24/0175 | 2025-09-03 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of EEEN | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted
809 |  | 3 | MDW-39231 | OLW-ME-24/0081 | 2025-05-14 | A | Internal Only | Detailed Design - Modification Work of M&E Cable Containment of Orange Line - Depot | 3.4 | EE | Kusuma K. | Montri S. | Sub | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | submitted
810 |  | 3 | MDW-39232 |  |  |  |  | Detailed Design - Level Crossing at Turnout and Track Slab Crossing on Main Line East Section | 3.14 | ST | Nichapa P. | Kamphol H. | Peerapat B. | Suchock P. | Supajak S. | Kamphol H. | Supajak S. | Suraphong S.
811 |  | 3 | MDW-39233 |  |  |  |  | Detailed Design - Main Line Cable Trough Modification on East Section | [12 empty] | CANCLE
812 |  | 3 | MDW-39233 |  |  |  |  | Detailed Design - Main Line Cable Trough Modification on East Section (PSY) | 3.10 | AR | Kusuma K. | Sahachart S. | Peerapat B. | Tanyawit K. | Supajak S. | Monchai R. | Supajak S. | Suraphong S.
813 |  | 3 | MDW-39234 |  |  |  |  | Detailed Design - Main Line Cable Trough Modification on East Section (SIG/COM) | 3.10 | AR | Kusuma K. | Montri S. | Peerapat B. | submitted | Supajak S. | Montri S. | Supajak S. | Suraphong S.
814 |  | 3 | MDW-39235 | OLW-ME-24/0055 | 2025-05-09 | A | Internal Only | Detailed Design - Raised Floor Installation on East Section | 3.3 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Supajak S. | Sahachart S. | Supajak S. | Suraphong S. |  |  | submitted
815 | [7 empty] | Detailed Design - Add Raised Floor and Finish Epoxy Floor in Commercial rm (Sig) at ELEV Station
816 | [7 empty] | Detailed Design - Add Raised Floor in SCADA / CCTV Maintenance Room
817 | [7 empty] | Detailed Design - Add Raised Floor in Maintenance Management Room
818 | [7 empty] | Detailed Design - Add Raised Floor in Playback and Training Room
819 | [7 empty] | Detailed Design - Add Raised Floor in Backup Control Room
820 | [7 empty] | Detailed Design - Finish Epoxy Floor in Commercial rm (UPS Room) at ELEV Station
821 | [7 empty] | Detailed Design - Add Raised Floor in Trainning Room (New SIG Maintenance Room)
822 |  | 3 | MDW-39236 | OLE-ME-24/0043 | 2025-08-19 | A | Internal Only | Detailed Design - Bird Protection System at Depot Buildings | 3.11 | AR | Wijittra M. | Sahachart S. | Peerapat | Tanyawit K. | Supajak S. | Sahachart S. | Supajak S. | Suraphong S. |  |  | submitted
823 |  | 3 | MDW-39237 |  |  |  |  | Detailed Design - Central BEMS for the MRT Orange Line System East Section | 3.21 | COM | Kusuma K. | Thanthip S. | Sub | Pratan L. | Supajak S. | Thanthip S. | Supajak S. | Suraphong S.
824 |  | 3 | MDW-39238 |  |  |  |  | Detailed Design - Central BEMS for the MRT Orange Line System West Section | 3.21 | COM | Kusuma K. | Thanthip S. | Sub | Pratan L. | Supajak S. | Thanthip S. | Supajak S. | Suraphong S.
825 |  | 3 | MDW-39239 | OLW-ME-24/0187 | 2025-10-01 | A | Internal Only | Detailed Design - Access Panel for TSS, SSS1,SSS2 Room in Depot | 3.13 | ST | Wijittra M. | Sahachart S. | Peerapat | Tanyawit K. | Supajak S. | Sahachart S. | Supajak S. | Suraphong S. |  |  | submitted
826 |  | 3 | MDW-39240 | OLW-ME-24/0216 | 2025-11-11 | A | Internal Only | Detailed Design - Driver Train Simulation Room and Train Crew Office at OR18 - Civil & AR | 3.12 | ST/AR | Nichapa P. | Sahachart S. | Peerapat | Tanyawit K. | Supajak S. | Sahachart S. | Supajak S. | Suraphong S. |  |  | submitted
827 |  | 3 | MDW-39241 | OLW-ME-24/0203 |  |  | Internal Only | Detailed Design - Driver Train Simulation Room and Train Crew Office at OR18 - Building Services | 3.12 | EE/ME | Nichapa P. | Jaturong W. | Sub | Pratan L. | Supajak S. | Jaturong W. | Supajak S. | Suraphong S.
828 |  | 3 | MDW-39242 | OLW-ME-24/0192 | 2025-10-07 | A | Internal Only | Detailed Design - Modification Works for Training Room at Ratchada Station | 3.1 | EE/ME | Nichapa P. | Boonprasert F. | Sub | Pratan L. | Supajak S. | Boonprasert F. | Supajak S. | Suraphong S. |  |  | submitted
829 |  | 3 | MDW-39243 | OLW-ME-24/0119 | 2025-07-21 | A | Internal Only | Detailed Design - Eye Adaptation Lighting at Transition Area and Depot Approach | 3.16 | EE | Nichapa P. | Jaturong W. | Sub | Pratan L. | Supajak S. | Jaturong W. | Supajak S. | Suraphong S. |  |  | submitted
830 |  | 3 | MDW-39244 |  |  |  |  | Detailed Design - AFC Training Room Modification - Civil & AR | 3.17 | ST/AR | Wijittra M. | Somsak S. | Peerapat | Suchock | Supajak S. | Somsak S. | Supajak S. | Suraphong S.
831 |  | 3 | MDW-39245 | OLW-ME-24/0312 | 2026-02-27 | A | Internal Only | Detailed Design - AFC Training Room Modification - Building Services | 3.17 | EE/ME | Nichapa P. | Jaturong W. | Sub | Pratan L. | Supajak S. | Jaturong W. | Supajak S. | Suraphong S. |  |  | submitted
832 | [7 empty] | Detailed Design - Rooms and Building Service Systems Modification in Stations Area | 3.1.1
833 |  | 3 | MDW-39246 | OLW-ME-24/0235 | 2025-12-11 | A | Internal Only | Detailed Design - Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR13 - OR17 | 3.1.1.10 | EE | Nichapa P. | Atiraj K. | Sub | Pratan L. | Supajak S. | Atiraj K. | Supajak S. | Suraphong S. |  |  | submitted
834 |  | 3 | MDW-39247 | OLW-ME-24/0185 | 2025-09-15 | A | Internal Only | Detailed Design - Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR18 - OR22 | 3.1.1.10 | EE | Nichapa P. | Atiraj K. | Sub | Pratan L. | Supajak S. | Atiraj K. | Supajak S. | Suraphong S. |  |  | submitted
835 |  | 3 | MDW-39247 | OLW-ME-24/0185 |  | B | Internal Only | Detailed Design - Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR18 - OR22 | 3.1.1.10 | EE | Nichapa P. | Atiraj K. | Sub | Pratan L. | Supajak S. | Atiraj K. | Supajak S. | Suraphong S.
836 |  | 3 | MDW-39248 | OLW-ME-24/0202 | 2025-10-22 | A | Internal Only | Detailed Design - Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR23 - OR29 | 3.1.1.10 | EE | Nichapa P. | Atiraj K. | Sub | Pratan L. | Supajak S. | Atiraj K. | Supajak S. | Suraphong S. |  |  | submitted
837 |  | 3 | MDW-39248 | OLW-ME-24/0202 | 2026-01-28 | B | Internal Only | Detailed Design - Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR23 - OR29 | 3.1.1.10 | EE | Nichapa P. | Atiraj K. | Sub | Pratan L. | Supajak S. | Atiraj K. | Supajak S. | Suraphong S. |  |  | submitted
838 |  | 3 | MDW-39249 | OLW-ME-24/0044 | 2025-05-19 | A | Internal Only | Detailed Design - SOR Counter and Workstation Hanging Support Installation on East Section | 3.1.1.12 | AR | Wijittra M. | Sahachart S. | Peerapat | Tanyawit K. | Supajak S. | Sahachart S. | Supajak S. | Suraphong S. |  |  | submitted
839 |  | 3 | MDW-39250 | OLW-ME-24/0051 | 2025-06-30 | A | Internal Only | Detailed Design - Ticket Office Modification on East Section | 3.1.1.12 | AR | Wijittra M. | Sahachart S. | Peerapat | Tanyawit K. | Supajak S. | Sahachart S. | Supajak S. | Suraphong S. |  |  | submitted
840 | [7 empty] | Detailed Design - Modify Raise Floor for Ticket Office Counter at OR23-29
841 | [7 empty] | Detailed Design - Modify Ticket Office Counter at OR20-22
842 |  | 3 | MDW-39251 |  |  |  |  | Detailed Design - Modification of Eletrical System in Telecommunication Room at OR14 | 3.1.1.1,3.1.1.2 | EE | Nichapa P. | Jaturong W. | Sub | Pratan L. | Supajak S. | Jaturong W. | Supajak S. | Suraphong S. |  |  | CANCLE
843 |  | 3 | MDW-39252 | OLW-ME-24/0230 | 2025-11-19 | A | Internal Only | Detailed Design - Modification of Fire Suppression System (N2) in Commerial Room at OR14 | 3.1.1.1,3.1.1.2 | ME | Nichapa P. | Boonprasert F. | Sub | Pratan L. | Supajak S. | Boonprasert F. | Supajak S. | Suraphong S. |  |  | submitted
844 |  | 3 | MDW-39253 | OLW-ME-24/0100 | 2025-07-08 | A | Internal Only | Detailed Design - Modification of Civil Work in Telecommunication Room at OR14 | 3.1.1.1,3.1.1.2 | ST | Wijittra M. | Sahachart S. | Peerapat | Tanyawit K. | Supajak S. | Sahachart S. | Supajak S. | Suraphong S. |  |  | submitted
845 |  | 3 | MDW-39254 | OLW-ME-24/0266 | 2026-01-15 | A | Internal Only | Detailed Design - Modification in Staff Mess Room at OR13-OR17 | 3.1.1.1,3.1.1.2 | ME | Nichapa P. | Atiraj K. | Sub | Pratan L. | Supajak S. | Atiraj K. | Supajak S. | Suraphong S. |  |  | submitted
846 |  | 3 | MDW-39255 | OLW-ME-24/0210 | 2025-11-10 | A | Internal Only | Detailed Design - Modification in Staff Mess Room at OR18-OR22 | 3.1.1.1,3.1.1.2 | ME | Nichapa P. | Atiraj K. | Sub | Pratan L. | Supajak S. | Atiraj K. | Supajak S. | Suraphong S. |  |  | submitted
847 |  | 3 | MDW-39256 | OLW-ME-24/0274 | 2026-01-28 | A | Internal Only | Detailed Design - Modification in Staff Mess Room at OR23-OR29 | 3.1.1.1,3.1.1.2 | ME | Nichapa P. | Atiraj K. | Sub | Pratan L. | Supajak S. | Atiraj K. | Supajak S. | Suraphong S. |  |  | submitted
848 |  | 3 | MDW-39257 | OLW-ME-24/0126 | 2025-08-18 | A |  | Detailed Design - Modification of Air Conditioning in CER and SER at OR13-OR19 | 3.1.1.1,3.1.1.2 | ME | Nichapa P. | Boonprasert F. | Sub | Pratan L. | Supajak S. | Boonprasert F. | Supajak S. | Suraphong S. |  |  | submitted
849 |  | 3 | MDW-39258 | OLW-ME-24/0117 | 2025-07-07 | A |  | Detailed Design - Modification of Air Conditioning in CER and SER at OR20-OR22 | 3.1.1.1,3.1.1.2 | ME | Nichapa P. | Boonprasert F. | Sub | Pratan L. | Supajak S. | Boonprasert F. | Supajak S. | Suraphong S. |  |  | submitted
850 |  | 3 | MDW-39258 | OLW-ME-24/0117 | 2025-08-18 | B |  | Detailed Design - Modification of Air Conditioning in CER and SER at OR20-OR22 | 3.1.1.1,3.1.1.2 | ME | Nichapa P. | Boonprasert F. | Sub | Pratan L. | Supajak S. | Boonprasert F. | Supajak S. | Suraphong S. |  |  | submitted
851 |  | 3 | MDW-39259 | OLW-ME-24/0120 | 2025-08-18 | A |  | Detailed Design - Modification of Air Conditioning in CER and SER at OR23-OR29 | 3.1.1.1,3.1.1.2 | ME | Nichapa P. | Boonprasert F. | Sub | Pratan L. | Supajak S. | Boonprasert F. | Supajak S. | Suraphong S. |  |  | submitted
852 |  | 3 | MDW-39260 | OLW-ME-24/0177 | 2025-10-27 | A |  | Detailed Design - Modification of Air Conditioning in M&E Room at OCC Building | 3.1.1.1,3.1.1.2 | ME | Nichapa P. | Boonprasert F. | Sub | Pratan L. | Supajak S. | Boonprasert F. | Supajak S. | Suraphong S. |  |  | submitted
853 | [7 empty] | Detailed Design - Rooms and Building Service Systems Modification in Depot Area | 3.2
854 |  | 3 | MDW-39261 | OLW-ME-24/0188 | 2025-10-01 | A | Internal Only | Detailed Design - Provision of UPS for MDB Control at Main Workshop, OCC Building, Admin Building, Stabling Yard and Train Washing Plant | 3.1.2 | EE | Nichapa P. | Jaturong W. | Sub | Pratan L. | Supajak S. | Jaturong W. | Supajak S. | Suraphong S. |  |  | submitted
855 |  | 3 | MDW-39262 | OLW-ME-24/0130 | 2025-08-18 | A | Internal Only | Detailed Design - Provision of Redundant MDB at OCC Building, Admin Building and Canteen | 3.1.2 | EE | Nichapa P. | Jaturong W. | Sub | Pratan L. | Supajak S. | Jaturong W. | Supajak S. | Suraphong S. |  |  | submitted
856 |  | 3 | MDW-39262 | OLW-ME-24/0130 | 2025-08-27 | B | Internal Only | Detailed Design - Provision of Redundant MDB at OCC Building, Admin Building and Canteen | 3.1.2 | EE | Nichapa P. | Jaturong W. | Sub | Pratan L. | Supajak S. | Jaturong W. | Supajak S. | Suraphong S. |  |  | submitted
857 |  | 3 | MDW-39262 | OLW-ME-24/0130 | 2025-11-18 | C | Internal Only | Detailed Design - Provision of Redundant MDB at OCC Building, Admin Building and Canteen | 3.1.2 | EE | Nichapa P. | Jaturong W. | Sub | Pratan L. | Supajak S. | Jaturong W. | Supajak S. | Suraphong S. |  |  | submitted
858 |  | 3 | MDW-39263 | OLW-ME-24/0221 | 2025-11-10 | A | Internal Only | Detailed Design - Additonal Lighting System at Depot Area | 3.1.2,.4,.5 | EE | Nichapa P. | Jaturong W. | Sub | Pratan L. | Supajak S. | Jaturong W. | Supajak S. | Suraphong S. |  |  | submitted
859 |  | 3 | MDW-39264 |  |  |  |  | Detailed Design - Block-out and Holes Modification at Depot Platform | 3.1.2,.4,.5 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Supajak S. | Sahachart S. | Supajak S. | Suraphong S. |  |  | CANCLE
860 |  | 3 | MDW-39268 |  |  |  |  | Detailed Design - Main Cable Containment Modification at Depot | 3.2 | EE | Kusuma K. | Montri S. | Peerapat B. | Pratan L. | Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | CANCLE
861 |  | 3 | MDW-39269 |  |  |  |  | Detailed Design - PSY Wayside Cable Containment for 24 KV Cable under Depot slab | 3.4 | EE | Kusuma K. | Monchai R. | Peerapat B. | Pratan L. | Supajak S. | Monchai R. | Supajak S. | Suraphong S. |  |  | CANCLE
862 |  | 3 | MDW-39270 |  |  |  |  | Detailed Design - SIG/COM Wayside Cable Containment in Depot | 3.4 | EE | Kusuma K. | Montri S. | Peerapat B. | Pratan L. | Supajak S. | Montri S. | Supajak S. | Suraphong S.
863 |  | 3 | MDW-39271 | OLW-ME-24/0082 | 2025-05-09 | A | Internal Only | Detailed Design - Wayside Cable Trough in Depot | 3.4 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Supajak S. | Sahachart S. | Supajak S. | Suraphong S. |  |  | submitted
864 |  | 3 | MDW-39271 | OLW-ME-24/0082 | 2025-07-24 | B | Internal Only | Detailed Design - Wayside Cable Trough in Depot | 3.4 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Supajak S. | Sahachart S. | Supajak S. | Suraphong S. |  |  | submitted
865 |  | 3 | MDW-39272 | OLW-ME-24/0101 | 2025-07-16 | A | Internal Only | Detailed Design - Modification of New M&E Room at IVS15 Civil & AR | 3.1.1.1 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Supajak S. | Sahachart S. | Supajak S. | Suraphong S. |  |  | submitted
866 |  | 3 | MDW-39272 | OLW-ME-24/0101 | 2025-10-01 | B | Internal Only | Detailed Design - Modification of New M&E Room at IVS15 Civil & AR | 3.1.1.1 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Supajak S. | Sahachart S. | Supajak S. | Suraphong S. |  |  | submitted
867 |  | 3 | MDW-39273 |  |  |  |  | Detailed Design - Modification of New M&E UPS Room at IVS15-IVS17 - Building Services | 3.1.1.1 | ME | Nichapa P. | Boonprasert F. | Sub | Pratan L. | Supajak S. | Boonprasert F. | Supajak S. | Suraphong S.
868 |  | 3 | MDW-39274 | OLW-ME-24/0214 | 2025-11-10 | A | Internal Only | Detailed Design - Modification of Air Conditioning at OR13-OR29 and OCC Building - Material Approval (Electrical System) | 3.1.1.1,3.1.1.2 | ME | Nichapa P. | Boonprasert F. | Sub | Pratan L. | Supajak S. | Boonprasert F. | Supajak S. | Suraphong S. |  |  | submitted
869 |  | 3 | MDW-39275 | OLW-ME-24/0190 | 2025-10-01 | A | Internal Only | Detailed Design - Modification of Air Conditioning at OR13-OR29 and OCC Building - Material Approval (Mechanical System) |  | ME | Nichapa P. | Boonprasert F. | Sub | Pratan L. | Supajak S. | Boonprasert F. | Supajak S. | Suraphong S. |  |  | submitted
870 |  | 3 | MDW-39276 | OLW-ME-24/0338 | 2026-04-24 | A | Internal Only | Detailed Design - Ticket Issuing Machine (TIM) Wall Opening and Closing on East Section | 5.2 | AFC/AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Anat U. / Supajak S. | Sahachart S. | Supajak S. | Suraphong S. |  |  | submitted
871 |  | 3 | MDW-39277 |  |  |  |  | Detailed Design - Modification Works for AFC - Balustrade Modification Along AFC Gate Line East Section |  | AFC/AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Anat U. / Supajak S. | Sahachart S. | Supajak S. | Suraphong S.
872 |  | 3 | MDW-39278 |  |  |  |  | Detailed Design - Underfloor Embedded Duct Modification for AFC Gates Line East Section | 5.4 | AFC | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Anat U. / Supajak S. | Sahachart S. | Supajak S. | Suraphong S.
873 |  | 3 | MDW-39279 |  |  |  |  | Detailed Design - Balustrade Modification Along AFC Gate Line East Section | 5.3 | AFC | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Anat U. / Supajak S. | Sahachart S. | Supajak S. | Suraphong S.
874 |  | 3 | MDW-39280 | OLW-ME-24/0195 | 2025-10-27 | A | Internal Only | Detailed Design - Platform Finishing on East Section | 4.3 | ST/AR | Nichapa P. | Kamphol H. | Sub | Suchock P. | Anat U. / Supajak S. | Kamphol H. | Supajak S. | Suraphong S. |  |  | submitted
875 |  | 3 | MDW-39281 | OLW-ME-24/0309 | 2026-06-11 | A | Internal Only | Detailed Design - Cladding Barrier between EWD and Station Structure on East Section | 4.4 | ST/AR | Nichapa P. | Kamphol H. | Sub | Suchock P. | Anat U. / Supajak S. | Kamphol H. | Supajak S. | Suraphong S. |  |  | submitted
876 |  | 3 | MDW-39282 |  |  |  |  | Detailed Design - Holes for PSD Cable Wiring on East Section | 4.1 | ST/AR | Nichapa P. | Kamphol H. | Sub | Suchock P. | Anat U. / Supajak S. | Kamphol H. | Supajak S. | Suraphong S.
877 |  | 3 | MDW-39283 |  |  |  |  | Detailed Design - Intercom System in Cash Handling Room East Section | 10.2 | COM | Nichapa P. | Sorawit P. | Sub | Pratan L. | Sukij U. / Supajak S. | Sorawit P. | Supajak S. | Suraphong S.
878 |  | 3 | MDW-39284 |  |  |  |  | Detailed Design - Power Cable and Conduits Modification for Walk-Through Metal Detector East Section | 10.3 | COM | Kusuma K. | Montri S. | Sub | Pratan L. | Sukij U. / Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | CANCLE
879 |  | 3 | MDW-39285 |  |  |  |  | Detailed Design - Provision of Cable Containment between OCC ORL and OCC BL | 10.8 | COM | Kusuma K. | Montri S. | Sub | Pratan L. | Sukij U. / Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | CANCLE
880 |  | 3 | MDW-39286 |  |  |  |  | Detailed Design - Underground Cable Containment at Station Public Areas East Section | 10.10 | COM | Kusuma K. | Montri S. | Sub | Pratan L. | Sukij U. / Supajak S. | Montri S. | Supajak S. | Suraphong S. |  |  | CANCLE
881 |  | 3 | MDW-39287 | OLW-ME-24/0151 | 2025-09-25 | A | Internal Only | Detailed Design - Strobe Light at Buffer Stops East Section | 6.5 | EE | Nichapa P. | Jaturong W. | Sub | Suchock P. | Eddy / Supajak S. | Jaturong W. | Supajak S. | Suraphong S. |  |  | submitted
882 |  | 3 | MDW-39288 | OLW-ME-24/0199 | 2025-10-27 | A | Internal Only | Detailed Design - Point Machine Foundation Construction on East Section | 6.3 | ST | Nichapa P. | Kamphol H. | Sub | Suchock P. | Eddy / Supajak S. | Kamphol H. | Supajak S. | Suraphong S. |  |  | submitted
883 |  | 3 | MDW-39289 |  |  |  |  | Detailed Design - Earthing and Bonding for Raised Floor on East Section |  | EE/ME | Nichapa P. | Jaturong W. | Sub | Pratan L. | Supajak S. | Jaturong W. | Supajak S. | Suraphong S.
884 |  | 3 | MDW-39290 | OLW-ME-24/0211 | 2025-10-23 | A | Internal Only | Detailed Design - Modification Room for PSY at Depot Buildings - Building Services |  | ME | Nichapa P. | Boonprasert F. | Sub | Pratan L. | Supajak S. | Boonprasert F. | Supajak S. | Suraphong S. |  |  | submitted
885 |  | 3 | MDW-39291 | OLW-ME-24/0375 (** แบงค์ & พี่กำพล) | 2026-04-28 | A | Internal Only | Detailed Design - Conductor Rail Arrangement Modification at Main Line East Section |  |  | Nichapa P. | Kamphol H. | Sub | Suchock P. | Supajak S. | Kamphol H. | Supajak S. | Suraphong S. |  |  | submitted
886 |  | 3 | MDW-39291 | OLW-ME-24/0375 (** แบงค์ & พี่กำพล) | 2026-06-08 | B | Internal Only | Detailed Design - Conductor Rail Arrangement Modification at Main Line East Section |  |  | Nichapa P. | Kamphol H. | Sub | Suchock P. | Supajak S. | Kamphol H. | Supajak S. | Suraphong S. |  |  | submitted
887 |  | 3 | MDW-39292 | OLW-ME--24/0384 (** แบงค์ & พี่กำพล) | 2026-05-18 | A | Internal Only | Detailed Design - Conductor Rail Arrangement Modification at Depot |  |  | Nichapa P. | Kamphol H. | Sub | Suchock P. | Supajak S. | Kamphol H. | Supajak S. | Suraphong S. |  |  | submitted
888 |  | 3 | MDW-39293 | OLW-ME-24/0104 | 2025-10-27 | A | Internal Only | Detailed Design - Stabling Walkway Modification at Stabling Yard - Civil & AR |  |  | Nichapa P. | Kamphol H. | Sub | Suchock P. | Supajak S. | Kamphol H. | Supajak S. | Suraphong S. |  |  | submitted
889 |  | 3 | MDW-39294 |  |  |  | Internal Only | Detailed Design - Provision of Architectural Work in new M&E UPS room at OR23 |  |  | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Supajak S. | Sahachart S. | Supajak S. | Suraphong S.
890 |  | 3 | MDW-39295 | OLW-ME-24/0303 | 2026-02-18 | A | Internal Only | Detailed Design - Dangerous Goods Building in Depot - Civil & AR | ADW | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Supajak S. | Suraphong S. |  |  | submitted
891 |  | 3 | MDW-39296 | OLW-ME-24/0311 | 2026-02-27 | A | Internal Only | Detailed Design - Dangerous Goods Building in Depot - Building Services | ADW | EE/ME | Nichapa P. | Boonprasert |  | Pratan L. | Supajak S. | Boonprasert | Supajak S. | Suraphong S. |  |  | submitted
892 |  | 3 | MDW-39297 | OLW-ME-24/0238 |  |  | Internal Only | Detailed Design - Training Room at Ratchada Station (Part 2) | ADW | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Supajak S. | Suraphong S.
893 |  | 3 | MDW-39298 |  |  |  | Internal Only | Detailed Design - Training Room at Ratchada Station (Part 2) - Building Services | ADW | EE/ME | Nichapa P. | Boonprasert |  | Pratan L. | Supajak S. | Boonprasert | Supajak S. | Suraphong S. |  |  | CANCLE
894 |  | 3 | MDW-39299 | OLW-ME-24/0254 | 2026-01-06 | A | Internal Only | Detailed Design - Provision of Air Conditioning System in Commercial Room at OR13-OR19 | ADW | ME | Nichapa P. | Boonprasert |  | Pratan L. | Supajak S. | Boonprasert | Supajak S. | Suraphong S. |  |  | submitted
895 |  | 3 | MDW-39300 | OLW-ME-24/0271 | 2026-01-23 | A | Internal Only | Detailed Design - Modification SIG-PSD Office at Main Workshop - Building Services | ADW |  | Nichapa P. | Boonprasert |  | Pratan L. | Supajak S. | Boonprasert | Supajak S. | Suraphong S. |  |  | submitted
896 |  | 3 | MDW-39301 | OLW-ME-24/0302 | 2026-02-18 | A | Internal Only | Detailed Design - Modification Backup CCR Room at Main Workshop - Building Services | ADW |  | Nichapa P. | Boonprasert |  | Pratan L. | Supajak S. | Boonprasert | Supajak S. | Suraphong S. |  |  | submitted
897 |  | 3 | MDW-39302 | OLW-ME-24/0283 | 2026-02-09 | A | Internal Only | Detailed Design - Modification SER at Main Workshop - Building Services | ADW |  | Nichapa P. | Boonprasert |  | Pratan L. | Supajak S. | Boonprasert | Supajak S. | Suraphong S. |  |  | submitted
898 |  | 3 | MDW-39303 | OLW-ME-24/0277 | 2026-02-03 | A | Internal Only | Detailed Design - Modification CER & SCADA Room at Main Workshop - Building Services | ADW |  | Nichapa P. | Boonprasert |  | Pratan L. | Supajak S. | Boonprasert | Supajak S. | Suraphong S. |  |  | submitted
899 |  | 3 | MDW-39304 | OLW-ME-24/0284 | 2026-02-26 | A | Internal Only | Detailed Design - MEA Radio | 10.5 | EE | Nichapa P. | Jaturong W. | Sub | Pratan L. | Sukij U. / Supajak S. | Jaturong W. | Sukij U. | Suraphong S. |  |  | submitted
900 |  | 3 | MDW-39305 | OLW-ME-24/0339 | 2026-03-26 | A | Internal Only | Detailed Design - Safety Provision for Maintenance Pits | [12 empty] | submitted
901 |  | 3 | MDW-39306 | OLW-ME-24/0402 | 2026-05-25 | A | Internal Only | Detilaed Design - Modification CER and First Aid Room at OR14 - Building Services | ADW |  | Nichapa P. | Boonprasert |  | Pratan L. | Supajak S. | Boonprasert | Supajak S. | Suraphong S. |  |  | submitted
902 |  | 3 | MDW-39307 | OLW-ME-24/0425 8 pages - A4 50 pages - A3 | 2026-07-01 | A | Internal Only | Detailed Design - Additional Fence at Back of House OR13 - OR22 and IVS East Section | ADW | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Supajak S. | Suraphong S. |  |  | submitted
903 |  | 3 | MDW-39308 |  |  |  | Internal Only | Detailed Design - Additional Locking Devices for Main Line Tandem Turnouts 2007, 2010 & 2013 and Depot Turnout D16 | ADW | TRW | Nichapa P. | Kamphol H. | Sub | Suchock P. | Supajak S. | Kamphol H. | Supajak S. | Suraphong S.
904 |  | 3 | MDW-39309 |  |  |  | Internal Only | Detailed Design - Modification Air Conditioning System at CCR | ADW | ME | Nichapa P. | Boonprasert |  | Pratan L. | Supajak S. | Boonprasert | Supajak S. | Suraphong S.
905 |  | 3 | MDW-39310 |  |  |  | Internal Only | Detailed Design - Modification AFC Training Center at OR19 - Civil & AR | ADW | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Supajak S. | Suraphong S.
906 |  | 3 | MDW-39311 |  |  |  | Internal Only | Detailed Design - Modification AFC Training Center at OR19 - Building Services | ADW | EE/ME | Nichapa P. | Jaturong W. |  | Pratan L. | Supajak S. | Jaturong W. | Supajak S. | Suraphong S.
907 |  | 3 | MDW-39312 |  |  |  | Internal Only | Detailed Design - Modification Electronic Workshop at Main Workshop - Building Services | ADW | ME | Nichapa P. | Boonprasert |  | Pratan L. | Supajak S. | Boonprasert | Supajak S. | Suraphong S.
908 |  | 3 | MDW-39313 |  |  |  | Internal Only | Detailed Design - Modification Battery Charger Room at Main Workshop - Building Services | ADW | ME | Nichapa P. | Boonprasert |  | Pratan L. | Supajak S. | Boonprasert | Supajak S. | Suraphong S.
909 |  | 3 | MDW-39314 |  |  |  | Internal Only | Detailed Design - Modification Machining Room at Main Workshop - Building Services | ADW | EE/ME | Nichapa P. | Atiraj K. |  | Pratan L. | Supajak S. | Atiraj K. | Ekasit L. | Suraphong S.
910 |  | 3 | MDW-39315 |  |  |  | Internal Only | Detailed Design - Modification Paint Shop Room at Main Workshop - Building Services | ADW | ME | Nichapa P. | Boonprasert |  | Pratan L. | Supajak S. | Boonprasert | Supajak S. | Suraphong S.
911 |  | 3 | MDW-39316 |  |  |  | Internal Only | Detailed Design - Modification Electronic Workshop, Battery Charger, Machining and Paint Shop at Main Workshop - Civil & AR | ADW | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Supajak S. | Suraphong S.
912 |  |  | Modification Works LOT 2
913 |  | 3 | MDW-39500 | OLW-ME-24/0198 | 2025-10-21 | A | Internal Only | Detailed Design - Modification Works : Storage Office in Main Workshop - Civil & AR | 55 | ST/AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  |  | submitted
914 |  | 3 | MDW-39501 | OLW-ME-24/0327 | 2026-03-18 | A | Internal Only | Detailed Design - Modification Works : Storage Office in Main Workshop - Building Services | 55 | EE/ME | Nichapa P. | Atiraj K. |  | Pratan L. | Supajak S. | Atiraj K. | Ekasit L. | Suraphong S. |  |  | submitted
915 |  | 3 | MDW-39502 |  |  |  | Internal Only | Detailed Design - Modification Works : all Fire Alarm System Controller in Depot | 54 | EE/ME | Nichapa P. | Atiraj K. | Sub | Pratan L. | Supajak S. | Atiraj K. | Ekasit L. | Suraphong S. |  |  | CANCLE
916 |  | 3 | MDW-39503 | OLW-ME-24/0194 | 2026-01-13 | A | Internal Only | Detailed Design - Modification Works : New MMC at Admin Building - Civil & AR | 53 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  |  | submitted
917 |  | 3 | MDW-39503 | OLW-ME-DAS-MDW-39503-001 | 2026-02-12 | A1 | Internal Only | Detailed Design - Modification Works : New MMC at Admin Building - Civil & AR | 53 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  |  | submitted
918 |  | 3 | MDW-39503 | OLW-ME-DAS-MDW-39503-002 |  | A2 | Internal Only | Detailed Design - Modification Works : New MMC at Admin Building - Civil & AR | 53 | AR | Wijittra M. | Sahachart S. | Peerapat B. | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S.
919 |  | 3 | MDW-39504 | OLW-ME-24/0388 | 2026-05-18 | A | Internal Only | Detailed Design - Modification Works : New MMC at Admin Building - Building Services | 53 | EE/ME | Nichapa P. | Atiraj K. | Sub | Pratan L. | Supajak S. | Atiraj K. | Ekasit L. | Suraphong S. |  |  | submitted
920 |  | 3 | MDW-39505 | OLW-ME-24/0241 | 2025-12-12 | A | Internal Only | Detailed Design - Modification Works : Walkway with Roof from Main Workshop to Stabling Yard - Civil & AR | 1 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  |  | submitted
921 |  | 3 | MDW-39505 | OLW-ME-DAS-MDW-39505-001 | 2026-02-25 | A1 | Internal Only | Detailed Design - Modification Works : Walkway with Roof from Main Workshop to Stabling Yard - Civil & AR | 1 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  |  | submitted
922 |  | 3 | MDW-39505 | OLW-ME-DAS-MDW-39505-002 | เตรียมออก 9/5/26, 2/6/26 | A2 | Internal Only | Detailed Design - Modification Works : Walkway with Roof from Main Workshop to Stabling Yard - Civil & AR | 1 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S.
923 |  | 3 | MDW-39506 | OLW-ME-24/0298 | 2026-02-17 | A | Internal Only | Detailed Design - Modification Works : Walkway with Roof from Main Workshop to Stabling Yard - Building Services | 1 | EE | Nichapa P. | Atiraj K. |  | Pratan L. | Supajak S. | Atiraj K. | Ekasit L. | Suraphong S. |  |  | submitted
924 |  | 3 | MDW-39507 | OLW-ME-24/0239 | 2025-12-11 | A | Internal Only | Detailed Design - Modification Works : High Roof in front of MWS Entrance and Store Entrance - Civil & AR | 2 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  |  | submitted
925 |  | 3 | MDW-39507 | OLW-ME-24/0239 | 2026-01-20 | DAS (A1) | Internal Only | Detailed Design - Modification Works : High Roof in front of MWS Entrance and Store Entrance - Civil & AR | 2 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  |  | submitted
926 |  | 3 | MDW-39508 |  |  |  | Internal Only | Detailed Design - Modification Works : High Roof in front of MWS Entrance and Store Entrance - Building Services | 2 | EE | Nichapa P. | Atiraj K. |  | Pratan L. | Supajak S. | Atiraj K. | Ekasit L. | Suraphong S. |  |  | CANCLE
927 |  | 3 | MDW-39509 | OLW-ME-24/0246 | 2025-12-18 | A | Internal Only | Detailed Design - Modification Works : High Roof at Under Floor Wheel Lathe - Civil & AR | 3 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  |  | submitted
928 |  | 3 | MDW-39510 |  |  |  | Internal Only | Detailed Design - Modification Works : High Roof at Under Floor Wheel Lathe - Building Services | 3 | EE | Nichapa P. | Atiraj K. |  | Pratan L. | Supajak S. | Atiraj K. | Ekasit L. | Suraphong S. |  |  | CANCLE
929 |  | 3 | MDW-39511 | OLW-ME-24/0248 | 2025-12-18 | A | Internal Only | Detailed Design - Modification Works : Maintenance Office Rooms at Main Workshop - Civil & AR | 4 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  |  | submitted
930 |  | 3 | MDW-39511 | OLW-ME-24/0248 | 2026-05-06 | B | Internal Only | Detailed Design - Modification Works : Maintenance Office Rooms at Main Workshop - Civil & AR | 4 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  |  | submitted
931 |  | 3 | MDW-39512 | OLW-ME-24/0411 | 2026-06-04 | A | Internal Only | Detailed Design - Modification Works : Maintenance Office Rooms at Main Workshop - Building Services | 4 | EE/ME | Nichapa P. | Atiraj K. |  | Pratan L. | Supajak S. | Atiraj K. | Ekasit L. | Suraphong S. |  |  | submitted
932 |  | 3 | MDW-39513 | OLW-ME-24/0200 | 2026-02-20 | A | Internal Only | Detailed Design - Modification Works : Concrete Car Barrier in front of Main Workshop | 5 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  |  | submitted
933 |  | 3 | MDW-39514 |  | 2025-12-11 | A | Internal Only | Detailed Design - Modification Works : Car Park Roof and Motorcycle in Depot - Civil & AR | 6 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  |  | submitted
934 |  | 3 | MDW-39515 | OLW-ME-24/0378 | 2026-05-05 | A | Internal Only | Detailed Design - Modification Works : Car Park Roof and Motorcycle in Depot - Building Services | 6 | EE | Nichapa P. | Atiraj K. |  | Pratan L. | Supajak S. | Atiraj K. | Ekasit L. | Suraphong S. |  |  | submitted
935 |  | 3 | MDW-39516 | OLW-ME-24/0247 | 2025-12-18 | A | Internal Only | Detailed Design - Modification Works : Walkway Bridge between BL Depot and ORL Depot - Civil & AR | 7 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  |  | submitted
936 |  | 3 | MDW-39517 | OLW-ME-24/0393 | 2026-05-20 | A | Internal Only | Detailed Design - Modification Works : Walkway Bridge between BL Depot and ORL Depot - Building Services | 7 | EE | Nichapa P. | Atiraj K. |  | Pratan L. | Supajak S. | Atiraj K. | Ekasit L. | Suraphong S. |  |  | submitted
937 |  | 3 | MDW-39518 | OLW-ME-24/0265 เตรียมออก 22/1/2026 |  |  | Internal Only | Detailed Design - Modification Works : Street Lighting between MRTA Fence and Depot Slab | 8 | EE | Nichapa P. | Jaturong W. |  | Pratan L. | Supajak S. | Jaturong W. | Ekasit L. | Suraphong S.
938 |  | 3 | MDW-39519 | OLW-ME-24/0279 | 2026-06-16 | A | Internal Only | Detailed Design - Modification Works : Walkway with Roof in Depot Area - Civil & AR | 9,10,14,15,20 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  |  | submitted
939 |  | 3 | MDW-39520 | เตรียมออก 9/7/26 OLW-ME-24/0452 |  |  | Internal Only | Detailed Design - Modification Works : Sliding Gate, Chain Link Fence and Walkway with Roof in Depot Area - Building Services | 9,10,14,15,20 | EE | Nichapa P. | Atiraj K. |  | Pratan L. | Supajak S. | Atiraj K. | Ekasit L. | Suraphong S.
940 |  | 3 | MDW-39521 | OLW-ME-24/0249 | 2026-01-05 | A | Internal Only | Detailed Design - Modification Works : Walkway Bridge and Walkway over Canal in Depot | 11,12 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  |  | submitted
941 |  | 3 | MDW-39522 | OLW-ME-24/0289 | 2026-02-17 | A | Internal Only | Detailed Design - Modification Works : Rain Protection and Zero Discharge Water treatment in Depot - Civil & AR | 13 23 | AR/ME | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  |  | submitted
942 |  | 3 | MDW-39523 | OLW-ME-24/0244 | 2025-12-15 | A | Internal Only | Detailed Design - Modification Works : Cold Water System at Admin Building Landscape | 16 | ME | Nichapa P. | Boonprasert |  | Pratan L. | Supajak S. | Boonprasert | Ekasit L. | Suraphong S. |  |  | submitted
943 |  | 3 | MDW-39524 | OLW-ME-24/0281 | 2026-02-24 | A | Internal Only | Detailed Design - Modification Works : Walkway under Depot Slab for Maintenance Service - Civil & AR | 17 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  |  | submitted
944 |  | 3 | MDW-39525 | OLW-ME-24/0398 | 2026-05-20 | A | Internal Only | Detailed Design - Modification Works : Walkway under Depot Slab for Maintenance Service - Building Services |  | EE | Nichapa P. | Atiraj K. |  | Pratan L. | Supajak S. | Atiraj K. | Ekasit L. | Suraphong S. |  |  | submitted
945 |  | 3 | MDW-39526 | OLW-ME-24/0240 | 2025-12-11 | A | Internal Only | Detailed Design - Modification Works : FHC Modification at Stabling Yard | 19 | ME | Nichapa P. | Boonprasert |  | Pratan L. | Supajak S. | Boonprasert | Ekasit L. | Suraphong S. |  |  | submitted
946 |  | 3 | MDW-39527 | OLW-ME-24/0331 | 2026-03-23 | A | Internal Only | Detailed Design - Modification Works : Hand Sink with Emergency Eye Wash Installation in Depot | 21 | ME | Nichapa P. | Boonprasert |  | Pratan L. | Supajak S. | Boonprasert | Ekasit L. | Suraphong S. |  |  | submitted
947 |  | 3 | MDW-39528 | OLW-ME-24/0256 | 2026-01-13 | A | Internal Only | Detailed Design - Modification Works : Washing Area in Cleaning Staff Room at Stabling Yard - Civil & AR | 22 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  |  | submitted
948 |  | 3 | MDW-39529 | OLW-ME-24/0267 | 2026-01-19 | A | Internal Only | Detailed Design - Modification Works : Washing Area in Cleaning Staff Room at Stabling Yard - Building Services |  | ME | Nichapa P. | Boonprasert |  | Pratan L. | Supajak S. | Boonprasert | Ekasit L. | Suraphong S. |  |  | submitted
949 |  | 3 | MDW-39530 | OLW-ME-24/0308 | 2026-02-21 | A | Internal Only | Detailed Design - Modification Works : Zero Discharge Water treatment in Depot - Building Services | 19 | ME | Nichapa P. | Boonprasert |  | Pratan L. | Supajak S. | Boonprasert | Ekasit L. | Suraphong S. |  |  | submitted
950 |  | 3 | MDW-39531 | OLW-ME-24/0335 | 2026-03-24 | A | Internal Only | Detailed Design - Modification Works : Guard rail protection for FHC in Depot Area | 24 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  |  | submitted
951 |  | 3 | MDW-39532 |  |  |  | Internal Only | Detailed Design - Modification Works : Barbed Wire Fences for MRTA Chain Link at Klong Chourdyai | 25 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S.
952 |  | 3 | MDW-39533 |  |  |  | Internal Only | Detailed Design - Modification Works : Car Barrier Gate at Depot Area | 26 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S.
953 |  | 3 | MDW-39534 | OLW-ME-24/0243 | 2026-03-23 | A | Internal Only | Detailed Design - Modification Works : Security Guard Box at ORL Depot Entrance - Civil & AR | 31 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  |  | submitted
954 |  | 3 | MDW-39534 | OLW-ME-24/0243 | เตรียมออก 27/7/26 | B | Internal Only | Detailed Design - Modification Works : Security Guard Box at ORL Depot Entrance - Civil & AR | 31 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S.
955 |  | 3 | MDW-39535 | เตรียมออก 18/7/26 OLW-ME-24/0475 |  |  | Internal Only | Detailed Design - Modification Works : Security Guard Box at ORL Depot Entrance - Building Services |  | EE/ME | Nichapa P. | Atiraj K. |  | Pratan L. | Supajak S. | Atiraj K. | Ekasit L. | Suraphong S.
956 |  | 3 | MDW-39536 | OLW-ME-24/0389 Total 24 pages A3 - 9 pages | 2026-06-06 | A | Internal Only | Detailed Design - Modification Works : Soundproof Installation and Company Logo at CCR Room | 33 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  |  | submitted
957 | [8 empty] | 34
958 |  | 3 | MDW-39537 |  |  |  | Internal Only | Detailed Design - Modification Works : Fence Installation at Ladder in VS, IVS Buildings | 40 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S.
959 |  | 3 | MDW-39538 |  |  |  | Internal Only | Detailed Design - Modification Works : Anti-Slide Signage at Escalator for all Stations | 41 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S.
960 |  | 3 | MDW-39539 |  |  |  | Internal Only | Detailed Design - Modification Works : Roofing over Control Panel Installation at VS, IVS Buildings | 42 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S.
961 |  | 3 | MDW-39540 |  |  |  | Internal Only | Detailed Design - Modification Works : Water Drop Protection for UPS Cabinet for all Stations and Depot | 44 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S.
962 |  | 3 | MDW-39541 |  |  |  | Internal Only | Detailed Design - Modification Works : Manual Call Point Cover in Public Area at all Stations | 45 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S.
963 |  | 3 | MDW-39542 |  |  |  | Internal Only | Detailed Design - Modification Works : Emergency Stop Button Cover for Escalator at all Stations | 46 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S.
964 |  | 3 | MDW-39543 | เตรียมออก 2/6/26 OLW-ME-24/0380 |  |  | Internal Only | Detailed Design - Modification Works : Bird & Rain Protection, Safety Hand Rail Installation at Admin Building | 47,48,49 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S.
965 |  | 3 | MDW-39544 |  |  |  | Internal Only | Detailed Design - Modification Works : Barbed Wire Fences for Depot slab | 50 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S.
966 |  | 3 | MDW-39545 | OLW-ME-24/0280 | 2026-02-10 | A | Internal Only | Detailed Design - Modification Works : Chain Link Installation at Cut & Cover Depot Access | 51 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  |  | submitted
967 |  | 3 | MDW-39546 | OLW-ME-24/0381 | 2026-06-20 | A | Internal Only | Detailed Design - Modification Works : Chain Link Installation under Depot Slab | 52 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  |  | submitted
968 |  | 3 | MDW-39547 | เตรียมออก 16/12/2025 |  |  | Internal Only | Detailed Design - Modification Works : Door and Lockset Modification at OCC Building | 56,57 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S.
969 |  | 3 | MDW-39548 | OLW-ME-24/0270 | 2026-01-26 | A | Internal Only | Detailed Design - Modification Works : Air Conditioning System Installation at Pantry room OCC Building | 59 | ME | Nichapa P. | Boonprasert |  | Pratan L. | Supajak S. | Boonprasert | Ekasit L. | Suraphong S. |  |  | submitted
970 |  | 3 | MDW-39549 | OLW-ME-24/0269 | 2026-01-23 | A | Internal Only | Detailed Design - Modification Works : Maintenance Room and Satellite Store at Stations - Building Services | 61 | EE/ME | Nichapa P. | Boonprasert |  | Pratan L. | Supajak S. | Boonprasert | Ekasit L. | Suraphong S. |  |  | submitted
971 |  | 3 | MDW-39550 |  |  |  | Internal Only | Detailed Design - Modification Works : Satellite Store at OR21 - Civil & AR | 61 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S.
972 |  | 3 | MDW-39551 | OLW-ME-24/0261 | 2026-01-13 | A | Internal Only | Detailed Design - Modification Works : Train Crew Office at OR29 (รวมงาน AR และ Builind Service) | 62 | AR/ME | Nichapa P. | Boonprasert |  | Pratan L. | Supajak S. | Boonprasert | Ekasit L. | Suraphong S. |  |  | submitted
973 |  | 3 | MDW-39552 | OLW-ME-24/0313 | 2026-05-08 | A | Internal Only | Detailed Design - Modification Works : Hand Rail Installation at Walk Way in Stabling Yard | 60 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S. |  |  | submitted
974 |  | 3 | MDW-39553 |  |  |  | Internal Only | Detailed Design - Modification Works : Ladder to Access the Fire Valve at Omega Joints for all Underground Stations | 43 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S.
975 | [6 empty] | Internal Only | Detailed Design - Modification Works : Fire Suspension Control Panel Cover Installation at Tunnel Main Line | 39 | ME |  |  |  |  | Supajak S. |  | Ekasit L. | Suraphong S. |  |  | CANCLE
976 |  | 3 | MDW-39554 | เตรียมออก 29/6/2026 Olw-ME-24/0437 | 10 pages, dwg 4 sheets |  | Internal Only | Detailed Design - Modification Works : Security Guard Box at OCC Parking Area - Civil & AR | 32 | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S.
977 |  | 3 | MDW-39555 |  |  |  | Internal Only | Detailed Design - Modification Works : Security Guard Box at OCC Parking Area - Building Services |  | EE | Nichapa P. | Atiraj K. |  | Pratan L. | Supajak S. | Atiraj K. | Ekasit L. | Suraphong S.
978 |  | 3 | MDW-39556 | OLW-ME-24/0259 | 2026-01-15 | A | Internal Only | Detailed Design - Modification Works : Additional Small Power System at OCC Building | 58 | EE | Nichapa P. | Atiraj K. |  | Pratan L. | Supajak S. | Atiraj K. | Ekasit L. | Suraphong S. |  |  | submitted
979 |  | 3 | MDW-39557 |  |  |  | Internal Only | Detailed Design - Modification Works : Sliding Gate and Chain Link Fence in Depot Area - Civil & AR |  | AR | Wijittra M. | Sahachart S. |  | Tanyawit K. | Supajak S. | Sahachart S. | Ekasit L. | Suraphong S.
980 | [7 empty] | Procurement / Manufacturing / Delivery Stage / FAT
981 | [7 empty] | Installation Menthod Statement
982 |  | 5 | MDW-59001 | OLW-ME-24/0251 | เตรียมออก 5/01/2026 | A |  | Installation Menthod Statement - Modification of Depot Track Alignment at Stabling Yard
983 |  | 5 | MDW-59002 |  |  |  |  | Installation Menthod Statement - Modification Motorized Gate and Shelters at Test Track Depot - Civil & AR | [12 empty] | CANCLE
984 |  | 5 | MDW-59003 |  |  |  |  | Installation Menthod Statement - Modification Motorized Gate and Shelters at Test Track Depot - Building Service | [12 empty] | CANCLE
985 |  | 5 | MDW-59004 | OLW-ME-24/0449 | 2026-07-13 | A |  | Installation Method Statement - Rubber Gap Fillers on Platform Edge on East Section | [12 empty] | submitted
986 |  | 5 | MDW-59200 |  |  |  |  | Method Statement - Cable Tray Installation
987 |  | 5 | MDW-59200 | OLW-ME-24/0229 | 2025-11-20 | A |  | Installation Menthod Statement - Modification Works for Training Room at Ratchada Station | [12 empty] | submitted
988 |  | 5 | MDW-59201 |  |  |  |  | Installation Menthod Statement - Modification of Air Conditioning in CER and SER at OR13-OR29
989 |  | 5 | MDW-59202 |  |  |  |  | Installation Menthod Statement - Modification of Air Conditioning in M&E Room at OCC Building
990 | [7 empty] | Installation Method Statement - Platform Finishing on East Section | [12 empty] | CANCLE
991 | [7 empty] | Installation Method Statement - Cladding Barrier between EWD and Station Structure on East Section | [12 empty] | CANCLE
992 |  | 5 | MDW-59203 |  |  |  |  | Installation Method Statement - Additional Locking Devices for Main Line Tandem Turnouts 2007, 2010 & 2013 and Depot Turnout D16
993 | [7 empty] | Testing and Commissioning Procedure
994 |  | 6 | MDW-69001 | เตรียมออก 1/7/26 OLW-ME-24/0434 | 10 pages |  |  | Test Procedure - Modification of Depot Track Alignment at Stabling Yard
995 |  | 6 | MDW-69003 | เตรียมออก 29/6/2026 24/7/26 OLW-ME-24/0427 | 14 pages |  |  | Test Procedure - Modification Motorized Gate and Shelters at Test Track Depot - Civil & AR
996 |  | 6 | MDW-69005 | OLW-ME-24/0386 | 2026-05-15 | A | BEM/M/ORM/S1394/69 | Test Procedure - Modification Motorized Gate and Shelters at Test Track Depot - Building Service | [12 empty] | submitted
997 |  | 6 | MDW-69007 | เตรียมออก 9/7/2026 OLW-ME-24/035 |  |  |  | Test Procedure - Rubber Gap Fillers on Platform Edge on East Section
998 |  | 6 | MDW-69200 |  |  |  | Internal Only | Test Procedure - Modification Work of M&E Cable Containment for East Section stations, VS, IVS, EEEN and Depot
999 |  | 6 | MDW-69232 |  |  |  | Internal Only | Test Procedure - Level Crossing at Turnout and Track Slab Crossing on Main Line East Section
1000 |  | 6 | MDW-69234 |  |  |  | Internal Only | Test Procedure - Main Line Cable Trough Modification on East Section for PSY and SIG/COM
1001 |  | 6 | MDW-69237 | เตรียมออก 3/7/26 OLW-ME-24/0442 |  |  | Internal Only | Test Procedure - Raised Floor Installation on East Section
1002 |  | 6 | MDW-69239 | OLW-ME-24/0443 8 pages | 2026-07-15 | A | Internal Only | Test Procedure - Bird Protection System at Depot Buildings | [12 empty] | submitted
1003 |  | 6 | MDW-69241 |  |  |  |  | Test Procedure - Central BEMS for the MRT Orange Line System East Section
1004 |  | 6 | MDW-69243 |  |  |  |  | Test Procedure - Central BEMS for the MRT Orange Line System West Section
1005 |  | 6 | MDW-69245 | OLW-ME-24/0444 14 pages | 2026-07-15 | A | Internal Only | Test Procedure - Access Panel Closeout for Traction Substation Room in Main Workshop | [12 empty] | submitted
1006 |  | 6 | MDW-69247 | OLW-ME-24/0445 18 pages | 2026-07-15 | A | Internal Only | Test Procedure - Driver Train Simulation Room and Train Crew Office at OR18 - Civil & AR | [12 empty] | submitted
1007 |  | 6 | MDW-69249 | OLW-ME-24/0318 | 2026-03-12 | A | Internal Only | Test Procedure - Driver Train Simulation Room and Train Crew Office at OR18 - Building Services | [12 empty] | submitted
1008 |  | 6 | MDW-69251 | OLW-ME-24/0324 | 2026-03-16 | A | Internal Only | Test Procedure - Modification Works for Training Room at Ratchada Station | [12 empty] | submitted
1009 |  | 6 | MDW-69253 | OLW-ME-24/0297 | 2026-02-18 | A | Internal Only | Test Procedure - Eye Adaptation Lighting at Transition Area and Depot Approach | [12 empty] | submitted
1010 |  | 6 | MDW-69255 |  |  |  |  | Test Procedure - AFC Training Room Modification - Civil & AR
1011 |  | 6 | MDW-69257 | OLW-ME-24/0342 | 2026-03-24 | A | Internal Only | Test Procedure - AFC Training Room Modification - Building Services | [12 empty] | submitted
1012 | GEN1 | 6 | MDW-69259 | OLW-ME-24/0363 | 2026-04-20 | A | Internal Only | Test Procedure - Power Outlet Installation in SOR, Ticket Office and Cash Handling OR13 - OR29 | [12 empty] | submitted
1013 | GEN1.6 | 6 | MDW-69263 | OLW-ME-24/0446 9 pages | 2026-07-15 | A | Internal Only | Test Procedure - SOR Counter and Workstation Hanging Support Installation on East Section | [12 empty] | submitted
1014 | GEN1.7 | 6 | MDW-69265 | OLW-ME-24/0447 8 pages | 2026-07-15 | A | Internal Only | Test Procedure - Ticket Office Modification on East Section | [12 empty] | submitted
1015 |  | 6 | MDW-69267 |  |  |  |  | Test Procedure - Modification of Eletrical System in Telecommunication Room at OR14 | [12 empty] | CANCLE
1016 | GEN1.11 | 6 | MDW-69269 | OLW-ME-24/0334 | 2026-03-23 | A | Internal Only | Test Procedure - Modification of Ventilation System, Fire Suspression System (N2) in Telecommunication Room at OR14 | [12 empty] | submitted
1017 | GEN1.12 | 6 | MDW-69271 | OLW-ME-24/0458 15 pages | 2026-07-15 | A | Internal Only | Test Procedure - Modification of Civil Work in Telecommunication Room at OR14 | [12 empty] | submitted
1018 | GEN1.13 | 6 | MDW-69273 | OLW-ME-24/0364 | 2026-04-20 | A | Internal Only | Test Procedure - Modification in Staff Mess Room at OR13-OR29 | [12 empty] | submitted
1019 |  | 6 | MDW-69277 | OLW-ME-24/0337 | 2026-03-24 | A | Internal Only | Test Procedure - Modification of Air Conditioning in CER and SER at OR13-OR29 | [12 empty] | submitted
1020 |  | 6 | MDW-69281 | OLW-ME-24/0340 | 2026-03-24 | A | Internal Only | Test Procedure - Modification of Air Conditioning in M&E Room at OCC Building | [12 empty] | submitted
1021 |  | 6 | MDW-69283 | OLW-ME-24/0310 | 2026-02-25 | A | Internal Only | Test Procedure - Provision of UPS for MDB Control at Main Workshop, OCC Building, Admin Building, Stabling Yard and Train Washing Plant | [12 empty] | submitted
1022 |  | 6 | MDW-69285 | OLW-ME-24/0304 | 2026-02-18 | A | Internal Only | Test Procedure - Provision of Redundant MDB at OCC Building, Admin Building and Canteen | [12 empty] | submitted
1023 |  | 6 | MDW-69287 | OLW-ME-24/0322 | 2026-03-14 | A | Internal Only | Test Procedure - Additonal Lighting System at Depot Area | [12 empty] | submitted
1024 |  | 6 | MDW-69289 |  |  |  |  | Test Procedure - Block-out and Holes Modification at Depot Platform | [12 empty] | CANCLE
1025 |  | 6 | MDW-69291 |  |  |  |  | Test Procedure - Main Cable Containment Modification at Depot
1026 |  | 6 | MDW-69293 |  |  |  |  | Test Procedure - PSY Wayside Cable Containment for 24 KV Cable under Depot slab | [12 empty] | CANCLE
1027 |  | 6 | MDW-69295 |  |  |  |  | Test Procedure - SIG/COM Wayside Cable Containment in Depot
1028 |  | 6 | MDW-69297 | OLW-ME-24/0460 11 pages | 2026-07-15 | A | Internal Only | Test Procedure - Wayside Cable Trough in Depot | [12 empty] | submitted
1029 |  | 6 | MDW-69299 | OLW-ME-24/0461 13 pages | 2026-07-15 | A | Internal Only | Test Procedure - Modification of New M&E Room at IVS15 - IVS17 Civil & AR | [12 empty] | submitted
1030 |  | 6 | MDW-69301 | OLW-ME-24/0343 | 2026-03-24 | A | Internal Only | Test Procedure - Modification of New M&E UPS Room at IVS15-IVS17 - Building Services | [12 empty] | submitted
1031 |  | 6 | MDW-69303 | เตรียมออก 7/8/26 OLW-ME-24/0513 total 10 pages |  | A | Internal Only | Test Procedure - Ticket Issuing Machine (TIM) Wall Opening and Closing East Section
1032 |  | 6 | MDW-69305 |  |  |  | Internal Only | Test Procedure - Modification Works for AFC - Balustrade Modification Along AFC Gate Line East Section
1033 |  | 6 | MDW-69307 |  |  |  | Internal Only | Test Procedure - Underfloor Embedded Duct Modification for AFC Gates Line East Section
1034 |  | 6 | MDW-69309 |  |  |  | Internal Only | Test Procedure - Balustrade Modification Along AFC Gate Line East Section
1035 |  | 6 | MDW-69311 |  |  |  | Internal Only | Test Procedure - Platform Finishing on East Section
1036 |  | 6 | MDW-69313 |  |  |  | Internal Only | Test Procedure - Cladding Barrier between EWD and Station Structure on East Section
1037 |  | 6 | MDW-69315 |  |  |  | Internal Only | Test Procedure - Holes for PSD Cable Wiring on East Section
1038 |  | 6 | MDW-69317 |  |  |  | Internal Only | Test Procedure - Intercom System in Cash Handling Room East Section
1039 |  | 6 | MDW-69319 |  |  |  |  | Test Procedure - Power Cable and Conduits Modification for Walk-Through Metal Detector East Section | [12 empty] | CANCLE
1040 |  | 6 | MDW-69321 |  |  |  |  | Test Procedure - Underground Cable Containment at Station Public Areas East Section | [12 empty] | CANCLE
1041 |  | 6 | MDW-69323 |  |  |  |  | Test Procedure - Strobe Light at Buffer Stops East Section | [12 empty] | CANCLE
1042 |  | 6 | MDW-69325 | OLW-ME-24/0319 | 2026-03-14 | A | Internal Only | Test Procedure - Strobe Light at Buffer Stops East Section | [12 empty] | submitted
1043 |  | 6 | MDW-69327 |  |  |  | Internal Only | Test Procedure - Point Machine Foundation Construction on East Section
1044 |  | 6 | MDW-69329 | OLW-ME-24/0315 | 2026-03-09 | A | Internal Only | Test Procedure - Earthing and Bonding for Raised Floor on East Section | [12 empty] | submitted
1045 |  | 6 | MDW-69331 | OLW-ME-24/0333 | 2026-03-23 | A | Internal Only | Test Procedure - Modification Room for PSY at Depot Buildings - Building Services | [12 empty] | submitted
1046 |  | 6 | MDW-69333 | เตรียมออก 10/7/26 OLW-ME-24/0472 |  |  | Internal Only | Test Procedure - Conductor Rail Arrangement Modification at Main Line East Section
1047 |  | 6 | MDW-69335 |  |  |  | Internal Only | Test Procedure - Conductor Rail Arrangement Modification at Depot
1048 |  | 6 | MDW-69337 |  |  |  | Internal Only | Test Procedure - Stabling Walkway Modification at Stabling Yard - Civil & AR
1049 |  | 6 | MDW-69339 | OLW-ME-24/0462 11 pages | 2026-07-15 | A | Internal Only | Test Procedure - Provision of Architectural Work in new M&E UPS room at OR23 | [12 empty] | submitted
1050 |  | 6 | MDW-69341 | เตรียมออก 7/8/26 OLW-ME-24/0514 11 pages |  | A | Internal Only | Test Procedure - Dangerous Goods Building in Depot - Civil & AR
1051 |  | 6 | MDW-69343 | OLW-ME-24/0358 | 2026-04-01 | A | Internal Only | Test Procedure - Dangerous Goods Building in Depot - Building Services | [12 empty] | submitted
1052 |  | 6 | MDW-69345 | เตรียมออก 21/7/26 OLW-ME-24/0463 11 pages |  |  | Internal Only | Test Procedure - Training Room at Ratchada Station (Part 2)
1053 |  | 6 | MDW-69347 |  |  |  | Internal Only | Test Procedure - Training Room at Ratchada Station (Part 2) - Building Services | [12 empty] | CANCLE
1054 |  | 6 | MDW-69349 | OLW-ME-24/0357 | 2026-04-01 | A | Internal Only | Test Procedure - Provision of Air Conditioning System in Commercial Room at OR13-OR19 | [12 empty] | submitted
1055 |  | 6 | MDW-69351 | OLW-ME-24/0345 | 2026-03-24 | A | Internal Only | Test Procedure - Modification SIG-PSD Office at Main Workshop - Building Services | [12 empty] | submitted
1056 |  | 6 | MDW-69353 | OLW-ME-24/0346 | 2026-03-24 | A | Internal Only | Test Procedure - Modification Backup CCR Room at Main Workshop - Building Services | [12 empty] | submitted
1057 |  | 6 | MDW-69355 | OLW-ME-24/0347 | 2026-03-24 | A | Internal Only | Test Procedure - Modification SER at Main Workshop - Building Services | [12 empty] | submitted
1058 |  | 6 | MDW-69357 | OLW-ME-24/0348 | 2026-03-31 | A | Internal Only | Test Procedure - Modification CER & SCADA Room at Main Workshop - Building Services | [12 empty] | submitted
1059 |  | 6 | MDW-69359 |  |  |  | Internal Only | Test Procedure - MEA Radio
1060 |  | 6 | MDW-69361 | เตรียมออก 7/8/26 OLW-ME-24/0515 total 8 pages |  | A | Internal Only | Test Procedure - Safety Provision for Maintenance Pits
1061 |  | 6 | MDW-69363 | OLW-ME-24/0414 | 2026-06-10 | A | Internal Only | Test Procedure - Modification CER and First Aid Room at OR14 - Building Services | [12 empty] | submitted
1062 |  | 6 | MDW-69365 | เตรียมออก 7/8/26 OLW-ME-24/0516 total 8 pages |  | A | Internal Only | Test Procedure - Additional Fence at Back of House OR13 - OR22 and IVS East Section
1063 |  | 6 | MDW-69367 |  |  |  | Internal Only | Test Procedure - Additional Locking Devices for Main Line Tandem Turnouts 2007, 2010 & 2013 and Depot Turnout D16
1064 |  | 6 | MDW-69369 |  |  |  |  | Test Procedure - Modification Air Conditioning System at CCR
1065 |  | 6 | MDW-69371 |  |  |  |  | Test Procedure - Modification AFC Training Center at OR19 - Civil & AR
1066 |  | 6 | MDW-69373 |  |  |  |  | Test Procedure - Modification AFC Training Center at OR19 - Building Services
1067 |  | 6 | MDW-69375 |  |  |  |  | Test Procedure - Modification Electronic Workshop at Main Workshop - Building Services
1068 |  | 6 | MDW-69377 |  |  |  |  | Test Procedure - Modification Battery Charger Room at Main Workshop - Building Services
1069 |  | 6 | MDW-69379 |  |  |  |  | Test Procedure - Modification Machining Room at Main Workshop - Building Services
1070 |  | 6 | MDW-69381 |  |  |  |  | Test Procedure - Modification Paint Shop Room at Main Workshop - Building Services
1071 |  | 6 | MDW-69383 |  |  |  |  | Test Procedure - Modification Electronic Workshop, Battery Charger, Machining and Paint Shop at Main Workshop - Civil & AR
1072 |  | 6 | MDW-69500 | เตรียมออก 7/8/26 OLW-ME-24/0517 total 19 pages |  | A | Internal Only | Test Procedure - Modification Works : Storage Office in Main Workshop - Civil & AR
1073 |  | 6 | MDW-69502 | OLW-ME-24/374 | 2026-05-05 | A | Internal Only | Test Procedure - Modification Works : Storage Office in Main Workshop - Building Services | [12 empty] | submitted
1074 |  | 6 | MDW-69504 |  |  |  | Internal Only | Test Procedure - Modification Works : all Fire Alarm System Controller in Depot | [12 empty] | CANCLE
1075 |  | 6 | MDW-69506 | เตรียมออก 7/8/26 OLW-ME-24/0518 total 12 pages |  |  | Internal Only | Test Procedure - Modification Works : New MMC at Admin Building - Civil & AR
1076 |  | 6 | MDW-69508 | เตรียมออก 31/7/26 OLW-ME-24/0477 Total 41 pages |  |  | Internal Only | Test Procedure - Modification Works : New MMC at Admin Building - Building Services
1077 |  | 6 | MDW-69510 | OLW-ME-24/0485 total 22 pages | 2026-07-24 | A | Internal Only | Test Procedure - Modification Works : Walkway with Roof from Main Workshop to Stabling Yard - Civil & AR | [12 empty] | submitted
1078 |  | 6 | MDW-69512 | OLW-ME-24/0373 | 2026-05-05 | A | Internal Only | Test Procedure - Modification Works : Walkway with Roof from Main Workshop to Stabling Yard - Building Services | [12 empty] | submitted
1079 |  | 6 | MDW-69514 | OLW-ME-24/0486 10 pages | 2026-07-24 | A | Internal Only | Test Procedure - Modification Works : High Roof in front of MWS Entrance and Store Entrance - Civil & AR | [12 empty] | submitted
1080 |  | 6 | MDW-69516 |  |  |  | Internal Only | Test Procedure - Modification Works : High Roof in front of MWS Entrance and Store Entrance - Building Services | [12 empty] | CANCLE
1081 |  | 6 | MDW-69518 | OLW-ME-24/0487 10 pages | 2026-07-24 | A | Internal Only | Test Procedure - Modification Works : High Roof at Under Floor Wheel Lathe - Civil & AR | [12 empty] | submitted
1082 |  | 6 | MDW-69520 |  |  |  | Internal Only | Test Procedure - Modification Works : High Roof at Under Floor Wheel Lathe - Building Services | [12 empty] | CANCLE
1083 |  | 6 | MDW-69522 | OLW-ME-24/0464 11 pages | 2026-07-15 | A | Internal Only | Test Procedure - Modification Works : Maintenance Office Rooms at Main Workshop - Civil & AR | [12 empty] | submitted
1084 |  | 6 | MDW-69524 | OLW-ME-24/0415 | 2026-06-10 | A | Internal Only | Test Procedure - Modification Works : Maintenance Office Rooms at Main Workshop - Building Services | [12 empty] | submitted
1085 |  | 6 | MDW-69526 |  |  |  | Internal Only | Test Procedure - Modification Works : Concrete Car Barrier in front of Main Workshop
1086 |  | 6 | MDW-69528 | OLW-ME-24/0488 total 12 pages | 2026-07-24 | A | Internal Only | Test Procedure - Modification Works : Car Park Roof and Motorcycle in Depot - Civil & AR | [12 empty] | submitted
1087 |  | 6 | MDW-69530 | OLW-ME-24/0391 | 2026-05-18 | A | Internal Only | Test Procedure - Modification Works : Car Park Roof and Motorcycle in Depot - Building Services | [12 empty] | submitted
1088 |  | 6 | MDW-69532 | OLW-ME-24/0489 total 16 pages | 2026-07-24 | A | Internal Only | Test Procedure - Modification Works : Walkway Bridge between BL Depot and ORL Depot - Civil & AR | [12 empty] | submitted
1089 |  | 6 | MDW-69534 | OLW-ME-24/0417 | 2025-06-16 | A | Internal Only | Test Procedure - Modification Works : Walkway Bridge between BL Depot and ORL Depot - Building Services | [12 empty] | submitted
1090 |  | 6 | MDW-69536 | OLW-ME-24/0332 | 2026-03-23 | A | Internal Only | Test Procedure - Modification Works : Street Lighting between MRTA Fence and Depot Slab | [12 empty] | submitted
1091 |  | 6 | MDW-69538 | OLW-ME-24/0490 total 17 pages | 2026-07-24 | A | Internal Only | Test Procedure - Modification Works : Walkway with Roof in Depot Area - Civil & AR | [12 empty] | submitted
1092 |  | 6 | MDW-69540 | OLW-ME-24/0478 22 pages | 2026-07-15 | A | Internal Only | Test Procedure - Modification Works : Sliding Gate, Chain Link Fence and Walkway with Roof in Depot Area - Building Services | [12 empty] | submitted
1093 |  | 6 | MDW-69542 | OLW-ME-24/0491 total 10 pages | 2026-07-24 | A | Internal Only | Test Procedure - Modification Works : Walkway Bridge and Walkway over Canal in Depot | [12 empty] | submitted
1094 |  | 6 | MDW-69544 | OLW-ME-24/0492 total 16 pages | 2026-07-24 | A | Internal Only | Test Procedure - Modification Works : Rain Protection and Zero Discharge Water treatment in Depot - Civil & AR | [12 empty] | submitted
1095 |  | 6 | MDW-69546 | OLW-ME-24/0349 | 2026-03-31 | A | Internal Only | Test Procedure - Modification Works : Cold Water System at Admin Building Landscape | [12 empty] | submitted
1096 |  | 6 | MDW-69548 |  |  |  | Internal Only | Test Procedure - Modification Works : Walkway under Depot Slab for Maintenance Service - Civil & AR
1097 |  | 6 | MDW-69550 | OLW-ME-24/0418 | 2026-06-10 | A | Internal Only | Test Procedure - Modification Works : Walkway under Depot Slab for Maintenance Service - Building Services | [12 empty] | submitted
1098 |  | 6 | MDW-69552 | OLW-ME-24/0328 | 2026-03-18 | A | Internal Only | Test Procedure - Modification Works : FHC Modification at Stabling Yard | [12 empty] | submitted
1099 |  | 6 | MDW-69554 | OLW-ME-24/0361 | 2026-04-01 | A | Internal Only | Test Procedure - Modification Works : Hand Sink with Emergency Eye Wash Installation in Depot | [12 empty] | submitted
1100 |  | 6 | MDW-69556 | OLW-ME-24/0493 9 pages | 2026-07-24 | A | Internal Only | Test Procedure - Modification Works : Washing Area in Cleaning Staff Room at Stabling Yard - Civil & AR | [12 empty] | submitted
1101 |  | 6 | MDW-69558 | OLW-ME-24/0350 | 2026-03-31 | A | Internal Only | Test Procedure - Modification Works : Washing Area in Cleaning Staff Room at Stabling Yard - Building Services | [12 empty] | submitted
1102 |  | 6 | MDW-69560 | OLW-ME-24/0360 | 2026-04-01 | A | Internal Only | Test Procedure - Modification Works : Zero Discharge Water treatment in Depot - Building Services | [12 empty] | submitted
1103 |  | 6 | MDW-69562 | OLW-ME-24/0465 8 pages | 2026-07-15 | A | Internal Only | Test Procedure - Modification Works : Guard rail protection for FHC in Depot Area | [12 empty] | submitted
1104 |  | 6 | MDW-69564 | เตรียมออก 1/7/26 OLW-ME-24/0421 |  |  | Internal Only | Test Procedure - Modification Works : Barbed Wire Fences for MRTA Chain Link at Klong Chourdyai
1105 |  | 6 | MDW-69566 | เตรียมออก 26/6/26 OLW-ME-24/0422 | 11 หน้า |  | Internal Only | Test Procedure - Modification Works : Car Barrier Gate at Depot Area
1106 |  | 6 | MDW-69568 |  |  |  | Internal Only | Test Procedure - Modification Works : Security Guard Box at ORL Depot Entrance - Civil & AR
1107 |  | 6 | MDW-69570 | OLW-ME-24/0479 24 pages | 2026-07-15 | A | Internal Only | Test Procedure - Modification Works : Security Guard Box at ORL Depot Entrance - Building Services | [12 empty] | submitted
1108 |  | 6 | MDW-69572 |  |  |  | Internal Only | Test Procedure - Modification Works : Soundproof Installation and Company Logo at CCR Room
1109 |  | 6 | MDW-69574 |  |  |  | Internal Only | Test Procedure - Modification Works : Fence Installation at Ladder in VS, IVS Buildings
1110 |  | 6 | MDW-69576 |  |  |  | Internal Only | Test Procedure - Modification Works : Anti-Slide Signage at Escalator for all Stations
1111 |  | 6 | MDW-69578 |  |  |  | Internal Only | Test Procedure - Modification Works : Roofing over Control Panel Installation at VS, IVS Buildings
1112 |  | 6 | MDW-69580 |  |  |  | Internal Only | Test Procedure - Modification Works : Water Drop Protection for UPS Cabinet for all Stations and Depot
1113 |  | 6 | MDW-69582 |  |  |  | Internal Only | Test Procedure - Modification Works : Manual Call Point Cover in Public Area at all Stations
1114 |  | 6 | MDW-69584 |  |  |  | Internal Only | Test Procedure - Modification Works : Emergency Stop Button Cover for Escalator at all Stations
1115 |  | 6 | MDW-69586 |  |  |  | Internal Only | Test Procedure - Modification Works : Bird & Rain Protetion, Safety Hand Rail Installation at Admin Building
1116 |  | 6 | MDW-69588 |  |  |  | Internal Only | Test Procedure - Modification Works : Barbed Wire Fences for Depot slab
1117 |  | 6 | MDW-69590 | OLW-ME-24/0494 total 8 pages | 2026-07-24 | A | Internal Only | Test Procedure - Modification Works : Chain Link Installation at Cut & Cover Depot Access | [12 empty] | submitted
1118 |  | 6 | MDW-69592 |  |  |  | Internal Only | Test Procedure - Modification Works : Chain Link Installation under Depot Slab
1119 |  | 6 | MDW-69594 | OLW-ME-24/0467 13 pages | 2026-07-15 | A | Internal Only | Test Procedure - Modification Works : Door and Lockset Modification at OCC Building | [12 empty] | submitted
1120 |  | 6 | MDW-69596 | OLW-ME-24/0351 | 2026-03-31 | A | Internal Only | Test Procedure - Modification Works : Air Conditioning System Installation at Pantry room OCC Building | [12 empty] | submitted
1121 |  | 6 | MDW-69598 | OLW-ME-24/0362 | 2026-04-01 | A | Internal Only | Test Procedure - Maintenance Room and Satellite Store at Stations - Building Services | [12 empty] | submitted
1122 |  | 6 | MDW-69600 |  |  |  | Internal Only | Test Procedure - Satellite Store at OR21 - Civil & AR
1123 |  | 6 | MDW-69602 | OLW-ME-24/0359 | 2026-04-01 | A | Internal Only | Test Procedure - Modification Works : Train Crew Office at OR29 | [12 empty] | submitted
1124 |  | 6 | MDW-69604 | เตรียมออก 6/8/26 OLW-ME-24/0520 total 8 pages |  | A | Internal Only | Test Procedure - Modification Works : Hand Rail Installation at Walk Way in Stabling Yard
1125 |  | 6 | MDW-69606 |  |  |  | Internal Only | Test Procedure - Modification Works : Ladder to Access the Fire Valve at Omega Joints for all Underground Stations
1126 | [6 empty] | Internal Only | Test Procedure - Modification Works : Fire Suspension Control Panel Cover Installation at Tunnel Main Line | [12 empty] | CANCLE
1127 |  | 6 | MDW-69608 |  |  |  | Internal Only | Test Procedure - Modification Works : Security Guard Box at OCC Parking Area - Civil & AR
1128 |  | 6 | MDW-69610 |  |  |  | Internal Only | Test Procedure - Modification Works : Security Guard Box at OCC Parking Area - Building Services
1129 |  | 6 | MDW-69612 | OLW-ME-24/0372 | 2026-05-05 | A | Internal Only | Test Procedure - Modification Works : Addition Small Power System at OCC Building | [12 empty] | submitted
1130 |  | 6 | MDW-69614 | เตรียมออก 6/8/26 OLW-ME-24/0521 9 pages |  | A | Internal Only | Test Procedure - Modification Works : Sliding Gate and Chain Link Fence in Depot Area - Civil & AR
1131 | [7 empty] | Testing and Commissioning Stage / System Integration and Handover Report
1132 |  | 6 | MDW-69002 |  |  |  |  | Test Report - Modification of Depot Track Alignment at Stabling Yard
1133 |  | 6 | MDW-69004 |  |  |  |  | Test Report - Modification Motorized Gate and Shelters at Test Track Depot - Civil & AR
1134 |  | 6 | MDW-69006 |  |  |  |  | Test Report - Modification Motorized Gate and Shelters at Test Track Depot - Building Service
1135 |  | 6 | MDW-69008 |  |  |  |  | Test Report - Rubber Gap Fillers on Platform Edge on East Section
1136 |  | 6 | MDW-69201 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of OR13
1137 |  | 6 | MDW-69202 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of OR14
1138 |  | 6 | MDW-69203 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of OR15
1139 |  | 6 | MDW-69204 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of OR16
1140 |  | 6 | MDW-69205 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of OR17
1141 |  | 6 | MDW-69206 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of OR18
1142 |  | 6 | MDW-69207 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of OR19
1143 |  | 6 | MDW-69208 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of OR20
1144 |  | 6 | MDW-69209 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of OR21
1145 |  | 6 | MDW-69210 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of OR22
1146 |  | 6 | MDW-69211 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of OR23
1147 |  | 6 | MDW-69212 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of OR24
1148 |  | 6 | MDW-69213 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of OR25
1149 |  | 6 | MDW-69214 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of OR26
1150 |  | 6 | MDW-69215 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of OR27
1151 |  | 6 | MDW-69216 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of OR28
1152 |  | 6 | MDW-69217 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of OR29
1153 |  | 6 | MDW-69218 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of VS02
1154 |  | 6 | MDW-69219 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of VS03
1155 |  | 6 | MDW-69220 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of IVS08
1156 |  | 6 | MDW-69221 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of IVS09
1157 |  | 6 | MDW-69222 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of IVS10
1158 |  | 6 | MDW-69223 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of IVS11
1159 |  | 6 | MDW-69224 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of IVS12
1160 |  | 6 | MDW-69225 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of IVS13
1161 |  | 6 | MDW-69226 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of IVS14
1162 |  | 6 | MDW-69227 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of IVS15
1163 |  | 6 | MDW-69228 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of IVS16
1164 |  | 6 | MDW-69229 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of IVS17
1165 |  | 6 | MDW-69230 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of EEEN
1166 |  | 6 | MDW-69231 |  |  |  |  | Test Report - Modification Work of M&E Cable Containment of Orange Line - Depot
1167 |  | 6 | MDW-69233 |  |  |  |  | Test Report - Level Crossing at Turnout and Track Slab Crossing on Main Line East Section
1168 |  | 6 | MDW-69235 |  |  |  |  | Test Report - Main Line Cable Trough Modification on East Section (PSY)
1169 |  | 6 | MDW-69236 |  |  |  |  | Test Report - Main Line Cable Trough Modification on East Section (SIG/COM)
1170 |  | 6 | MDW-69238 |  |  |  |  | Test Report - Raised Floor Installation on East Section
1171 |  | 6 | MDW-69240 |  |  |  |  | Test Report - Bird Protection System at Depot Buildings
1172 |  | 6 | MDW-69242 |  |  |  |  | Test Report - Central BEMS for the MRT Orange Line System East Section
1173 |  | 6 | MDW-69244 |  |  |  |  | Test Report - Central BEMS for the MRT Orange Line System West Section
1174 |  | 6 | MDW-69246 |  |  |  |  | Test Report - Access Panel Closeout for Traction Substation Room in Main Workshop
1175 |  | 6 | MDW-69248 |  |  |  |  | Test Report - Driver Train Simulation Room and Train Crew Office at OR18 - Civil & AR
1176 |  | 6 | MDW-69250 |  |  |  |  | Test Report - Driver Train Simulation Room and Train Crew Office at OR18 - Building Services
1177 |  | 6 | MDW-69252 | OLW-ME-24/0408 | 2026-05-24 | A |  | Test Report - Modification Works for Training Room at Ratchada Station | [12 empty] | submitted
1178 |  | 6 | MDW-69254 |  |  |  |  | Test Report - Eye Adaptation Lighting at Transition Area and Depot Approach
1179 |  | 6 | MDW-69256 |  |  |  |  | Test Report - AFC Training Room Modification - Civil & AR
1180 |  | 6 | MDW-69258 |  |  |  |  | Test Report - AFC Training Room Modification - Building Services
1181 |  | 6 | MDW-69260 |  |  |  |  | Test Report - Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR13 - OR17
1182 |  | 6 | MDW-69261 |  |  |  |  | Test Report - Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR18 - OR22
1183 |  | 6 | MDW-69262 |  |  |  |  | Test Report - Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR22 - OR29
1184 |  | 6 | MDW-69264 |  |  |  |  | Test Report - SOR Counter and Workstation Hanging Support Installation on East Section
1185 |  | 6 | MDW-69266 |  |  |  |  | Test Report - Ticket Office Modification on East Section
1186 |  | 6 | MDW-69268 |  |  |  |  | Test Report - Modification of Eletrical System in Telecommunication Room at OR14 | [12 empty] | CANCLE
1187 |  | 6 | MDW-69270 |  |  |  |  | Test Report - Modification of Ventilation System, Fire Suspression System (N2) in Telecommunication Room at OR14
1188 |  | 6 | MDW-69272 |  |  |  |  | Test Report - Modification of Civil Work in Telecommunication Room at OR14
1189 |  | 6 | MDW-69274 |  |  |  |  | Test Report - Modification in Staff Mess Room at OR13-OR17
1190 |  | 6 | MDW-69275 |  |  |  |  | Test Report - Modification in Staff Mess Room at OR18-OR22
1191 |  | 6 | MDW-69276 |  |  |  |  | Test Report - Modification in Staff Mess Room at OR23-OR29
1192 |  | 6 | MDW-69278 |  |  |  |  | Test Report - Modification of Air Conditioning in CER and SER at OR13-OR19
1193 |  | 6 | MDW-69279 |  |  |  |  | Test Report - Modification of Air Conditioning in CER and SER at OR20-OR22
1194 |  | 6 | MDW-69280 |  |  |  |  | Test Report - Modification of Air Conditioning in CER and SER at OR23-OR29
1195 |  | 6 | MDW-69282 |  |  |  |  | Test Report - Modification of Air Conditioning in M&E Room at OCC Building
1196 |  | 6 | MDW-69284 |  |  |  |  | Test Report - Provision of UPS for MDB Control at Main Workshop, OCC Building, Admin Building, Stabling Yard and Train Washing Plant
1197 |  | 6 | MDW-69286 |  |  |  |  | Test Report - Provision of Redundant MDB at OCC Building, Admin Building and Canteen
1198 |  | 6 | MDW-69288 |  |  |  |  | Test Report - Additonal Lighting System at Depot Area
1199 |  | 6 | MDW-69290 |  |  |  |  | Test Report - Block-out and Holes Modification at Depot Platform | [12 empty] | CANCLE
1200 |  | 6 | MDW-69292 |  |  |  |  | Test Report - Main Cable Containment Modification at Depot
1201 |  | 6 | MDW-69294 |  |  |  |  | Test Report - PSY Wayside Cable Containment for 24 KV Cable under Depot slab | [12 empty] | CANCLE
1202 |  | 6 | MDW-69296 |  |  |  |  | Test Report - SIG/COM Wayside Cable Containment in Depot
1203 |  | 6 | MDW-69298 |  |  |  |  | Test Report - Wayside Cable Trough in Depot
1204 |  | 6 | MDW-69300 |  |  |  |  | Test Report - Modification of New M&E Room at IVS15 - IVS17 Civil & AR
1205 |  | 6 | MDW-69302 |  |  |  |  | Test Report - Modification of New M&E UPS Room at IVS15-IVS17 - Building Services
1206 |  | 6 | MDW-69304 |  |  |  |  | Test Report - Ticket Issuing Machine (TIM) Wall Opening and Closing East Section
1207 |  | 6 | MDW-69306 |  |  |  |  | Test Report - Modification Works for AFC - Balustrade Modification Along AFC Gate Line East Section
1208 |  | 6 | MDW-69308 |  |  |  |  | Test Report - Underfloor Embedded Duct Modification for AFC Gates Line East Section
1209 |  | 6 | MDW-69310 |  |  |  |  | Test Report - Balustrade Modification Along AFC Gate Line East Section
1210 |  | 6 | MDW-69312 |  |  |  |  | Test Report - Platform Finishing on East Section
1211 |  | 6 | MDW-69314 |  |  |  |  | Test Report - Cladding Barrier between EWD and Station Structure on East Section
1212 |  | 6 | MDW-69316 |  |  |  |  | Test Report - Holes for PSD Cable Wiring on East Section
1213 |  | 6 | MDW-69318 |  |  |  |  | Test Report - Intercom System in Cash Handling Room East Section
1214 |  | 6 | MDW-69320 |  |  |  |  | Test Report - Power Cable and Conduits Modification for Walk-Through Metal Detector East Section | [12 empty] | CANCLE
1215 |  | 6 | MDW-69322 |  |  |  |  | Test Report - Underground Cable Containment at Station Public Areas East Section | [12 empty] | CANCLE
1216 |  | 6 | MDW-69324 |  |  |  |  | Test Report - Strobe Light at Buffer Stops East Section | [12 empty] | CANCLE
1217 |  | 6 | MDW-69326 |  |  |  |  | Test Report - Strobe Light at Buffer Stops East Section
1218 |  | 6 | MDW-69328 |  |  |  |  | Test Report - Point Machine Foundation Construction on East Section
1219 |  | 6 | MDW-69330 |  |  |  |  | Test Report - Earthing and Bonding for Raised Floor on East Section
1220 |  | 6 | MDW-69332 |  |  |  |  | Test Report - Modification Room for PSY at Depot Buildings - Building Services
1221 |  | 6 | MDW-69334 |  |  |  |  | Test Report - Conductor Arrangement Modification at Main Line East Section
1222 |  | 6 | MDW-69336 |  |  |  |  | Test Report - Conductor Rail Arrangement Modification at Depot
1223 |  | 6 | MDW-69338 |  |  |  |  | Test Report - Stabling Walkway Modification at Stabling Yard - Civil & AR
1224 |  | 6 | MDW-69340 |  |  |  |  | Test Report - Provision of Architectural Work in new M&E UPS room at OR23
1225 |  | 6 | MDW-69342 |  |  |  |  | Test Report - Dangerous Goods Building in Depot - Civil & AR
1226 |  | 6 | MDW-69344 |  |  |  |  | Test Report - Dangerous Goods Building in Depot - Building Services
1227 |  | 6 | MDW-69346 |  |  |  |  | Test Report - Training Room at Ratchada Station (Part 2)
1228 |  | 6 | MDW-69348 |  |  |  |  | Test Report - Training Room at Ratchada Station (Part 2) - Building Services | [12 empty] | CANCLE
1229 |  | 6 | MDW-69350 |  |  |  |  | Test Report - Provision of Air Conditioning System in Commercial Room at OR13-OR19
1230 |  | 6 | MDW-69352 |  |  |  |  | Test Report - Modification SIG-PSD Office at Main Workshop - Building Services
1231 |  | 6 | MDW-69354 |  |  |  |  | Test Report - Modification Backup CCR Room at Main Workshop - Building Services
1232 |  | 6 | MDW-69356 |  |  |  |  | Test Report - Modification SER at Main Workshop - Building Services
1233 |  | 6 | MDW-69358 |  |  |  |  | Test Report - Modification CER & SCADA Room at Main Workshop - Building Services
1234 |  | 6 | MDW-69360 |  |  |  |  | Test Report - MEA Radio
1235 |  | 6 | MDW-69362 |  |  |  |  | Test Report - Safety Provision for Maintenance Pits
1236 |  | 6 | MDW-69364 |  |  |  |  | Test Report - Modification CER and First Aid Room at OR14 - Building Services
1237 |  | 6 | MDW-69366 |  |  |  |  | Test Report - Additional Fence at Back of House OR13 - OR22 and IVS East Section
1238 |  | 6 | MDW-69368 |  |  |  |  | Test Report - Additional Locking Devices for Main Line Tandem Turnouts 2007, 2010 & 2013 and Depot Turnout D16
1239 |  | 6 | MDW-69370 |  |  |  |  | Test Report - Modification Air Conditioning System at CCR
1240 |  | 6 | MDW-69372 |  |  |  |  | Test Report - Modification AFC Training Center at OR19 - Civil & AR
1241 |  | 6 | MDW-69374 |  |  |  |  | Test Report - Modification AFC Training Center at OR19 - Building Services
1242 |  | 6 | MDW-69376 |  |  |  |  | Test Report - Modification Electronic Workshop at Main Workshop - Building Services
1243 |  | 6 | MDW-69378 |  |  |  |  | Test Report - Modification Battery Charger Room at Main Workshop - Building Services
1244 |  | 6 | MDW-69380 |  |  |  |  | Test Report - Modification Machining Room at Main Workshop - Building Services
1245 |  | 6 | MDW-69382 |  |  |  |  | Test Report - Modification Paint Shop Room at Main Workshop - Building Services
1246 |  | 6 | MDW-69384 |  |  |  |  | Test Report - Modification Electronic Workshop, Battery Charger, Machining and Paint Shop at Main Workshop - Civil & AR
1247 |  | 6 | MDW-69501 |  |  |  |  | Test Report - Modification Works : Storage Office in Main Workshop - Civil & AR
1248 |  | 6 | MDW-69503 |  |  |  |  | Test Report - Modification Works : Storage Office in Main Workshop - Building Services
1249 |  | 6 | MDW-69505 |  |  |  |  | Test Report - Modification Works : all Fire Alarm System Controller in Depot | [12 empty] | CANCLE
1250 |  | 6 | MDW-69507 |  |  |  |  | Test Report - Modification Works : New MMC at Admin Building - Civil & AR
1251 |  | 6 | MDW-69509 |  |  |  |  | Test Report - Modification Works : New MMC at Admin Building - Building Services
1252 |  | 6 | MDW-69511 |  |  |  |  | Test Report - Modification Works : Walkway with Roof from Main Workshop to Stabling Yard - Civil & AR
1253 |  | 6 | MDW-69513 |  |  |  |  | Test Report - Modification Works : Walkway with Roof from Main Workshop to Stabling Yard - Building Services
1254 |  | 6 | MDW-69515 |  |  |  |  | Test Report - Modification Works : High Roof in front of MWS Entrance and Store Entrance - Civil & AR
1255 |  | 6 | MDW-69523 |  |  |  |  | Test Report - Modification Works : Maintenance Office Rooms at Main Workshop - Civil & AR
1256 |  | 6 | MDW-69525 |  |  |  |  | Test Report - Modification Works : Maintenance Office Rooms at Main Workshop - Building Services
1257 |  | 6 | MDW-69527 |  |  |  |  | Test Report - Modification Works : Concrete Car Barrier in front of Main Workshop
1258 |  | 6 | MDW-69529 |  |  |  |  | Test Report - Modification Works : Car Park Roof and Motorcycle in Depot - Civil & AR
1259 |  | 6 | MDW-69531 |  |  |  |  | Test Report - Modification Works : Car Park Roof and Motorcycle in Depot - Building Services
1260 |  | 6 | MDW-69533 |  |  |  |  | Test Report - Modification Works : Walkway Bridge between BL Depot and ORL Depot - Civil & AR
1261 |  | 6 | MDW-69535 |  |  |  |  | Test Report - Modification Works : Walkway Bridge between BL Depot and ORL Depot - Building Services
1262 |  | 6 | MDW-69537 |  |  |  |  | Test Report - Modification Works : Street Lighting between MRTA Fence and Depot Slab
1263 |  | 6 | MDW-69539 |  |  |  |  | Test Report - Modification Works : Walkway with Roof in Depot Area - Civil & AR
1264 |  | 6 | MDW-69541 |  |  |  |  | Test Report - Modification Works : Sliding Gate, Chain Link Fence and Walkway with Roof in Depot Area - Building Services
1265 |  | 6 | MDW-69543 |  |  |  |  | Test Report - Modification Works : Walkway Bridge and Walkway over Canal in Depot
1266 |  | 6 | MDW-69545 |  |  |  |  | Test Report - Modification Works : Rain Protection and Zero Discharge Water treatment in Depot - Civil & AR
1267 |  | 6 | MDW-69547 | OLW-ME-24/0471 20 pages | 2026-07-10 | A |  | Test Report - Modification Works : Cold Water System at Admin Building Landscape | [12 empty] | submitted
1268 |  | 6 | MDW-69549 |  |  |  |  | Test Report - Modification Works : Walkway under Depot Slab for Maintenance Service - Civil & AR
1269 |  | 6 | MDW-69551 |  |  |  |  | Test Report - Modification Works : Walkway under Depot Slab for Maintenance Service - Building Services
1270 |  | 6 | MDW-69553 | OLW-ME-24/0387 | 2026-05-15 | A |  | Test Report - Modification Works : FHC Modification at Stabling Yard | [12 empty] | submitted
1271 |  | 6 | MDW-69555 |  |  |  |  | Test Report - Modification Works : Hand Sink with Emergency Eye Wash Installation in Depot
1272 |  | 6 | MDW-69557 |  |  |  |  | Test Report - Modification Works : Washing Area in Cleaning Staff Room at Stabling Yard - Civil & AR
1273 |  | 6 | MDW-69559 | OLW-ME-24/0470 13 pages | 2026-07-10 | A |  | Test Report - Modification Works : Washing Area in Cleaning Staff Room at Stabling Yard - Building Services | [12 empty] | submitted
1274 |  | 6 | MDW-69561 |  |  |  |  | Test Report - Modification Works : Zero Discharge Water treatment in Depot - Building Services
1275 |  | 6 | MDW-69563 |  |  |  |  | Test Report - Modification Works : Guard rail protection for FHC in Depot Area
1276 |  | 6 | MDW-69565 |  |  |  |  | Test Report - Modification Works : Barbed Wire Fences for MRTA Chain Link at Klong Chourdyai
1277 |  | 6 | MDW-69567 |  |  |  |  | Test Report - Modification Works : Car Barrier Gate at Depot Area
1278 |  | 6 | MDW-69569 |  |  |  |  | Test Report - Modification Works : Security Guard Box at ORL Depot Entrance - Civil & AR
1279 |  | 6 | MDW-69571 |  |  |  |  | Test Report - Modification Works : Security Guard Box at ORL Depot Entrance - Building Services
1280 |  | 6 | MDW-69573 |  |  |  |  | Test Report - Modification Works : Soundproof Installation and Company Logo at CCR Room
1281 |  | 6 | MDW-69575 |  |  |  |  | Test Report - Modification Works : Fence Installation at Ladder in VS, IVS Buildings
1282 |  | 6 | MDW-69577 |  |  |  |  | Test Report - Modification Works : Anti-Slide Signage at Escalator for all Stations
1283 |  | 6 | MDW-69579 |  |  |  |  | Test Report - Modification Works : Roofing over Control Panel Installation at VS, IVS Buildings
1284 |  | 6 | MDW-69581 |  |  |  |  | Test Report - Modification Works : Water Drop Protection for UPS Cabinet for all Stations and Depot
1285 |  | 6 | MDW-69583 |  |  |  |  | Test Report - Modification Works : Manual Call Point Cover in Public Area at all Stations
1286 |  | 6 | MDW-69585 |  |  |  |  | Test Report - Modification Works : Emergency Stop Button Cover for Escalator at all Stations
1287 |  | 6 | MDW-69587 |  |  |  |  | Test Report - Modification Works : Bird & Rain Protetion, Safety Hand Rail Installation at Admin Building
1288 |  | 6 | MDW-69589 |  |  |  |  | Test Report - Modification Works : Barbed Wire Fences for Depot slab
1289 |  | 6 | MDW-69591 |  |  |  |  | Test Report - Modification Works : Chain Link Installation at Cut & Cover Depot Access
1290 |  | 6 | MDW-69593 |  |  |  |  | Test Report - Modification Works : Chain Link Installation under Depot Slab
1291 |  | 6 | MDW-69595 |  |  |  |  | Test Report - Modification Works : Door and Lockset Modification at OCC Building
1292 |  | 6 | MDW-69597 | OLW-ME-24/0469 40 pages | 2026-07-10 | A |  | Test Report - Modification Works : Air Conditioning System Installation at Pantry room OCC Building | [12 empty] | submitted
1293 |  | 6 | MDW-69599 |  |  |  |  | Test Report - Maintenance Room and Satellite Store at Stations - Building Services
1294 |  | 6 | MDW-695601 |  |  |  |  | Test Report - Satellite Store at OR21 - Civil & AR
1295 |  | 6 | MDW-69603 |  |  |  |  | Test Report - Modification Works : Train Crew Office at OR29
1296 |  | 6 | MDW-69605 |  |  |  |  | Test Report - Modification Works : Hand Rail Installation at Walk Way in Stabling Yard
1297 |  | 6 | MDW-69607 |  |  |  |  | Test Report - Modification Works : Ladder to Access the Fire Valve at Omega Joints for all Underground Stations
1298 | [7 empty] | Test Report - Modification Works : Fire Suspension Control Panel Cover Installation at Tunnel Main Line | [12 empty] | CANCLE
1299 |  | 6 | MDW-69609 |  |  |  |  | Test Report - Modification Works : Security Guard Box at OCC Parking Area - Civil & AR
1300 |  | 6 | MDW-69611 |  |  |  |  | Test Report - Modification Works : Security Guard Box at OCC Parking Area - Building Services
1301 |  | 6 | MDW-69613 | เตรียมออก 6/8/26 OLW-ME-24/0507 Total 45 pages | A |  |  | Test Report - Modification Works : Addition Small Power System at OCC Building
1302 |  | 6 | MDW-69615 |  |  |  |  | Test Report - Modification Works : Sliding Gate and Chain Link Fence in Depot Area - Civil & AR
1303 | [7 empty] | Training
1304 |  | 7 | MDW-79001 |  |  |  |  | Training Manual - Modification Motorized Gate and Shelters at Test Track Depot - English | [12 empty] | CANCLE
1305 |  | 7 | MDW-79002 |  |  |  |  | Training Manual - Modification Motorized Gate and Shelters at Test Track Depot - EThai Translation | [12 empty] | CANCLE
1306 | [7 empty] | As-Built Drawing, As-Built Configuration Data
1307 |  | 8 | MDW-89001 |  |  |  |  | As-Built - Modification of Depot Track Alignment at Stabling Yard
1308 |  | 8 | MDW-89002 |  |  |  |  | As-Built - Modification of Depot Track Alignment at Stabling Yard - Functional Location Data (FLD) | [12 empty] | CANCLE
1309 |  | 8 | MDW-89003 |  |  |  |  | As-Built - Modification Motorized Gate and Shelters at Test Track Depot - Civil & AR
1310 |  | 8 | MDW-89004 |  |  |  |  | As-Built - Modification Motorized Gate and Shelters at Test Track Depot - Building Service
1311 |  | 8 | MDW-89005 |  |  |  |  | As-Built - Rubber Gap Fillers on Platform Edge on East Section
1312 |  | 8 | MDW-89200 |  |  |  |  | As-Built - Modification Work of M&E Cable Containment of OR13
1313 |  | 8 | MDW-89201 |  |  |  |  | As-Built - Modification Work of M&E Cable Containment of OR14
1314 |  | 8 | MDW-89202 |  |  |  |  | As-Built - Modification Work of M&E Cable Containment of OR15
1315 |  | 8 | MDW-89203 |  |  |  |  | As-Built - Modification Work of M&E Cable Containment of OR16
1316 |  | 8 | MDW-89204 |  |  |  |  | As-Built - Modification Work of M&E Cable Containment of OR17
1317 |  | 8 | MDW-89205 |  |  |  |  | As-Built - Modification Work of M&E Cable Containment of OR18
1318 |  | 8 | MDW-89206 |  |  |  |  | As-Built - Modification Work of M&E Cable Containment of OR19
1319 |  | 8 | MDW-89207 |  |  |  |  | As-Built - Modification Work of M&E Cable Containment of OR20
1320 |  | 8 | MDW-89208 |  |  |  |  | As-Built - Modification Work of M&E Cable Containment of OR21
1321 |  | 8 | MDW-89209 |  |  |  |  | As-Built - Modification Work of M&E Cable Containment of OR22
1322 |  | 8 | MDW-89210 |  |  |  |  | As-Built - Modification Work of M&E Cable Containment of OR23
1323 |  | 8 | MDW-89211 |  |  |  |  | As-Built - Modification Work of M&E Cable Containment of OR24
1324 |  | 8 | MDW-89212 |  |  |  |  | As-Built - Modification Work of M&E Cable Containment of OR25
1325 |  | 8 | MDW-89213 |  |  |  |  | As-Built - Modification Work of M&E Cable Containment of OR26
1326 |  | 8 | MDW-89214 |  |  |  |  | As-Built - Modification Work of M&E Cable Containment of OR27
1327 |  | 8 | MDW-89215 |  |  |  |  | As-Built - Modification Work of M&E Cable Containment of OR28
1328 |  | 8 | MDW-89216 |  |  |  |  | As-Built - Modification Work of M&E Cable Containment of OR29
1329 |  | 8 | MDW-89217 |  |  |  |  | As-Built - Modification Work of M&E Cable Containment of VS02
1330 |  | 8 | MDW-89218 |  |  |  |  | As-Built - Modification Work of M&E Cable Containment of VS03
1331 |  | 8 | MDW-89219 |  |  |  |  | As-Built - Modification Work of M&E Cable Containment of IVS08
1332 |  | 8 | MDW-89220 |  |  |  |  | As-Built - Modification Work of M&E Cable Containment of IVS09
1333 |  | 8 | MDW-89221 |  |  |  |  | As-Built - Modification Work of M&E Cable Containment of IVS10
1334 |  | 8 | MDW-89222 |  |  |  |  | As-Built - Modification Work of M&E Cable Containment of IVS11
1335 |  | 8 | MDW-89223 |  |  |  |  | As-Built - Modification Work of M&E Cable Containment of IVS12
1336 |  | 8 | MDW-89224 |  |  |  |  | As-Built - Modification Work of M&E Cable Containment of IVS13
1337 |  | 8 | MDW-89225 |  |  |  |  | As-Built - Modification Work of M&E Cable Containment of IVS14
1338 |  | 8 | MDW-89226 |  |  |  |  | As-Built - Modification Work of M&E Cable Containment of IVS15
1339 |  | 8 | MDW-89227 |  |  |  |  | As-Built - Modification Work of M&E Cable Containment of IVS16
1340 |  | 8 | MDW-89228 |  |  |  |  | As-Built - Modification Work of M&E Cable Containment of IVS17
1341 |  | 8 | MDW-89229 |  |  |  |  | As-Built - Modification Work of M&E Cable Containment of EEEN
1342 |  | 8 | MDW-89230 |  |  |  |  | As-Built - Modification Work of M&E Cable Containment of Orange Line - Depot
1343 |  | 8 | MDW-89231 |  |  |  |  | As-Built - Modification of Depot Track Alignment at Stabling Yard - Functional Location Data (FLD) | [12 empty] | submitted
1344 |  | 8 | MDW-89232 |  |  |  |  | As-Built - Level Crossing at Turnout and Track Slab Crossing on Main Line East Section
1345 |  | 8 | MDW-89233 |  |  |  |  | As-Built - Main Line Cable Trough Modification on East Section (PSY)
1346 |  | 8 | MDW-89234 |  |  |  |  | As-Built - Main Line Cable Trough Modification on East Section (SIG/COM)
1347 |  | 8 | MDW-89235 |  |  |  |  | As-Built - Raised Floor Installation on East Section
1348 |  | 8 | MDW-89236 |  |  |  |  | As-Built - Bird Protection System at Depot Buildings
1349 |  | 8 | MDW-89237 |  |  |  |  | As-Built - Central BEMS for the MRT Orange Line System East Section
1350 |  | 8 | MDW-89238 |  |  |  |  | As-Built - Central BEMS for the MRT Orange Line System West Section
1351 |  | 8 | MDW-89239 |  |  |  |  | As-Built - Access Panel Closeout for Traction Substation Room in Main Workshop
1352 |  | 8 | MDW-89240 |  |  |  |  | As-Built - Driver Train Simulation Room and Train Crew Office at OR18 - Civil & AR
1353 |  | 8 | MDW-89241 |  |  |  |  | As-Built - Driver Train Simulation Room and Train Crew Office at OR18 - Building Services
1354 |  | 8 | MDW-89242 | OLW-ME-24/0404 | 2026-05-25 | A |  | As-Built - Modification Works for Training Room at Ratchada Station | [12 empty] | submitted
1355 |  | 8 | MDW-89243 |  |  |  |  | As-Built - Eye Adaptation Lighting at Transition Area and Depot Approach
1356 |  | 8 | MDW-89244 |  |  |  |  | As-Built - AFC Training Room Modification - Civil & AR
1357 |  | 8 | MDW-89245 |  |  |  |  | As-Built - AFC Training Room Modification - Building Services
1358 |  | 8 | MDW-89246 |  |  |  |  | As-Built - Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR13 - OR17
1359 |  | 8 | MDW-89247 |  |  |  |  | As-Built - Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR18 - OR22
1360 |  | 8 | MDW-89248 |  |  |  |  | As-Built - Power Outlet Installation in SOR, Ticket Office and Cash Handling for OR22 - OR29
1361 |  | 8 | MDW-89249 |  |  |  |  | As-Built - SOR Counter and Workstation Hanging Support Installation on East Section
1362 |  | 8 | MDW-89250 |  |  |  |  | As-Built - Ticket Office Modification on East Section
1363 |  | 8 | MDW-89252 |  |  |  |  | As-Built - Modification of Ventilation System, Fire Suspression System (N2) in Telecommunication Room at OR14
1364 |  | 8 | MDW-89253 |  |  |  |  | As-Built - Modification of Civil Work in Telecommunication Room at OR14
1365 |  | 8 | MDW-89254 |  |  |  |  | As-Built - Modification in Staff Mess Room at OR13-OR17
1366 |  | 8 | MDW-89255 |  |  |  |  | As-Built - Modification in Staff Mess Room at OR18-OR22
1367 |  | 8 | MDW-89256 |  |  |  |  | As-Built - Modification in Staff Mess Room at OR23-OR29
1368 |  | 8 | MDW-89257 |  |  |  |  | As-Built - Modification of Air Conditioning in CER and SER at OR13-OR19
1369 |  | 8 | MDW-89258 |  |  |  |  | As-Built - Modification of Air Conditioning in CER and SER at OR20-OR22
1370 |  | 8 | MDW-89259 |  |  |  |  | As-Built - Modification of Air Conditioning in CER and SER at OR23-OR29
1371 |  | 8 | MDW-89260 |  |  |  |  | As-Built - Modification of Air Conditioning in M&E Room at OCC Building
1372 |  | 8 | MDW-89261 |  |  |  |  | As-Built - Provision of UPS for MDB Control at Main Workshop, OCC Building, Admin Building, Stabling Yard and Train Washing Plant
1373 |  | 8 | MDW-89262 |  |  |  |  | As-Built - Provision of Redundant MDB at OCC Building, Admin Building and Canteen
1374 |  | 8 | MDW-89263 |  |  |  |  | As-Built - Additonal Lighting System at Depot Area
1375 |  | 8 | MDW-89264 |  |  |  |  | As-Built - Block-out and Holes Modification at Depot Platform | [12 empty] | CANCLE
1376 |  | 8 | MDW-89268 |  |  |  |  | As-Built - Main Cable Containment Modification at Depot
1377 |  | 8 | MDW-89269 |  |  |  |  | As-Built - PSY Wayside Cable Containment for 24 KV Cable under Depot slab | [12 empty] | CANCLE
1378 |  | 8 | MDW-89270 |  |  |  |  | As-Built - SIG/COM Wayside Cable Containment in Depot
1379 |  | 8 | MDW-89271 |  |  |  |  | As-Built - Wayside Cable Trough in Depot
1380 |  | 8 | MDW-89272 |  |  |  |  | As-Built - Modification of New M&E Room at IVS15 - IVS17 Civil & AR
1381 |  | 8 | MDW-89273 |  |  |  |  | As-Built - Modification of New M&E UPS Room at IVS15-IVS17 - Building Services
1382 |  | 8 | MDW-89276 |  |  |  |  | As-Built - Ticket Issuing Machine (TIM) Wall Opening and Closing East Section
1383 |  | 8 | MDW-89277 |  |  |  |  | As-Built - Modification Works for AFC - Balustrade Modification Along AFC Gate Line East Section
1384 |  | 8 | MDW-89278 |  |  |  |  | As-Built - Underfloor Embedded Duct Modification for AFC Gates Line East Section
1385 |  | 8 | MDW-89279 |  |  |  |  | As-Built - Balustrade Modification Along AFC Gate Line East Section
1386 |  | 8 | MDW-89280 |  |  |  |  | As-Built - Platform Finishing on East Section
1387 |  | 8 | MDW-89281 |  |  |  |  | As-Built - Cladding Barrier between EWD and Station Structure on East Section
1388 |  | 8 | MDW-89282 |  |  |  |  | As-Built - Holes for PSD Cable Wiring on East Section
1389 |  | 8 | MDW-89283 |  |  |  |  | As-Built - Intercom System in Cash Handling Room East Section
1390 |  | 8 | MDW-89284 |  |  |  |  | As-Built - Power Cable and Conduits Modification for Walk-Through Metal Detector East Section | [12 empty] | CANCLE
1391 |  | 8 | MDW-89285 |  |  |  |  | As-Built - Provision of Cable Containment between OCC ORL and OCC BL | [12 empty] | CANCLE
1392 |  | 8 | MDW-89286 |  |  |  |  | As-Built - Underground Cable Containment at Station Public Areas East Section | [12 empty] | CANCLE
1393 |  | 8 | MDW-89287 |  |  |  |  | As-Built - Strobe Light at Buffer Stops East Section
1394 |  | 8 | MDW-89288 |  |  |  |  | As-Built - Point Machine Foundation Construction on East Section
1395 |  | 8 | MDW-89289 |  |  |  |  | As-Built - Earthing and Bonding for Raised Floor on East Section
1396 |  | 8 | MDW-89290 |  |  |  |  | As-Built - Modification Room for PSY at Depot Buildings - Building Services
1397 |  | 8 | MDW-89291 |  |  |  |  | As-Built - Conductor Arrangement Modification at Main Line East Section
1398 |  | 8 | MDW-89292 |  |  |  |  | As-Built - Conductor Arrangement Modification at Main Line East Section - Functional Location Data (FLD)
1399 |  | 8 | MDW-89293 |  |  |  |  | As-Built - Conductor Arrangement Modification at Depot
1400 |  | 8 | MDW-89294 |  |  |  |  | As-Built - Conductor Arrangement Modification at Depot - Functional Location Data (FLD)
1401 |  | 8 | MDW-89295 |  |  |  |  | As-Built - Stabling Walkway Modification at Stabling Yard - Civil & AR
1402 |  | 8 | MDW-89296 |  |  |  |  | As-Built - Provision of Architectural Work in new M&E UPS room at OR23
1403 |  | 8 | MDW-89297 |  |  |  |  | As-Built - Dangerous Goods Building in Depot - Civil & AR
1404 |  | 8 | MDW-89298 |  |  |  |  | As-Built - Dangerous Goods Building in Depot - Building Services
1405 |  | 8 | MDW-89299 |  |  |  |  | As-Built - Training Room at Ratchada Station (Part 2)
1406 |  | 8 | MDW-89300 |  |  |  |  | As-Built - Training Room at Ratchada Station (Part 2) - Building Services | [12 empty] | CANCLE
1407 |  | 8 | MDW-89301 |  |  |  |  | As-Built - Provision of Air Conditioning System in Commercial Room at OR13-OR19
1408 |  | 8 | MDW-89302 |  |  |  |  | As-Built - Modification SIG-PSD Office at Main Workshop - Building Services
1409 |  | 8 | MDW-89303 |  |  |  |  | As-Built - Modification Backup CCR Room at Main Workshop - Building Services
1410 |  | 8 | MDW-89304 |  |  |  |  | As-Built - Modification SER at Main Workshop - Building Services
1411 |  | 8 | MDW-89305 |  |  |  |  | As-Built - Modification CER & SCADA Room at Main Workshop - Building Services
1412 |  | 8 | MDW-89306 |  |  |  |  | As-Built - MEA Radio
1413 |  | 8 | MDW-89307 |  |  |  |  | As-Built - Safety Provision for Maintenance Pits
1414 |  | 8 | MDW-89308 |  |  |  |  | As-Built - Modification CER and First Aid Room at OR14 - Building Services
1415 |  | 8 | MDW-89309 |  |  |  |  | As-Built - Additional Fence at Back of House OR13 - OR22 and IVS East Section
1416 |  | 8 | MDW-89310 |  |  |  |  | As-Built - Additional Locking Devices for Main Line Tandem Turnouts 2007, 2010 & 2013 and Depot Turnout D16
1417 |  | 8 | MDW-89311 |  |  |  |  | As-Built - Modification Air Conditioning System at CCR
1418 |  | 8 | MDW-89312 |  |  |  |  | As-Built - Modification AFC Training Center at OR19 - Civil & AR
1419 |  | 8 | MDW-89313 |  |  |  |  | As-Built - Modification AFC Training Center at OR19 - Building Services
1420 |  | 8 | MDW-89314 |  |  |  |  | As-Built - Modification Electronic Workshop at Main Workshop - Building Services
1421 |  | 8 | MDW-89315 |  |  |  |  | As-Built - Modification Battery Charger Room at Main Workshop - Building Services
1422 |  | 8 | MDW-89316 |  |  |  |  | As-Built - Modification Machining Room at Main Workshop - Building Services
1423 |  | 8 | MDW-89317 |  |  |  |  | As-Built - Modification Paint Shop Room at Main Workshop - Building Services
1424 |  | 8 | MDW-89318 |  |  |  |  | As-Built - Modification Electronic Workshop, Battery Charger, Machining and Paint Shop at Main Workshop - Civil & AR
1425 |  | 8 | MDW-89500 |  |  |  |  | As-Built - Modification Works : Storage Office in Main Workshop - Civil & AR
1426 |  | 8 | MDW-89501 |  |  |  |  | As-Built - Modification Works : Storage Office in Main Workshop - Building Services
1427 |  | 8 | MDW-89503 |  |  |  |  | As-Built - Modification Works : New MMC at Admin Building - Civil & AR
1428 |  | 8 | MDW-89504 |  |  |  |  | As-Built - Modification Works : New MMC at Admin Building - Building Services
1429 |  | 8 | MDW-89505 |  |  |  |  | As-Built - Modification Works : Walkway with Roof from Main Workshop to Stabling Yard - Civil & AR
1430 |  | 8 | MDW-89506 |  |  |  |  | As-Built - Modification Works : Walkway with Roof from Main Workshop to Stabling Yard - Building Services
1431 |  | 8 | MDW-89507 |  |  |  |  | As-Built - Modification Works : High Roof in front of MWS Entrance and Store Entrance - Civil & AR
1432 |  | 8 | MDW-89508 |  |  |  |  | As-Built - Modification Works : High Roof in front of MWS Entrance and Store Entrance - Building Services | [12 empty] | CANCLE
1433 |  | 8 | MDW-89509 |  |  |  |  | As-Built - Modification Works : High Roof at Under Floor Wheel Lathe - Civil & AR
1434 |  | 8 | MDW-89510 |  |  |  |  | As-Built - Modification Works : High Roof at Under Floor Wheel Lathe - Building Services | [12 empty] | CANCLE
1435 |  | 8 | MDW-89511 |  |  |  |  | As-Built - Modification Works : Maintenance Office Rooms at Main Workshop - Civil & AR
1436 |  | 8 | MDW-89512 |  |  |  |  | As-Built - Modification Works : Maintenance Office Rooms at Main Workshop - Building Services
1437 |  | 8 | MDW-89513 |  |  |  |  | As-Built - Modification Works : Concrete Car Barrier in front of Main Workshop
1438 |  | 8 | MDW-89514 |  |  |  |  | As-Built - Modification Works : Car Park Roof and Motorcycle in Depot - Civil & AR
1439 |  | 8 | MDW-89515 |  |  |  |  | As-Built - Modification Works : Car Park Roof and Motorcycle in Depot - Building Services
1440 |  | 8 | MDW-89516 |  |  |  |  | As-Built - Modification Works : Walkway Bridge between BL Depot and ORL Depot - Civil & AR
1441 |  | 8 | MDW-89517 |  |  |  |  | As-Built - Modification Works : Walkway Bridge between BL Depot and ORL Depot - Building Services
1442 |  | 8 | MDW-89518 |  |  |  |  | As-Built - Modification Works : Street Lighting between MRTA Fence and Depot Slab
1443 |  | 8 | MDW-89519 |  |  |  |  | As-Built - Modification Works : Walkway with Roof in Depot Area - Civil & AR
1444 |  | 8 | MDW-89520 |  |  |  |  | As-Built - Modification Works : Sliding Gate, Chain Link Fence and Walkway with Roof in Depot Area - Building Services
1445 |  | 8 | MDW-89521 |  |  |  |  | As-Built - Modification Works : Walkway Bridge and Walkway over Canal in Depot
1446 |  | 8 | MDW-89522 |  |  |  |  | As-Built - Modification Works : Rain Protection and Zero Discharge Water treatment in Depot - Civil & AR
1447 |  | 8 | MDW-89523 | เตรียมออก 20/7/26 OLW-ME-24/0482 |  |  |  | As-Built - Modification Works : Cold Water System at Admin Building Landscape
1448 |  | 8 | MDW-89524 |  |  |  |  | As-Built - Modification Works : Walkway under Depot Slab for Maintenance Service - Civil & AR
1449 |  | 8 | MDW-89525 |  |  |  |  | As-Built - Modification Works : Walkway under Depot Slab for Maintenance Service - Building Services
1450 |  | 8 | MDW-89526 | OLW-ME-24/0407 | 2026-05-25 | A |  | As-Built - Modification Works : FHC Modification at Stabling Yard | [12 empty] | submitted
1451 |  | 8 | MDW-89527 |  |  |  |  | As-Built - Modification Works : Hand Sink with Emergency Eye Wash Installation in Depot
1452 |  | 8 | MDW-89528 |  |  |  |  | As-Built - Modification Works : Washing Area in Cleaning Staff Room at Stabling Yard - Civil & AR
1453 |  | 8 | MDW-89529 | เตรียมออก 20/7/26 OLW-ME-24/0483 |  |  |  | As-Built - Modification Works : Washing Area in Cleaning Staff Room at Stabling Yard - Building Services
1454 |  | 8 | MDW-89530 |  |  |  |  | As-Built - Modification Works : Zero Discharge Water treatment in Depot - Building Services
1455 |  | 8 | MDW-89531 |  |  |  |  | As-Built - Modification Works : Guard rail protection for FHC in Depot Area
1456 |  | 8 | MDW-89532 |  |  |  |  | As-Built - Modification Works : Barbed Wire Fences for MRTA Chain Link at Klong Chourdyai
1457 |  | 8 | MDW-89533 |  |  |  |  | As-Built - Modification Works : Car Barrier Gate at Depot Area
1458 |  | 8 | MDW-89534 |  |  |  |  | As-Built - Modification Works : Security Guard Box at ORL Depot Entrance - Civil & AR
1459 |  | 8 | MDW-89535 |  |  |  |  | As-Built - Modification Works : Security Guard Box at ORL Depot Entrance - Building Services
1460 |  | 8 | MDW-89536 |  |  |  |  | As-Built - Modification Works : Soundproof Installation and Company Logo at CCR Room
1461 |  | 8 | MDW-89537 |  |  |  |  | As-Built - Modification Works : Fence Installation at Ladder in VS, IVS Buildings
1462 |  | 8 | MDW-89538 |  |  |  |  | As-Built - Modification Works : Anti-Slide Signage at Escalator for all Stations
1463 |  | 8 | MDW-89539 |  |  |  |  | As-Built - Modification Works : Roofing over Control Panel Installation at VS, IVS Buildings
1464 |  | 8 | MDW-89540 |  |  |  |  | As-Built - Modification Works : Water Drop Protection for UPS Cabinet for all Stations and Depot
1465 |  | 8 | MDW-89541 |  |  |  |  | As-Built - Modification Works : Manual Call Point Cover in Public Area at all Stations
1466 |  | 8 | MDW-89542 |  |  |  |  | As-Built - Modification Works : Emergency Stop Button Cover for Escalator at all Stations
1467 |  | 8 | MDW-89543 |  |  |  |  | As-Built - Modification Works : Bird & Rain Protetion, Safety Hand Rail Installation at Admin Building
1468 |  | 8 | MDW-89544 |  |  |  |  | As-Built - Modification Works : Barbed Wire Fences for Depot slab
1469 |  | 8 | MDW-89545 |  |  |  |  | As-Built - Modification Works : Chain Link Installation at Cut & Cover Depot Access
1470 |  | 8 | MDW-89546 |  |  |  |  | As-Built - Modification Works : Chain Link Installation under Depot Slab
1471 |  | 8 | MDW-89547 |  |  |  |  | As-Built - Modification Works : Door and Lockset Modification at OCC Building
1472 |  | 8 | MDW-89548 | เตรียมออก 20/7/26 OLW-ME-24/0484 |  |  |  | As-Built - Modification Works : Air Conditioning System Installation at Pantry room OCC Building
1473 |  | 8 | MDW-89549 |  |  |  |  | As-Built - Modification Works : Maintenance Room and Satellite Store at Stations - Building Services
1474 |  | 8 | MDW-89550 |  |  |  |  | As-Built - Satellite Store at OR21 - Civil & AR
1475 |  | 8 | MDW-89551 |  |  |  |  | As-Built - Modification Works : Train Crew Office at OR29
1476 |  | 8 | MDW-89552 |  |  |  |  | As-Built - Modification Works : Hand Rail Installation at Walk Way in Stabling Yard
1477 |  | 8 | MDW-89553 |  |  |  |  | As-Built - Modification Works : Ladder to Access the Fire Valve at Omega Joints for all Underground Stations
1478 | [7 empty] | As-Built - Modification Works : Fire Suspension Control Panel Cover Installation at Tunnel Main Line | [12 empty] | CANCLE
1479 |  | 8 | MDW-89554 |  |  |  |  | As-Built - Modification Works : Security Guard Box at OCC Parking Area - Civil & AR
1480 |  | 8 | MDW-89555 |  |  |  |  | As-Built - Modification Works : Security Guard Box at OCC Parking Area - Building Services
1481 |  | 8 | MDW-89556 |  |  |  |  | As-Built - Modification Works : Addition Small Power System at OCC Building
1482 |  | 8 | MDW-89557 |  |  |  |  | As-Built - Modification Works : Sliding Gate and Chain Link Fence in Depot Area - Civil & AR
1483 | [7 empty] | O&M Manual
1484 |  | 9 | MDW-99001 |  |  |  |  | O&M Manual - Modification Motorized Gate and Shelters at Test Track Depot - English | [12 empty] | CANCLE
1485 |  | 9 | MDW-99003 |  |  |  |  | O&M Manual - Rubber Gap Fillers on Platform Edge on East Section - English | [12 empty] | CANCLE
1486 |  | 9 | MDW-99200 |  |  |  |  | O&M Manual - Intercom System in Cash Handling Room East Section - English
1487 |  | 9 | MDW-99202 |  |  |  |  | O&M Manual - Strobe Light at Buffer Stops - English
1488 |  | 9 | MDW-99204 |  |  |  |  | O&M Manual - MEA Radio - English
1489 |  | 9 | MDW-99206 |  |  |  |  | O&M Manual - Additional Locking Devices for Main Line Tandem Turnouts 2007, 2010 & 2013 and Depot Turnout D16 - English
1490 |  | 9 | MDW-99002 |  |  |  |  | O&M Manual - Modification Motorized Gate and Shelters at Test Track Depot - Thai Translation | [12 empty] | CANCLE
1491 |  | 9 | MDW-99004 |  |  |  |  | O&M Manual - Rubber Gap Fillers on Platform Edge on East Section - Thai Translation | [12 empty] | CANCLE
1492 |  | 9 | MDW-99201 |  |  |  |  | O&M Manual - Intercom System in Cash Handling Room East Section - Thai Translation
1493 |  | 9 | MDW-99203 |  |  |  |  | O&M Manual - Strobe Light at Buffer Stops - Thai Translation
1494 |  | 9 | MDW-99205 |  |  |  |  | O&M Manual - MEA Radio - Thai Translation
1495 |  | 9 | MDW-99207 |  |  |  |  | O&M Manual - Additional Locking Devices for Main Line Tandem Turnouts 2007, 2010 & 2013 and Depot Turnout D16 - Thai Translation
1496
1497
1498
1499
1500 | [7 empty] | RST
1501 | [7 empty] | Outline Design
1502 |  | 1 | RST-19002 | OLW-ME-24/0001 | 2024-11-19 | A | BEM/M/ORM/S0002/67 | Outline Design - Driver Training Simulator | [12 empty] | submitted
1503 |  | 1 | RST-19002 | OLW-ME-24/0001 | 2025-01-23 | B | BEM/M/ORM/S0007/68 | Outline Design - Driver Training Simulator | [12 empty] | submitted
1504 | [7 empty] | Definitive Design
1505 |  | 2 | RST-29001 |  |  |  |  | Definitive Design - Driver Training Simulator | [12 empty] | CANCLE
1506 | [7 empty] | Detailed Design
1507 |  | 3 | RST-39001 |  |  |  |  | Detailed Design - Driver Training Simulator |  |  | Nichapa P. | Somsak S. | Sub | Suchock P. | Komsun N./ Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  | CANCLE
1508 |  | 3 | RST-39002 |  |  |  |  | Detailed Design - List of Spare Part - Driver Training Simulator |  |  | Nichapa P. | Somsak S. | Sub | Suchock P. | Komsun N./ Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  | CANCLE
1509 |  | 3 | RST-39003 |  |  |  |  | Detailed Design - Sample List - Driver Training Simulator |  |  | Nichapa P. | Somsak S. | Sub | Suchock P. | Komsun N./ Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  | CANCLE
1510 |  | 3 | RST-39004 |  |  |  |  | Detailed Design - RAM Report - Driver Training Simulator |  |  | Nichapa P. | Somsak S. | Sub | Suchock P. | Komsun N./ Supajak S. | Somsak S. | Komsun N. | Suraphong S.
1511 |  | 3 | RST-39005 |  |  |  |  | Detailed Design - Mechanism Design - Driver Training Simulator |  |  | Nichapa P. | Somsak S. | Sub | Suchock P. | Komsun N./ Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  | CANCLE
1512 |  | 3 | RST-39006 |  |  |  |  | Detailed Design - Electrical Circuit Design - Driver Training Simulator |  |  | Nichapa P. | Somsak S. | Sub | Suchock P. | Komsun N./ Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  | CANCLE
1513 |  | 3 | RST-39007 |  |  |  |  | Detailed Design - Room Layout Design - Driver Training Simulator |  |  | Nichapa P. | Somsak S. | Sub | Suchock P. | Komsun N./ Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  | CANCLE
1514 |  | 3 | RST-39008 |  |  |  |  | Detailed Design - Failure Mode and Criticality Analysis - Driver Training Simulator |  |  | Nichapa P. | Somsak S. | Sub | Suchock P. | Komsun N./ Supajak S. | Somsak S. | Komsun N. | Suraphong S.
1515 |  | 3 | RST-39009 |  |  |  |  | Detailed Design - Functional Location Data - Driver Trianing Simulator |  |  | Nichapa P. | Somsak S. | Sub | Suchock P. | Komsun N./ Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  | CANCLE
1516 |  | 3 | RST-39010 |  |  |  |  | Detailed Design - Maintenance Planning Data - Driver Training Simulator |  |  | Nichapa P. | Somsak S. | Sub | Suchock P. | Komsun N./ Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  | CANCLE
1517 |  | 3 | RST-39011 |  |  |  |  | Detailed Design - Materials Management Data - Driver Training Simulator |  |  | Nichapa P. | Somsak S. | Sub | Suchock P. | Komsun N./ Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  | CANCLE
1518 |  | 3 | RST-39012 |  |  |  |  | Detailed Design - Scenario Document - Driver Training Simulator |  |  | Nichapa P. | Somsak S. | Sub | Suchock P. | Komsun N./ Supajak S. | Somsak S. | Komsun N. | Suraphong S. |  |  | CANCLE
1519 | [7 empty] | Procurement / Manufacturing / Delivery Stage / FAT
1520 |  | 4 | RST-49001 |  |  |  |  | FAT Procedure - Test Plan - Driver Training Simulator
1521 |  | 4 | RST-49002 |  |  |  |  | FAT Report - Material Factory Test Certificate Report - Driver Training Simulator
1522 |  | 4 | RST-49003 |  |  |  |  | FAT Procedure - Factory Inspection and Testing Procedure - Driver Training Simulator
1523 |  | 4 | RST-49004 |  |  |  |  | FAT Report - Factory Inspection and Testing Report - Driver Training Simulator
1524 | [7 empty] | Installation Menthod Statement
1525 |  | 5 | RST-59001 |  |  |  |  | Installation Method Statement - Driver Training Simulator
1526 | [7 empty] | Testing and Commissioning Procedure
1527 |  | 6 | RST-69001 |  |  |  |  | On-site Inspection and Test Report - Walk-Through Metal Detector East Section
1528 |  | 6 | RST-69002 |  |  |  |  | On-site Inspection and Test Report - Walk-Through Metal Detector West Section
1529 |  | 6 | RST-69003 |  |  |  |  | On-site Inspection and Testing Procedure - Driver Training Simulator
1530 |  | 6 | RST-69004 |  |  |  |  | On-site Inspection and Test Report - Driver Training Simulator
1531 |  | 6 | RST-69005 |  |  |  |  | On-site Inspection and Test Report - Traceability Report - Driver Training Simulator
1532 |  | 6 | RST-69006 |  |  |  |  | On-site Inspection and Test Report - Taking Over Certificate Application - Driver Training Simulator
1533 |  | 6 | RST-69007 |  |  |  |  | On-site Inspection and Test Report - Taking Over Certificate DRACAS Report - Driver Training Simulator
1534 |  | 6 | RST-69008 |  |  |  |  | On-site Inspection and Test Report - Provisional Acceptance Certificate DRACAS Report - Driver Training Simulator
1535 | [7 empty] | Testing and Commissioning Stage / System Integration and Handover Report
1536 | [7 empty] | Training
1537 |  | 7 | RST-79001 |  |  |  |  | Training Manual - Individual Training Plan - Driver Training Simulator
1538 |  | 7 | RST-79002 |  |  |  |  | Training Manual - Instructor Guide (English) - Driver Training Simulator
1539 |  | 7 | RST-79003 |  |  |  |  | Training Manual - Instructor Guide (Thai) - Driver Training Simulator
1540 |  | 7 | RST-79004 |  |  |  |  | Training Manual - Trainee Manual (English) - Driver Training Simulator
1541 |  | 7 | RST-79005 |  |  |  |  | Training Manual - Trainee Manual (Thai) - Driver Training Simulator
1542 |  | 7 | RST-79006 |  |  |  |  | Training Manual - Trouble Shooting & First Aid Manual Instructor - Driver Training Simulator
1543 | [7 empty] | As-Built Drawing, As-Built Configuration Data
1544 |  | 8 | RST-89001 |  |  |  |  | As-Built Drawing - Mechanism Design - Driver Training Simulator
1545 |  | 8 | RST-89002 |  |  |  |  | As-Built Drawing - Electrical Circuit Design - Driver Training Simulator
1546 |  | 8 | RST-89003 |  |  |  |  | As-Built Drawing - Room Layout Design - Driver Training Simulator
1547 | [7 empty] | O&M Manual
1548
1549
1550

## Master Data Lot1 (hidden)
No | Item | BEM Item | Submission No. | Lot | Description | Expected Completion Month | Design % | Plan Finish (Design) | Status Design | Procurement % | Plan Finish (Procurement) | Status Procurement | Construction % | Plan Finish (Construction) | Status Construction | Overall Progress | Location Rev.01 | Location Rev.02 | CK Responsible Person | Type of Work | Detail
1 | GEN1
2 | GEN1.1
3 | GEN1.2
4 | GEN1.3
5 | GEN1.4
6 | GEN1.5
7 | GEN1.6
8 | GEN1.7
9 | #REF!
10 | #REF!
11 | GEN1.10
12 | GEN1.11
13 | GEN1.12
14 | GEN1.13
15 | GEN1.14
16 | GEN1.15
17 | GEN1.16
18 | GEN1.17
19 | #REF!
20 | GEN1.19
21 | GEN1.20
22 | GEN2
23 | GEN3
24 | GEN4
25 | GEN5
26 | GEN6
27 | GEN6.1
28 | GEN6.2
29 | GEN7
30 | GEN7.1
31 | GEN7.2
32 | GEN8
33 | GEN8.1
34 | GEN8.2
35 | GEN9
36 | GEN10.1
37 | GEN10.2
38 | GEN10.3
39 | GEN11
40 | GEN12
41 | GEN12.1
42 | GEN12.2
43 | GEN13
44 | GEN14
45 | GEN14.1
46 | GEN14.2
47 | GEN15
48 | GEN16
49 | GEN17
50 | #REF!
51 | #REF!
52 | GEN19.1
53 | GEN19.2
54 | GEN20
55 | GEN21
56 | GEN22
57 | GEN23
58 | PSD1
59 | PSD2
60 | PSD3
61 | PSD4
62 | AFC1
63 | AFC2
64 | AFC3
65 | AFC4
66 | SIG1
67 | SIG2
68 | SIG3
69 | SIG4
70 | SIG5
71 | DWE1
72 | DWE2
73 | DWE3
74 | DWE4
75 | DWE5
76 | DWE6
77 | DWE7
78 | DWE8
79 | DWE9
80 | DWE10
81 | DWE11
82 | DWE12
83 | DWE13
84 | DWE14
85 | DWE15
86 | DWE16
87 | DWE17
88 | DWE18
89 | DWE19
90 | DWE19.1
91 | DWE19.2
92 | DWE19.3
93 | DWE19.4
94 | DWE19.5
95 | DWE19.6
96 | DWE19.7
97 | DWE19.8
98 | DWE19.9
99 | DWE20
100 | PSY1
101 | PSY2
102 | PSY3
103 | PSY4
104 | SCA1
105 | SCA2
106 | SCA3
107 | SCA4
108 | COM1
109 | COM2
110 | COM3
111 | COM4
112 | COM5
113 | COM6
114 | COM7
115 | COM8
116 | COM9
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149